## Projects
ProjectId | FMSID | Benchmark (Y/N) | DivisionName | UnitName | ProjectDescription | Scope | WebScope | Borough | ClientAgencyCode | Sponsor | PhaseName | ProjectType | Priority | DesignContractType | ConstructionContractType | SourceSystem | MultipleFMSIds | BenchmarkStatus | DesignFiscalYear | ConstructionFiscalYear | CreatedDate | ManageAgency
ACEDOS501 | ACEDOS501 | Y | Public Buildings | ONENYC | DSNY - LIGHTING DEBUNDLING PROJECTS | The scope for Lighting Debundle work at 6 DSNY sites consists of: Providing lighting controller, local controls, occupancy sensors and photo sensors for the garages, along with all other required work associated with the scope. | Implement a building-wide energy efficiency retrofit of electrical systems for six (6) sites. | Unknown |  | DCAS | Completed Project | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
ACEDOS503 | ACEDOS503 | Y | Public Buildings | TRANSPORTATION | DSNY Betts Ave. Incinerator Boilers Replacement | Removal of two old inefficient oversized Tampella dual-fuel (natural gas / #6 fuel oil) boilers and replacement with high efficiency dual-fuel (natural gas / #2 fuel oil) boilers. The new boilers will have electronic controls which will fine-tune the firing rate and the replacement blowers will have variable speed drives. | Removal of two old inefficient oversized Tampella dual-fuel (natural gas / #6 fuel oil) boilers and replacement with high efficiency dual-fuel (natural gas / #2 fuel oil) boilers. The new boilers will have electronic controls which will fine-tune the firing rate and the replacement blowers will have variable speed drives. | Queens |  | Sanitation | Construction 0-25% | New Construction | Court Mandated | CM-Build | CM-Build | PIMS | FALSE |  | 2017 | 2017 |  | DDC
ACEDOT601 | ACEDOT601 | Y | Public Buildings | TRANSPORTATION | EE Measures at Hamilton Administrative Building | The building, which was constructed in the 1990s, still retains many of its original heating, cooling, and lighting components. We observed that there are many inefficiencies, in addition to the fact that many of the building’s systems are past their useful life. With these energy conservation measures implemented, electricity demand and consumption will be reduced by 36.49 kW and 175,547 kWh respectively. In addition the consumption and natural gas can be reduced by 3,891 therms. |  | Brooklyn |  | DCAS |  | Upgrade | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
ACEDOT602 | ACEDOT602 | Y | Public Buildings | TRANSPORTATION | Solar Systems at Two DOT Sights | This project is being done to help the agency meet the City’s sustainability initiatives—specifically the carbon emissions targets, by reducing GHG emissions by 80% by 2050. The solar panels will offset the energy use at each of these facilities. Industry standards recommend that solar systems be installed on roofs that are not nearing the end of their useful lives. The Williams bridge Road location has a new roof, and the 206th Street location has a roof that is ten years old, but with many useful years still expected for that facility. No other major renovations are planned for these facilities that would have negative impacts on the solar system after it is installed. |  | Manhattan |  | DCAS |  | Upgrade | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
ACSLSPCAR | ACSLSPCAR | Y | Public Buildings | CORRECTIONS | 1125 CARROLL ST BKLN LSP FACILITY | Complete the renovation of a State-owned, City-leased facility located at 1125 Carroll Street in Brooklyn that will br used as a limited secure placement facility to be operated by Leake and Watts Services., Inc. | All contract work has been completed. Change order work is 99% and substantial walkthrough took place on 03/24/2017. | Brooklyn |  | Children Services | Substantial Completion | Renovation | Emergency | Standard Consultant | CM-Managed | PIMS | FALSE
ADULTCARE | ADULTCARE | Y | Public Buildings | EXECUTIVE | Nursing Home/Adult Care Facility (HMGP) | Flood mitigation to ensure continuation of power at historically vulnerable long term care facilities through protection and elevation of existing backup power generators and emergency electrical systems to current 500 year flood plain. |  | Citywide |  |  |  | Other |  |  |  | PIMS | FALSE |  |  |  |  | DDC
AGD_MET | AGD_MET | N |  | Miscellaneous | Met Council Multi-Service Center
AGDCPC | AGDCPC | N |  | Miscellaneous | Chinese Planning Council Computers/Condo Space Pur
AGDDORT | AGDDORT | N |  | Miscellaneous | DOROT, INC.
AGCOVELLO | AGCOVELLO | Y | Public Buildings | Human Services | LEONARD COVELLO | Scope is to restore the damaged brickwork of the exposed side elevation that is adjacent to a community garden. The scope also will address the deteriorating masonry chimney. | Restore damaged brickwork, including deteriorating masonry chimney, on side elevation adjacent to the community garden. |  |  | Aging | Maintenance | Renovation | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
BED776 | BED-776 | Y | Infrastructure | BROOKLYN | WM REPLMT EAST NEW YORK AVE | Trunk Water Main replacement in: 1. East New York Avenue between Howard Avenue and Pacific Street. 2. Jamaica Avenue between Herkimer Street and Vermont Street. 3. Atlantic Avenue between Van Sinderen Avenue and Pennsylvania Avenue. | Trunk Water Main replacement in East New York Avenue between Howard Avenue and Pacific Street; Jamaica Avenue between Herkimer Street and Vermont Street; and Atlantic Avenue between Van Sinderen Avenue and Pennsylvania Avenue. | Brooklyn |  | Environmental Protection | Pre-Design/PrgDevelopment | Water | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2015 | 2018 |  | DDC
BED777 | BED-777 | Y | Infrastructure | BROOKLYN | TRUNK & DIST. WM REPLMT IN LEONARD STREET | Trunk and distribution water mains replacement in: Leonard Street between Driggs Avenue and Maujer Street WM-6 1. Leonard Street between Driggs Avenue and Maujer Street 2. Intersection of Leonard Street and Maujer Street WM-1 1. Leonard Street between Driggs Avenue and Maujer Street including all intersections. Sanitary Sewer in: 1. Leonard Street between Driggs Ave and Manhattan Ave Combined Sewers in: 1. Leonard Street between Engert Avenue and Bayard Street 2. Leonard Street between Richardson Street and Meeker Avenue 3. Along Skillman Avenue at Leonard Street 4. Metropolitan Avenue between Leonard Street and Manhattan Avenue 5. Leonard Street betweeb Devoe Street and Ainsile Street | Trunk and distribution water mains replacement in: Leonard Street between Driggs Avenue and Maujer Street | Brooklyn |  | Environmental Protection | Construction 0-25% | Water | Standard | Standard Consultant | Standard Consultant | PIMS | FALSE |  | 2014 | 2016 |  | DDC
BED778A | BED-778A | Y | Infrastructure | BROOKLYN | REPLACEMENT OF TRUNK WATER MAINS IN ATLANTIC AVE | Trunk and Distribution Water Mains Replacement in Atlantic Avenue between Carlton Avenue and Portland Avenue in the Borough of Brooklyn. Water Main (WM-6) in: 1. Atlantic Avenue from Carlton Avenue to South Portland Avenue. 2. Intersection of Atlantic Avenue and Carlton Avenue. Water Main(WM -1) in: 1. Atlantic Avenue(SS) from Carlton Avenue to South Portland Avenue 2. Intersection of Atlantic Avenue and Carlton Avenue 3. Intersection of Atlantic Avenue and Cumberland Street. | Trunk and Distribution Water Mains Replacement in Atlantic Avenue between Carlton Avenue and Portland Avenue in the Borough of Brooklyn. Water Main (WM-6) in: 1. Atlantic Avenue from Carlton Avenue to South Portland Avenue. 2. Intersection of Atlantic Avenue and Carlton Avenue. Water Main(WM -1) in: 1. Atlantic Avenue(SS) from Carlton Avenue to South Portland Avenue 2. Intersection of Atlantic Avenue and Carlton Avenue 3. Intersection of Atlantic Avenue and Cumberland Street. | Brooklyn |  | Environmental Protection | On-Hold | Water | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2014 | 2019 |  | DDC
E3000M019R | E3000DDC | N | Public Buildings | Schools | PS19 M Phase I (Roof) FY 1997 | Roof Rehab. |  |  |  | Education | Completed Project | Renovation | Mayoral In |  | CM-Build | [6 empty] | DDC
E3000M020 | E3000DDC | N | Public Buildings | Schools | PS20 M Phase I (Masonry) FY 1997 | The work entails replacement of deteriorated metal shelf angles at North elevation, minor repair; and replacement of roof and masonry and exterior doors. |  | Manhattan |  | Education | Completed Project | Renovation | Mayoral In |  | CM-Build |  |  |  |  | 1997 |  | DDC
E3000M020A | E3000DDC | N | Public Buildings | Schools | PS 20 M PHASE II (Windows) FY 1997 | Windows Replacement |  |  |  | Education | Completed Project | Renovation | Mayoral In |  | CM-Manage | [6 empty] | DDC
BED798 | BED798 | Y | Infrastructure | BROOKLYN | REPLACEMENT OF 72" TRUNK WM IN FLATBUSH AVE | 72" Trunk Water Main and Combined Sewer Replacement in Flatbush Ave. between Sterling Pl. and 8th Ave., etc., Borough of Brooklyn. WM-6 in: 1. Flatbush Ave. between Park Place and 8th Ave 2. 8th Ave. between Flatbush Ave. and Lincoln Place 3. Park Place between 5th Ave. and 6th Avenue 4. St. Johns Place between 5th Ave. and 8th Ave 5. 6th Avenue between Park Place and Union Street WM-1 in: 1. Flatbush Avenue between Park Place and 8th Avenue Combined sewer in: 1. Park Place between 5th Ave. and 6th Avenue 2. St. Johns Place between 5th Ave. and Flatbush Ave. 3. 6th Avenue between Park Place and Union Street 4. 8th Ave. between St. John's Place and Lincoln Place Additional scope: Reconstruction of triangle at 8th Avenue and Flatbush Avenue removed from HWK300-01 and to be constructed under the BED-798. | 72" Trunk Water Main and Combined Sewer Replacement in Flatbush Ave. between Sterling Pl. and 8th Ave., etc., Borough of Brooklyn. WM-6 in: | Brooklyn |  | Environmental Protection | Construction 0-25% | Water | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2018 |  | DDC
BED809 | BED-809 | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF WATER MAIN IN AVENUE S, BK | RECONSTRUCTION OF WATER MAIN IN AVENUE S, BK | Replacement of Water Mains in Avenue S between Coney Island Avenue and E18th street, Borough of Brooklyn. | Brooklyn |  | Environmental Protection | Compliance | Water | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2016 | 2018 |  | DDC
BED819 | BED-819 | Y | Infrastructure | BROOKLYN | WATERMAIN REPLACEMENT IN ORIENTAL BLVD, BROOKLYN | WATERMAIN REPLACEMENT IN ORIENTAL BLVD, BROOKLYN | WATERMAIN REPLACEMENT IN ORIENTAL BLVD, BROOKLYN | Brooklyn |  | Environmental Protection | Design Development | Water | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2017 | 2019 |  | DDC
BEDA001 | BEDA-001 | Y | Infrastructure | BROOKLYN | ACCELERATED DIST. WM REPL. & SEWER REHAB., BK | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BK | Accelerated Distribution Water Main Replacement and Sewer Rehabilitation/Replacement, Brooklyn | Brooklyn |  | Environmental Protection | Substantial Completion | Water | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
BEDA002 | BEDA-002 | Y | Infrastructure | BROOKLYN | ACCELERATED DIST WATER MAIN REPLACEMENT, BK | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BROOKLYN | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BROOKLYN | Brooklyn |  | Environmental Protection | Construction 0-25% | Water | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
BEDA003 | BEDA-003 | Y | Infrastructure | BROOKLYN | ACCELERATED DIST WATER MAIN REPLACEMENT, BK | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BROOKLYN | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BROOKLYN | Brooklyn |  | Environmental Protection | Construction 0-25% | Water | Critical | Requirements TO | Requirement Contract | PIMS | FALSE |  | 2016 | 2018 |  | DDC
C75FCADGRVC | C75-FCAD | Y | Public Buildings | Corrections | FACADE RECONSTRUCTION AT GRVC | The project includes the design and construction services for the compliance of the 6th cycle of Local Law 11/98 for the exterior façade of 200 and 300 bed buildings at GRVC. | Design and construction services for exterior facade Local Law 11/98 compliance--GRVC 200 and 300 bed buildings. |  |  | Corrections | Substantial Completion | Renovation | Standard | Standard Consultant | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
E3000M180P | E3000DDC | N | Public Buildings | Schools | PS180 M Phase I (Parapet) FY 1997 | Repointing masonry facade |  |  |  | Education | Completed Project | Renovation | Mayoral In |  | CM-Build | [6 empty] | DDC
E3000M180R | E3000DDC | N | Public Buildings | Schools | PS180 M Phase I ( Roof) FY 1997 | repalce deteriorated roof. |  |  |  | Education | Completed Project | Renovation | Mayoral In |  | CM-Build | [6 empty] | DDC
C114NEWRI | C114NEWRI | Y | Public Buildings | CORRECTIONS | NEW RIKERS ISLAND FACILTY | The Rikers Island New Facility is part of an overall DOC Capacity Replacement Program plan which proposes the demolition of the temporary deteriorating constructions and building new state-of –the –art facilities. The program includes: housing of 1300-bed male detention center with 200-bed infirmary, central intake with a central storage, outside parking areas and a study of the new building traffic impact. The gross area is 607,000sqf. The building seeks silver LEED certification. | The Rikers Island New Facility is part of an overall DOC Capacity Replacement Program plan which proposes the demolition of the temporary deteriorating constructions and building new state-of –the –art facilities. The program includes: housing of 1300-bed male detention center with 200-bed infirmary, central intake with a central storage, outside parking areas and a study of the new building traffic impact. The gross area is 607,000sqf. The building seeks silver LEED certification. | Bronx |  | Corrections | Cancelled Project | New Construction | Standard | Standard Consultant |  | PIMS | FALSE |  |  |  |  | DDC
C114NEWRIP1 | C114NEWRI | Y | Public Buildings | Corrections | NEW RIKERS ISLAND FACILTY SITE PREPARATION PHASE 1 | Demolish 12 existing Sprung type temporary enclosures; 12 attached bathroom unit including fixtures and finishes; four raised site trailers including all interior mechanical,electrical and plumbing installations. The site electrical distribution to the Sprungs is to be disconnected and demolished to the power source. |  |  |  | Corrections | Substantial Completion | New Construction | Standard | Standard Consultant | JOCs | Project Info | FALSE |  |  |  |  | DDC
C114NEWRIP2 | C114NEWRI | Y | Public Buildings | CORRECTIONS | NEW RIKERS ISLAND FACILTY SITE PREPARATION PHASE 2 | This project consists of demolition of the existing modular buildings, fencing,trees, trailers, electrical substations and transformers,underground utilities. New paved access road and three new recreation areas. New electrical transformer, underground feeders,manholes.emergency genarator and fuel oil tank. New fencing. | This project consists of demolition of the existing modular buildings, fencing,trees, trailers, electrical substations and transformers,underground utilities. New paved access road and three new recreation areas. New electrical transformer, underground feeders,manholes.emergency genarator and fuel oil tank. New fencing. | Bronx |  | Corrections | Construction 75%-Subst. | New Construction | Standard | Standard Consultant | CM-Managed | PIMS | FALSE |  |  | 2015 |  | DDC
C75FCADEMDC | C75FCADE | Y | Public Buildings | CORRECTIONS | Facade Reconstruction LL11 compliance MDC | The project includes the design and construction of exterior masonry façade repairs at the Manhattan Detention Center (MDC) facility. The facades will first be surveyed, and based on the findings, repair work will be designed and implemented. | The project includes the design and construction of exterior masonry façade repairs at the Manhattan Detention Center (MDC) facility. The facades will first be surveyed, and based on the findings, repair work will be designed and implemented. | Manhattan |  | Corrections | Construction Procurement | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
C75-FCADEMT | C75-FCAD | Y | Public Buildings | Corrections | Facade reconstruction at EMTC | The project includes the design and construction of exterior masonry facade repairs at the Eric M. Taylor Center l(EMTC) facility on Rikers Island. The facades will first be surveyed, and based on the findings, repair work will be designed and implemented. | Exterior masonry facade repairs at EMTC, Rikers Island. |  |  | Corrections | Construction 75%-Subst. | Renovation | Standard | Standard Consultant | JOCs | PIMS | FALSE |  |  |  |  | DDC
ENGINSP3 | ENGINSP3 | N | Safety and Site Support | Quality Assurance | Engineering Inspection Contract
ENGINSP4 | ENGINSP4 | N | Safety and Site Support | Quality Assurance | Engineering Inspection Contract #4
C75-FCADNIC | C75-FCAD | Y | Public Buildings | Corrections | Facade reconstruction at NIC | The project involves the compliance of the 6th cycle of Local Law 11/98 for the exterior facade of the North Infirmary Command Center(NIC) at Rikers Island. The facades must be surveyed and reports are to be filed with DOB. Based on the survey results, any necessary repair work will be designed and constructed. | Perform exterior survey and related facade work on the North Infirmary Command Center at Rikers Island for compliance with Local Law 11. |  |  | Corrections | Substantial Completion | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
CC1C3 | CC1C3 | Y | Public Buildings | Human Services | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 22 | The project involves renovation work on part of the 22nd floor at 1 Centre St, Manhattan Municipal Building. The work consists of a complete renovation including but not limited to new lighting, HVAC, interior construction and plumbing. This project is part of the overall Civic Center Plan to dispose of three city-owned buildings. This project will backfill vacancies and increase efficiency as well as update the space into modern open-office work environments. | Renovation work on the 22nd floor of 1 Centre Street (Municipal Building), Manhattan, including new lighting, HVAC, interior reconfiguration and plumbing. |  |  | DCAS | Maintenance | Renovation | Critical | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
CC253B-1 | CC253B | Y | Public Buildings | Human Services | 100 Gold 3rd Fl Reno | The renovation of 3rd Floor at 100 Gold St to accommodate DOE, Parks &Grow NYC. | Renovation of 3rd Floor at 100 Gold Street to accommodate DOE, Parks &Grow NYC. |  |  | DCAS | Acceptance/Final Completion | Renovation | Standard | Requirements TO | Requirements TO | PIMS | TRUE |  |  |  |  | DDC
CC253B-1 | CC253B-1 | Y | Public Buildings | Human Services | 100 Gold 3rd Fl Reno | The renovation of 3rd Floor at 100 Gold St to accommodate DOE, Parks &Grow NYC. | Renovation of 3rd Floor at 100 Gold Street to accommodate DOE, Parks &Grow NYC. |  |  | DCAS | Acceptance/Final Completion | Renovation | Standard | Requirements TO | Requirements TO | PIMS | TRUE |  |  |  |  | DDC
CITYHALLR | CITYHALLR | Y | Public Buildings | Human Services | CITY HALL ROOF REPAIR AND CITY HALL RENOVATION PRO | Phase 4 work: 1. Replace deteriorated concrete deck above Rotunda with new metal deck. 2. Replace entire roof with new zinc-coated copper metal roofing system. 3. Balustrade repairs and waterproofing. 4. Bluestone restoration (FMS ID:P-3PL14A2) - COMPLETED. 5.ADA lift upgrade | Replace deteriorated concrete deck above Rotunda with new metal deck; replace entire roof with new zinc-coated copper metal roofing system; balustrade repairs and waterproofing. |  |  | DCAS | Completed Project | Renovation | Standard | Standard Consultant | CM-Build | PIMS | FALSE
CJCREN | CJCREN | Y | Public Buildings | Courts | Crossroads Juvenile Center | Major renovation and upgrade of all building systems |  | Brooklyn |  |  |  | Renovation |  |  |  | PIMS | FALSE |  |  |  |  | DDC
CMEHVAC | CMEHVAC | Y | Public Buildings | HEALTH | OCME: HIRSCH CENTER 421 EAST 26TH. HVAC & ANCILLAR | HVAC upgrades for the Evidence Area of OCME-Hirsh Center at 421 E. 26th St, Manh. sub-level 1. Install secured doors between Lab and Evidence Holding Office on 5th Fl. | OCME Hirsch Center, Evidence Area - Indoor Air Quality (IAQ) remediation and ancillary works. | Manhattan |  | Health | Design Development | Upgrade |  | Requirements TO | JOCS | PIMS | FALSE |  | 2017 | 2018
HL82RVREX-I | HL82RVREX | N | Public Buildings | Health | INTERIOR RENOVATION OF RIVERSIDE HEALTH CENTER |  |  |  |  | Health | Cancelled Project | Renovation | Critical | Requirements TO | DDC Managed | [6 empty] | DDC
HL82S001B | HL82S001B | N | Public Buildings | Health | PUB HEALTH LAB FACADE RECON | Public Health Laboratory 455 First Ave. New York, N.Y. (First Ave. & East 26th Street) Stabilization of stone panels and general rehabilitation of exterior envelope. |  | Manhattan |  | Health | Completed Project | Renovation | Standard |  | Standard Design/Const. |  |  |  |  | 2000 |  | DDC
CO272ELC2 | CO272ELC2 | Y | Public Buildings | COURTS | 45 MONROE PL - ELECTRICAL / FA UPGRADE | Replace and upgrade the switchgear and the electrical distribution panels. Replace feeder/ riser wiring. Provide a new Emergency Generator for all Life Safety Systems. Provide a new Fire Alarm System to replace existing. Comply with new 2014 NYC Electrical Code. | 1)AECOM start on 5/26/16 to do the roof top probes in the vicinity of emergency generator, and electrical closet location to meet the requirement of 3 feet clearance in front of panels 2) FDNY requested AECOM to submit the sign and seal drawings and a check for $420 payable to NYC FDNY. 3) The roof top investigation cut 2ft x 1ft shows roof insulation was very slightly wet and can be squeezed the water out, DDC notified the DCAS on 6/3/16 the roof top condition. 4) AECOM to perform their internal constructability review at 45 Monroe place approx. need three days after roof top investigation completed. | Brooklyn |  | DCAS | Construction Procurement | Upgrade | Standard | Requirements TO |  | PIMS | FALSE |  | 2016 |  |  | DDC
CO272ELV2 | CO272ELV2 | Y | Public Buildings | COURTS | 45 MONROE PL - ELEVATOR Modernization | Modernization of the two elevators at the Appelate Court in Brooklyn. Location - 45 Monroe Place, Brooklyn NY. All major components will be replaced both in kind and with technology upgrades: for example, existing DC geared traction hoist machines will be replaced with AC gearless VVVF - AC drives and corresponding controllers. | On 4/17/17 Controller registered the project for construction cost. NTP letter was issued to contractor Knightsbridge on 4/18/17 start for construction. The kick-off meeting held on Monday 4/17/17, DDC, DCAS, and Knightsbridge all attend the meeting. | Brooklyn |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO |  | PIMS | FALSE |  | 2016 |  |  | DDC
CO277ELV2 | CO277ELV2 | Y | Public Buildings | COURTS | 25-10 COURT HOUSE SQ.- ELEVATORS | The project provides for a comprehensive renovation of the facility's two elevators. | The project provides for a comprehensive renovation of the facility's two elevators. | Queens |  | DCAS | Construction 0-25% | Renovation | Standard | Requirement Contract | Individual Contract(s) | PIMS | FALSE |  |  |  |  | DDC
CO277FA | CO277FA | Y | Public Buildings | COURTS | 126 Long Island City Courthouse: Fire Alarms | CO277FA Long Island Courthouse Fire Alarm upgrade | This project is to upgrade 60-year old electrical and FA infrastructure to the current codes and standards. Work includes but is not limited to: analysis and replacement of the switchgear, electrical distribution panels and MCC's; complete replacement of all braided cloth type wiring; installation of a computerized energy management system; upgrade the emergency generator plant and power distribution for all life safety systems; and, complete replacement of the fire alarm system to be in compliance with current code. | Queens |  | DCAS | On-Hold | Upgrade | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
CO283SID2 | CO283SID2 | Y | Public Buildings | COURTS | 100 Centre Sidewalk Stabilization and Ramps | Sidewalk replacement and handicap accessibility. Project involves replacement of the sidewalk, restoration of the entrances to the building, new handicap ramps on the North and Side entrances to the building on Centre Street. | Sidewalk replacement and handicap accessibility. Project involves replacement of the sidewalk, restoration of the entrances to the building, new handicap ramps on the North and Side entrances to the building on Centre Street. | Manhattan |  | DCAS | Construction 0-25% | Sidewalks | Standard | Standard Consultant | CM-Managed | PIMS | FALSE |  | 2016 | 2017 |  | DDC
CO283TOIL | CO283TOIL | Y | Public Buildings | Courts | Criminal Courthouse: 100 Centre Street | ADA & Code Compliant Public Restroom/Holding Cell Toilet Upgrade/Renovations | 850 CO283TOIL Criminal Courthouse: 100 Centre Street. Code Compliant ADA Men's/Women's Public Restroom(s) Upgrade/Renovation. | Manhattan |  | DCAS | Pre-Preliminary Design | Upgrade | Standard | Requirement Contract | Requirement Contract | PIMS | FALSE |  | 2017 | 2017 |  | DDC
CO278EXT2 | CO278EXT2 | Y | Public Buildings | COURTS | Brooklyn Supreme Court Facade Rehabilitation | Undertake a comprehensible restoration of the façade and its elements as well as removing and replacing sections of the roof parapet and associated flashing. Secure loose parapets stone coping and repointing parapet. Reinforced and/or replace damaged and/or displaced stone panels. Reinforcement and/or replacement of deteriorated/rusty structural steel behind the façade as well as sagging steel above wall openings, seal windows and adjuncts openings. Rehabilitation of large section of deteriorate masonry as well as cleaning of the stone façade and aluminum fenestration to protect pedestrians and restore the building appearance to an esthetically acceptable state. | Undertake a comprehensible rehabilitation/restoration of the façade and its elements as well as removing/replacing section(s) of the roof parapets and its associated flashing. Replacement of deteriorated/rusty structural steel behind the faced and above wall openings, windows and adjuncts openings. The work will also include cleaning of the stone façade envelope. The work will address Local Law 11 requirements, protect pedestrians, waterproof the building envelope and prevent further damage to the stone cladding. | Brooklyn |  | DCAS | Schematic Design | Renovation | Standard | Requirements TO | Requirements TO | PIMS | TRUE |  |  |  |  | DDC
CO278FA3 | CO278FA3 | Y | Public Buildings | Courts | Brooklyn Supreme court 360 Adams Fire Alarms | New addressable non-proprietary Fire Detection & Alarm system in full compliance with current Building, Electrical & Fire Protection Codes of the City of New York as mandated by Local Law #5 of 1973 and its latest amendments. New sprinkler system prior to 2019 as mandated by Local Law 26. | New addressable non-proprietary Fire Detection & Alarm system in full compliance with current Building, Electrical & Fire Protection Codes of the City of New York as mandated by Local Law #5 of 1973 and its latest amendments. New sprinkler system prior to 2019 as mandated by Local Law 26. | Brooklyn |  | DCAS | Design Development | Upgrade | Standard | Standard Consultant | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
CO281BOIL | CO281BOIL | Y | Public Buildings | Courts | Boiler feed upgrade. | Boiler water feed replacement |  |  |  | DCAS | Maintenance | New Construction | Standard | Standard Consultant | DDC Managed | PIMS | FALSE
CO281ELEC | CO281ELEC | Y | Public Buildings | Courts | 120 Schermerhorn Elec & Emerg Generator Upgrade | The Intent of this Electrical Upgrade project is to update 80+ Years old Central Criminal Court Building with new Electrical power. Con ED Electrical Service is increase from 4,000 Amp to 8,000 Amp New Emergency Generator, installed on the roof, will provide 1,25 MW of Backup Power for engineering systems in Building. (Old / Existing Generator was supplying only 250 KW electrical powers) | Upgrade 80 year old Central Criminal Court building with new 8000 amp. electrical power service and install new emergency generator which will provide 1,25 MW of backup power. |  |  | DCAS | Substantial Completion | Upgrade | Standard |  | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
CO281FA | CO281FA | Y | Public Buildings | Courts | Kings County Criminal Court - Fire Alarm | Provide a complete Class "E" Fire Alarm System of the addressable non- coded type to complement the new existing System installed as a part of the Kings County Criminal Court Renovation project ( Phase I) .In the Phase I of the Renovation project new system was installed in the area of Construction only. The additional System will cover all spaces to constitute one Fire Alarm System for the entire building. | Install a complete Class "E" Fire Alarm System of the addressable non- coded type, augmenting work done in Phase I of this project, to provide one Fire Alarm System for the entire building. |  |  | DCAS | Maintenance | Upgrade | Standard | Requirements TO |  | PIMS | FALSE |  |  |  |  | DDC
CO281TOIL | CO281TOIL | Y | Public Buildings | Courts | Central Courts Building:120 Schermerhorn St. | ADA & Code Compliant Public Restroom/ Holding Cell Toilet Upgrade. | 1. DDC's In-House design consultant had presented three design schemes for the Schematic Design Presentation to DCAS. After presenting the three design concepts, It was determined from the reviews & comments that another meeting would be arrange to determine a final selection of a final design scheme for the public restrooms schematic design presentation.. 2. For the Holding Cell Toilet Upgrade, In-House designer requested information as to DOC operational procedures in separating user type cell as it relate to holding of inmates. Arrangement of cell(s) user types shall determine the number ADA toilet to provide. DOC has responded and the schematic design drawings will be revised. 3. Since DCAS will only provide funding for design work, DOC has been informed about this situation regarding no construction funding will be provided by DCAS for the holding cell toilet upgrade. DOC was informed about this matter and is looking into giving DDC a direction. 4. DDC's Asbestos unit has completed a asbestos report for the project. 5. DDC's estimating unit has prepared an estimate for the project. | Brooklyn |  | DCAS | Design Development | Upgrade | Standard | In-House | Requirement Contract | PIMS | FALSE |  | 2016 | 2018 |  | DDC
CO283CTSP | CO283CTSP | Y | Public Buildings | Courts | 100 Centre St Cooling Towers to Replace Spray Pond | This project involves the demolition of the existing HVAC equipment and assoccieted Asbestos abatemend, installation of cooling towers to replace existing spray ponds on the 19th and 20th floors, condenser water risers and pumps and installation of controls from new cooling towers and associated new equipment. The new cooling towers system will provide infrastucture required to fully meet the condenser water demand for the existing chillers and for future expansion of the chilled water plant to meet the centralized cooling loads of the entire building. | Installation of cooling towers, replacing existing spray ponds, to meet the condenser water demand for existing chillers and for future expansion to cooling the entire building. |  |  | DCAS | Substantial Completion | Renovation | Standard | Standard Consultant | DDC Managed/Consultant | PIMS | FALSE |  |  |  |  | DDC
CO283ELEV | CO283ELEV | Y | Public Buildings | Human Services | 100 Centre Street Elevator Modernization - 28 Elev | A complete modernization of all 28 elevators at 100 Centre Street to include controls, dispatchers, motor drives, hoists, door equipment, deflector sheaves, 2:1 sheaves, compensation sheaves, wires, ropes, cabs, and fixtures.Replace CCTV system with cameras, cables, and monitors. Work also includes lump sum GC and HVAC work. | A complete modernization of all 28 elevators at 100 Centre Street. |  |  | DCAS | Substantial Completion | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE
CO283FIRE | CO283FIRE | Y | Public Buildings | Human Services | 100 Centre Street Fire Alarm Upgrade | Installation of a new fire alarm system for 100 Centre Street which will include new data gathering panels at various floors and all other necessary conduit, wires, speakers, strobes, combos, etc to make a new system. Old system will be removed. Components will also involve the DA wing and the Department of Corrections. | Installation of a new fire alarm system for various floors of 100 Centre Street. The scope includes the DA wing and the Department of Corrections. |  |  | DCAS | Substantial Completion | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HWQC063H | HWQC063H | N | Infrastructure | Bronx & N. Queens | 23rd Ave Center Mall |  |  | Queens |  | Trans. & Env. Protection | Cancelled Project | Street Reconstruction | [7 empty] | 2020 |  | DDC
CO284EXT2 | CO284EXT2 | Y | Public Buildings | COURTS | 111 CENTRE ST.- EXTERIOR | Bulkhead restoration: Structural steel repair, replace façade bricks, coping stones, lintels, louvers, roof flashing, | Bulkhead restoration: Structural steel repair, replace façade bricks, coping stones, lintels, louvers, roof flashing | Unknown |  | DCAS | Construction 0-25% | Renovation | Standard | DCAS | Individual Contract(s) | PIMS | FALSE |  |  |  |  | DDC
CO285FIRE | CO300ELV2 | Y | Public Buildings | COURTS | Family Crthouse:60 Lafayette St NY.FireAlarmUpgrad | Upgrade of the Fire Alarm system |  | Queens |  | DCAS | On-Hold | Upgrade | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
CO290BCHJ | CO290BCHJ | Y | Public Buildings | COURTS | BCHJ-Post Construction Work | Remediation work at the Bronx County Hall of Justice as indicated in the Project Objectives, Exhibit C. Work includes HVAC, roof leaks, glass breakage, intumescent paint, plumbing and audio/visual. | Remediation work at the Bronx County Hall of Justice. Scope of work includes installing a new door into the mechanical room at the Jury Assembly room, replacement of intumescent paint at the structural steel members supporting stairs A & B, replacement of the Jury Assembly building roof over the interior ramped corridor & waterproofing of the exterior public space plaza that is over the underground garage. The audio visual component addresses various problems with equipment in the courtrooms. Sections of HVAC duct in the underground garage are being replaced due to damage from the plaza leaks above. Replacement of approximately 15 lineal feet of underground storm drain line / pipe including a new manhole and link seal at the cellar wall. Replacement of approximately 100 lineal feet of undersized sewer line at the cellar level. Increasing the size of undersized plumbing vent lines at various locations. Installation of chilled and hot water balancing valves for heating and cooling equipment. | Bronx |  | DCAS | Construction 25-50% | Other | Standard | Standard Consultant | CM-Managed | PIMS | FALSE |  |  | 2017 |  | DDC
CO294BOIL | CO294BOIL | Y | Public Buildings | COURTS | Bronx Courthouse:215 East 161st:Boiler Replacement | BOILER REPLACEMENT AT BRONX FAMILY COURT | This project is to replace aging and inefficient boilers with new efficient dual gas/oil fired boilers. It includes selective demolition of the existing boilers and installation of new dual fuel boilers and all auxiliaries along with all associated electrical and GC work. | Bronx |  | DCAS | On-Hold | Renovation | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
CO294ELEC | CO294ELEC | Y | Public Buildings | Human Services | 215 E. 161st Street-Electrical Upgrade | The Electric Upgrade consists of new distribution system, new generator, and new 4,000 amp power. The building was built in 1975 with not enough electrical circuit capacity for today's usage. | Install a new electrical distribution system and new emergency generator. |  |  | DCAS | Acceptance/Final Completion | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
CO294LL | CO294LL | Y | Public Buildings | Courts | Bronx Family Court Exterior Rehab. | The project consists of rehabilitating the façade to conform with the City's façade ordinance Local Law 11 by addressing any conditions identified in the Seventh Cycle report as requiring rehabilitation and replacement including existing building low-sloped roofing assemblies. | The project consists of repairing the façade to conform with the City's façade ordinance Local Law 11 by addressing any conditions identified in the Seventh Cycle report as requiring repair and replacement including existing building low-sloped roofing assemblies. | Bronx |  | DCAS | On-Hold | Renovation | Standard | Requirement Contract |  | PIMS | FALSE |  |  |  |  | DDC
CO296ELEC | CO296ELEC | Y | Public Buildings | COURTS | ELECTRICAL AND FIRE UPGRADE CRIMINAL COURTHOUSE | Upgrade of the Electrical and Fire Alarm systems at Queens Criminal Court | Upgrade of the Electrical and Fire Alarm systems at Queens Criminal Court | Queens |  | DCAS | Pre-Design/PrgDevelopment | Upgrade | Standard | Requirement Contract | CM-Build | PIMS | FALSE |  |  |  |  | DDC
CO290BCHJ-2 | CO290BCHJ | Y | Public Buildings | COURTS | BRONX HALL OF JUSTICE POST CONSTRUCTION | BRONX HALL OF JUSTICE POST CONSTRUCTION BID PACKAGE 2- HVAC AIRFLOW ISSUES This scope includes the installation of a new transfer air fan and associated ductwork with sound attenuation on the inlet and outlet of a fan serving the Judge’s Lounge located at the 7th Floor. New transfer air ducts are being installed on floors 2, 7 & 8 to assist in the proper function of the return air system. Additional fan coil units are being installed to serve several rooms on the 8th floor & the 7th floor elevator lobby. ENGINATOR EXHAUST HEAT This scope involves a means of venting excessive heat that builds up in a shaft way that houses the enginator exhaust pipe that begins in lower level 2 up and out through the roof of the building. The heat emanates through the shaft way walls into the building. This will be accomplished by installing a new exhaust fan and a makeup air fan that pumps outside air into the shaft way. CURTAINWALL SHADOW BOX HEAT TRANSFER Original design created conditions where curtain wall mullions heated to temperatures in excess of 110 F. This scope of works involves installing new metal stud with sheetrock finishes over interior curtain wall mullions. Affected locations are portions of the 2nd floor east side exposure. WATER PENETRATION THROUGH UNDERGROUND CONDUITS An existing underground conduit experienced water infiltration which caused those conductors to fail. Those conductors are going to be removed and the conduit abandoned. A new above ground path has been designed for the new feeder. INTERIOR GLASS REPLACEMENT Replace 4 sections of glazing at Stair A and 1 section at Stair B. CONDENSER WATER SYSTEM WITH THREE ROOF TOP DRY COOLERS Furnish and install a complete new A/C condenser cooling glycol system that includes roof top dry coolers and associated piping. This new system will serve chilled water A/C units in IT closets and elevator machine rooms throughout the building. | HVAC AIRFLOW ISSUES This scope includes the installation of a new transfer air fan and associated ductwork with sound attenuation on the inlet and outlet of a fan serving the Judge’s Lounge located at the 7th Floor. New transfer air ducts are being installed on floors 2, 7 & 8 to assist in the proper function of the return air system. Additional fan coil units are being installed to serve several rooms on the 8th floor & the 7th floor elevator lobby. ENGINATOR EXHAUST HEAT This scope involves a means of venting excessive heat that builds up in a shaft way that houses the enginator exhaust pipe that begins in lower level 2 up and out through the roof of the building. The heat emanates through the shaft way walls into the building. This will be accomplished by installing a new exhaust fan and a makeup air fan that pumps outside air into the shaft way. CURTAINWALL SHADOW BOX HEAT TRANSFER Original design created conditions where curtain wall mullions heated to temperatures in excess of 110 F. This scope of works involves installing new metal stud with sheetrock finishes over interior curtain wall mullions. Affected locations are portions of the 2nd floor east side exposure. WATER PENETRATION THROUGH UNDERGROUND CONDUITS An existing underground conduit experienced water infiltration which caused those conductors to fail. Those conductors are going to be removed and the conduit abandoned. A new above ground path has been designed for the new feeder. INTERIOR GLASS REPLACEMENT Replace 4 sections of glazing at Stair A and 1 section at Stair B. CONDENSER WATER SYSTEM WITH THREE ROOF TOP DRY COOLERS Furnish and install a complete new A/C condenser cooling glycol system that includes roof top dry coolers and associated piping. This new system will serve chilled water A/C units in IT closets and elevator machine rooms throughout the building. REMOVAL OF EXCESS HEAT FROM COURTROOM AV CLOSETS This scope of work involve installing fans in the ceilings of all the audio visual closets to vent out heated air from all the equipment inside the closet on floors 3-6. New hollow metal doors with louvers will also be installed. | Bronx |  | DCAS | Construction 0-25% | Other |  | Standard Consultant | CM-Managed | PIMS | FALSE |  |  | 2018 |  | DDC
CO293BOIL | CO293BOIL | Y | Public Buildings | COURTS | Bronx Courthouse:851 Grand Concourse Boiler Downsi | Boiler Replacement at Bronx County Courthouse | Boiler replacement/re-tubing at Bronx County Courthouse. | Bronx |  | DCAS | On-Hold | Renovation | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
CO293ELEC | CO293ELEC | Y | Public Buildings | Human Services | 851 GRAND CONCOURSE ELECTRICAL UPGRADE | The electrical upgrade consists of New Generator New Distribution System. November 1, 2012 (910 calendar days). Revised to November 1, 2013 (1276 calendar days) Revised to October 31, 2014 (1640 Calendar Days) | Install a new emergency generator and new distribution system. |  |  | DCAS | Acceptance/Final Completion | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
CO293SP | CO293SP | Y | Public Buildings | COURTS | Supreme Courthouse Fire Alarm/ Protection Upgrade | Provide new addressable non-proprietary Fire Detection & Alarm system in full compliance with the 2008/2014 fire code, Local Law 5, Local Law 26 and all codes related to fire and life safety in the City of New York; provide new sprinkler system prior to 2019 as mandated by Local Law 26. The project is necessary to replace the existing Edwards EST3 Fire Alarm system (originally installed in 1992 - beyond the life expectancy) in over 70-years old Landmark in full compliance with all latest applicable codes and regulations & provide new sprinkler system prior to 2019 as mandated by Local Law 26 | Replaced the beyond life expectancy and existing 1992 Edwards EST3 fire alarm system and install a new sprinkler system prior to 2019 as mandated by Local Law 26 and in compliance with the 2008/2014 fire code and Local Law 5. | Bronx |  | DCAS | Pre-Design/PrgDevelopment | Upgrade | Standard | Requirement Contract | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
CO296EX7B | CO296EX7B | Y | Public Buildings | COURTS | FACADE RESTORE/REHAB QUEENS CRIMINAL COURTHOUSE | This project is being done to eliminate the unsafe conditions per facade inspection report cycle 7 and to enable DCAS remove sidewalk shed already in place for more than 5 years. The law requires owners of buildings 6 stories and higher to have their building's exterior walls and elements inspected once every 5 years in to make the necessary repairs to make them safe. No pre-preliminary phase is needed |  | Queens |  | DCAS |  | Renovation | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
CO296EXT7 | CO296EXT7 | Y | Public Buildings | Courts | QueensCriminal Court:125-01 Queens Blvd, Facade | Exterior façade rehabilitation and renovation. Renovation to the building façade exterior at the Queens Criminal Courthouse. The project consists of façade restoration and repairing the building façade in compliance with Local Law 11/98; façade inspection safety program. The project is being done to eliminate constant leaks throughout the interior of the building, which also requires restoring the deteriorated seals around the building. The project includes repairs/replacement of façade stones, coping stones, roofing, flashing, installation of missing parapet railing, re-caulking of coping stones, etc. The law requires owners of buildings 6 stories and higher to have their building's exterior walls and elements inspected once every 5 years and make necessary repairs to make them safe. The restoration consists of the entire building. However, our client, DCAS, has requested to restore unsafe conditions at the Queens District Attorney's building façade as Phase I of the project. | Exterior façade rehabilitation and renovation. Renovation to the building façade exterior at the Queens Criminal Courthouse. The project consists of façade restoration and repairing the building façade in compliance with Local Law 11/98; façade inspection safety program. The project is being done to eliminate constant leaks throughout the interior of the building, which also requires restoring the deteriorated seals around the building. The project includes repairs/replacement of façade stones, coping stones, roofing, flashing, installation of missing parapet railing, re-caulking of coping stones, etc. The law requires owners of buildings 6 stories and higher to have their building's exterior walls and elements inspected once every 5 years and make necessary repairs to make them safe. The restoration consists of the entire building. However, our client, DCAS, has requested to restore unsafe conditions at the Queens District Attorney's building façade as Phase I of the project. | Queens |  | DCAS | Schematic Design | Renovation | Critical | Requirements TO | DDC Managed | PIMS | FALSE |  | 2017 | 2017 |  | DDC
CO299EXTR | CO299EXTR | Y | Public Buildings | COURTS | Queens Civil Court Plaza/Sidewalk Reconstruction | Renovation of the building envelope |  | Queens |  | Corrections | Pre-Design/PrgDevelopment | Renovation | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
CO299FIRE | CO299FIRE | Y | Public Buildings | COURTS | Civil Courthouse:89-17 Sutphin BLVD,NY.FireAlarmUp | 89-17 Sutphin Blvd Fire alarm replacement |  | Queens |  | DCAS | On-Hold | Upgrade | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
CO81ELEC | CO81ELEC | Y | Public Buildings | HUMAN SERVICES | Surrogate Courthouse:31 Chambers.Elec Upgrade, | systems upgrade | Install new building wide fire alarm system and electrical upgrade | Manhattan |  | DCAS | Pre-Preliminary Design | Upgrade | Critical | Requirement Contract | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
CO81SKY2 | CO81SKY2 | Y | Public Buildings | HUMAN SERVICES | 31 CHAMBERS ST.- RENOVATE SKYLIGHT | The project involves renovation work on the existing Skylight over the main lobby space in 31 Chambers Street. There also will be restoration work on lunettes on either end of the Skylight. | The project is to renovate the existing skylight and laylight over the main lobby space at 31 Chambers Street. | Manhattan |  | DCAS | Construction 25-50% | Renovation | Standard | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
CO300ELV2 | CO300ELV2 | Y | Public Buildings | COURTS | 88-11 SUTPHIN BLVD.- ELEVATOR | Replacement of six (6) passenger elevators and four (4) existing Judges' elevators; provide new exterior Main Entrance ADA elevator (handicapped access.) at Queens Supreme Court. Due to high rate of the existing equipment failure (outdated + obsolete,) it is imperative to expedite the bidding and construction phase of the project, complete within 3 years; 2 phases; 5 elevators per phase. | Replacement of six (6) passenger elevators and four (4) existing Judges' elevators; provide new exterior Main Entrance ADA elevator (handicapped access.) at Queens Supreme Court. Due to high rate of the existing equipment failure (outdated + obsolete,) it is imperative to expedite the bidding and construction phase of the project, complete within 3 years; 2 phases; 5 elevators per phase. | Queens |  | DCAS | Substantial Completion | Upgrade | Mayoral Initiative | Standard Consultant | DDC Managed/Consultant | PIMS | FALSE |  |  |  |  | DDC
CO300EXT2 | CO300EXT2 | Y | Public Buildings | Courts | Queens Supreme Court Building Facade | This project consists of repairing the Façade. This project is being done to eliminate the constant leaks throughout the interior of the building. It will also restore the deteriorated seals around the exterior of the building |  | Queens |  | DCAS |  | Renovation |  |  |  | PIMS | FALSE |  |  |  |  | DDC
CO301LL | CO301LL | Y | Public Buildings | Courts | 130 STUYVESANT PLACE EXTERIOR REHAB, DESIGN PHASE | The scope of this project is to reconstruct the entire envelope including the restoration of the curtain wall system on the north, east and west facades, the reconstruction of the masonry walls at the south façade and bulkhead, replacement of the roofs at each level and related work required at the roof parapets, copings and railings. | The scope of this project is to reconstruct the entire envelope including the restoration of the curtain wall system on the north, east and west facades, the reconstruction of the masonry walls at the south façade and bulkhead, replacement of the roofs at each level and related work required at the roof parapets, copings and railings. | Staten Is. |  | DCAS | Pre-Design/PrgDevelopment | Renovation | Standard | Requirement Contract |  | PIMS | FALSE |  |  |  |  | DDC
CO301PD | CO301PD | Y | Public Buildings | COURTS | 130 Stuyvesant Pl. - Parking Garage Deck | The scope of this project is to renovate the surface deck of the parking garage attached to the Mark A. Costantino Judicial Center. The project scope includes replacement of the top deck waterproofing membrane and wear surfacing, the replacement of flashing at all mechanical penetrations, and the replacement of the parking surface on-grade continuous with the top parking deck. Also included will be new parking deck drains, new surface lighting, installation of automatic pop-up vehicle access gates and modification of vertical access to the building entrance from the parking deck for ADA accessibility will be part of this project. | The scope of this projects is to renovate the surface deck of the parking garage attached to the Mark A. Costantino Judicial Center. The project scope includes replacement of the top deck waterproofing membrane and wear surfacing, the replacement of flashing at all mechanical penetrations, and the replacement of the parking surface on-grade continuous with the top parking deck. Also included will be new parking deck drains, new surface lighting, installation of automatic pop-up vehicle access gates and modification of vertical access to the building entrance from the parking deck for ADA accessibility. | Staten Is. |  | DCAS | Pre-Preliminary Design | Renovation | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
CO304LL11 | CO304LL11 | Y | Public Buildings | COURTS | MANHATTAN SUPREME COURT, EXTERIOR FACADE | This project consists of repairing the façade. This project is being done to eliminate the constant leaks throughout the interior of the building. It will also restore the deteriorated seals around the exterior of the building. |  | Manhattan |  | DCAS |  | Upgrade | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
CO305REHB | CO305REHB | Y | Public Buildings | Courts | Midtown Community Court Rehabilitation | Midtown Community Court & theater, built in 1865 and designated as a New York Historic Landmark, is approximately 25,000 square feet and comprises of a sub-cellar and cellar, a mezzanine level, and six floors. The general scope of work involves the demolition of an existing exterior stair, masonry wall with its foundation in the rear courtyard to be replaced with an new two hours fire resistive curtain wall/foundation addition which provides extra cellar space for new infrastructure equipment, a large conference room on the first floor, and an enclosed new egress stairwell from the sub cellar to the 6th floor. As part of the building’s envelope upgrade, the scope will include the rehabilitation of the landmark front façade, east & west masonry walls to receive stucco, new windows, new roofing with a major skylight restoration. In addition to the scope of work, the building will receive infrastructure upgrade affecting the mechanical, heating, cooling, plumbing, sprinkler, fire alarm, electrical and lighting system for the building. To monitor the efficient of some of these new systems, a Building Management System will be included in the scope of work. As for interior scope of work, upgrade public restrooms in floors 1thur 6 to incorporate ADA compliance & new restroom design, built interior walls to modify existing wall layout to incorporate separate or combine systems in one location, and built an enclosed north & south shaft walls to incorporate new mechanical supply & return ducts to the roof. Replace existing ceiling with new non-rated & fire rated ceiling thru out. Restore/rebuild and add new elevator’s shaft walls to modernized and install two new elevators. | Demolition of existing stairs and construction of new exterior stairs, new elevator shaft and elevator lobby. Work also includes new cooling system with associated duct work throughout the building, fire alarm system, new boiler, toilet upgrade, new heating system, sprinklers, plumbing and lighting up grade. |  |  | DCAS | Substantial Completion | Renovation | Standard | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
CO306REHB | CO306REHB | Y | Public Buildings | COURTS | HARLEM COURTHOUSE: 170-74 E 121 st. | Provide new addressable non-proprietary Fire Detection & Alarm system in full compliance with current Building, Electrical & Fire Protection Codes of the City of New York as mandated by Local Law #5 of 1973 and its latest amendments. Provide new sprinkler system prior to 2019 as mandated by Local Law 26. | Provide new addressable non-proprietary Fire Detection & Alarm system in full compliance with current Building, Electrical & Fire Protection Codes of the City of New York as mandated by Local Law #5 of 1973 and its latest amendments. Provide new sprinkler system prior to 2019 as mandated by Local Law 26. | Manhattan |  | DCAS | On-Hold | Upgrade | Standard | Requirement Contract |  | PIMS | FALSE |  |  |  |  | DDC
CO80ROOF2 | CO80ROOF2 | Y | Public Buildings | COURTS | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UP | The project involves renovation/alterations work of the Appellate Court building. The work includes demolition, concrete , caulking , marble repairs ,waterproofing,roofing, mechanical, plumbing electrical/lighting and mural rehabilitation . | The project involves renovation/alterations work of the Appellate Court building. The work includes demolition, concrete , caulking , marble repairs ,waterproofing, roofing, mechanical, plumbing electrical/lighting and mural rehabilitation | Manhattan |  | DCAS | Construction 50-75% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
PV205-TUB | PV205-TUB | N | Public Buildings | Culturals | NYBG - New York Botanical Garden - Compost Equipme
PV205-VH2 | PV205-VH2 | N |  | Miscellaneous | vehicle purchases
CONISPH01 | CONISPH01 | Y | Infrastructure | Brooklyn | STM, SAN SEWERS & WM IN CONEY ISLAND AREA, BK | Installation of Storm and Sanitary sewers, Trunk and Distribution water mains in Coney Area, Phase I, Borough of Brooklyn. Storm Sewer in: 1. West 15th Street between Hart Place and Surf Avenue 2. Outfall at West 15th Street and Hart Avenue to Coney Island Creek 3. Surf Avenue between w 17th Street and W 12th Street Sanitary Sewer in: 1. West 15th street(both east side and west side) between Hart Place and Neptune Avenue Water Main(WM-6): 1. Neptune Avenue at intersection with W 15th Street Water Main(WM-1): 1. Neptune Avenue at intersection with W 15th Street | Installation of Storm and Sanitary sewers, Trunk and Distribution water mains in Coney Area, Phase I, Borough of Brooklyn. | Brooklyn |  | Environmental Protection | Substantial Completion | Sewer | Mayoral In | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
CONISPH2A | CONISPH2A | Y | Infrastructure | BROOKLYN | STM, SAN SEWERS & WM IN CONEY ISLAND AREA, BK | The Construction Of Storm And Sanitary Sewers And Trunk Water Mains And Appurtenances In: Neptune Avenue Between West 20th Street And West 22nd Avenue; West 21st Street Between Neptune Avenue And Surf Avenue; Surf Avenue Between West 20th Street And West 22nd Street; And, Mermaid Avenue Between West 21st Street And West 24th Street Including Water Main Work, Together With All Work Incidental Thereto, Phase-2A, Borough of Brooklyn Storm Sewer 1-West 21st St. b/t Neptune Ave. and Surf Ave. 2-Mermaid Ave b/t West 21st St. and West 24th St. 3-Outfall at West 21st St. and Neptune Ave. to Coney Island Creek Sanitary Sewer 1-West 21st St. b/t Mermaid Ave. and Surf Ave. 2-Mermaid Ave. b/t west 21st ST. and West 24th St.(both North and South side) Watermain (WM-6) 1-Intersection of W. 21 St. and Neptune Ave. Water Main (WM-1) 1-Mermaid Ave. b/t W.21st St and W.24th St. 2-Intersection of W. 21st St. and Neptune Ave. 3-Intersection of W. 21 St. and Surf Ave. | The Construction Of Storm, Sanitary Sewers, and Trunk Water Mains and Appurtenances In Coney Island Area, Phase 2A, Brooklyn. | Brooklyn |  | Environmental Protection | Substantial Completion | Sewer | Standard | Requirements TO | Individual Contract(s) | PIMS | FALSE |  | 2013 | 2015 |  | DDC
CONISPH2B | CONISPH2B | Y | Infrastructure | BROOKLYN | STM, SAN SEWERS & WM IN CONEY ISLAND AREA-PH2B, BK | Storm and Sanitary sewer, Trunk and distribution water main in Coney Island area, Borough of Brooklyn Phase-2B Storm Sewer 1-Neptune Ave. b/t Stillwell Ave. and West 12th St. (both North & South side) 2-Stillwell Ave. b/t Coney Island Creek and Surf Ave. 3-Outfall at West 12th St.and Neptune Ave. to Coney Is Land Creek Sanitary Sewer 1-Stillwell Ave. b/t Coney Island Creek to Surf Ave. 2-Neptune Ave. b/t Stillwell Ave. and West 12th St.(both North side and South side) Watermain 1-Neptune Ave b/t Stillwell Ave. and W. 12th St. 2-Stillwell Ave. b/t Surf Ave. and Coney Island Creek | Reconstruction of Storm and Sanitary sewer, Trunk and distribution water main in Coney Island area - Phase-2B, Borough of Brooklyn. | Brooklyn |  | Environmental Protection | Construction 0-25% | Sewer | Standard | Requirements TO | Standard Consultant | PIMS | FALSE |  | 2015 | 2016 |  | DDC
CRO-AGS | CRO-AGS | Y | Public Buildings | DEP | CROTON ABOVE GROUND STRUCTURE AND LANDSCAPING | The new Mosholu Golf Course Club House, together with fifty-five Driving Range Tee Boxes and ten-acres of re-landscaping comprise the phase IV and final of the vast DEP Croton Water Treatment Plant project, currently under construction in Van Cortlandt Park in the Bronx. Through a multifunctional design strategy the project reinstates the pre-existing golf program and facility, creates civic space for community use and ensures security for a multi-billion dollar public works facility. |  |  |  | Environmental Protection | [5 empty] | Project Info | FALSE |  |  |  | 2017-10-17 07:00:23.0770000 +00:00
CONISPH3A | CONISPH3A | Y | Infrastructure | BROOKLYN | STM, SAN SEWERS & WM IN CONEY ISLAND AREA, PH3A,BK | Storm and Sanitary sewer, Trunk and distribution water main in Coney Island area, Borough of Brooklyn Storm Sewer 1-West 16 St. b/t Surf Ave. and Hart Pl. 2-Surf Ave b/t West 12 St. and West 17 St. 3-Mermaid Ave b/t W 16 St. and Stillwell Ave. 4.-Neptune Ave b/t W 17 St. and Stillwell Ave. 5- Hart Pl. b/t Cropsey Ave and W 15 St. Sanitary Sewer 1-West 16 St. b/t Surf Ave and Mermaid Ave. 2-West 16 St. b/t Mermaid Ave. and Hart Pl (both East and West side of W 16 St) 3-Surf Ave b/t West 12 St. and West 17 St. (both north and south side of Surf Ave) 4-Mermaid Ave b/t W 17 St. and Stillwell Ave. 5.-Neptune Ave b/t W 17 St. and W 15 St. (both north and south side of Neptune Ave) 6- Hart Pl. b/t W 16 St. and W 15 St. (North Side) 7.-Hart Pl. b/t Cropsey Ave and W 16 St.(both north and south sides) Watermain (WM-6) 1-Neptune Ave b/t Stillwell Ave. and W 17 St. 2- Surf Ave b/t W 17 St and W 12 St Water Main (WM-1) 1-Neptune Ave b/t Stillwell Ave. and W 17 St. 2-Mermaid Ave b/t Stillwell Ave. and W 17 St. 3- Surf Ave b/t W 17 St and Stillwell Ave (north and south sides of the strret) 4- Hart Pl. b/t W 16 St. and W 15 St. 5 - W 16 St b/t Surf Ave & Hart Pl. | Reconstruction of Storm and Sanitary sewer, Trunk and distribution water main in Coney Island area - Phase 3A, Borough of Brooklyn | Brooklyn |  | Environmental Protection | Compliance | Sewer | Standard | Requirements TO | Standard Consultant | PIMS | FALSE |  | 2015 | 2018 |  | DDC
CONISPH3B | CONISPH3B | Y | Infrastructure | BROOKLYN | STM, SAN SEWERS & WM IN CONEY ISLAND AREA-PH3B, BK | Reconstruction of Storm and Sanitary sewer, Trunk and distribution water main in Coney Island area - Phase 3B, Borough of Brooklyn STORM SEWER IN: ----------------------------- 1. W17 St b/t Surf Ave and Neptune Ave, 2. Cropsey Ave b/t Neptune Ave and Hart Pl 3. W19 St b/t Surf Ave and Neptune Ave 4. W20 St b/t Surf Ave and Neptune Ave 5. W24 St b/t Surf Ave and Mermaid Ave 6. Neptune Ave b/t Cropsey Ave and W21 St 7. Mermaid Ave b/t W16 St and W21 St (revised sketch received on 3/27/13) 8. Surf Ave b/t W17 St and W22 St (both North and South side) 9. Surf Ave b/t W22 St and W24 St (north side) together with all work incidental thereto. SANITARY SEWER IN ---------------------------------- 1. Cropsey Ave b/t Neptune Ave and Hart Pl (both east and west side) 2. W17 St b/t Mermaid Ave and Neptune Ave (both east and west side) 3. W17 St b/t Mermaid Ave and Surf Ave 4. W19 St b/t Surf Ave and Neptune Ave 5. W20 St b/t Neptune Ave and Mermaid Ave (both east and west side) 6. W20 St b/t Mermaid Ave and Surf Ave 7. W24 St b/t Surf Ave and Mermaid Ave 8. Neptune Ave b/t Cropsey Ave and W24 St (both north and south side) 9. Neptune Ave b/t W20 St and W21 St 10. Mermaid Ave b/t W17 St and W21 St 11. Surf Ave b/t W17 St and W24 St (both north and south side) together with incidental thereto. WATER MAIN (WM-6) --------------------------------- 1. Neptune Ave b/t Cropsey Ave and W21 St 2. Surf Ave b/t W17 St and W24 St, together with all work incidental thereto. WATER MAIN (WM-1) ------------------------------- 1. Neptune Ave b/t Cropsey Ave and W21 St 2. Mermaid Ave b/t W17 St and W21 St 3. Surf Ave b/t W17 St and W24 St 4. W17 St b/t Neptune Ave and Surf Ave 5. W19 St b/t Neptune Ave and Surf Ave 6. W20 St b/t Neptune Ave and Surf Ave 7. W24 St b/t Mermaid Ave and Surf Ave 8. Cropsey Ave b/t Neptune Ave and Hart Pl Together with all work incidental thereto. | Reconstruction of Storm and Sanitary sewer, Trunk and distribution water main in Coney Island area - Phase 3B, Borough of Brooklyn | Brooklyn |  | Environmental Protection | Cancelled Project | Sewer | Standard | In-House | Standard Consultant | PIMS | FALSE |  | 2015 | 2017 |  | DDC
PW311GENV | PW311GENV | N | Safety and Site Support | HAZMAT | Geotechnical & Environmental Service Contract
CS-ER-WCP | CS-ER-WCP | Y | Infrastructure | BRONX & N. QUEENS | PUGSLEY CREEK RELIEF SEWER / REPAIR OF EXISTING WM | Pugsley Creek Relief Sewer and Repair of Existing Combined Trunk, with Water Main work, Borough of the Bronx. | Pugsley Creek Relief Sewer and Repair of Existing Combined Trunk, with Water Main work, Borough of the Bronx | Bronx |  | Environmental Protection | Construction 0-25% | Sewer | Standard | In-House | Standard Consultant | PIMS | FALSE |  |  | 2017 |  | DDC
CS-FB-LLD | CS-FB-LLD | Y | Infrastructure | BRONX & N. QUEENS | FLUSHING BAY LOW LYING DIVERSION SEWER | Sanitary Sewer Replacement in Berrian Blvd. and 19th Avenue between 43rd Street and 45th Street. New 48" Venturi meter installation on Steinway Street between 19th Avenue and Berrian Blvd. | Sanitary Sewer Replacement in Berrian Blvd. and 19th Avenue between 43rd Street and 45th Street and new 48" Venturi meter installation on Steinway Street between 19th Avenue and Berrian Blvd. | Queens |  | Environmental Protection | Substantial Completion | Sewer | Standard | In-House | DDC Managed | PIMS | FALSE |  | 2014 | 2015 |  | DDC
CT2-INTER | CT2-INTER | Y | Infrastructure | BROOKLYN | INSTALL. OF NEW TRUNK MAIN, VALVES & APPURT. @16A | INSTALLATION OF NEW TRUNK MAIN, VALVES & APPURTENANCES IN SHAFT 16A, BK | INSTALLATION OF NEW TRUNK MAIN, VALVES & APPURTENANCES IN SHAFT 16A, BROOKLYN. | Brooklyn |  | Environmental Protection | Final Design | Water | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2016 | 2018 |  | DDC
DDC7PSAC2 | DDC7PSAC2 | Y | Public Buildings | Executive | PUBLIC SAFETY ANSWERING CENTER II | Revised 12/08: New construction of a 500,000 square foot building to house 911 call taking and dispatch and related administrative functions. Building height reduced to 260' triggering need for a radio tower. Client agencies remain NYPD, FDNY, and DOITT. New construction of 700,000 square foot building with redundent MEP systems that will house 911 call taking and dispatch as well as command operations for NYPD and FDNY. Client agencies are: NYPD, FDNY and DoITT. | New construction of 400,000 square foot building that will house 911 call taking and dispatch as well as command operations for NYPD and FDNY. Client agencies are: NYPD, FDNY and DoITT. |  |  | Police | Completed Project | New Construction | Mayoral Initiative | Requirements TO | CM-Build | PIMS | FALSE |  |  |  |  | DDC
DOIT1CNET | DOIT1CNET | Y | Public Buildings | HUMAN SERVICES | CitNet Upgrade Queens | DOITT - CityNet Upgrade |  | Citywide |  |  | Completed Project | Other | Standard | None | DDC Managed | PIMS | TRUE |  |  |  |  | DDC
DOIT1CQN | DOIT1CNET | Y | Public Buildings | HUMAN SERVICES | CItyNet Upgrade Queens | Install new air conditioning including the exterior condensor unit | Installation of A/C units for Queens Doitt office | Queens |  | DCAS | Maintenance | Upgrade | Standard | Standard Consultant | Requirements TO | PIMS | TRUE |  |  |  |  | DDC
DOIT1CQN | DOIT1CQN | Y | Public Buildings | HUMAN SERVICES | CItyNet Upgrade Queens | Install new air conditioning including the exterior condensor unit | Installation of A/C units for Queens Doitt office | Queens |  | DCAS | Maintenance | Upgrade | Standard | Standard Consultant | Requirements TO | PIMS | TRUE |  |  |  |  | DDC
DOTSEQ01 | DOTSEQ01 | Y | Infrastructure | S. QUEENS | SOUTHEAST QUEENS - DOT PRIORITY GRIDS 1 | PROJECT DOTSEQ01 (SECONDARY ID IS SEQPGRD1) SEP IS A SEQ JOINT PROGRAM BETWEEN THE DOT AND DEP TO IMPROVE DRAINAGE CONDITIONS. SCOPE OF WORK UNDER THIS ID AND THE SECONDARY ID WILL INCLUDE STREET RESURFACING, GRADE ADJUSTMENT, STREET RECON, AND/OR NEW SIDWALKS AND CURB RECON. ALSO, INSTALLATION OF NEW STORM SEWERS AND WATER MAINS. |  |  |  | Environmental Protection | Pre-Design/PrgDevelopment | Sewer | Mayoral Initiative | Requirements TO |  | Project Info | FALSE |  |  |  | 2017-11-27 13:00:24.5500000 +00:00
PW311S01B | PW311S01B | N | Safety and Site Support | Site Engineering | Geotechnical
PW311S01D | PW311S01D | N | Safety and Site Support | Site Engineering | SUBSURFACE BORINGS
PW311S01E | PW311S01E | N | Safety and Site Support | Site Engineering | SUBSURFACE BORINGS BROOKLYN & QUEENS
PW311S01F | PW311S01F | N | Safety and Site Support | Site Engineering | GEOTECHNICAL
DOTSEQ02 | DOTSEQ02 | Y | Infrastructure | S. QUEENS | SOUTHEAST QUEENS - DOT PRIORITY GRIDS 2 | PROJECT DOTSEQ02 (SECONDARY ID IS SEQPGRD2) SEP IS A SEQ JOINT PROGRAM BETWEEN THE DOT AND DEP TO IMPROVE DRAINAGE CONDITIONS. SCOPE OF WORK UNDER THIS ID AND THE SECONDARY ID WILL INCLUDE STREET RESURFACING, GRADE ADJUSTMENT, STREET RECON, AND/OR NEW SIDWALKS AND CURB RECON. ALSO, INSTALLATION OF NEW STORM SEWERS AND WATER MAINS. |  |  |  | Environmental Protection | Pre-Design/PrgDevelopment | Sewer | Mayoral Initiative | Requirements TO |  | Project Info | FALSE |  |  |  | 2017-11-27 13:00:25.7500000 +00:00
E12-0023 | E12-0023 | Y | Public Buildings | ONENYC | DCA;BPL: Brooklyn Museum; Brooklyn Central Library | To implement a building-wide energy efficiency retrofit of the Brooklyn Central Library (Brooklyn Musuem was deleted from scope at end of DD phase by Client). The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming systems by improving energy performance and allowing for more efficient building operation. | Brooklyn Public Library Central Library Implementation of HVAC and electrical energy efficiency measures. | Brooklyn |  | DCAS | Construction 75%-Subst. | Upgrade | Standard | Requirement Contract | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E12-0024 | E12-0024 | Y | Public Buildings | ONENYC | DPR: Roy Wilkins,Brwnsvll, Chels Ctrs, - EE Upgrad | The purpose of this project is to implement a building-wide energy efficiency retrofit of the Roy Wilkins and Brownsville Recreation Centers. Chelsea Recreation Center was eliminated from scope by DCAS at Final Design phase. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. | DPR Roy Wilkins and Brownsville Recreation Centers Implementation of energy efficient lighting retrofit. | Queens |  | DCAS | Maintenance | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E12-0031 | E12-0031 | Y | Public Buildings | ONENYC | Bx Conc Plza: Bergen, hsg ct marc judic ctr, - EE | To implement a building-wide energy efficiency retrofit of the Bronx Concourse Plaza, Bergen Building, Bronx Housing Court, and Mark A. Constantino Judicial Center. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming systems by improving energy performance and allowing for more efficient building operation. | Bronx Concourse Plaza, Bronx Housing Court, and Mark A. Constantino Judicial Center implementation of HVAC and Electrical energy efficiency upgrades. | Staten Is. |  | DCAS | Maintenance | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E12-0035 | E12-0035 | Y | Public Buildings | ONENYC | Manhattan Deten. GRVC and Otis Bantum Correc Fac- | The purpose of this project is to implement a building-wide energy efficiency retrofit of the Manhattan Detention Center, George R. Vierno Center (GRVC), and the Otis Bantum Correctional Facility. The design, construction and commissioing of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. | Implement a building-wide energy efficiency retrofit of electrical and HVAC systems. | Manhattan |  | DCAS | Construction 50-75% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
PW311S03C | PW311S03C | N | Safety and Site Support | HAZMAT | Deep Borings Citywide
PW311S04A | PW311S04A | N | Safety and Site Support | HAZMAT | Ground Penetrating Radar Services, Citywide
PW311S06A | PW311S06A | N | Safety and Site Support | HAZMAT | SERVICE CONTRACTS FOR GEOTECHNICAL INVESTIGATIONS
PW311S07B | PW311S07B | N | Safety and Site Support | HAZMAT | Marine Borings Citywide
PW311S08A | PW311S08A | N | Safety and Site Support | HAZMAT | Geotechnical Investigations Citywide
PW311S08D | PW311S08D | N | Safety and Site Support | HAZMAT | Subsurface Borings Manhattan, Bronx & Staten Islan
E12-0037 | E12-0037 | Y | Public Buildings | ONENYC | Queens West Cent Repair Shop: Fr.Kills, BK W11G- E | The purpose of this project is to implement a building-wide energy efficiency retrofit of the Queens West Central Repair Shop, Fresh Kills Landfill SI 3 District Garage, and the Brooklyn W11G. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. | Energy Efficiency project at three DSNY sites: Queens West Central Repair Shop, Fresh Kills Landfill SI 3 District Garage, and the Brooklyn W11G. | Brooklyn |  | DCAS | Construction 50-75% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E12-0043 | E12-0043 | Y | Public Buildings | ONENYC | NYPD 84th Precinct & BK N Narc Div, Bklyn - EE Upg | PROJECT IS NOW SPLIT INTO TWO "PROJECT INFO" IDs. 84TH PRECINCT IS NOW E12-0043A. B.N.N.D. WILL REMAIN E12-0043. The purpose of this project is to implement a building-wide energy efficiency retrofit of the NYPD 84th Precinct and Bklyn North Narcotics Division. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. | Implementation of energy efficient lighting retrofit at NYPD Brooklyn North Narcotics. Canceled. | Brooklyn |  | DCAS | Cancelled Project | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E12-0043A | E12-0043 | Y | Public Buildings | ONENYC | NYPD 84th Precinct - EE Upgrade | NYPD 84th Precinct and FDNY Engine Co.207 Implementation of HVAC upgrade | NYPD 84th Precinct and FDNY Engine Co.207 Implementation of HVAC upgrade. | Unknown |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | TRUE |  |  |  |  | DDC
E12-0043A | E12-0043A | Y | Public Buildings | ONENYC | NYPD 84th Precinct - EE Upgrade | NYPD 84th Precinct and FDNY Engine Co.207 Implementation of HVAC upgrade | NYPD 84th Precinct and FDNY Engine Co.207 Implementation of HVAC upgrade. | Unknown |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | TRUE |  |  |  |  | DDC
E12-0043B | E12-0043 | Y | Public Buildings | ONENYC | NYPD 84th Precinct - EE Upgrade | NYPD 84th Precinct - EE Upgrade |  | Brooklyn |  | Police | Construction Procurement | Upgrade | Standard | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
E14-0001 | E14-0001 | Y | Public Buildings | ONENYC | NYPD-FDNY - Energy Conservation at 67Pct EC248 | This site is 1 of 6 sites combined to create one project with estimated construction cost of $4.6M. The scope of this project is to implement a building-wide energy efficiency retrofit of the 67th Precinct and Engine Company 248, 2820 Snyder Avenue, Brooklyn, NY 11226. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy consuming equipment systems by improving energy performance and allowing for more efficient building operation. | The purpose of this project is to implement HVAC and Electrical energy efficiency upgrades at the NYPD 67th Precinct and FDNY Engine Company 248. | Brooklyn |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0003 | E14-0003 | Y | Public Buildings | ONENYC | DCAS - Energy Conserv. at Bx Family & Criminal Ct. | This site is 1 of 4 sites combined to create one project with estimated construction cost of $5.3M. Scope: To implement a building-wide energy efficiency retrofit of the Bronx Family and Criminal Court at 215 East 161St Street, Bronx, NY 10451. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation. | Energy Conservation Measures at the Bronx Family & Criminal Court. | Unknown |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0006 | E14-0006 | Y | Public Buildings | ONENYC | DCAS - Energy Conservation at Manh. Health Bldg. | This site is 2 of 4 sites combined to create one project with estimated construction cost of $5.3M Scope: To implement a building-wide energy efficiency retrofit of the 125 Worth Street, NY, NY, 10013. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation. | Manhattan Health Building project to implement HVAC and Electrical energy efficiency upgrades. | Unknown |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0007 | E14-0007 | Y | Public Buildings | ONENYC | DCAS - Enery Conservation at LIC Courthouse | This site is 1 of 3 sites combined to create one project with estimated construction cost of $3M. The purpose of this project is to implement a building-wide energy efficiency retrofit of the Long Island City Courthouse. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. | Long Island City Courthouse implementation of a building-wide energy efficiency retrofit. | Queens |  | DCAS | Cancelled Project | Upgrade | Mayoral In | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0008 | E14-0008 | Y | Public Buildings | ONENYC | DCAS - Energy Conservation at Manhattan Supreme Ct | The purpose of this project is to implement a building-wide energy efficiency retrofit of theManhattan Supreme Court. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. | Manhattan Supreme Court implementation of a building-wide energy efficiency retrofit. | Unknown |  | DCAS | Construction 0-25% | Upgrade | Standard | Individual Contract(s) | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0010 | E14-0010 | Y | Public Buildings | ONENYC | DCAS - Energy Conservation at Queens Supreme Ct. | This site is 3 of 4 sites combined to create one project with estimated construction cost of $5.3M Scope: The purpose of this project is to implement a building-wide energy efficiency retrofit of the Queens Supreme Court at 88-11 Sutphin Boulevard, Jamaica, NY 11435. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation | Implement a building-wide energy efficiency retrofit of electrical and HVAC systems. | Unknown |  | DCAS | Cancelled Project | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0011 | E14-0011 | Y | Public Buildings | ONENYC | DCAS - Energy Conservation at SI BOROUGH HALL | This site is 4 of 4 sites combined to create one project with estimated construction cost of $5.3M Scope: The purpose of this project is to implement a building-wide energy efficiency retrofit of the 10 Richmond Terrace, Staten Island, NY 10301. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation. | Scope: The purpose of this project is to implement a building-wide energy efficiency retrofit of the 10 Richmond Terrace, Staten Island, NY 10301. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation. | Unknown |  | DCAS | Construction Procurement | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
E14-0012 | E14-0012 | Y | Public Buildings | ONENYC | DCAS - Energy Conservation at Manh. Sun Building | This site is 3 of 3 sites combined to create one project with estimated construction cost of $3M. The purpose of this project is to implement a building-wide energy efficiency retrofit of the Sun Building. The design, construction and commissioning of the energy conservation measures ECMs consist of work on the Electrical and HVAC systems. | Sun Building implementation of a building-wide energy efficiency retrofit. | Unknown |  | DCAS | Construction 0-25% | Upgrade | Standard | Individual Contract(s) | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0016 | E14-0016 | Y | Public Buildings | ONENYC | DHS - Energy Conserv at Atlantic Ave Men's Shelter | This site is 2 of 6 sites combined to create one project with estimated construction cost of $4.6M. To scope of this project is to implement a building-wide energy efficiency retrofit of the Atlantic Men’s Shelter, 1322 Bedford Avenue, Brooklyn, NY 11216. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation. | The purpose of this project is to implement HVAC and Electrical energy efficiency upgrades at the DHS Atlantic Men’s Shelter. | Brooklyn |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0017 | E14-0017 | Y | Public Buildings | ONENYC | DHS - Energy Conserv. at Bellevue Men's Shelter | This site is 3 of 6 sites combined to create one project with estimated construction cost of $4.6M. The scope of this project is to implement a building-wide energy efficiency retrofit of the Bellevue Men’s Shelter, located at 400 East 30th Street in New York, NY 10016. The energy conservation measures (ECMs) to be designed, installed, and commissioned comprise improvements of the electrical system and HVAC system, along with the installation of energy meters and data-gathering equipment to ensure the correct operation of the other improvements. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation. | The purpose of this project is to implement HVAC and Electrical energy efficiency upgrades at the DHS Bellevue Men’s Shelter. | Manhattan |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0018 | E14-0018 | Y | Public Buildings | ONENYC | DHS - Energy Conserv at Ft Wash Armory Shelter | This site is 4 of 6 sites combined to create one project with estimated construction cost of $4.6M. The scope of this project is to implement a building-wide energy efficiency retrofit of the Fort Washington Armory Shelter located at 216 Fort Washington Avenue, New York, NY 10032. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation. | The purpose of this project is to implement HVAC and Electrical energy efficiency upgrades at the DHS Fort Washington Armory Shelter. | Manhattan |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
PW311S11A | PW311S11A | N | Safety and Site Support | HAZMAT | Geotechnical Engineering Services, Citywide
PW311S11B | PW311S11B | N | Safety and Site Support | HAZMAT | Marine Borings Citywide
PW311S11D | PW311S11D | N | Safety and Site Support | HAZMAT | Subsurface Borings, Manhattan, Bronx, Staten Islan
PW311S11E | PW311S11E | N | Safety and Site Support | HAZMAT | Subsurface Borings Brooklyn & Queens
PW311S14A | PW311S14A | N | Safety and Site Support | HAZMAT | Geotechnical Service Contract
E14-0019 | E14-0019 | Y | Public Buildings | ONENYC | DHS - Energy Conserv. at Franklin Women's Shelter | This site is 5 of 6 sites combined to create one project with estimated construction cost of $4.6M. The scope of this project is to implement a building-wide energy efficiency retrofit of the Franklin Women’s Shelter, 1122 Franklin Avenue, Bronx, NY 10456. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation. | The purpose of this project is to implement HVAC and Electrical energy efficiency upgrades at the DHS Franklin Women’s Shelter. | Bronx |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0020 | E14-0020 | Y | Public Buildings | ONENYC | DHS - Energy Conservation at Regent Hotel Shelter | This site is 2 of 6 sites combined to create one project with estimated construction cost of $4.6M. The scope of this project is to implement a building-wide energy efficiency retrofit of the Regent Hotel Shelter, 2720 Broadway, New York, NY 10025. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. These ECMs will increase the fitness of energy-consuming equipment systems by improving energy performance and allowing for more efficient building operation. | The purpose of this project is to implement HVAC and Electrical energy efficiency upgrades at the DHS Regent Hotel Shelter. | Manhattan |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E14-0060 | E14-0060 | Y | Public Buildings | ONENYC | OEM - Energy Conservation at OEM Headquarters | This site is 4 of 4 sites combined to create one project with estimated construction cost of $10.6M. The purpose of this project is to implement a building-wide energy efficiency retrofit of the OEM Building. The design, construction and commissioning of the energy conservation measures (ECMs) consist of work on the Electrical and HVAC systems. | OEM Building implementation of a building-wide HVAC energy efficiency retrofit. | Unknown |  | DCAS | Construction 0-25% | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E16-0002 | E16-0002 | Y | Public Buildings | ONENYC | Queens Civil Court: 8917 Sutphin Blvd. Lighting & | Energy efficiency upgrades at Queens Civil Court. Upgrades will include work on HVAC and Electrical systems. | Energy efficiency upgrades at Queens County Civil Court. Upgrades will include work on HVAC and Electrical systems. | Queens |  | DCAS | Schematic Design | Upgrade | Standard | Requirements TO |  | PIMS | FALSE |  |  |  |  | DDC
E16-0003 | E16-0003 | Y | Public Buildings | ONENYC | Manhattan Civil CRT: 111 Centre ST.HVAC Upgrade | Manhattan Civil Court Comprehensive Energy Efficiency HVAC upgrade | Energy Efficiency Upgrade at Manhattan Civil Court for HVAC and Electrical upgrade | Manhattan |  | DCAS | Schematic Design | Upgrade | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
E16-0004 | E16-0004 | Y | Public Buildings | ONENYC | Queens 7 District Garage: 3019 122nd HVAC Upgrade | Queens 7 District Garage Annex Lighting & HVAC Energy Efficiency Upgrades | DSNY Queens District 7 Garage Annex implementation of Energy Efficiency Measures | Queens |  | DCAS | Design Development | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
E16-0005 | E16-0005 | Y | Public Buildings | ONENYC | Manhattan 3 District Garage: South ST. Pier 36 Hva | Manhattan 3 District Garage Lighting & HVAC Energy Efficiency Upgrades | Energy Efficiency Measures at Manhattan District 3 Garage | Manhattan |  | DCAS | Schematic Design | Upgrade | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
PW311S97C |  | N | Safety and Site Support |  | Deep Land Borings at various sites within the City |  |  |  |  | Unknown
PW311S97D |  | N | Safety and Site Support |  | Borings in Manhattan, The Bronx and Staten Island |  |  |  |  | Unknown
E16-0012 | E16-0012 | Y | Public Buildings | PASS THROUGH | Brooklyn Museum: 1000 washington ave. Bklyn | This project will address energy use by either upgrading or replacing air conditioning equipment and controls. It will complement other work completed in the Museum’s Master Plan for Climate Control – a multi-year capital effort to bring air conditioning and/or humidification to spaces requiring them in a 21st century museum. There is no significant relationship to previous City-funded HVAC related work. The three air handlers to be replaced in this project are 38 years old and have reached the end of their life span. All the other proposed ECM work improves the performance of HVAC systems that are already in place. |  | Unknown |  | DCAS |  | Upgrade |  |  |  | PIMS | FALSE |  |  |  |  | DDC
E17-0001 | E17-0001 | Y | Public Buildings | ONENYC | Louis Lefkowitz Building Energy Efficiency Upgrade | Lighting upgrade, occupancy sensors, DCV, thermostatic radiator valves, and condensate heat recovery Energy Efficiency project to improve building performance and reduce energy consumption and greenhouse gas. |  | Unknown |  | DCAS | Pre-Design/PrgDevelopment | Upgrade | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
E17-0002 | E17-0002 | Y | Public Buildings | ONENYC | Manhattan Family Court Energy Efficiency Upgrades | Lighting upgrade, occupancy sensors, BMS, VFDs installation, DCV, and condensate heat recovery |  | Unknown |  | DCAS | Pre-Design/PrgDevelopment | Upgrade | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
E17-0005 | E17-0005 | Y | Public Buildings | ONENYC | BRONX 12 DISTRICT GARAGE | Lighting and controls upgrade, solar PV installation, battery storage, premium efficiency motors, HVAC controls and geothermal heat pumps. |  | Bronx |  | DCAS | Cancelled Project | Upgrade | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
E17-0006 | E17-0006 | Y | Public Buildings | ONENYC | BROOKLYN NORTH 1 & 4 DISTRICT GARAGES | Lighting and controls upgrade, solar PV installation, battery storage, new BMS, demand controlled ventilation, HVAC controls and geothermal heat pumps. |  | Brooklyn |  | DCAS | Scope Development | Upgrade | Standard | Design Excellence/24 |  | PIMS | FALSE |  |  |  |  | DDC
EP06-REM | EP06-REM | Y | Public Buildings | Courts | DEP Remsen Avenue Yard Reconstruction | New offices, locker rooms, shops and storage including indoor vehicle storage for the Bureau of Water and Sewer Operations, Department of Environmental Protection. | New offices, locker rooms, workshops and storage for the Department of Environmental Protection. |  |  | Environmental Protection | Acceptance/Final Completion | New Construction | Standard | Standard Consultant | CM-Build | PIMS | FALSE |  |  |  |  | DDC
EP16-CLOVE | EP16-CLOVE | Y | Public Buildings | DEP | Clove Road:Demolition/Construction of new Facility | The prime objective for the Capital Project Scope Development (CPSD) exercise is to determine the scope of work and budget necessary to allow the redevelopment of the site at 288 Clove Road in Staten Island to accommodate the Staten Island Sewer Maintenance Unit, Staten Island Repair Unit and Staten Island Water Maintenance Unit under the Department of Environmental Protection (DEP). | The prime objective for the Capital Project Scope Development (CPSD) exercise is to determine the scope of work and budget necessary to allow the redevelopment of the site at 288 Clove Road in Staten Island to accommodate the Staten Island Sewer Maintenance Unit, Staten Island Repair Unit and Staten Island Water Maintenance Unit under the Department of Environmental Protection (DEP). | Staten Is. |  | Environmental Protection | Design | Feasibility Study | Standard | Requirement Contract |  | PIMS | FALSE |  |  |  |  | DDC
PW311T01C | PW311S01C | N | Safety and Site Support | Site Engineering | LAND SURVEYS BROOKLYN
PW311T01C | PW311T01C | N | Safety and Site Support | Site Engineering | LAND SURVEYS BROOKLYN
PW311T01D | PW311T01D | N | Safety and Site Support | Site Engineering | LAND SURVEYS MANHATTAN
PW311T01E | PW311T01E | N | Safety and Site Support | Site Engineering | LAND SURVEYS QUEENS
EP6-KENTD | EP6-KENT2 | Y | Public Buildings | DEP | DESIGN Rehab and Upgrade DEP Shaft Maint Build | The project will provide for selective renovations of DEP's Kent Avenue Facility, under a multi-phase design program, within a $12 million construction budget. The 100 year old structure, which is located at 356 Flushing Avenue in Brooklyn, presently serves as DEP’s base for shaft and deep water supply tunnels maintaince crews and vehicles. Also know as the Shaft Maintenance Building, the floor area gross117,576 square feet, sitting on a city block measuring 187’ x 169’. Existing functions includes storage for parts and equipment, machine shop and garage, locker room and showers, and administrative offices and archive. Upgrade will include code egress and ADA, new female workers locker room, central heating, garage ventilation, full sprinklering, archival quality mechanical and fire suppression, passenger and freight elevator, waterproofing and stabilizing of the building’s envelope, extensive plumbing upgrades, and interior lighting replacement. The design program will also consider LEED and historic preservation. | Perform a full functional upgrade of the interior and exterior of this century old structure, providing all new building systems. The design will include ADA compliance, and LEED and historic preservation standards. | Brooklyn |  | Environmental Protection | Construction 75%-Subst. | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
F1755C099 | F1755CO99 | Y | Public Buildings | Fire | FDNY's Five Communications offices | Upgrading Fire Dispatch facilities at each borough. 1-35 Empire Blvd, Bklyn 2-Manhattan @ Transverse Rd. (79St.) 3-1129 East 180 th St., Bronx 4-65 Slosson Ave, Staten Island 5-83-98 Woodhaven Blvd, Queens | Upgrade fire dispatch facilities in all five boroughs. |  |  | Fire | Maintenance | Renovation | Critical | Standard Consultant | CM-Build | PIMS | FALSE |  |  |  |  | DDC
F175COMP6-1 | F175COMP6 | Y | Public Buildings | Fire | Renovation and expansion of Engine company 309 | Apparatus floor replacement and new addition to EC 309 | Replace apparatus floor, renovate the kitchen and upgrade the electrical system at Engine Company 309. |  |  | Fire | Maintenance | Renovation | Standard | Requirements TO | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
F175EC293A | F175EC293 | Y | Public Buildings | FIRE | GUT REHAB OF EC 293 | Complete rehabilitation of Engine Company 293 with a third floor addition to an existing 2-story building. | Complete rehabilitation of Engine Company 293 with a third floor addition to an existing 2-story building. | Queens |  | Fire | Construction 50-75% | Renovation | Standard | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
F175EC63 | F175EC63 | Y | Public Buildings | Fire | Renovation and expansion of EC63 | Renovation and expansion of existing Fire House. | Renovate and expand existing facility. |  |  | Fire | Completed Project | Renovation | Critical | Requirements TO | DDC Managed | PIMS | FALSE
F175GREEN | F175GREEN | Y | Public Buildings | Fire | New Greenpoint EMS station 35 | Demolition of existing building; design and construction of a new facility for Greenpoint EMS station. | Design and construction of new EMS facility; demolish existing building on site. |  |  | Fire | Maintenance | New Construction | Critical | Requirements TO | CM-Managed | PIMS | FALSE
F175LC8 | F175LC8 | Y | Public Buildings | Fire | Mini Gut Renovation at Ladder Company 8 | Mini gut renovation at LC 8. Manhattan | Renovate fire house facility. |  |  | Fire | Construction 75%-Subst. | Renovation | Standard | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
F175MCE23 | F175MCE23 | Y | Public Buildings | FIRE | FDNY Engine Company 23 Renovation | Major kitchen, toliet and complete HVAC upgrade in occupied fire house. | Multi-component Renovation: Major kitchen, toilet and complete HVAC upgrade; and Façade repair. | Manhattan |  | Fire | Construction 0-25% | Renovation | Standard | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
F175QUEEN1B | F175QUEEN | Y | Public Buildings | Fire | New Queens Hospital EMS Station 50 | New Ambulance Station to be constructed as part of a rapid response network for the FDNY Emergency Medical Service. | Build new EMS station as part of an FDNY rapid response network. |  |  | Fire | Completed Project | New Construction | Critical | Requirements TO | CM-Managed | Project Info | FALSE |  |  |  |  | DDC
F175RES2 | F175RES2 | Y | Public Buildings | FIRE | New Firehouse for Rescue 2 | New construction of a replacement facility @ 20,000 SF for current antiquated Rescue 2 Firehouse, with capability for training on-site. 3000 SF of the parking space in plan. Located in Crown Heights/Weeksville section of Brooklyn at 1815 Sterling Place off Eastern Parkway. | The Stair and Elevator towers are being completed. The CMU walls in Cellar under construction. Placing rebars to Pour concrete to stairs at lower level. Backfilling along perimeter of building foundation walls.Electrical roughing in cellar. Removal of braces in cellar. Installation of door frames in cellar. All Precast panel walls, precast beams, precast slabs have been installed. | Brooklyn |  | Fire | Construction 50-75% | New Construction | Standard | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
F175SOUND | F175SOUND | Y | Public Buildings | Fire | Construction of a new EMS 3 station at Zerega Ave | Construction of a new 11,461 SF Zerega EMS Station 3 for the FDNY in the Soundview section of Bronx. | A new 13,500 square foot EMS Station on Zerega Avenue, in the Bronx, for the FDNY. |  |  | Fire | Completed Project | New Construction | Critical | Requirements TO | CM-Managed | PIMS | FALSE
FD175273H | FD175273H | Y | Public Buildings | Fire | Installation of New HVAC system at EC273 | HVAC system upgrade on the first and the second floors in an occupied Fire house | Upgrade HVAC system. |  |  | Fire | Completed Project | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE
FORTWSH2 | FORTWSH2 | Y | Public Buildings | Pass Through | Renovation of Fort Washington Armory | The project will consist of key components, such as Air Conditioning of the Track, resurfacing of the running track, and an Audio/ Visual system. Other smaller components of the project include a Donor Wall, Track & Field/Museum Store, a Ticketing System and installation of a new Elevator. |  |  |  | Homeless Services | Substantial Completion | Renovation | Standard |  | Pass Through | PIMS | FALSE |  |  |  |  | DDC
FRTWASH2 | FORTWASH | Y | Public Buildings | Pass Through | Fort Washington Track & Field Hall 2 | Renovation of a portion of the Ft. Washington Armory Building into a Museum for the National Track and Field Hall of Fame, including exhibit space, accessibility and orientation film viewing auditorium. The scope of the first phase was general construction. The second phase will provide for the exhibit cabinetwork and large video display screen above track. The Armory Foundation has previously rehabilitated the exterior and provided the nation's largest indoor track. | Phase 2: Exhibitry and large Video screen. |  |  | Homeless Services | Substantial Completion | Renovation | Standard |  | Pass Through | PIMS | FALSE
GCHP24-01 | GCHP24-01 | Y | Infrastructure | BRONX & N. QUEENS | GREEN INFRASTRUCTURE IN HUTCHINSON RIVER AREA-PH I | Green Infrastructure in Hutchinson River Area, Phase-I | Green Infrastructure in Hutchinson River Area, Phase-I | Bronx |  | Environmental Protection | Substantial Completion | Other | Standard | In-House/Consultant | DDC Managed | PIMS | FALSE |  |  | 2015 |  | DDC
GCHP24-02 | GCHP24-02 | Y | Infrastructure | BRONX & N. QUEENS | GREEN INFRASTRUCTURE IN HUTCHINSON RIVER AREA-PH 2 | Green Infrastructure in Hutchinson River Area, Phase-I | Green Infrastructure in Hutchinson River Area (Sidewalk Permeable Pavers Pilot locations ) | Bronx |  | Environmental Protection | Construction Procurement | Other | Standard | Requirements TO | DDC Managed/Consultant | PIMS | FALSE |  | 2015 |  |  | DDC
PW311T04B | PW311T04B | N | Safety and Site Support | Site Engineering | Topographical Surveys Staten Island
PW311T04C | PW311T04C | N | Safety and Site Support | Site Engineering | Topographical Surveys Brooklyn
GCJA03-3A | GCJA03-3A | Y | Infrastructure | BRONX & N. QUEENS | GI - Cons of ROW Bioswales & Stormwater GS in JAM- | GI - Cons of ROW Bioswales & Stormwater GS in JAM-003, 3A | Construction of ROW Green Infrastructure in CSO Tributary Area JAM-003 and JAM-003A |  |  | Environmental Protection | Final Design | New Construction | Standard | Requirements TO | DDC Managed | Project Info | FALSE |  |  |  | 2017-12-14 07:00:20.8300000 +00:00
GCJAM-01 | GCJAM-01 | Y | Infrastructure | S. QUEENS | GI IN THE JAM-003/006 CSO PH 1 TRIBUTARY AREA, ST1 | GREEN INFRASTRUCTURE IN THE JAM-003/006 CSO PHASE 1 TRIBUTARY AREA, STAGE 1, QNS | CONSTRUCTION OF RIGHT-OF-WAY GREEN INFRASTRUCTURE IN THE CSO TRIBUTARY AREAS, STAGE 1, BOROUGH OF QUEENS. | Queens |  | Environmental Protection | Construction 25-50% | Other | Critical | In-House | DDC Managed | PIMS | FALSE |  | 2015 | 2016 |  | DDC
GCNC77-01 | GCNC77-01 | Y | Infrastructure | S. QUEENS | GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA - PH 1 | GREEN INFRASTRUCTURE -NEWTOWN CREEK | GREEN INFRASTRUCTURE -NEWTOWN CREEK | Queens |  | Environmental Protection | Completed Project | Other | Standard | Requirements TO | DDC Managed Consultant | PIMS | FALSE |  | 2014 | 2015 |  | DDC
GCNC77-02 | GCNC77-02 | Y | Infrastructure | BRONX & N. QUEENS | GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA - PH 2 | GREEN INFRASTRUCTURE -NEWTOWN CREEK | GREEN INFRASTRUCTURE IN NEWTOWN CREEK AREA - PHASE 2 | Queens |  | Environmental Protection | Completed Project | Other | Standard | Requirements TO | DDC Managed Consultant | PIMS | FALSE |  | 2014 | 2015 |  | DDC
GCTI11-01 | GCTI11-01 | Y | Infrastructure | BRONX & N. QUEENS | GI - GREEN INFRASTRUCTURE IN FLUSHING CREEK | GI - GREEN INFRASTRUCTURE IN FLUSHING CREEK | GI - GREEN INFRASTRUCTURE IN FLUSHING CREEK | Queens |  | Environmental Protection | Substantial Completion | Sewer | Critical |  |  | PIMS | FALSE |  |  | 2016 |  | DDC
GCTI11-02 | GCTI11-02 | Y | Infrastructure | BRONX & N. QUEENS | GI-Construct ROW Bioswales Stormwater Greenstreets | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 | GI-Construct ROW Bioswales Stormwater Greenstreets in TI-011 |  |  | Environmental Protection | Final Design | New Construction | Standard |  |  | PIMS | FALSE |  |  |  | 2017-09-27 13:00:19.8370000 +00:00
GE353 | GE-353 | Y | Infrastructure | MANHATTAN & CITYWIDE | DISTRIBUTION WM EXTENSION/REPLACEMENTS; NEW BLDGS | Distribution Water Main extension/ replacement; new buildings, hydrant, and valve replacement; adjacent to TA facilities, Citywide, at the following locations: Brooklyn Locations: 1. Driggs Avenue between Lorimer Street and Union Avenue (Brooklyn). (Survey & records available on shared network as of 6/19/13 as per ESSU) 2. Union Avenue between North 12th Street; 3. Union Avenue bt North 12th St. and Richardson Street (Brooklyn). (Survey and records available on shared network as of 6/19/13 as per ESSU) 4. Flatbush Avenue between Atlantic Avenue and 5th Avenue (Brooklyn). (Survey CADD files,Carlson Design Files and non-DEP Record utility maps - Transit drawings included, are in the shared network server as of 07-02-13, as per ESSU) N. Queens Locations: 1. Rockaway Freeway bet. Beach 98th Street and Beach 101 Street. 2. Beach 99th St. bet. Rockaway Beach Blvd. and Rockaway Freeway; (location DELETED - to be implemented under SEQ200550) 3. Beach 100th St. bet. Rockaway Beach Blvd. and Rockaway Freeway; 4. Beach 98th St. between Rockaway Beach Blvd. and Beach Channel Drive, 5. Beach 101th St. between Rockaway Beach Blvd. and Beach Channel Drive; 6. Intersection of Beach 98th St. and Beach Channel Drive; 7. Intersection of Beach 101st St. and Beach Channel Drive. The approximate length (N. Queens): 1875LF; Survey order 03/04/2013; approximate delivery date 07/15/13 | Distribution Water Main extension/replacement; new buildings, hydrant, and valve replacement; adjacent to TA facilities, Citywide. | Brooklyn |  | Environmental Protection | Substantial Completion | Water | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2014 | 2015 |  | DDC
GE354 | GE354 | Y | Infrastructure | MANHATTAN & CITYWIDE | EMERGENCY RECONSTRUCTION OF WATER MAINS | Relocation and Replacement of Broken Water Mains, on an Emergency Basis, Citywide. | Relocation and Replacement of Broken Water Mains on an Emergency Basis, Citywide | Citywide |  | Environmental Protection | Completed Project | Water | Emergency | In-House | DEP Managed | PIMS | TRUE |  | 2013 | 2014 |  | DDC
GE354 | GE-354 | Y | Infrastructure | MANHATTAN & CITYWIDE | EMERGENCY RECONSTRUCTION OF WATER MAINS | Relocation and Replacement of Broken Water Mains, on an Emergency Basis, Citywide. | Relocation and Replacement of Broken Water Mains on an Emergency Basis, Citywide | Citywide |  | Environmental Protection | Completed Project | Water | Emergency | In-House | DEP Managed | PIMS | TRUE |  | 2013 | 2014 |  | DDC
GE-355 | GE-355 | Y | Infrastructure | MANHATTAN & CITYWIDE | EMERGENCY RECONSTRUCTION OF WATER MAINS, CW | EMERGENCY RECONSTRUCTION OF WATER MAINS, CW | EMERGENCY RECONSTRUCTION OF WATER MAINS, CW |  |  | Environmental Protection | Completed Project | Water | Critical | In-House | DEP Managed | PIMS | FALSE
GE-356 | GE-356 | Y | Infrastructure | MANHATTAN & CITYWIDE | DIST. WM EXTENSION/REPLACEMNTS; NEW BLDGS, ETC | DIST. WATER MAIN EXTENSION/REPLACEMNTS; NEW BLDGS, ETC | DIST. WATER MAIN EXTENSION/REPLACEMNTS; NEW BLDGS, ETC |  |  | Environmental Protection | Completed Project | Water | Critical | In-House | DEP Managed | PIMS | FALSE
GE357 | GE-357 | Y | Infrastructure | MANHATTAN & CITYWIDE | EMERGENCY RECONSTRUCTION OF WATER MAINS, CW | EMERGENCY RECONSTRUCTION OF WATER MAINS, CITYWIDE | EMERGENCY RECONSTRUCTION OF WATER MAINS, CITYWIDE | Citywide |  | Environmental Protection | Completed Project | Water | Critical | In-House | DEP Managed | PIMS | FALSE |  | 2015 | 2017 |  | DDC
GE358 | GE-358 | Y | Infrastructure | MANHATTAN & CITYWIDE | DIST. MAIN EXTENSIONS (NEW BLDG), CW | DISTRIBUTION MAIN EXTENSIONS (NEW BLDG), CITYWIDE | DISTRIBUTION MAIN EXTENSIONS (NEW BLDG), CITYWIDE |  |  | Environmental Protection | Completed Project | Water | Critical | In-House | DEP Managed | PIMS | FALSE
GE-359 | GE-359 | Y | Infrastructure | MANHATTAN & CITYWIDE | CITYWIDE EMERGENCY RECON OF WATER MAINS | CITYWIDE EMERGENCY RECONSTRUCTION OF WATER MAINS | CITYWIDE EMERGENCY RECONSTRUCTION OF WATER MAINS | Citywide |  | Environmental Protection | Design Development | Water | Critical | In-House | DEP Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
GE-360-KR | GE-360-KR | Y | Infrastructure | BROOKLYN | DISTRIBUTION WATER MAIN EXTENSION/REPLACEMENT,BKSI | ACCELERATED DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENT, NEW BUILDINGS, HYDRANT AND VALVE REPLACEMENTS IN BROOKLYN AND STATEN ISLAND | ACCELERATED DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENT, NEW BUILDINGS, HYDRANT AND VALVE REPLACEMENTS IN BROOKLYN AND STATEN ISLAND | Brooklyn |  | Environmental Protection | Final Design | Water | Critical | Requirements TO | DEP Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
GE-360-MX | GE-360MX | Y | Infrastructure | MANHATTAN & CITYWIDE | DISTRIBUTION WM EXTENSIONS REPLACE, NEW BLDGS, MX | ACCELERATED DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENTS, NEW BUILDINGS, HYDRANT AND VALVE REPLACEMENTS IN MANHATTAN AND THE BRONX. EMERGENCY CONSTRUCTION CAPITAL PROGRAM | ACCELERATED DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENTS, NEW BUILDINGS IN MANHATTAN AND THE BRONX | Citywide |  | Environmental Protection | Design Development | New Construction | Critical | In-House | DEP Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
GE-360-Q | GE-360-Q | Y | Infrastructure | S. QUEENS | DISTRIBUTION WATER MAIN EXTENSIONS, REPLACEMENT, Q | ACCELERATED DISTRIBUTION WATER MAIN EXTENSIONS/REPLACEMENTS, NEW BUILDINGS, HYDRANT AND VALVE REPLACEMENT IN QUEENS. EMERGENCY CONSTRUCTION CAPITAL PROGRAM. | Accelerated Distribution Water Main Extensions/Replacements, New Buildings, Hydrant and Valve Replacement in Queens | Queens |  | Environmental Protection | Construction Procurement | New Construction | Critical | In-House | DEP Managed | PIMS | FALSE |  |  | 2018 |  | DDC
GI-NTWN-A | GI-NTWN-A | Y | Infrastructure | BRONX & N. QUEENS | GI - NEWTOWN CREEK CLUSTER, QNS/BK | DESIGN PHASE - GREEN INFRASTRUCTURE IN NEWTOWN CREEK CLUSTER, QNS/BK | GREEN INFRASTRUCTURE IN NEWTOWN CREEK CLUSTER, QNS/BK | Queens |  | Environmental Protection | Design Development | Sewer | Critical |  |  | PIMS | FALSE |  | 2015 | 2017 |  | DDC
GI-UTOP-1 | GI-UTOP-1 | Y | Infrastructure | S. QUEENS | GI - GREEN INFRASTRUCTURE IN UTOPIA PARKWAY, QNS | GI - GREEN INFRASTRUCTURE IN UTOPIA PARKWAY, QUEENS | GI - GREEN INFRASTRUCTURE IN UTOPIA PARKWAY, QUEENS | Queens |  | Environmental Protection | Construction 50-75% | Other | Critical |  |  | PIMS | FALSE |  | 2014 | 2015 |  | DDC
GK-CM-01 | GK-CM-01 | Y | Infrastructure | BROOKLYN | REI SERVICES FOR GKRH34-02 | REI SERVICES FOR GKRH34-02 | REI SERVICES FOR GKRH34-02 | Brooklyn |  | Environmental Protection | Completed Project | New Construction | Critical | In-House | Requirement Contract | PIMS | FALSE |  |  | 2015 |  | DDC
GKNC14-05 | GKNC14-05 | Y | Infrastructure | BROOKLYN | Construction of Green Infrastructure in Brooklyn. | Construction of Green Infrastructure(BIOSWALES & STORMWATER) in the Crown Heights area of Brooklyn. | Construction of Green Infrastructure(BIOSWALES & STORMWATER) in the Crown Heights area of Brooklyn. | Brooklyn |  | Environmental Protection | Compliance | Sewer | Critical | Requirement Contract | Requirements TO | PIMS | FALSE |  | 2015 | 2018 |  | DDC
GKNC14-06 | GKNC14-06 | Y | Infrastructure | BROOKLYN | Construction of Green Infrastructure in Brooklyn | Construction of Green Infrastructure in the Bedford-Stuyvesant area of Brooklyn | Construction of Green Infrastructure in the Bedford-Stuyvesant area of Brooklyn | Brooklyn |  | Environmental Protection | Compliance | Sewer | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2018 |  | DDC
GKNC14-07 | GKNC14-07 | Y | Infrastructure | BROOKLYN | Construction of Green Infrastructure in Brooklyn | Construction of Green Infrastructure in the Fort Green & Clinton Hill area of Brooklyn | Construction of Green Infrastructure in the Fort Green & Clinton Hill area of Brooklyn | Brooklyn |  | Environmental Protection | Compliance | Sewer | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2018 |  | DDC
GKOH15-01 | GKOH15-01 | Y | Infrastructure | BROOKLYN | GI - GRAVESEND BAY CSO - PHASE I | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 1 | Brooklyn |  | Environmental Protection | Pre-Design/PrgDevelopment | Sewer | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2017 | 2020 |  | DDC
GKOH15-02 | GKOH15-02 | Y | Infrastructure | BROOKLYN | GI - GRAVESEND BAY CSO - PHASE II | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 2 | Brooklyn |  | Environmental Protection | Pre-Design/PrgDevelopment | Sewer | Critical | Requirement Contract | Requirements TO | PIMS | FALSE |  | 2018 | 2020 |  | DDC
GKOH15-03 | GKOH15-03 | Y | Infrastructure | BROOKLYN | GI - GRAVESEND BAY CSO - PHASE III | GI - GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | GREEN INFRASTRUCTURE IN OH-015 GRAVESEND BAY CSO PH 3 | Brooklyn |  | Environmental Protection | Pre-Design/PrgDevelopment | Sewer | Critical | Requirement Contract | Requirements TO | PIMS | FALSE |  | 2018 | 2020 |  | DDC
GKOH15-04 | GKOH15-04 | Y | Infrastructure | BROOKLYN | GI-OWLS HEAD TRIBUTARY DRAINAGE AREAS, BROOKLYN | GREEN INFRASTRUCTURE IN OWLS HEAD TRIBUTARY DRAINAGE AREAS, BROOKLYN | GREEN INFRASTRUCTURE IN OWLS HEAD TRIBUTARY DRAINAGE AREAS, BROOKLYN |  |  | Environmental Protection | [5 empty] | PIMS | FALSE |  |  |  | 2017-12-01 07:00:23.0270000 +00:00
GNCB14-1A | GNCB14-1A | Y | Infrastructure | BROOKLYN | GI IN THE NCB-014 CSO PH1 TRIBUTARY AREA, STAGE 1 | GREEN INFRASTRUCTURE IN THE NCB-014 CSO PH1 TRIBUTARY AREA, STAGE 1, BK | GREEN INFRASTRUCTURE IN THE NCB-014 CSO PH1 TRIBUTARY AREA, STAGE 1, BK | Brooklyn |  | Environmental Protection | Construction Procurement | Other | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2016 | 2018 |  | DDC
GNCB14-2A | GNCB14-2A | Y | Infrastructure | BROOKLYN | GI IN THE NCB-014 CSO PH 2 TRIBUTARY AREA, STAGE 1 | GREEN INFRASTRUCTURE IN THE NCB-014 CSO PHASE 2 TRIBUTARY AREA, STAGE 1, BK | GREEN INFRASTRUCTURE IN THE NCB-014 CSO PHASE 2 TRIBUTARY AREA, STAGE 1, BK |  |  | Environmental Protection | Cancelled Project | Other | Critical | Requirements TO | Requirements TO | PIMS | FALSE
PW311T04E | PW311T04E | N | Safety and Site Support | Site Engineering | Topographical Surveys Queens
PW311T07A | PW311T07A | N | Safety and Site Support | Site Engineering | Structures Surveys Bronx
GNCB14-3A | GNCB14-3A | Y | Infrastructure | BROOKLYN | GI IN THE NCB-014 CSO PH 3 TRIBUTARY AREA, STAGE 1 | GREEN INFRASTRUCTURE IN THE NCB-014 PHASE 3 TRIBUTARY AREA, STAGE 1, BK | GREEN INFRASTRUCTURE IN THE NCB-014 PHASE 3 TRIBUTARY AREA, STAGE 1, BK |  |  | Environmental Protection | Cancelled Project | Other | Critical | Requirements TO | Requirements TO | PIMS | FALSE
GQBB09-01 | GQBB09-01 | Y | Infrastructure | BRONX & N. QUEENS | GI IN THE BB-09 CSO TRIBUTARY AREA, STAGE 1 | GREEN INFRASTRUCTURE IN THE BB-009 CSO TRIBUTARY AREA, STAGE 1, QNS | GREEN INFRASTRUCTURE IN THE BB-009 CSO TRIBUTARY AREA, STAGE 1, QNS | Queens |  | Environmental Protection | Construction 0-25% | Other | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
GQ-CM-01 | GQ-CM-01 | Y | Infrastructure | S. QUEENS | REI SERVICES FOR GQBB06-03/GQBB08-01/GQROWB-01 | REI SERVICES FOR GQBB06-03/GQBB08-01/GQROWB-01 |  | Queens |  | Environmental Protection |  | New Construction | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
GQJA03-01 | GQJA03-01 | Y | Infrastructure | S. QUEENS | GI - GREEN INFRASTRUCTURE IN JAMAICA AREA | GI - GREEN INFRASTRUCTURE IN JAMAICA AREA | GI - GREEN INFRASTRUCTURE IN JAMAICA AREA | Queens |  | Environmental Protection | Design Development | Sewer | Critical |  |  | PIMS | FALSE |  | 2016 | 2017 |  | DDC
GQJA03-02 | GQJA03-02 | Y | Infrastructure | S. QUEENS | GI - GREEN INFRASTRUCTURE IN JAMAICA AREA | GI - GREEN INFRASTRUCTURE IN JAMAICA AREA | GREEN INFRASTRUCTURE FOR JAMAICA BAY, QUEENS. | Queens |  | Environmental Protection | Final Design | Sewer | Critical |  |  | PIMS | FALSE |  | 2018 | 2019 |  | DDC
GQJA03-03 | GQJA03-03 | Y | Infrastructure | S. QUEENS | GI - GREEN INFRASTRUCTURE IN JAMAICA AREA | GI - GREEN INFRASTRUCTURE IN JAMAICA AREA | GI - GREEN INFRASTRUCTURE IN JAMAICA AREA | Queens |  | Environmental Protection | Final Design | Sewer | Critical |  |  | PIMS | FALSE |  | 2016 | 2017 |  | DDC
GQTI03-23 | GQTI03-23 | Y | Infrastructure | BRONX & N. QUEENS | GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO | GI - GREEN INFRASTRUCTURE IN TI-003 & TI-023 EAST RIVER CSO |  |  | Environmental Protection | [5 empty] | Project Info | FALSE |  |  |  | 2017-11-06 13:00:21.6400000 +00:00
GQTI10-01 | GQTI10-01 | Y | Infrastructure | BRONX & N. QUEENS | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUE | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUEENS | GI - DESIGN & CONSTUCTION OF BIOSWALES & GREENSTREETS, QUEENS | Queens |  | Environmental Protection | Final Design | New Construction | Critical |  |  | PIMS | TRUE |  | 2015 | 2018 |  | DDC
GQTI10-01 | GQTI10-02 | Y | Infrastructure | BRONX & N. QUEENS | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUE | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUEENS | GI - DESIGN & CONSTUCTION OF BIOSWALES & GREENSTREETS, QUEENS | Queens |  | Environmental Protection | Final Design | New Construction | Critical |  |  | PIMS | TRUE |  | 2015 | 2018 |  | DDC
GQTI10-02 | GQTI10-02 | Y | Infrastructure | BRONX & N. QUEENS | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUE | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUEENS | GI - DESIGN & CONSTRUCTION OF BIOSWALES & GREENSTREETS, QUEENS | Queens |  | Environmental Protection | Final Design | New Construction | Critical |  |  | PIMS | TRUE |  | 2015 | 2018 |  | DDC
GQTI10-02 | GQTI10-03 | Y | Infrastructure | BRONX & N. QUEENS | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUE | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUEENS | GI - DESIGN & CONSTRUCTION OF BIOSWALES & GREENSTREETS, QUEENS | Queens |  | Environmental Protection | Final Design | New Construction | Critical |  |  | PIMS | TRUE |  | 2015 | 2018 |  | DDC
GQTI10-03 | GQTI10-03 | Y | Infrastructure | BRONX & N. QUEENS | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUE | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUEENS | GI - DESIGN & CONSTRUCTION OF BIOSWALES & GREENSTREETS, QUEENS | Queens |  | Environmental Protection | Design Development | New Construction | Critical |  |  | PIMS | TRUE |  | 2015 | 2018 |  | DDC
GQTI10-03 | GQTI10-04 | Y | Infrastructure | BRONX & N. QUEENS | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUE | GI - DSGN & CONST OF BIOSWALES & GREENSTREETS, QUEENS | GI - DESIGN & CONSTRUCTION OF BIOSWALES & GREENSTREETS, QUEENS | Queens |  | Environmental Protection | Design Development | New Construction | Critical |  |  | PIMS | TRUE |  | 2015 | 2018 |  | DDC
GQTI10-04 | GQTI10-04 | Y | Infrastructure | BRONX & N. QUEENS | GI-DSGN & CONST OF BIOSWALES & GREENSTREETS QUEENS | GI - DESIGN AND CONSTRUCTION OF BIOSWALES AND GREENSTREETS | GI - Design phase of Green Infrastructure in Flushing Creek | Queens |  | Environmental Protection | Design Development | New Construction | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
GQTI11-22 | GQTI11-22 | Y | Infrastructure | BRONX & N. QUEENS | GI - GREEN INFRASTRUCTURE IN TI-11 AND TI-22, QNS | GI - GREEN INFRASTRUCTURE IN TI-11 AND TI-22, QNS | GI - GREEN INFRASTRUCTURE IN TI-11 AND TI-22, QUEENS | Queens |  | Environmental Protection | Final Design | Sewer | Critical |  |  | PIMS | FALSE |  | 2015 | 2017 |  | DDC
GRANSTBID | GRANSTBID | Y | Infrastructure | BROOKLYN | GRAND ST. STREETSCAPE IMPROVEMENTS | Replace/reconstruct the existing curb and sidewalk on both sides of the Grand street from Union Street to Bushwick Avenue and curb extensions at key intersections. | Replace/reconstruct the existing curb and sidewalk on both sides of the Grand street from Union Street to Bushwick Avenue and curb extensions at key intersections | Brooklyn |  | Transportation | Substantial Completion | Sidewalks | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2015 |  | DDC
GRINFRA01 | GRINFRA01 | Y | Infrastructure | Bronx & N. Queens | GREEN INFRASTRUCTURE DESIGN REQUIREMENT CONTRACT | Green Infrastructure in Hutchinson River Area | Design contract for green infrastructure improvements in the Hutchinson River area. | Bronx |  | Environmental Protection | Cancelled Project | Other | Standard | Standard Consultant | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
GRINFRA02 | GRINFRA02 | Y | Infrastructure | Bronx & N. Queens | GREEN INFRASTRUCTURE DESIGN REQUIREMENT CONTRACT | Green Infrastructure in Newtown Creek Area | Design contract for green infrastructure improvements in the Newtown Creek area. | Queens |  | Environmental Protection | Design Development | Other | Standard | Standard Consultant | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
GXHP24-01 | GXHP24-01 | Y | Infrastructure | BRONX & N. QUEENS | GREEN INFRASTRUCTURE IN HUTCHINSON RIVER AREA, PH1 | Design Contract for Green Infrastructure in Hutchinson River Area | Design phase for Green Infrastructure in Hutchinson River Area | Bronx |  | Environmental Protection | Cancelled Project | Sewer | Standard | In-House/Consultant | Requirements TO | PIMS | FALSE |  | 2013 |  |  | DDC
HAM16MRCC | HAM16MRCC | Y | Public Buildings | HUMAN SERVICES | Weeksville Gardens-BKLYN Kindergarten , asbestos | To renovation and convert the existing community center at Weeksville Gardens in Brooklyn into a Pre-Kindergarten program for early childhood education. | Renovation of existing community center to convert to Universal Pre-Kindergarten program for early childhood education. | Brooklyn |  | HPD | Completed Project | Renovation | Critical | None | JOCS | PIMS | FALSE |  |  |  |  | DDC
HBMA24529 | HBMA24529 | Y | Infrastructure | EXECUTIVE | WEST 155TH ST PED BRIDGE OVER AMTRAK BIN:224529 | REHABILITATION/REPLACEMENT OF WEST 155TH STREET PEDESTRIAN BRIDGE OVER AMTRAK - WEST SIDE CONNECTION (BIN:2-24529-0), BOROUGH OF MANHATTAN. |  |  |  | Transportation | [5 empty] | Project Info | FALSE |  |  |  | 2017-10-05 13:00:19.0670000 +00:00
HBMA24662 | HBMA24662 | Y | Infrastructure | MANHATTAN & CITYWIDE | E128th Street Pedestrian Bridge, Manhattan | Rehabilitation or replacement of the E 128th Street Pedestrian Bridge over 3rd Avenue in Manhattan |  |  |  | Transportation | [5 empty] | Project Info | FALSE |  |  |  | 2017-12-01 07:00:24.2230000 +00:00
HBPED100M | HBPED100M | Y | Infrastructure | MANHATTAN & CITYWIDE | E 81 STREET PEDESTRIAN BRIDGE OVER FDR, MANHATTAN | E 81 STREET PEDESTRIAN BRIDGE OVER FDR, MANHATTAN | E 81 STREET PEDESTRIAN BRIDGE OVER FDR, MANHATTAN | Manhattan |  | Parks & Recreation | Construction 75%-Subst. | New Construction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  | 2014 |  | DDC
PW311T07D | PW311T07D | N | Safety and Site Support | Site Engineering | structures surveys manhattan
PW311T07E | PW311T07E | N | Safety and Site Support | Site Engineering | surveys topo queens
PW311T95B | PW311T95B | N | Safety and Site Support | Site Engineering | Topographical Services Citywide
HBPED100Q | HBPED100Q | Y | Infrastructure | Bronx & N. Queens | PEDESTRIAN BRIDGES AT 51 AV | 51st Avenue, Pedestrian Bridges over LIRR in the borough of Queens (East 81st Street Pedestrian Bridge over FDR in the borough of Manhattan removed from this Contract and placed in HBPED100M) (216th Street Pedestrian Bridges over LIRR in the borough of Queens removed from this Contract and placed in HBPED216S) | Replace pedestrian bridge over the LIRR at 51st Avenue. | Queens |  | Transportation | Final Design | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HBPED216S | HBPED216S | Y | Infrastructure | BRONX & N. QUEENS | PED BRIDGE 216 ST QUEENS | DEMOLITION OF PEDESTRIAN BRIDGE AT 216TH STREET OVER L.I.R.R. | DEMOLITION OF PEDESTRIAN BRIDGE AT 216TH STREET OVER L.I.R.R. |  |  | Transportation | Compliance | Other | Standard | Requirement Contract | Requirement Contract | PIMS | FALSE |  |  |  | 2017-12-14 13:00:23.5200000 +00:00
HBPED700E | HBPED700E | Y | Infrastructure | BRONX & N. QUEENS | EMERGENCY REPAIR - PASSERELLE BRIDGE, QUEENS | PASSERELLE BRIDGE - EMERGENCY REPAIR CONTRACT | PASSERELLE BRIDGE - EMERGENCY REPAIR CONTRACT | Queens |  | Parks & Recreation | Completed Project | Renovation | Critical |  |  | PIMS | FALSE |  | 2014 | 2014 |  | DDC
HBPED700Q | HBPED700Q | Y | Infrastructure | BRONX & N. QUEENS | FMCP - PASSERELLE PEDESTRIAN BRIDGE, QNS | Preliminary study for Reconstruction or Rehabilition of Passerelle Overpass in the Flushing Meadows-Corona park. | Preliminary study for Reconstruction or Rehabilition of Passerelle Overpass in the Flushing Meadows-Corona park | Queens |  | Parks & Recreation | Completed Project | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HBPED800Q | HBPED800Q | Y | Infrastructure | BRONX & N. QUEENS | PORPOISE BRIDGE IN FLUSHING MEADOWS-CORONA PARK | Feasibility Study for the repair and or restoration for Porpoise (Tide Gate) Bridge in Flushing Meadows Corona Park. | Feasibility Study for the repair and or restoration for Porpoise (Tide Gate) Bridge in Flushing Meadows Corona Park. | Queens |  | Transportation | Pre-Design/PrgDevelopment | Other | Standard | Requirements TO | None | PIMS | FALSE |  | 2015 |  |  | DDC
HBPEDMRS | HBPEDMRS | Y | Infrastructure | MANHATTAN & CITYWIDE | MORRIS ST. PEDESTRIAN BRIDGE REPLACEMENT | Replacement of pedestrian bridge superstructures and necessary portions of Morris St. Pedestrian Bridge over Brooklyn Battery Tunnel Plaza, BIN 2-20893-0, along with provisions for ADA compliant ramps where feasible. | Replacement of pedestrian bridge superstructures and necessary portions of Morris St. Pedestrian Bridge over Brooklyn Battery Tunnel Plaza, BIN 2-20893-0, along with provisions for ADA compliant ramps where feasible. |  |  | Transportation | On-Hold | Other | Standard | Standard Consultant | Standard Consultant | PIMS | FALSE
HBQA70551 | HBQA70551 | Y | Infrastructure | EXECUTIVE | 167TH ST PED BRIDGE OVER LIRR BIN 7705510 | REHABILITATION/REPLACEMENT OF 167TH STREET PEDESTRIAN BRIDGE OVER LIRR PORT WASHINGTON BRANCH (BIN 7-70551-0), BOROUGH OF QUEENS |  |  |  | Transportation | [5 empty] | Project Info | FALSE |  |  |  | 2017-10-05 13:00:20.3830000 +00:00
HD153C1 | HD-153C1 | Y | Infrastructure | S. Queens | EDGEMERE (PHASE C1) - (INCLUDING SEQ002562/200406) | Project Limit / Locations Edgemere Phase C1, Construction of Infrastructure, including street, sidewalk, storm and sanitary sewers and water main. This Phase includes Beach 43rd north of Beach Channel Drive to the Conch Basin Beach 44th north of Beach Channel Drive to the Conch Basin Beach 45th north of Beach Channel Drive to the Conch Basin Hantz Rd. between B44 and B45 street Norton Ave. between B44 and B45 street Edgemere Dr Conch Rd. | New streets, sidewalks, storm and sanitary sewers and water mains: 43rd, 44th, and 45th Streets north of Beach Channel Drive, including sections of Hantz Road, Norton Avenue, Edgemere Drive and Conch Road within this area. |  |  | Environmental Protection | Substantial Completion | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | FALSE
HD153C1 | SEQ002562 | Y | Infrastructure | S. Queens | EDGEMERE (PHASE C1) - (INCLUDING SEQ002562/200406) | Project Limit / Locations Edgemere Phase C1, Construction of Infrastructure, including street, sidewalk, storm and sanitary sewers and water main. This Phase includes Beach 43rd north of Beach Channel Drive to the Conch Basin Beach 44th north of Beach Channel Drive to the Conch Basin Beach 45th north of Beach Channel Drive to the Conch Basin Hantz Rd. between B44 and B45 street Norton Ave. between B44 and B45 street Edgemere Dr Conch Rd. | New streets, sidewalks, storm and sanitary sewers and water mains: 43rd, 44th, and 45th Streets north of Beach Channel Drive, including sections of Hantz Road, Norton Avenue, Edgemere Drive and Conch Road within this area. |  |  | Environmental Protection | Substantial Completion | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | FALSE
HD153C1 | SEQ200406 | Y | Infrastructure | S. Queens | EDGEMERE (PHASE C1) - (INCLUDING SEQ002562/200406) | Project Limit / Locations Edgemere Phase C1, Construction of Infrastructure, including street, sidewalk, storm and sanitary sewers and water main. This Phase includes Beach 43rd north of Beach Channel Drive to the Conch Basin Beach 44th north of Beach Channel Drive to the Conch Basin Beach 45th north of Beach Channel Drive to the Conch Basin Hantz Rd. between B44 and B45 street Norton Ave. between B44 and B45 street Edgemere Dr Conch Rd. | New streets, sidewalks, storm and sanitary sewers and water mains: 43rd, 44th, and 45th Streets north of Beach Channel Drive, including sections of Hantz Road, Norton Avenue, Edgemere Drive and Conch Road within this area. |  |  | Environmental Protection | Substantial Completion | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | FALSE
HD153C2 | HD-153C2 | Y | Infrastructure | S. Queens | EDGEMERE (PHASE C2), Including SEQ200421/SEQ002576 | Project Limit / Locations: Norton Avenue between B49th St. and B45th St. Intersection of Elizabeth Avenue, and Norton Avenue, and B49th Street Elizabeth Avenue between B49th Street and B51st Street B51st Street between Alameda Avenue and Beach Channel Drive B46th Street between Rockaway Beach Boulevard and Norton Avenue B47th Street between Rockaway Beach Boulevard and Norton Avenue B48th Street between Rockaway Beach Boulevard and Norton Avenue B49th Street between Rockaway Beach Boulevard and Norton Avenue Beach Channel Drive between B49th Street and B45th Street Rockaway Beach Boulevard between B49th Street and B45th Street | New streets, sidewalks, storm and sanitary sewers and water mains: 46th, 47th, 48th and 49th Streets between Norton Avenue and Rockaway Beach Boulevard, including sections of Norton and Elizabeth Avenues, 51st Street, Beach Channel Drive and Rockaway Beach Boulevard. |  |  | Environmental Protection | Substantial Completion | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE
HED553 | HED-553 | Y | Infrastructure | BRONX & N. QUEENS | TRUNK WATER MAIN IN SOUTHERN BLVD (w/ SEX002245) | Replacement of water main and sewer work on Southern Boulevard from Boston Road to Westchester Ave. Water main replacemnt on Boston Road from East Tremont Ave to E 179th Street. | Replacement of water main and sewer work on Southern Boulevard from Boston Road to Westchester Ave. Water main replacemnt on Boston Road from East Tremont Ave to E 179th Street. | Bronx |  | Environmental Protection | Construction 0-25% | Water | Standard | In-House | Standard Consultant | PIMS | TRUE |  | 2013 | 2015 |  | DDC
PW335A21 | PW335A21 | N | Safety and Site Support | HAZMAT | Asbestos Abatement Citywide
PW335A22 | PW335A22 | N | Safety and Site Support | HAZMAT | Asbestos Abatement Citywide
PW335A23 | PW335A23 | N | Safety and Site Support | HAZMAT | Asbestos Abatement Contract #23
PW335A24 | PW335A24 | N | Safety and Site Support | HAZMAT | Asbestos Abatement #24
PW335A25 | PW335A25 | N | Safety and Site Support | HAZMAT | Asbestos Abatement Citywide
HD153C2 | SEQ002576 | Y | Infrastructure | S. Queens | EDGEMERE (PHASE C2), Including SEQ200421/SEQ002576 | Project Limit / Locations: Norton Avenue between B49th St. and B45th St. Intersection of Elizabeth Avenue, and Norton Avenue, and B49th Street Elizabeth Avenue between B49th Street and B51st Street B51st Street between Alameda Avenue and Beach Channel Drive B46th Street between Rockaway Beach Boulevard and Norton Avenue B47th Street between Rockaway Beach Boulevard and Norton Avenue B48th Street between Rockaway Beach Boulevard and Norton Avenue B49th Street between Rockaway Beach Boulevard and Norton Avenue Beach Channel Drive between B49th Street and B45th Street Rockaway Beach Boulevard between B49th Street and B45th Street | New streets, sidewalks, storm and sanitary sewers and water mains: 46th, 47th, 48th and 49th Streets between Norton Avenue and Rockaway Beach Boulevard, including sections of Norton and Elizabeth Avenues, 51st Street, Beach Channel Drive and Rockaway Beach Boulevard. |  |  | Environmental Protection | Substantial Completion | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE
HD153C2 | SEQ200421 | Y | Infrastructure | S. Queens | EDGEMERE (PHASE C2), Including SEQ200421/SEQ002576 | Project Limit / Locations: Norton Avenue between B49th St. and B45th St. Intersection of Elizabeth Avenue, and Norton Avenue, and B49th Street Elizabeth Avenue between B49th Street and B51st Street B51st Street between Alameda Avenue and Beach Channel Drive B46th Street between Rockaway Beach Boulevard and Norton Avenue B47th Street between Rockaway Beach Boulevard and Norton Avenue B48th Street between Rockaway Beach Boulevard and Norton Avenue B49th Street between Rockaway Beach Boulevard and Norton Avenue Beach Channel Drive between B49th Street and B45th Street Rockaway Beach Boulevard between B49th Street and B45th Street | New streets, sidewalks, storm and sanitary sewers and water mains: 46th, 47th, 48th and 49th Streets between Norton Avenue and Rockaway Beach Boulevard, including sections of Norton and Elizabeth Avenues, 51st Street, Beach Channel Drive and Rockaway Beach Boulevard. |  |  | Environmental Protection | Substantial Completion | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE
HD161C | HD-161C | Y | Infrastructure | Brooklyn | GATEWAY ESTATE - PHASE C | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase C Scope of project :- Schroeders Ave. from Elton St. to Erskine St. Erskine St. from Flatlands Ave. to limit of the project Berriman St. from Vandalia Ave. to Schroeders Ave. Vandalia Ave. from Berriman St. to Fountain Ave. Egan St. from Erskine St. to Fountain Ave. Milford St. from Egan St. to Vandalia Ave. Fountain Ave. from Vandalia Ave. to Egan St. | Roadway reconstruction, including sanitary and storm sewers, water main, traffic management and street lighting: Gateway Estates area of East New York, Brooklyn. | Brooklyn |  | HPD | Cancelled Project | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HD161C | SEK002353 | Y | Infrastructure | Brooklyn | GATEWAY ESTATE - PHASE C | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase C Scope of project :- Schroeders Ave. from Elton St. to Erskine St. Erskine St. from Flatlands Ave. to limit of the project Berriman St. from Vandalia Ave. to Schroeders Ave. Vandalia Ave. from Berriman St. to Fountain Ave. Egan St. from Erskine St. to Fountain Ave. Milford St. from Egan St. to Vandalia Ave. Fountain Ave. from Vandalia Ave. to Egan St. | Roadway reconstruction, including sanitary and storm sewers, water main, traffic management and street lighting: Gateway Estates area of East New York, Brooklyn. | Brooklyn |  | HPD | Cancelled Project | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HD161C | SEK20056 | Y | Infrastructure | Brooklyn | GATEWAY ESTATE - PHASE C | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase C Scope of project :- Schroeders Ave. from Elton St. to Erskine St. Erskine St. from Flatlands Ave. to limit of the project Berriman St. from Vandalia Ave. to Schroeders Ave. Vandalia Ave. from Berriman St. to Fountain Ave. Egan St. from Erskine St. to Fountain Ave. Milford St. from Egan St. to Vandalia Ave. Fountain Ave. from Vandalia Ave. to Egan St. | Roadway reconstruction, including sanitary and storm sewers, water main, traffic management and street lighting: Gateway Estates area of East New York, Brooklyn. | Brooklyn |  | HPD | Cancelled Project | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HD-161C | HD-161C | Y | Infrastructure | BROOKLYN | GATEWAY ESTATE - PHASE C | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase C Scope of project :- Schroeders Ave. from Elton St. to Erskine St. Erskine St. from Flatlands Ave. to limit of the project Berriman St. from Vandalia Ave. to Schroeders Ave. Vandalia Ave. from Berriman St. to Fountain Ave. Egan St. from Erskine St. to Fountain Ave. Milford St. from Egan St. to Vandalia Ave. Fountain Ave. from Vandalia Ave. to Egan St. | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase C | Brooklyn |  | HPD | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirement Contract | PIMS | TRUE |  | 2012 | 2013 |  | DDC
HD-161C | SEK002353 | Y | Infrastructure | BROOKLYN | GATEWAY ESTATE - PHASE C | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase C Scope of project :- Schroeders Ave. from Elton St. to Erskine St. Erskine St. from Flatlands Ave. to limit of the project Berriman St. from Vandalia Ave. to Schroeders Ave. Vandalia Ave. from Berriman St. to Fountain Ave. Egan St. from Erskine St. to Fountain Ave. Milford St. from Egan St. to Vandalia Ave. Fountain Ave. from Vandalia Ave. to Egan St. | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase C | Brooklyn |  | HPD | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirement Contract | PIMS | TRUE |  | 2012 | 2013 |  | DDC
HD-161C | SEK20056 | Y | Infrastructure | BROOKLYN | GATEWAY ESTATE - PHASE C | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase C Scope of project :- Schroeders Ave. from Elton St. to Erskine St. Erskine St. from Flatlands Ave. to limit of the project Berriman St. from Vandalia Ave. to Schroeders Ave. Vandalia Ave. from Berriman St. to Fountain Ave. Egan St. from Erskine St. to Fountain Ave. Milford St. from Egan St. to Vandalia Ave. Fountain Ave. from Vandalia Ave. to Egan St. | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase C | Brooklyn |  | HPD | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirement Contract | PIMS | TRUE |  | 2012 | 2013 |  | DDC
PW335AS13 | PW335AS13 | N | Safety and Site Support | HAZMAT | Air Sampling Contract #13 |  |  |  |  | Unknown
PW335AS14 | PW335AS14 | N | Safety and Site Support | HAZMAT | AIR SAMPLING VARIOUS LOCATIONS |  |  |  |  | Unknown
PW335AS15 | PW335AS15 | N | Safety and Site Support | HAZMAT | Air Sampling #15
PW335AS16 | PW335AS16 | N | Safety and Site Support | HAZMAT | Air Sampling Contract #16
PW335AS17 | PW335AS17 | N | Safety and Site Support | HAZMAT | Air Sampling Contract #17
PW335AS18 | PW335AS18 | N | Safety and Site Support | HAZMAT | Air Sampling Citywide #18
PW335AS19 | PW335AS19 | N | Safety and Site Support | HAZMAT | Air Sampling Citywide
HD-161D | HD-161D | Y | Infrastructure | BROOKLYN | GATEWAY ESTATE - PHASE D/SEK002354 | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. - Phase D Final Scope -------------------------------------------------------------------------------- 1. Vandalia Ave Gateway Drive 250 L.F. east of Elton Street 2. Schroeders Ave Gateway Drive 250 L.F. east of Elton Street 3. Gateway Drive Vandalia Ave. 250 L.F. south of Schroeders Avenue 4. Jerome Street Vandalia Avenue Schroeders Avenue 5. Walker Street Vandalia Avenue Schroeders Avenue 6. Lower Ashford Street Schroeders Avenue 250 L. F. North of Vandalia Avenue | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. - Phase D | Brooklyn |  | HPD | Construction 50-75% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | TRUE |  | 2012 | 2013 |  | DDC
HD-161D | SEK002354 | Y | Infrastructure | BROOKLYN | GATEWAY ESTATE - PHASE D/SEK002354 | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. - Phase D Final Scope -------------------------------------------------------------------------------- 1. Vandalia Ave Gateway Drive 250 L.F. east of Elton Street 2. Schroeders Ave Gateway Drive 250 L.F. east of Elton Street 3. Gateway Drive Vandalia Ave. 250 L.F. south of Schroeders Avenue 4. Jerome Street Vandalia Avenue Schroeders Avenue 5. Walker Street Vandalia Avenue Schroeders Avenue 6. Lower Ashford Street Schroeders Avenue 250 L. F. North of Vandalia Avenue | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. - Phase D | Brooklyn |  | HPD | Construction 50-75% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | TRUE |  | 2012 | 2013 |  | DDC
HD-161D | SEK20057 | Y | Infrastructure | BROOKLYN | GATEWAY ESTATE - PHASE D/SEK002354 | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. - Phase D Final Scope -------------------------------------------------------------------------------- 1. Vandalia Ave Gateway Drive 250 L.F. east of Elton Street 2. Schroeders Ave Gateway Drive 250 L.F. east of Elton Street 3. Gateway Drive Vandalia Ave. 250 L.F. south of Schroeders Avenue 4. Jerome Street Vandalia Avenue Schroeders Avenue 5. Walker Street Vandalia Avenue Schroeders Avenue 6. Lower Ashford Street Schroeders Avenue 250 L. F. North of Vandalia Avenue | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. - Phase D | Brooklyn |  | HPD | Construction 50-75% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | TRUE |  | 2012 | 2013 |  | DDC
PW335BS11 | PW335BS11 | N | Safety and Site Support | HAZMAT | Bulk Sampling Contract #11
PW335BS12 | PW335BS12 | N | Safety and Site Support | HAZMAT | Bulk Sampling Contract #12
PW335EPS2 | PW335EPS2 | N | Safety and Site Support | HAZMAT | Environmental Services Citywide
PW335EPS3 | PW335EPS3 | N | Safety and Site Support | HAZMAT | ENVIRONMENTAL CONSULTANT REQUIREMENT CONTRACT
PW335EPS4 | PW335EPS4 | N | Safety and Site Support | HAZMAT | ENVIROMENTAL CONSULTING REQUIREMENTS CONTRACT
PW335EPS5 | PW335EPS5 | N | Safety and Site Support | HAZMAT | LEAD ABATEMENT |  |  |  |  | Unknown
HD161E | HD-161E | Y | Infrastructure | BROOKLYN | GATEWAY ESTATE - PHASE E/BED-805 | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase E DEP scope: water Main:New 1. Locke Street between Gateway Drive and Elton Street 2. Egan Street between Vandalia Avenue and Elton Street 3. Gateway Drive between Flatlands Avenue and Vandalia Avenue 4. Ashford Street between Flatlands Avenue and Vandalia Avenue 5. Cleveland Street between Locke Street and Vandalia Avenue Sanitary Sewers: New 1. Locke Street between Gateway Drive and Elton Street 2. Egan Street between Gateway Drive and Elton Street 3. Gateway Drive between Egan Street and Flatlands Avenue 4. Ashford Street between Egan Street and Flatlands Avenue 5. Cleveland Street between Egan Street and Locke Street Storm Sewer: New 1. Gateway Drive between Egan Street and Flatlands Avenue 2. Ashford Street between Egan Street and Flatlands Avenue 3. Locke Street between Gateway Drive and Cleveland Street | Reconstruction of Gateway Estates Area (Nehemiah Creek) including sewer, watermain, street lighting and traffic signal work. Phase E | Brooklyn |  | HPD | Construction 0-25% | New Construction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HDWR17K | HDWR17K | Y | Infrastructure | BROOKLYN | REPLACEMENT/REPAIR MANHOLE HARDWARE, BROOKLYN | REPLACEMENT/REPAIR IN KIND OF MANHOLE HARDWARE (INCLUDING CASTINGS AND CHIMNEY ADJUSTMENTS). NO RINGS SHALL BE ALLOWED. | REPLACEMENT/REPAIR IN KIND OF MANHOLE HARDWARE (INCLUDING CASTINGS AND CHIMNEY ADJUSTMENTS). NO RINGS SHALL BE ALLOWED. | Brooklyn |  | Environmental Protection | Construction Procurement | Renovation | Critical | In-House | DDC Managed | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HDWR17M | HDWR17M | Y | Infrastructure | MANHATTAN & CITYWIDE | REPLACEMENT/REPAIR MANHOLE HARDWARE, MANHATTAN | REPLACEMENT/REPAIR IN KIND OF MANHOLE HARDWARE (INCLUDING CASTINGS AND CHIMNEY ADJUSTMENTS). NO RINGS SHALL BE ALLOWED. | REPLACEMENT/REPAIR IN KIND OF MANHOLE HARDWARE (INCLUDING CASTINGS AND CHIMNEY ADJUSTMENTS). NO RINGS SHALL BE ALLOWED. | Manhattan |  | Environmental Protection | Construction Procurement | Renovation | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HDWR17Q | HDWR17Q | Y | Infrastructure | S. QUEENS | REPLACEMENT/REPAIR MANHOLE HARDWARE, QUEENS | Replacement/Repair in Kind of Manhole Hardware (including castings and chimney adjustments) - no rings shall be allowed | Replacement/Repair in Kind of Manhole Hardware (including castings and chimney adjustments) - no rings shall be allowed | Queens |  | Environmental Protection | Construction 0-25% | Upgrade | Critical | In-House |  | PIMS | FALSE |  |  |  |  | DDC
HDWR17R | HDWR17R | Y | Infrastructure | STATEN ISLAND | REPLACEMENT/REPAIR MANHOLE HARDWARE, STATEN ISLAND | REPLACEMENT/REPAIR IN KIND OF MANHOLE HARDWARE (INCLUDING CASTINGS AND CHIMNEY ADJUSTMENTS). NO RINGS SHALL BE ALLOWED. | REPLACEMENT/REPAIR IN KIND OF MANHOLE HARDWARE | Staten Is. |  | Environmental Protection | Construction 0-25% | Sewer | Standard | In-House | Individual Contract(s) | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HDWR17X | HDWR17X | Y | Infrastructure | BRONX & N. QUEENS | REPLACEMENT/REPAIR MANHOLE HARDWARE, BRONX | REPLACEMENT/REPAIR IN KIND OF MANHOLE HARDWARE (INCLUDING CASTINGS AND CHIMNEY ADJUSTMENTS). NO RINGS SHALL BE ALLOWED. | Replacement / Repair in Kind of Manhole Hardware (including castings and chimney adjustments). No rings shall be allowed. | Bronx |  | Environmental Protection | Construction 0-25% | Renovation | Standard | DDC Managed/Consultant |  | PIMS | FALSE |  |  |  |  | DDC
PW335ES12 | PW335ES12 | N | Safety and Site Support | HAZMAT | Environmental Service Contract #12
PW335ES13 | PW335ES13 | N | Safety and Site Support | HAZMAT | Environmental Services Contract #13
PW335ES14 | PW335ES14 | N | Safety and Site Support | HAZMAT | Environmental Services Contract #14
PW335ES15 | PW335ES15 | N | Safety and Site Support | HAZMAT | Environmental & Lab Services for bklyn & Queens
HED553 | SEX002245 | Y | Infrastructure | BRONX & N. QUEENS | TRUNK WATER MAIN IN SOUTHERN BLVD (w/ SEX002245) | Replacement of water main and sewer work on Southern Boulevard from Boston Road to Westchester Ave. Water main replacemnt on Boston Road from East Tremont Ave to E 179th Street. | Replacement of water main and sewer work on Southern Boulevard from Boston Road to Westchester Ave. Water main replacemnt on Boston Road from East Tremont Ave to E 179th Street. | Bronx |  | Environmental Protection | Construction 0-25% | Water | Standard | In-House | Standard Consultant | PIMS | TRUE |  | 2013 | 2015 |  | DDC
HED-556A | HED-556A | Y | Infrastructure | BRONX & N. QUEENS | LINING OF EXISTING TRUNK WM IN BOTANICAL GARDENS | Cleaning, surveying, lining and replacing 36" and 48" water mains, and upgrade existing distribution water mains in Botanical Gardens Area | Cleaning, surveying, lining and replacing 36" and 48" water mains, and upgrade existing distribution water mains in Botanical Gardens Area | Bronx |  | Environmental Protection | On-Hold | Water | Standard | In-House | None | PIMS | FALSE |  |  |  |  | DDC
HED562 | HED-562 | Y | Infrastructure | BRONX & N. QUEENS | NEW 48" TRUNK WATER MAIN IN E 233 STREET | New 48" Trunk Water Main in E 233rd Street between Bronxwood Avenue & Baychester Avenue, etc. | New 48" Trunk Water Main in E 233rd Street between Bronxwood Avenue & Baychester Avenue, etc. | Bronx |  | Environmental Protection | Final Design | Water | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HED563 | HED-563 | Y | Infrastructure | BRONX & N. QUEENS | WATER MAIN WORK IN VARIOUS LOCATIONS, BX | Replace old unlined cast iron pipe water main and improve water distribution in project area. Water main in: 1. W. Kingsbridge Road between Webb Avenue and University Avenue (20") 2. Webb Avenue between W.190th Street and W. Kingsbridge Road (12") 3. University Avenue between W.188th Street and W. Kingsbridge Road (12") 4. W. Kingsbridge Road between Webb Avenue and Grand Avenue (12") 5. Devoe Terrace between W.188th Street and W.190th Street (8") 6. Aqueduct Avenue between W.190th Stree and W. Kingsbridge Road (8") | REPLACEMENT OF WATER MAINS & APPURTENANCES IN WEST KINGBRIDGE ROAD ETC., BRONX | Bronx |  | Environmental Protection | Substantial Completion | Water | Standard | In-House | DDC Managed | PIMS | FALSE |  | 2013 | 2015 |  | DDC
HED564 | HED-564 | Y | Infrastructure | BRONX & N. QUEENS | NEW 20" SUB-AQUEOUS WATER MAIN TO CITY ISLAND | New 20" sub-aqueous water mains on City Island Road (City Island Bridge) between Park Road and City Island Avenue | New 20" sub-aqueous water mains on City Island Road (City Island Bridge) between Park Road and City Island Avenue | Bronx |  | Environmental Protection | Construction Procurement | Water | Standard | Standard Consultant | DDC Managed/Consultant | PIMS | FALSE |  | 2011 |  |  | DDC
HED568 | HED-568 | Y | Infrastructure | BRONX & N. QUEENS | NEW 20" SUB-AQUEOUS WM EXT. TO RANDALL'S ISLAND | New 20" sub-aqueous water main extension to Randall's Island. 20" water main connected from existing 36" water main in Brook Ave and Bruckner Blvd, Bronx to existing 20" water main in Randall's Island. | NEW 20" SUB-AQUEOUS WATER MAIN EXTENSION TO RANDALL'S ISLAND | Bronx |  | Environmental Protection | Construction 50-75% | Water | Standard | Standard Consultant | DDC Managed Consultant | PIMS | FALSE |  | 2012 | 2015 |  | DDC
HED569 | HED569 | Y | Infrastructure | BRONX & N. QUEENS | NSTALLATION OF TRUNK MAIN IN BAINBRIDGE AVE., ETC. | Replacement of Trunk Water Main in Bainbridge Avenue Between Gunhill Road and Holly Lane and in Jerome Avenue Between Holly Lane and E233th Street, etc. Also, New 36" WM in West Burnside Avenue & Phelan Place | Replacement of Trunk Water Main in Bainbridge Avenue Between Gunhill Road and Holly Lane and in Jerome Avenue Between Holly Lane and E233th Street, etc. Also, New 36" WM in West Burnside Avenue & Phelan Place | Bronx |  | Environmental Protection | Construction 0-25% | Water | Standard | DDC Managed/Consultant | DDC Managed/Consultant | PIMS | TRUE |  |  |  |  | DDC
HED569 | HED-569 | Y | Infrastructure | BRONX & N. QUEENS | NSTALLATION OF TRUNK MAIN IN BAINBRIDGE AVE., ETC. | Replacement of Trunk Water Main in Bainbridge Avenue Between Gunhill Road and Holly Lane and in Jerome Avenue Between Holly Lane and E233th Street, etc. Also, New 36" WM in West Burnside Avenue & Phelan Place | Replacement of Trunk Water Main in Bainbridge Avenue Between Gunhill Road and Holly Lane and in Jerome Avenue Between Holly Lane and E233th Street, etc. Also, New 36" WM in West Burnside Avenue & Phelan Place | Bronx |  | Environmental Protection | Construction 0-25% | Water | Standard | DDC Managed/Consultant | DDC Managed/Consultant | PIMS | TRUE |  |  |  |  | DDC
HED570 | HED-570 | Y | Infrastructure | BRONX & N. QUEENS | REPLACEMENT OF TRUNK & DIST WM IN UNIVERSITY AVE | REPLACEMENT OF TRUNK AND DISTRIBUTION WM AND COMBINED SEWER IN UNIVERSITY AVE, BX | Replacement of Trunk and Distribution Water Main and Combined Sewer in University Avenue, Bronx | Bronx |  | Environmental Protection | Pre-Design/PrgDevelopment | Water | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2018 | 2020 |  | DDC
HED573 | HED-573 | Y | Infrastructure | BRONX & N. QUEENS | REPLACEMENT OF WATER MAINS IN WALDO AVE, BX | REPLACEMENT OF WATER MAINS / COMBINED SEWER IN WALDO AVENUE, BX | Trunk & distribution water main work and combined sewer replacement in Waldo Ave between greystone Ave and Irwin Ave, etc. Borough of The Bronx | Bronx |  | Environmental Protection | Construction Procurement | Water | Critical |  |  | PIMS | FALSE |  | 2016 | 2018 |  | DDC
HED574 | HED-574 | Y | Infrastructure | BRONX & N. QUEENS | REPLACEMENT OF WATER MAIN IN BOSTON ROAD, BRONX | REPLACEMENT OF WATER MAIN IN BOSTON ROAD, BRONX | REPLACEMENT OF WATER MAIN IN BOSTON ROAD, BRONX | Bronx |  | Environmental Protection | Cancelled Project | Water | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HEDA001 | HEDA-001 | Y | Infrastructure | BRONX & N. QUEENS | WM - WATER MAINS | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BX | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BX | Bronx |  | Environmental Protection | Substantial Completion | Water | Standard | In-House | Requirement Contract | PIMS | FALSE |  | 2015 | 2015 |  | DDC
HEDA002 | HEDA-002 | Y | Infrastructure | BRONX & N. QUEENS | ACCELERATED DIST. WM REPL.& SE REHAB. BX | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BX | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BX | Bronx |  | Environmental Protection | Construction 25-50% | Water | Critical | In-House | DDC Managed Consultant | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HEDA003 | HEDA-003 | Y | Infrastructure | BRONX & N. QUEENS | ACCELERATED DIST. WM REPL.& SE REHAB. BX | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BX | ACCELERATED DISTRIBUTION WATER MAIN REPLACEMENT AND SEWER REHABILITATION/REPLACEMENT, BX | Bronx |  | Environmental Protection | Construction Procurement | Water | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH112BLEL | HH112BLEL | Y | Public Buildings | HUMAN SERVICES | BELLEVUE SHELTER-ELEVATOR REHAB | Rehabilitation of three (3) 3 Elevators at Bellevue Mens Shelter - 400 E 30th St, NYC | Rehabilitation of 3 Elevators at Bellevue Mens Shelter - 400 E 30th St, NYC | Manhattan |  | Homeless Services | Construction 75%-Subst. | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HH112BLEN | HH112BLEN | Y | Public Buildings | HUMAN SERVICES | Bellevue Mens Shelter: Atrium Area Reconstruction | BELLEVUE MEN'S RESIDENCE- RECONSTRUCT ATRIUM AREA | Reconstruct Atrium area at Bellevue Men's Residence | Manhattan |  | Homeless Services | Scope Development | Renovation | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 |  |  | DDC
HH112BLFS | HH112BDFA | Y | Public Buildings | HUMAN SERVICES | Bellvue Shelter:400 East 30th st. Fire Alarm Alarm | Borden Avenue Fire Safety | Installation of new building wide fire alarm system at Bellevue Men's Shelter | Queens |  | Homeless Services | Scope Development | Upgrade | Critical | Requirement Contract | CM-Managed | PIMS | TRUE |  | 2017 | 2018 |  | DDC
HED-CLUB | HED-CLUB | Y | Public Buildings | DEP | Croton Filtration Plant | The new Mosholu Golf Course Club House, together with fifty-five Driving Range Tee Boxes and ten-acres of re-landscaping comprise the phase IV and final of the vast DEP Croton Water Treatment Plant project, currently under construction in Van Cortlandt Park in the Bronx. Through a multifunctional design strategy the project reinstates the pre-existing golf program and facility, creates civic space for community use and ensures security for a multi-billion dollar public works facility. | The new Mosholu Golf Course Club House, together with fifty-five Driving Range Tee Boxes and ten-acres of re-landscaping comprise the phase IV and final of the vast DEP Croton Water Treatment Plant project, currently under construction in Van Cortlandt Park in the Bronx. Through a multifunctional design strategy the project reinstates the pre-existing golf program and facility, creates civic space for community use and ensures security for a multi-billion dollar public works facility. | Bronx |  | Environmental Protection | Construction Procurement | New Construction | Standard | Standard Consultant | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
HH112AAFS | HH112AAFS | Y | Public Buildings | HUMAN SERVICES | Atlantic Armory:1322 Bedord.BKLYN Fire Alarm Upgra | HH112AAFS Atlantic Avenue Armory Fire Safety | Installation of new building wide fire alarm for Atlantic Armory | Brooklyn |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirement Contract | CM-Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112BATV | HH112BATV | Y | Public Buildings | HUMAN SERVICES | BEDFORD ATLANTIC ARMORY RESIDENCE: CCTV | BEDFORD ATLANTIC Closed Circuit TV | Installation of a building wide CCTV system. | Brooklyn |  | Homeless Services | On-Hold | Other | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH112BDFA | HH112BDFA | Y | Public Buildings | HUMAN SERVICES | Borden Ave Veterans Residence:Fire Alarm Upgrade | Installation of new building wide fire alarm system for Borden Avenue Veteran's Shelter | Installation of new building wide fire alarm system for Borden Avenue Veteran's Shelter | Queens |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112BEES | HH112BEES | Y | Public Buildings | HUMAN SERVICES | BELLEVUE MENS RESIDENCE:ELECTRICAL UPGRADE | BELLEVUE - ELECT SVC UPGRADE | Upgrade electrical service for building including meter room distribution panels. | Manhattan |  | Homeless Services | Final Design | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH112BEES-G | HH112BEES | Y | Public Buildings | HUMAN SERVICES | Bellevue Electrical Upgrade & New Generator | Project ID for bidding HH112BBES and HH112BEGE combined. | Project ID for bidding HH112BEES and HH112BEGE combined. | Manhattan |  | Homeless Services | Final Design | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
HH112BEGE | HH112BEGE | Y | Public Buildings | HUMAN SERVICES | BELLEVUE MENS RESIDENCE: INSTALL NEW GENERATOR | Install natural gas fired emergency generator for building life safety and elevators. | Install natural gas fired emergency generator for building life safety and elevators. | Manhattan |  | Homeless Services | Final Design | Upgrade | Critical | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HH112BLBR | HH112BLBR | Y | Public Buildings | HUMAN SERVICES | Bellevue Men's Shelter: Bathroom Upgrade | The purpose of the project a complete upgrade of all the bathroom throughout the facility for clients, staff and the general public in the facility. | Renovation of all bathroom facilities through out the building; to include new fixtures, ventilation, ADA compliance | Manhattan |  | Homeless Services | Scope Development | Renovation | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 |  |  | DDC
HH112BLCY | HH112BLCY | Y | Public Buildings | HUMAN SERVICES | Bellevue Men's Shelter: Courtyard Reconstruction | Reconstruct Courtyard at Bellevue Shelter | Reconstruct Courtyard at Bellevue Men's Shelter | Manhattan |  | Homeless Services | Scope Development | Renovation | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 |  |  | DDC
HH112BLRR | HH112BLRR | Y | Public Buildings | HUMAN SERVICES | BELLEVUE MENS RESIDENCE: 400-430 30TH | Building envelope rehabilitation with roof and window replacement. | Building roof replacement. | Manhattan |  | Homeless Services | Construction Procurement | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 | 2019 |  | DDC
HH112BLRRFW | HH112BLRR | Y | Public Buildings | Human Services | Bellevue Facade Rehab & Window Replacement | Bellevue Facade Rehab & Window Replacement | Bellevue Facade Rehab & Window Replacement | Manhattan |  | Homeless Services | Construction Procurement | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
HH112BLRR-FW | HH112BLRR | Y | Public Buildings | HUMAN SERVICES | Bellevue Facade Rehab & Window Replacement | Façade and Window Replacement at Bellevue Men's Shelter | Façade and Window Replacement at Bellevue Men's Shelter | Manhattan |  | Homeless Services | Cancelled Project | Upgrade |  | Requirement Contract | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
HH112BLTV | HH112BLTV | Y | Public Buildings | HUMAN SERVICES | BELLEVUE MENS RESIDENCE | HH112BLTV Install new CCTV system in facility | CCTV system installation | Manhattan |  | Homeless Services | Completed Project | Upgrade | Critical | Requirements TO | None | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112BLVT | HH112BLVT | Y | Public Buildings | HUMAN SERVICES | Bellevue Mens Shelter | Bathroom Ventilation Upgrade | Upgrade of Bathroom Ventilation for code compliance | Manhattan |  | Homeless Services | Scope Development | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 |  |  | DDC
HH112BVDV | HH112BVDV | Y | Public Buildings | HUMAN SERVICES | Bellevue Diversion Reconstruction | Complete reconstruction of space to house office and interview spaces, including initial outfitting and furnishing. Space has been taken down to stud level and reconstructed. | Complete reconstruction of space to accommodate client agency office and interview spaces, including initial outfitting and furnishing. Space has been taken down to stud level and reconstructed. | Manhattan |  | Homeless Services | Construction 75%-Subst. | Renovation | Critical | None | JOCS | PIMS | FALSE |  |  |  |  | DDC
HH112BVFA | HH112BVFA | Y | Public Buildings | HUMAN SERVICES | Brownsville Women's Center:357 Saratoga Fire Alarm | Brownsville Women's Fire Safety | Installation of new building wide fire alarm system at Brownsville Women's Shelter | Brooklyn |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112CGIU | HH112CGIU | Y | Public Buildings | HUMAN SERVICES | Keener Assessment Shelter: Fire Alarm Upgrade | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY AND the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | Provide a new code compliant fire alarm system meet to meet FDNY and State OTDA standards. | Manhattan |  | Homeless Services | Scope Development | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2017 |  |  | DDC
HH112CTFS | HH112CTFS | Y | Public Buildings | HUMAN SERVICES | Clarke Thomas Help USA: Fire Alarm Upgrade | Clarke Thomas Fire Safety | Installation of new building wide fire alarm system for Clarke Thomas | Manhattan |  | Homeless Services | Scope Development | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112CWFR | HH112CWFR | Y | Public Buildings | HUMAN SERVICES | 1150 Commonwealth Ave: Fire Alarm Upgrade | Commonwealth Avenue; Fire Safety System | Installation of new building wide fire alarm system for Commonwealth Avenue Shelter | Bronx |  | Homeless Services | Construction Procurement | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112FBFS | HH112FBFS | Y | Public Buildings | HUMAN SERVICES | Fannie Barnes:829 Saratoga Ave.Fire Alarm Upgrade | Fannie Barnes: Fire Safety | Installation of new building wide fire alarm system at Fannie Barnes | Brooklyn |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
PW335MA01 | PW335MA01 | N | Safety and Site Support | HAZMAT | Environmental Database Search
PW335SS01 | PW335SS01 | N | Agency-wide | Agency-wide | Site Safety Citywide
HH112FWFA | HH112FWFA | Y | Public Buildings | HUMAN SERVICES | FORT WASHINGTON ARMORY: FIRE ALARM UPGRADE | HH112FWFA: Fort Washington Armory - Fire Alarm Upgrade | New building wide fire alarm system | Manhattan |  | Homeless Services | Final Design | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH112GDFA | HH112GDFA | Y | Public Buildings | HUMAN SERVICES | G. Daly House: 269 East 4th NY. Fire Alarm Upgrade | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY and the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | Installation of new building wide fire alarm system at George Daly House | Manhattan |  | Homeless Services | On-Hold | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2017 |  |  | DDC
HH112HMFA | HH112HMFA | Y | Public Buildings | HUMAN SERVICES | Harlem 1:2960 FDR Blvd. Fire Alarm Upgrade | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY and the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | Installation of new building wide fire alarm at Harlem 1 Shelter | Manhattan |  | Homeless Services | Design Development | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112HSFA | HH112HSFA | Y | Public Buildings | HUMAN SERVICES | HELP USA:1 Wards Island: Fire Alarm Upgrade | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY AND the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | Installation on new building wide fire alarm system at HELP 1 - Wards Island | Manhattan |  | Homeless Services | Scope Development | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112HWFS | HH112HWFS | Y | Public Buildings | HUMAN SERVICES | Help Womens Center:116 Williams.Fire Alarm Upgrad | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY AND the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | Installation of new building wide fire alarm system at Help Women's Center | Brooklyn |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112KEFA | HH112KEFA | Y | Public Buildings | HUMAN SERVICES | Kenton Hall Shelter:333 Bowery NY.Fire Alarm Upgra | The purpose of the project is to upgrade the existing fire alarm system. The current system does not comply with Code and has had numerous OTDA violations related to the fire alarm system. The fire alarm system has not been approved by FDNY | Installation of new building wide fire alarm system at Kenton Hall | Manhattan |  | Homeless Services | Scope Development | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112LXFA | HH112LXFA | Y | Public Buildings | HUMAN SERVICES | 85 Lexington BKLYN: Fire Alarm Upgrade | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY AND the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | Installation of new building wide fire alarm at 85 Lexington Ave | Brooklyn |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112NPFS | HH112NPFS | Y | Public Buildings | HUMAN SERVICES | New Providence:215-225 East 45th St. Fire Alarm Up | The purpose of the project is to upgrade the existing fire alarm system. The current system does not comply with Code and has had numerous OTDA violations related to the fire alarm system. The fire alarm system has not been approved by FDNY | New fire alarm system at New Providence shelter. | Manhattan |  | Homeless Services | Design Development | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112PJBO | HH112PJBO | Y | Public Buildings | HUMAN SERVICES | PAMOJA HOUSE:357 MARCUS GARVEY BLVD.BOILER REPLACE | Boiler replacement. | Boiler replacement. | Brooklyn |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
HH112PJRC | HH112PJRC | Y | Public Buildings | HUMAN SERVICES | Pamoja House:357 Marcus Garvey Fire Alarm Upgrade | The purpose of the project is to upgrade the existing fire alarm system. The current system does not comply with Code and has had numerous OTDA violations related to the fire alarm system. The fire alarm system has not been approved by FDNY | New fire alarm system at Pamoja House shelter. | Brooklyn |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112POTV | HH112POTV | Y | Public Buildings | HUMAN SERVICES | POWERS FAMILY SHELTER: CCTV | Installation of new building wide CCTV system. | Installation of new building wide CCTV system. | Bronx |  | Homeless Services | On-Hold | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
HH112SKFA | HH112SKFA | Y | Public Buildings | HUMAN SERVICES | B. Kleiman:300 Skillman Ave. Fire Alarm Upgrade | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY AND the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | New fire alarm system at the Barbara S Kleiman shelter. | Brooklyn |  | Homeless Services | Cancelled Project | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112SKTV | HH112SKTV | Y | Public Buildings | HUMAN SERVICES | BARBARA KLEIN MAN: CCTV | Installation of new building wide CCTV system. | Installation of new building wide CCTV system. | Brooklyn |  | Homeless Services | Cancelled Project | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH112SWFA | HH112SWFA | Y | Public Buildings | HUMAN SERVICES | Schwartz Asses:1 Wards Island.Fire Alarm Upgrade | The purpose of the project is to upgrade the existing fire alarm system. The current system does not comply with Code and has had numerous OTDA violations related to the fire alarm system. The fire alarm system has not been approved by FDNY | New fire alarm system at the Shwartz Assessment Center, Wards Island. | Manhattan |  | Homeless Services | Scope Development | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112THFA | HH112THFA | Y | Public Buildings | HUMAN SERVICES | 3rd Shelter: 8 East 3rd St. Fire Alarm Upgrade | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY AND the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | New fire alarm system at 8 East 3rd Street shelter. | Manhattan |  | Homeless Services | Design Development | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112VEFP | HH112VEFP | Y | Public Buildings | HUMAN SERVICES | Street Vets Residence:E.119th Fire Alarm Upgrade | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY AND the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | New fire alarm system at the E119th Street Veteran's Residence shelter. | Manhattan |  | Homeless Services | Scope Development | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH112WBLR | HH112WBLR | Y | Public Buildings | Health | WARDS ISLAND-BOILERS AND FUEL STORAGE TANKS | To furnish and provide for all Architectural, Engineering and Construction related services necessary to support the installation a New Central Boiler Plant and Fuel Tanks at Wards Island. (Randall's Island) | Provide architectural, engineering and construction related services to support installation of new Boilers and fuel storage tanks |  |  | Homeless Services | Acceptance/Final Completion | New Construction | Critical | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
PWD5JCCR | PWD5JCCR | N | Public Buildings | Pass Through | Jewish Comm Council of Rockaway Peninsula-Ph II |  |  |  |  | Aging | Cancelled Project | Renovation | Standard | Pass Through | Pass Through | [6 empty] | DDC
PWD5LIUC2 | PWD5LIUC2 | N | Law | Miscellaneous | BROOKLYN CAMPUS - LIU CYBER CENTER
HH112WLFA | HH112WLFA | Y | Public Buildings | HUMAN SERVICES | Willow Ave Family Residence:Fire Alarm Upgrade | The purpose of the project is to upgrade the existing fire alarm system. The current system does not comply with Code and has had numerous OTDA violations related to the fire alarm system. The fire alarm system has not been approved by FDNY | New fire alarm system at the Willow Ave Family Residence shelter. | Bronx |  | Homeless Services | Construction Procurement | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH115BWFA | HH115BWFA | Y | Public Buildings | HUMAN SERVICES | Briarwood Family Residence: Fire Alarm Upgrade | HH115BWFA: Briarwood - Fire Alarm Upgrade | Installation of a new building wide fire alarm system. | Queens |  | Homeless Services | Construction 0-25% | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115BWKF | HH115BWKF | Y | Public Buildings | HUMAN SERVICES | Bushwick Family Residence: FIRE ALARM UPGRADE | HH115BWKF: Bushwick Fire Alarm System Upgrade | Installation of new building wide fire alarm system. | Brooklyn |  | Homeless Services | Construction Procurement | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115CSBR-F | HH115CSBR | Y | Public Buildings | Health | GENERATOR-FLUE AT CATHERINE STREET RESIDENCE | Extension of emergency generator flue. Address: 78 Catherine Street New York, NY 10038 Block:111 Lot: 150 | Provide extension to the emergency generator flue. |  |  | Homeless Services | Maintenance | Upgrade | Standard | Requirements TO | JOCs | Project Info | FALSE |  |  |  |  | DDC
HH115CSRR | HH115CSRR | Y | Public Buildings | Health | DHS 78 Catherine Street - Roof Replacement | 78 Catherine Street New York, NY 10038 Block: #111 Lot: #150 Replacement of roof and court yard parapet and façade renovation | Replace roof and courtyard parapet, and perform façade restoration. |  |  | Homeless Services | Maintenance | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HH115DSFA | HH115DSFA | Y | Public Buildings | HUMAN SERVICES | Dean Street Family Residence-Fire Alarm Upgrade | Install new fire alarm devices including asbestos abatement, FACP, smoke Detectors, manual pull stations, strobes and horn/strobes on all floors and egress corridors to meet current Code requirements. Obtain FNDY approval for entire fire alarm system. Provide fire stropping at all floor and corridor penetrations. | Install new building wide fire alarm system and obtain FNDY approval. | Brooklyn |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
HH115FFTV | HH115FFTV | Y | Public Buildings | HUMAN SERVICES | FLATLANDS FAMILY CCTV | Installation of new CCTV system through out facility | Installation of new CCTV system throughout facility | Brooklyn |  | Homeless Services | Design Development | Renovation | Critical | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
HH115FRFA | HH115FRFA | Y | Public Buildings | HUMAN SERVICES | FREEMAN HOUSES: FIRE ALARM UPGRADE | HH115FRFA: Freeman Family Residence - Fire Alarm System Upgrade | Installation of a new building wide fire alarm system. | Bronx |  | Homeless Services | Construction 0-25% | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115FTXUCW | HH115FTXU | Y | Public Buildings | Health | FORT WASHINGTON ARMORY-CLEAR STOREY WINDOW | Scope of Work provides for the complete refurbishing of the existing clerestory glazing with all steel framing scraped, primed and painted. | Refurbishing of the clerestory glazing with all steel framing scraped, primed and painted. |  |  | Homeless Services | Maintenance | Renovation | Standard | Requirements TO | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
HH115HHFA | HH115HHFA | Y | Public Buildings | HUMAN SERVICES | Hospitality House:100 Central House- fire alarm | Hospitality at 100 Central Ave., 10301 - Fire Alarm Upgrade | Installation of new building wide fire alarm system. | Staten Is. |  | Homeless Services | Construction 0-25% | Other | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115HLEK | HH115HLEK | Y | Public Buildings | HUMAN SERVICES | HELP 1: 515 BLAKE AVE ELECTRICAL UPGRADE | Upgrade all electrical wiring and receptacles and upgrade kitchen cabinets and countertops. | Upgrade all electrical wiring and receptacles and upgrade kitchen cabinets and countertops. | Brooklyn |  | Homeless Services | Cancelled Project | Upgrade | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HH115HLFS | HH112HLFS | Y | Public Buildings | HUMAN SERVICES | 515 BLAKE AVE, | Envelope rehabilitation including parapets, roof, and window replacement. | Envelope rehabilitation including parapets, roof, and window replacement. | Brooklyn |  | Homeless Services | Cancelled Project | Upgrade | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HH115JCFB | HH115JCFB | Y | Public Buildings | HUMAN SERVICES | Jennie Clark: Fire Alarm Upgrade | JENNIE CLARK RESIDENCE - FIRE ALARM UPGRADE | Installation of new building wide fire alarm system. | Manhattan |  | Homeless Services | Construction Procurement | Other | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115JCFS | HH115JCFS | Y | Public Buildings | HUMAN SERVICES | Jackson Family Residence:Fire Alarm Upgrade | The purpose of the project is to have a Code compliant fire alarm system (meet FDNY AND the State OTDA standards) and protect the multiple clients, staff and the general public in the facility. | New fire alarm system for the Jackson Family Residence shelter. | Bronx |  | Homeless Services | Construction Procurement | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH115JCTV | HH115JCTV | Y | Public Buildings | HUMAN SERVICES | jENNIE A CLARK: 179-191 EAST 100 ST. CCTV | Installation of new building wide CCTV system. | Installation of new building wide CCTV system. | Manhattan |  | Homeless Services | On-Hold | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
HH115JWTV | HH115JWTV | Y | Public Buildings | HUMAN SERVICES | JAMAICA ASSESSMENT CENTER: CCTV | HH115JWTV JAMAICA FAMILY SHELTER CCTV | New CCTV system installation at the Jamaica Family Residence Shelter. | Queens |  | Homeless Services | On-Hold | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115LFAU | HH115LFAU | Y | Public Buildings | HUMAN SERVICES | Linden Family Residence:501 New Lots.Fire Alarm | HH115LFAU Linden Fire Alarm Upgrade | New fire alarm system installation at the Linden Family Residence Shelter. | Brooklyn |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HH115LFTV | HH115LFTV | Y | Public Buildings | Health | LIFE FAMILY CENTER-INSTALLATION OF CCTV | Installation of CCTV (closed circuit television system). | Installation of CCTV (closded circuit television system). |  |  | Homeless Services | Maintenance | Other | Standard | None | JOCs | PIMS | FALSE
HH115REGX-1 | HH115REGX | Y | Public Buildings | HUMAN SERVICES | Regents Family Residence Ext Rest Conslt Dsgn | The consultant shall prepare the Preliminary and Final Design documents and render the necessary Services during Construction required to provide for the complete restoration and rehabilitation of the facility, including the removal of all exterior violations and the filing of required LL 10/80 and LL 11/98 Reports. | Exterior envelope rehabilitation. | Manhattan |  | Homeless Services | Construction Procurement | Renovation | Standard | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
HH115RFEU | HH115RFEU | Y | Public Buildings | HUMAN SERVICES | REGENT FAMILY RESIDENCE, APT ELECTRICAL UPGRADE | Electrical upgrade of all wiring from the distribution panel to the apartment units. | Electrical upgrade of all wiring from the distribution panel to the apartment units. | Manhattan |  | Homeless Services | Schematic Design | Upgrade | Critical | Requirement Contract | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HH115RGEL | HH115RGEL | Y | Public Buildings | HUMAN SERVICES | REGENT FAMILY RESIDENCE | Regent Elevator Reconstruction | Regent Family Residence Elevator Reconstruction | Manhattan |  | Homeless Services | Schematic Design | Other | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  | 2017 |  |  | DDC
HH115SFFA | HH115SFFA | Y | Public Buildings | HUMAN SERVICES | STOCKHOLM FAMILY RESIDENCE: FIRE ALARM UPGRADE | HH115SFFA-Stockholm at 99-103 Stockholm St, 11221 - Fire Alarm Upgrade | Installation of new building wide fire alarm system. | Brooklyn |  | Homeless Services | Construction 0-25% | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115SGFA | HH115SGFA | Y | Public Buildings | HUMAN SERVICES | SPRINGFIELD GDNS FAMILY RESIDENCE: FIRE ALARM UPGR | Installation of new building wide fire alarm system. | Installation of new building wide fire alarm system. | Queens |  | Homeless Services | Construction 0-25% | Upgrade | Critical | Requirements TO | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115SNFA | HH115SNFA | Y | Public Buildings | HUMAN SERVICES | SENECA HOUSE: FIREM ALARM UPGRADE | Installation of new building wide fire alarm system. | Installation of new building wide fire alarm system. | Bronx |  | Homeless Services | Final Design | Upgrade | Critical | Requirement Contract | CM-Managed | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115SRFA | HH115SRFA | Y | Public Buildings | HUMAN SERVICES | Rose McCarthy Family Residence: Fire alarm Upgrade | Installation of new building wide fire alarm system. | Installation of new building wide fire alarm system. | Brooklyn |  | Homeless Services | Construction Procurement | Upgrade | Critical | Requirement Contract | JOCS | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HH115UNFA | HH115UNFA | Y | Public Buildings | HUMAN SERVICES | UNIV. fAMILY RESIDENCE FIRE ALARM UPGRADE BRONX | Installation of new building wide fire alarm system. | Installation of new building wide fire alarm system. | Bronx |  | Homeless Services | Final Design | Upgrade | Critical | Requirement Contract | CM-Managed | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HL82125VR | HL82125VR | Y | Public Buildings | Health | 125 Worth St 1st Fl Vital records | Renovation for the Public Services Operation (PSO) Unit of DOHMH’s Office of vital records (Birth certificates). | Perform renovation work for the Public Service Operations Unit of the DOHMH Office of Vital Records. |  |  | Health | Acceptance/Final Completion | Renovation | Critical | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HL82BRKLN | HL82BRKLN | Y | Public Buildings | HEALTH | Upgrades at Brooklyn Animal Shelter | A complete HVAC & selected building upgrades, including but not limited to: New HVAC equipment, commissioning, building components upgrade as required, new roofing, skylights, ceilings, lighting, finishes, doors, windows, screens, and site upgrade as needed. | A complete HVAC & selected building upgrades, including but not limited to: new HVAC equipment, commissioning, building components upgrade as required, new roofing, skylights, ceilings, lighting, finishes, doors, windows, screens, and site upgrade as needed. | Brooklyn |  | Health | Schematic Design | Renovation | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  | 2016 | 2018 |  | DDC
HL82BUSHX-1 | HL82BUSHX | Y | Public Buildings | HEALTH | Bushwick Health Ctr Exter Restor Consul dsgn | The consultant shall prepare the Preliminary and Final Design documents and render the necessary Services during Construction required to provide for the complete restoration and rehabilitation of the facility. The building envelope and all of its components shall be restored to alleviate moisture penetration and to restore the interior spaces damaged by water infiltration. | Bushwick Health Center Exterior rehabilitation including roof, windows/lintels, parapets and site work. | Brooklyn |  | Health | Final Design | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HL82CHELI-R | HL82CHELI | Y | Public Buildings | Health | CHELSEA HEALTH CENTER UPGRADES | The work involves general construction, new elevator, total upgrade of the HVAC & electrical systems at basement, 1st & 2nd floors. ADA accessibility and compliance. | General construction incuding new elevator, upgraded HVAC & electrical systems, ADA accessibility compliance. |  |  | Health | Construction 75%-Subst. | Renovation | Standard | Requirements TO | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
HL82CORHC | HL82CORHC | Y | Public Buildings | HEALTH | Renovations at Corona Health Center | The project is an overall site and entire building envelope renovation/upgrade. The building envelope and all of its components shall be renovated and upgraded to correct façade deterioration and eliminate unsafe conditions. The Entrance, Lobby and Cellar level (gut renovations) shall be redesigned as well. See attachment “B”,( Outline Scope of Work) |  | Queens |  | Health | Scope Development | Renovation | Standard | Requirements TO |  | PIMS | FALSE |  |  |  |  | DDC
HL82FGHVC-B | HL82FGHVC | Y | Public Buildings | Health | BASEMENT & VAULT RENOVATION AT FORT GREENE HEALTH | Gut renovation of basement and subbasement vault area including new fire suppression and climate control systems, and upgrades to building-wide ventilation systems. | Install/modify RPZ (reduced pressure zone) valves which prevent backflow into the public water system.. |  |  | Health | Maintenance | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HL82GRPRSIT | HL82GRPRS | Y | Public Buildings | Health | PRISON HEALTH WAREHOUSE-IT ROOM | Construction of New IT room including required HVAC units, FA & sprinkler modifications. | Construction of new IT room including required HVAC units, fire alarm and sprinkler systems.. |  |  | Health | Maintenance | Renovation | Standard | Requirements TO | JOCs | Project Info | FALSE
HL82HCRST | HL82HCRST | Y | Public Buildings | Health | EXTERIOR RENOVATIONS @ HOMECREST HC | - Installation of new roofs, flashing and associated parapet repair or replacement as needed. - Seal, repoint and repair all existing masonry and stone as required, with special attention to structural elements. - Replace corroded lintels with new as required at windows, exterior doors and skylights with caulk and flashing throughout. - Replace doors, windows, and security screens as needed. - Provide new stair bulkhead skylight. - Repair or replace exterior site elements, such as site drainage, handicap ramp, retaining walls, fencing, sidewalks, paved areas. | Exterior renovation including installation of new roofs and associated components; repair and repointing of masonry and stone; new lintels, windows, exterior doors and skylights as needed; repair/replace site elements including handicap ramp, retaining walls, fencing, sidewalks and paving. |  |  | Health | Maintenance | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE
HL82JAMCXF | HL82JAMCX | Y | Public Buildings | Health | JAMAICA HEALTH CENTER-FIRE ALARM | Install new fire alarm system in the Main and Annex Buildings. | Install new fire alarm system in the Main and Annex Buildings. |  |  | Health | Maintenance | Renovation | Standard | Standard Consultant | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
HL82MANAT | HL82MANAT | Y | Public Buildings | Health | Manhattan Animal Apoption Shelter Center: Upgrade | Upgrade existing Garage to an Adoption Center at 323 E 109 St., Selected Upgrades to Site and Shelter at 326 E 110 St. -Installation of new HVAC equipment w/ commissioning -Installation of architectural elements; spaces, roof, skylights, ceilings, lighting and finishes -Replace or refurbish selected additional site elements such as exterior kennels, site drainage, sidewalks parking lot or paved areas etc. as needed | Upgrade existing garage to an Animal Adoption Center. | Manhattan |  | Health | Schematic Design | Renovation | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  | 2016 | 2021 |  | DDC
HL82RPZ2-1 | HL82RPZ2 | Y | Public Buildings | Health | Install RPZ Valves at Morrisania Health Center | Install/modify RPZ (reduced pressure zone) valves which prevent backflow into the public water system. | Install/modify RPZ (reduced pressure zone) valves which prevent backflow into the public water system. |  |  | Health | Maintenance | Upgrade | Standard | Requirements TO | JOCs | Project Info | FALSE |  |  |  |  | DDC
PWD998SFY | PWD998SFY | N | Law | Miscellaneous | SAMUEL FIELD YMHA
PWD998TLL | PWD998TLL | N |  | Miscellaneous | THERESA LONG THEATER LIGHTING
PWD998YWC | PWD998YWC | N |  | Miscellaneous | YWCA OF NYC EQUIPMENT
HL82RPZ2-2 | HL82RPZ2 | Y | Public Buildings | Health | INSTALLATION OF RPZ VALVES AT WILLIAMSBURG | Install/modify RPZ (reduced pressure zone) valves which prevent backflow into the public water system. | Install/modify RPZ (reduced pressure zone) valves which prevent backflow into the public water system. |  |  | Health | Maintenance | Upgrade | Standard | Requirements TO | JOCs | Project Info | FALSE |  |  |  |  | DDC
HL82RPZ2-3 | HL82RPZ2 | Y | Public Buildings | Health | INSTALLATION OF RPZ VALVES AT JAMAICA | Install/modify RPZ (reduced pressure zone) valves which prevent backflow into the public water system. | Install/modify RPZ (reduced pressure zone) valves which prevent backflow into the public water system. |  |  | Health | Maintenance | Upgrade | Standard | Requirements TO | JOCs | Project Info | FALSE |  |  |  |  | DDC
HL82RVREX-E | HL82RVREX | Y | Public Buildings | Health | Extension & Gut Renovation: Riverside Health Ctr. | Exterior upgrade and gut interior renovation, including new building extension. Project is targeted for a Percent for Art installation and LEED Silver certification. | Exterior upgrade and gut interior renovation, including new building extension. Project is targeted for a Percent for Art installation and LEED Silver certification. |  |  | Health | Maintenance | Upgrade | Critical | Requirements TO | CM-Managed | PIMS | FALSE |  |  |  |  | DDC
HL82SIABEX | HL82SIABE | Y | Public Buildings | Health | S. I. ANIMAL SHELTER - Expansion & Renovation | This project has phased renovation and expansion of the existing building totaling 5,300 square foot animal care and control facility. The expansion and renovation involves new electrical, plumbing and mechanical ventilation system utilizing 100% fresh air. The renovation and expansion is to achieve a LEED silver certification. 3139 Veterans Road West Staten Island, New York 10309 | Renovation and expansion of the existing facility including new electrical, plumbing and ventilation systems. This project is targeted for LEED silver certification. |  |  | Health | Construction 50-75% | Renovation | Critical | Individual Contract(s) | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
HLEXP17BR | HLEXP17BR | Y | Public Buildings | HEALTH | Brownsville Health Center:259 Bristol St, Brooklyn | Brownsville health center | Brownsville Health Center Renovation | Brooklyn |  | Health | Maintenance | Renovation | Critical | JOCS |  | PIMS | FALSE |  |  |  |  | DDC
HR25FACA-1 | HR25FACA | Y | Public Buildings | Health | Facade Restoration - Brooklyn | The scope of work is the exterior restoration of two buildings in Brooklyn. This includes the replacement of roof, façade restoration and replacement of windows. | Exeterior restoration of two buildings in Brooklyn including roof replacement, facade renovation and window replacement. |  |  | SocialServices-HRA | Construction 75%-Subst. | Renovation | Standard | Requirements TO | DDC Managed | Project Info | FALSE
HR25FACA-2 | HR25FACA | Y | Public Buildings | HUMAN SERVICES | FACADE RESTORATION - BRONX | The scope of work is the exterior restoration of two buildings in Bronx. This includes the replacement of roof, façade restoration and replacement of windows. | Exterior restoration of two buildings in the Bronx. This includes the replacement of roof, facade restoration and replacement of windows. | Unknown |  |  | Substantial Completion | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HR25FACA-3 | HR25FACA | Y | Public Buildings | HUMAN SERVICES | Facade Retoration - Manhattan | The scope of work is the exeterior restoration of three buildings in Manhattan. This includes the replacement of roof, façade restoration and replacement of windows. | The scope of work is the exterior restoration of three buildings in Manhattan. This includes the replacement of roof, façade restoration and replacement of windows. | Manhattan |  |  | Construction 0-25% | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
RQ_QU | RQ_QU | N | Infrastructure | S. Queens | Holding Code for RCs for S. Queens
RQ_SC | RQ_SC | N | Public Buildings | Schools | Holding Code for RCs for Schools Unit
HW2CR14B | HW2CR14B | Y | Infrastructure | MANHATTAN & CITYWIDE | CITYWIDE MILLING - BX & MN | Milling Contract for Boroughs of Bronx and Manhattan Milling of Streets in Preparation for Resurfacing by DOT Roadway Repair & Maintenance. | Milling Contract - citywide | Citywide |  | Transportation | Substantial Completion | Street Resurfacing | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2013 | 2014 |  | DDC
HW2CR14C | HW2CR14C | Y | Infrastructure | S. QUEENS | BOROUGH WIDE MILLING - QUEENS | Milling contract Borough Wide. Milling of streets in preparation for resurfacing by DOT Highway Operations.Locations to be determined by DOT Highway Operations | Milling contract Borough Wide. Milling of streets in preparation for resurfacing by DOT Highway Operations.Locations to be determined by DOT Highway Operations | Queens |  | Transportation | Substantial Completion | Street Resurfacing | Standard | In-House | Requirements TO | PIMS | FALSE |  |  | 2014 |  | DDC
HW2CR15A | HW2CR15A | Y | Infrastructure | BROOKLYN | MILLING - BROOKLYN AND STATEN ISLAND | Milling for Brooklyn and Staten Island. Milling for streets in preparation for resurfacing by DOT Highway Operations | Milling for Brooklyn and Staten Island. Milling for streets in preparation for resurfacing by DOT Highway Operations | Citywide |  | Transportation | Substantial Completion | Street Resurfacing | Standard | In-House | Requirement Contract | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HW2CR15CW | HW2CR15CW | Y | Infrastructure | MANHATTAN & CITYWIDE | CITYWIDE MILLING | Milling contract for all Five Boroughs. Milling of streets in preparation for Resurfacing by DOT Roadway Repair & Maintenance (RRM) division. | Milling Contract - citywide | Citywide |  | Transportation | Substantial Completion | Street Resurfacing | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2015 | 2015 |  | DDC
HW2CR16B | HW2CR16B | Y | Infrastructure | MANHATTAN & CITYWIDE | CITYWIDE MILLING - BX & MN | CITYWIDE MILLING - BX & MN | Citywide Milling - Bronx & Manhattan | Citywide |  | Transportation | Completed Project | Street Resurfacing | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HW2CR16C | HW2CR16C | Y | Infrastructure | S. QUEENS | BOROUGH-WIDE MILLING IN QUEENS | BOROUGH-WIDE MILLING IN QUEENS | Locations will be provided by NYC DOT, Division of Roadway Repaire and Maintenance. | Queens |  | Transportation | Completed Project | Street Resurfacing | Critical | In-House | DDC Managed/Consultant | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HW2CR16D | HW2CR16D | Y | Infrastructure | BRONX & N. QUEENS | CITYWIDE MILLING - BRONX, MANHATTAN & QUEENS | CITYWIDE MILLING - BRONX, MANHATTAN & QUEENS | Milling of asphaltic concrete asphalt on designated streets in the boroughs of Manhattan and Queens | Citywide |  | Transportation | Construction Procurement | Street Resurfacing | Critical |  |  | PIMS | FALSE |  | 2016 | 2016 |  | DDC
HW2CR16E | HW2CR16E | Y | Infrastructure | BROOKLYN | CITYWIDE MILLING - BROOKLYN, QUEENS & SI | CITYWIDE MILLING - BROOKLYN, QUEENS & STATEN ISLAND | CITYWIDE MILLING - BROOKLYN, QUEENS & STATEN ISLAND | Citywide |  | Transportation | Construction 25-50% | Street Resurfacing | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2016 |  | DDC
HW2CR17A | HW2CR17A | Y | Infrastructure | BROOKLYN | CITYWIDE MILLING - BROOKLYN & STATEN ISLAND | CITYWIDE MILLING - BROOKLYN & STATEN ISLAND | CITYWIDE MILLING - BROOKLYN & STATEN ISLAND |  |  | Transportation | Construction 0-25% | Street Resurfacing | Critical | In-House | Requirements TO | PIMS | FALSE
HW2CR17CW | HW2CR17CW | Y | Infrastructure | MANHATTAN & CITYWIDE | CITYWIDE MILLING - CITYWIDE | CITYWIDE MILLING - CITYWIDE | CITYWIDE MILLING - CITYWIDE | Citywide |  | Transportation | Cancelled Project | Street Resurfacing | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HW2CR18B | HW2CR18B | Y | Infrastructure | MANHATTAN & CITYWIDE | Citywide Milling-Bronx & Manhattan | MILLING OF STREETS IN PREPARATION FOR PAVING BY DOT'S ROADWAY REPAIR & MAINTENANCE(RRM) DIVISION. | MILLING OF STREETS IN PREPARATION FOR PAVING BY DOT'S ROADWAY REPAIR & MAINTENANCE(RRM) DIVISION. | Citywide |  | Transportation | Cancelled Project | Street Resurfacing | Critical | In-House |  | PIMS | FALSE |  |  | 2018 |  | DDC
HW2CR18C | HW2CR18C | Y | Infrastructure | S. QUEENS | Citywide Milling - Queens | MILLING OF STREETS IN PREPARATION FOR PAVING BY DOT'S ROADWAY REPAIR & MAINTENANCE (RRM) DIVISION. | Milling of streets in Queens in preparation for DOT's Roadway Repair & Maintenance (RRM) division. This scope calls for the paving and micro-milling of 295.45 lane miles. This contract has a two year duration with two one year renewal options (with escalations). | Queens |  | Transportation | Cancelled Project | Street Reconstruction | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HW2CR18D | HW2CR18D | Y | Infrastructure | BRONX & N. QUEENS | Citywide Milling-Bronx Manhattan & Queens | MILLING OF STREETS IN PREPARATION FOR RESURFACING BY DOT'S ROADWAY REPAIR & MAINTENANCE (RRM) DIVISION. | MILLING OF STREETS IN PREPARATION FOR RESURFACING BY DOT'S ROADWAY REPAIR & MAINTENANCE (RRM) DIVISION. | Bronx |  | Transportation | Cancelled Project | Street Resurfacing | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HW2CR18E | HW2CR18E | Y | Infrastructure | STATEN ISLAND | Citywide Milling-Brooklyn Queens & Staten Island | MILLING OF STREETS IN PREPARATION FOR RESURFACING BY DOT'S ROADWAY REPAIR & MAINTENANCE (RRM) DIVISION. | MILLING OF STREETS IN PREPARATION FOR RESURFACING BY DOT'S ROADWAY REPAIR & MAINTENANCE (RRM) DIVISION. | Brooklyn |  | Transportation | Cancelled Project | Street Resurfacing | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HW349FED2 | HW349FED2 | Y | Infrastructure | STATEN ISLAND | ENGINEERING RESURFACING PHASE II, CITYWIDE | ENGINEERING RESURFACING PHASE II, CITYWIDE | ENGINEERING RESURFACING PHASE II, CITYWIDE(X761.19)(D034790) | Staten Is. |  | Transportation | Substantial Completion | Street Resurfacing | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HW349FED3 | HW349FED3 | Y | Infrastructure | S. QUEENS | CITYWIDE MILLING (FEDERAL EARMARK) - QUEENS | RESURFACING, PAVEMENT IMPROVEMENTS, AND GENERAL REPAIRS CONTRACT TO REHABILITATE SECTIONS OF JAMAICA AVENUE (FROM 168 STREET TO FRANCIS LEWIS BOULEVARD) AND 21 STREET (FROM 47 AVENUE/JACKSON AVENUE TO BROADWAY) IN QUEENS. | RESURFACING, PAVEMENT IMPROVEMENTS, AND GENERAL REPAIRS CONTRACT TO REHABILITATE SECTIONS OF JAMAICA AVENUE (FROM 168 STREET TO FRANCIS LEWIS BOULEVARD) AND 21 STREET (FROM 47 AVENUE/JACKSON AVENUE TO BROADWAY) IN QUEENS. | Queens |  | Transportation | Substantial Completion | Street Resurfacing | Critical | In-House |  | PIMS | FALSE |  |  |  |  | DDC
HWBARUCH | HWBARUCH | Y | Infrastructure | MANHATTAN & CITYWIDE | BARUCH COLLEGE PLAZA - E. 25TH STREET (MED-634) | 1. HWBARUCH - Construction of a permanent pedestrian plaza, on East 25th Street from Lexington Ave. to Third Avenue. The plaza will include seating, plantings, pedestrian lighting, etc., Borough of Manhattan 2. MED634 - WM work in E25th Street between 3rd Ave and Lexington Ave. | 1. HWBARUCH - Construction of a permanent pedestrian plaza, on East 25th Street from Lexington Ave. to Third Avenue. The plaza will include seating, plantings, pedestrian lighting, etc., Borough of Manhattan 2. MED634 - WM work in E25th Street between 3rd Ave and Lexington Ave. | Manhattan |  | Transportation | Construction Procurement | Other | Standard | Requirements TO | DDC Managed/Consultant | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWBUSPAD6 | HWBUSPAD6 | Y | Infrastructure | S. QUEENS | Citywide Bus Pad Contract (SIM) | Citywide Bus Pad Contract (SIM) | Citywide Bus Pad Contract | Citywide |  | Transportation | Construction 0-25% | Other | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWCBLSTN1 | HWCBLSTN1 | Y | Infrastructure | MANHATTAN & CITYWIDE | WOOSTER STREET RECONSTRUCTION (MED605) | Rehabilitation of Cobblestone Street in Historic District: Wooster St. from Canal Street to W. Houston St., Manhattan. The street bed shall be rehabilitated curb to curb. The project will include some curb replacement, pedestrian ramps, catch basins, replacement of watermain and sewers, etc. | Rehabilitation of Cobblestone Street in Historic District: Wooster St. from Canal Street to W. Houston St., Manhattan |  |  | Transportation | Cancelled Project | Street Reconstruction | Standard | In-House | DDC Managed/Consultant | PIMS | FALSE
HWCBLSTN1 | MED-605 | Y | Infrastructure | MANHATTAN & CITYWIDE | WOOSTER STREET RECONSTRUCTION (MED605) | Rehabilitation of Cobblestone Street in Historic District: Wooster St. from Canal Street to W. Houston St., Manhattan. The street bed shall be rehabilitated curb to curb. The project will include some curb replacement, pedestrian ramps, catch basins, replacement of watermain and sewers, etc. | Rehabilitation of Cobblestone Street in Historic District: Wooster St. from Canal Street to W. Houston St., Manhattan |  |  | Transportation | Cancelled Project | Street Reconstruction | Standard | In-House | DDC Managed/Consultant | PIMS | FALSE
HWCPEDLOC | HWCPEDLOC | Y | Infrastructure | MANHATTAN & CITYWIDE | PERIMETER SECURITY MEASURES | This project will install security features around six locations within Manhattan: 1. Broadway at Bowling Green 2. Penn Station 3. Rockefellar Center and St. Patrick's Cathedral 4. Herald Square 5. The Empire State Building 6. Flatiron Plaza |  |  |  | Transportation | [5 empty] | Project Info | FALSE |  |  |  | 2017-12-01 13:00:19.9570000 +00:00
HWCSCH3A | HWCSCH3A | Y | Infrastructure | STATEN ISLAND | SCHOOL SAFETY IMPROVEMENT, PHASE III - 4 SCHOOLS | Implementation of school-safety intended street improvements at 3 school locations in Queens, Manhattan and Brooklyn (1 each per borough, revised total). Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals g. Landscaping h. Water main replacement i. Sewer replacement Locations include: Queens: PS 136 - 201-15 115th Ave., Q/cb 12 Manhattan: PS 7 - 160 East 120th St., M/cb 11 (Force Account Approval 04/02/10) Brooklyn: PS 6 - 43 Snyder Ave., K/cb 14 DELETED - Holy Cross - 2520 Church Ave., K/cb 14 DOT indicates school is now closed | Implementation of school-safety intended street improvements at 3 school locations in Queens, Manhattan and Brooklyn (1 each per borough, revised total). Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals g. Landscaping h. Water main replacement i. Sewer replacement Locations include: Queens: PS 136 - 201-15 115th Ave., Q/cb 12 Manhattan: PS 7 - 160 East 120th St., M/cb 11 (Force Account Approval 04/02/10) Brooklyn: PS 6 - 43 Snyder Ave., K/cb 14 DELETED - Holy Cross - 2520 Church Ave., K/cb 14 DOT indicates school is now closed | Citywide |  |  | Substantial Completion | Street Reconstruction | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
HWCSCH3B2 | HWCSCH3B | Y | Infrastructure | MANHATTAN & CITYWIDE | SAFE ROUTES TO SCHOOLS-(X770.66 P I) 4 MAN | Implementation of school-safety intended street improvements at 4 Manhattan schools located in Manhattan community boards 7 & 12-(X770.66 P I) . Four (4) Manhattan schools: 1. Collegiate School - 260 W 78th St; M/cb 7 2. MS 54 - 103 W 107th St; M/cb 7 3. Ascension School - 220 W 108th St; M/cb 7 4. Incarnation School - 570 W 175th St;M/cb 12 | Implementation of school-safety intended street improvements at 4 Manhattan schools located in Manhattan community boards 7 & 12-(X770.66 P I) . Four (4) Manhattan schools: | Manhattan |  | Transportation | Construction 50-75% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2010 | 2015 |  | DDC
RQ_T | RQ_T | N | Public Buildings | Transportation | Holding Code for RCs for Transportation Unit
RQCM_LRG | RQCM_LRG | N | Agency-wide | Miscellaneous | Requirements CM Large
HWCSCH3B3 | HWCSCH3B | Y | Infrastructure | S. QUEENS | SAFE ROUTES TO SCHOOLS-(X770.66 P II) 4 QNS | REVISED: Implementation of school-safety intended street improvements at 4 Queens schools. (Subproject of HWCSCH 3-series program.) Work scope includes, but not limited to: a. street resurfacing b. curb and sidewalk work c. bus pads d. pedestrian ramps e. infrastructure utility work f. speed reducers g. street lights and traffic signals h. landscaping REVISED 4 Queens schools 1. PS 108 - 108-10 109th Ave; Q/cb 10 2. St. Stanislaus Kostka School - 61-17 Grand Ave; Q/cb 5 3. St. Joan of Arc School - 35-27 82nd Street; Q/cb 3 4. I.S. 77 - 976 Seneca Ave; Q/cb 5 * 07/30/12: Transferred to HWCSC3MM: PS 17 - 28-37 29th Street | Implementation of school-safety intended street improvements at 4 Queens schools. | Queens |  | Transportation | Completed Project | Street Reconstruction | Standard | In-House/Consultant | Requirements TO | PIMS | FALSE |  |  | 2013 |  | DDC
HWCSCH3E1 | HWCSCH3E1 | Y | Infrastructure | BROOKLYN | SAFE ROUTES TO SCHOOLS, PHASE II | REVISED: Implementation of school-safety intended street improvements at 6 Brooklyn school locations - PIN X501.87 (Design PIN X770.40 Phase II). Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals g. landscaping Locations in Brooklyn: 1. PS 329 - 2929 W 30th St. - K/cb 13 2. J.H.S. 275 - 985 Rockaway Ave - K/cb 16 3. PS 59 - 211 Throop Ave. - K/cb 3 4. P.S. 155 - 1355 Herkimer St. - K/cb 16 5. PS / MS 375 Jackie Robinson - 46 McKeever Place - K/cb 9 6. PS 106 - 1314 Putnam Ave. - K/cb 4 | Safe Route to four (6) Schools,Borough of Brooklyn. |  |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE
HWCSCH3E-R | HWCSCH3E | Y | Infrastructure | S. QUEENS | SAFE ROUTES TO SCHOOLS-(X770.40 P I) 3M 3Q(RE-BID) | Implementation of school-safety intended street improvements at 6 school locations. (3 schools each in Queens and Manhattan). Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals g. landscaping CURRENT REVISED LOCATIONS:: QUEENS: 1. formerly known as: JHS 198 - 365 B. 56th St. - Q/cb 14 11/05/09: Current NEW name: PS-IS 133 / Golden Maple Academy 2. PS 199 - 39-20 48th Ave - Q/cb 2 3. St. Matthias School - 58-25 Catalpa Ave. - Q/cb 5 MANHATTAN: 4. Mesivtha Tifereth Jerusalem - 141 East Broadway - M/cb 3 (07/19/10: Re-inserted for inclusion) 5. St. Charles Borromeo School - 214 W 142nd St - M/cb 10 6. PS 8 - 465 W 167th Street - M/cb 12 | Implementation of school-safety intended street improvements at 6 school locations. (3 schools each in Queens and Manhattan). | Queens |  | Transportation | Completed Project | Street Reconstruction | Standard | Requirements TO | Standard Consultant | PIMS | FALSE |  |  | 2014 |  | DDC
WIN98FMUS | F175WIN98 | N | Public Buildings | Fire | WINDOW REPLACEMENT @FMUS | Replace windows through out facility |  |  |  | Fire | Cancelled Project | Renovation | Standard |  | JOCs | [6 empty] | DDC
WIN98LC25 | F175WIN98 | N | Public Buildings | Fire | WINDOW REPLACEMENT @LC25 | Window Replacements |  |  |  | Fire | Cancelled Project | Renovation | Standard |  | JOCs |  |  |  |  | 1998 |  | DDC
WP97BEC005 | F175WP97B | N | Public Buildings | Fire | WATERPROOFING & REPOINTING @EC005 | Exterior Facade restoration |  |  |  | Fire | Completed Project | Upgrade | Standard |  | JOCs |  |  |  |  | 1998 |  | DDC
HWCSCH3F | HWCSCH3F | Y | Infrastructure | STATEN ISLAND | SAFE ROUTES TO SCHOOLS - Staten Island | REVISED: Implementation of school-safety intended street improvements at 2school locations in Staten Island). Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals Staten Island: 1. St. Charles Sch. - 200 Penn Ave - SI/cb 3 2. PS 18 - 221 Broadway; SI/cb 1 a. 10/18/10 from DDC Design: Reprogramming of intersections to 3H-2: 1. N. Burgher Avenue / Castleton Avenue 2. N. Burgher Avenue / Cary Avenue 3. IS 27 - 11 Clove Lake Place - SI/cb 1 The Bronx: 4. PS 53 - 360 E. 168th St - BX/cb 4 5. JHS 22 - 207 E. 167th St. - BX/cb 4 6. CES 55 450 St. Paul's Place - BX/cb 3 7. MS 399 - 120 E. 184th St - BX/cb 5 ADDED LOCATION: 8. PS 21- H. Sheridan Sch. - 715 E. 225th St. - BX/cb 12 12/22/09: Added for neckdown improvements: 8a. White Plains Rd / East 226 St 8b. East 226th / Barnes Ave 09/22/09 DELETION: JHS 117 - 207 E. 167th St.; BX/cb 5 04/06/09: STV and RBA agree to exchange sites 5 Bronx schools from -3E now transferred into -3F; 6 Brooklyn schools from -3F now transferred to -3E | Implementation of school-safety improvements at two locations in Staten Island. P.S. 18 (John G. Whittier School) - SI/cb 1 St. Charles Sch. - 200 Penn Ave - SI/cb 2 | Staten Is. |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | DDC Managed/Consultant | PIMS | FALSE |  | 2013 | 2015 |  | DDC
HWCSCH3F1 | HWCSCH3F | Y | Infrastructure | BRONX & N. QUEENS | SAFE ROUTES TO SCHOOLS-(X770.40P IV) 5 Bx | Implementation of school-safety intended street improvements at 5 school locations in the Borough of the Bronx. Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals 5 BRONX SCHOOLS: 1. PS 53 - Basheer Quisim 360 E. 168th St - BX/cb 4 2. JHS 22 - Jordan L. Mott JHS., 207 E. 167th St. - BX/cb 4 3. CES 55 - Benjamin Franklin Sch., 450 St. Paul's Pl - BX/cb 3 4. MS 399 / M.S. 319 - 120 E. 184th St - BX/cb 5 5. PS 21 - Philip H. Sheridan Sch., 715 E. 225th St. - BX/cb 12 | Implementation of school-safety intended street improvements at 5 school locations in the Borough of the Bronx | Bronx |  | Transportation | Substantial Completion | Street Reconstruction | Standard | In-House/Consultant | DDC Managed Consultant | PIMS | FALSE |  | 2010 | 2014 |  | DDC
SE432BC10GG |  | N | Safety and Site Support |  | Borings in Manhattan, The Bronx and Staten Island |  |  |  |  | Unknown
SE432BC10HH |  | N | Safety and Site Support |  | Borings in Manhattan, The Bronx and Staten Island |  |  |  |  | Unknown
SE432SWM | SE432SWM | N | Safety and Site Support | Site Engineering | Topo Surveying Svcs for Stormwater Mgmt Systems
SE432SWM | SE-432SWM | N | Safety and Site Support | Site Engineering | Topo Surveying Svcs for Stormwater Mgmt Systems
HWCSCH3G1 | HWCSCH3G | Y | Infrastructure | BRONX & N. QUEENS | SAFE ROUTES TO SCHOOLS -(X501.78 P I) 4 BX | REVISED: Implementation of school-safety intended street improvements at 3 Bronx schools. (reduced from 4 Bx schools). Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals g. Landscaping 3 REVISED BRONX LOCATIONS: 1. St. Angelea Merici School - 266 E. 163 St; BX/cb 4 2. Immaculate Conception - 378 E. 151 St; BX/cb 1 3. PS 33 - 2424 Jerome Ave.; BX/cbs 5 & 7 10/08/13: DELETION OF: . CIS 303 - 1700 Macombs Rd. BX/cb 5 | Implementation of school-safety intended street improvements at 3 Bronx schools. | Bronx |  | Transportation | Substantial Completion | Street Reconstruction | Standard | In-House/Consultant | DDC Managed | PIMS | FALSE |  | 2010 | 2015 |  | DDC
HWCSCH3G2 | HWCSCH3G | Y | Infrastructure | Bronx & N. Queens | SAFE ROUTES TO SCHOOLS-(X501.86) 4 Bx 1 MAN 1 BK | Implementation of school-safety intended street improvements at 6 REVISED school locations; HWCSCH3: G2 = 4 Bronx- + 1 Manhattan- schools REVISED: HWCSCH3H1 = 1 Bklyn school Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals g. Landscaping 6 TOTAL SCHOOL LOCATIONS: HWCSCH3G2: 4 Bronx locations: 1. St. Anselm School - 685 Tinton Ave.; BX/cb 1 2. PS 306 - 40 W. Tremont Ave.; BX/cb 5 3. PS 79 (MS 279) - BX/cb 5 125 E. 181 St., (2100 Walton Ave); 06/24/09 Addendum added Walton Ave location 4. St. Margaret Mary School - 121 East 177 St.; BX/cb 5 One Manhattan location: 5. PS 132 - 185 Wadsworth Ave.; M/cb 12 REVISED: HWCSCH3H1: one BKLYN school: inserted-/substituted-: Yeshiva Torah Temimahl 555 Ocean Pkwy; K/cb 12 deleted: Oholei Torah Elementary School 667 Eastern Parkway | Implementation of school-safety improvements at Six (6) locations four (4) Bx, one (1) Man and one (1) Bklyn-(X501.86); | Brooklyn |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2010 | 2015 |  | DDC
SEK0201A7 | SEK0201A7 | N | Infrastructure | Brooklyn | VIT CLAY PIPE, BK | Reconstruction of Collapsed or Otherwise Defective Sanitary, Storm and Combined Vitrified Clay Pipe Sewers in Various Locations- Brooklyn. | Reconstruction of vitrified clay pipe sewers, various locations. | Brooklyn |  | Environmental Protection | Completed Project | Sewer | Standard | In-House | DEP Managed |  |  |  |  | 2005 |  | DEP
SEK0201A8 | SEK0201A8 | N | Infrastructure | Brooklyn | RECON OF VIT CLAY PIPE SEWERS | Reconstruction of Collapsed or Otherwise Defective Sanitary, Storm and Combined Vitrified Clay Pipe Sewers in Various Locations- Brooklyn. | Reconstruct vitrified clay pipe sewers, various locations. | Brooklyn |  | Environmental Protection | Completed Project | Sewer | Standard | In-House | DEP Managed |  |  |  |  | 2006 |  | DEP
SEK0201A9 | SEK0201A9 | N | Infrastructure | Brooklyn | RECON OF VIT CLAY PIPE SEWERS | Reconstruction of Collapsed or Otherwise Defective Sanitary, Storm and Combined Vitrified Clay Pipe Sewers in Various Locations- Brooklyn. | Reconstruction of vitrified clay pipe sewers, various locations in Brooklyn. | Brooklyn |  | Environmental Protection | Completed Project | Sewer | Standard | In-House | DEP Managed |  |  |  |  | 2007 |  | DEP
HWCSCH3G3 | HWCSCH3G | Y | Infrastructure | S. QUEENS | SAFE ROUTES TO SCHOOLS-(X501.78P III) 6 QNS | Implementation of school-safety intended street improvements at 6 Queens school locations. Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals g. landscaping 6 QUEENS LOCATIONS 1. St Michael School - 136-58 41st Avenue; Q/cb 7 2. Learning Tree Multi-Cultural - 103-02 Northern Boulevard; Q/cb 3 3. IS 238 - I88-15 182nd Street; Q/cbs 8 & 12 4. PS 82 - 88-02 144th Street; Q/cb 12 5. Presentation / BVM School - 88-13 Parsons Blvd; Q/cb 12 | Implementation of school-safety intended street improvements at 6 Queens school locations. Work scope includes, but not limited to: a. curb and sidewalk work b. bus pads c. pedestrian ramps d. infrastructure utility work e. speed reducers f. street lights and traffic signals g. landscaping 6 QUEENS LOCATIONS 1. St Michael School - 136-58 41st Avenue; Q/cb 7 2. Learning Tree Multi-Cultural - 103-02 Northern Boulevard; Q/cb 3 3. IS 238 - I88-15 182nd Street; Q/cbs 8 & 12 4. PS 82 - 88-02 144th Street; Q/cb 12 5. Presentation / BVM School - 88-13 Parsons Blvd; Q/cb 12 | Queens |  | Transportation | Completed Project | Street Reconstruction | Standard | In-House/Consultant | Standard Consultant | PIMS | FALSE |  |  | 2014 |  | DDC
HWCSCH3H1 | HWCSCH3H | Y | Infrastructure | Staten Island | SAFE ROUTES TO SCHOOLS-(X501.78P IV) 1 BK | 5th REVISON: HWCSCH3H1 MERGED with -3G2 One NEW Bklyn location to be merged with: HWCSCH3G2 = 4 Bronx-, 1 Manhattan- school pedestrian intended street improvements Work scope includes, but not limited to: a. street resurfacing b. curb and sidewalk work c. bus pads d. pedestrian ramps e. infrastructure utility work f. speed reducers g. street lights and traffic signals h. Landscaping 5TH REVISION LOCATIONS (6 schools): 3G2: 5 schools PLUS 3H1: one NEW BKLYN school: Yeshiva Torah Temimahl 555 Ocean Pkwy; K/cb 12 4th REVISION: one Bklyn location (NEW): Yeshiva Torah 555 Ocean Pkwy; K/cb 12 delete all prior locations 3rd REVISION: Moved to HWK1130B: 2 Brooklyn schools; K/cbs 8 & 9: 1. Oholei Torah Elementary School - 667 Eastern Parkway * Brooklyn Ave / Eastern Pkwy = raised center median @ west leg of Eastern Pkwy 2. Arista Prep School - 755 Eastern Parkway * Kingston Ave / Eastern Pkwy = raised center median PRIOR REVISIONS: FORMERLY 6 Bklyn schools. 4 schools transferred to HWCSCH3MM: PS 299 - 88 Woodbine St.; K/cb 4 IS 383 - 1200 Greene Ave; K/cb 4 JHS 291 - 231 Palmetto Street; K/cb 4 Yeshiva Torah Temimahl - 555 Ocean Pkwy; K/cb 12 | Implementation of school-safety improvements at Yeshiva Torah, 555 Ocean Parkway, K/cb 12 |  |  | Transportation | Cancelled Project | Street Reconstruction | Standard | In-House/Consultant | DDC Managed | Project Info | FALSE
HWCSCH3H2 | HWCSCH3H | Y | Infrastructure | STATEN ISLAND | SAFE ROUTES TO SCHOOLS-(X501.78P V)3 SI | REVISED: Implementation of school-safety intended street improvements at 3 Staten Island-schools (Bklyn PS 299 transferred to HWCSCH3MM ) Work scope includes, but not limited to: a. street resurfacing b. curb and sidewalk work c. bus pads d. pedestrian ramps e. infrastructure utility work f. speed reducers g. street lights and traffic signals h. landscaping LOCATIONS (all SI / cb1) : 1 St. Teresa 1032 Victory Blvd. 2. PS 22 - 1860 Forest Ave. 3. Sacred Heart - 301 N. Burgher Ave * 07/30/12: Transfer 1 Bklyn/cb 4 school to HWCSCH3MM: PS 299: 88 Woodbine St. | Implementation of school-safety improvements at 3 locations in Staten Island. St. Teresa 1032 Victory Blvd.; PS 22 - 1860 Forest Ave.; Sacred Heart - 301 N. Burgher Ave. | Staten Is. |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  | 2013 | 2014 |  | DDC
HWCSCH3MM | HWCSCH3MM | Y | Infrastructure | BROOKLYN | SAFE ROUTES TO SCHOOLS- 7 SCHOOLS | REVISED to: a. 7 sites = 6 Bklyn + 1 Qns schools b. no federal reimbursemt. = NYC capital project SCOPE: Implementation of pedestrian safety-intended street improvements at 6 BKLYN- and ONE QUEENS- schools: Locations: BKLYN: 1. P.S. 59 211 Throop Ave. K/cb 3 2. J.H.S. 291 231 Palmetto St K/cb 4 3. I.S. 383 1200 Greene Ave K/cb4 (from HWCSCH3H1) 4. PS 299 88 Woodbine St.; K/cb 4 5. PS 116 515 Knickerbocker Ave; K/cb 4 6. PS 86 220 Irving Ave; K/cb 4 QNS: 7. PS 17 28-37 29th Street; Q/cb 1 Work scope includes, but not limited to: a. street resurfacing b. curb and sidewalk work c. bus pads d. pedestrian ramps e. infrastructure utility work f. speed reducers g. street lights and traffic signals h. Landscaping PRIOR SCOPE: 5 public schools (4 Bklyn; 1 Qns.) Brooklyn locations: 1. P.S. 59 211 Throop Ave. K/cb 3 (from HWCSCH3E1) 2. J.H.S. 291 231 Palmetto St K/cb 4 (from HWCSCH3H1) 3. I.S. 383 1200 Greene Ave K/cb4 (from HWCSCH3H1) 4. PS 299 88 Woodbine St.; K/cb 4 (from HWCSCH3H2) Queens location: 5. PS 17 28-37 29th Street; Q/cb 1 (from HWCSCH3D) | Implementation of school-safety improvements at 7 locations Six (6) Bklyn + One (1) Qns | Brooklyn |  | Transportation | Construction 25-50% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWCSCH4A | HWCSCH4A | Y | Infrastructure | MANHATTAN & CITYWIDE | SAFE ROUTE TO SCHOOLS PH 4-5 SCHOOLS, MN (MED635) | Final design and construction of pedestrian safty Improvements at 5 schools in Manhattan. The 5 Schools include: P.S. 154 - Harriet Tubman School P.S. 347- American Sign Language and English Lower School Ramaz Lower School, Park Ave. Christian Church Day School St. Joseph's Yorkville School Each school should have its own bid items along with total cost (separate budget line). MED635 - Replacement of WM in E 25th Street bet. 3rd Ave and Lexington Ave. | Pedestrian Safty Improvements at 5 schools in Manhattan: P.S. 154 - Harriet Tubman School P.S. 347- American Sign Language and English Lower School Ramaz Lower School, Park Ave. Christian Church Day School St. Joseph's Yorkville School | Manhattan |  | Transportation | Construction 50-75% | Sidewalks | Standard | Requirement Contract | Requirements TO | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWCSCH4B1 | HWCSCH4B1 | Y | Infrastructure | BROOKLYN | SAFE ROUTES TO SCHOOLS - PHASE 4B1 | To include construction of pedestrian safety improvements in 4 schools in Brooklyn. Schools Included: 1. M.S. 136, Charles G. Dewey School 2. P.S. 226, Alfred de Baron Mason Street 3. P.S. 398, Walter Weaver School 4. P.S. 13, Roberto Clemento School DOT has requested to remove the proposed median reconstruction on 4th Ave between 40th St and 41st St (near M.S. 136) e-mail on 1/30/14 | Safe Routes to Schools, Phase 4B1, Borough of Brooklyn | Brooklyn |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWCSCH4B3 | HWCSCH4B3 | Y | Infrastructure | BROOKLYN | School Safety Program 4-Phase 4B3,Brooklyn | Safe Routes to Schools - Phase 4B3 - Pedestrian safety improvements at three shools, PS 134, PS 207 Annex and Central Brooklyn Ascend Lower School (formerly St. Jerome School) in Brooklyn. | Safe Routes to Schools - Phase 4B3 - Pedestrian safety improvements at three schools, PS 134, PS 207 Annex and Central Brooklyn Ascend Lower School (formerly St. Jerome School) in Brooklyn. | Brooklyn |  | Transportation | Final Design | Street Reconstruction | Critical | Requirement Contract | Requirements TO | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HWCSCH4C1 | HWCSCH4C1 | Y | Infrastructure | S. QUEENS | Safe Routes to School - Phase 4C1 | Safe Routes to Schools - Phase 4C1 | The final design, procurement, and construction of pedestrian safety improvements at three schools - Allen Christian School, P.S. 16, and P.S. 169 - Bay Terrace School - in Queens | Citywide |  | Transportation | Construction Procurement | Street Reconstruction | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HWCSCH4C2 | HWCSCH4C2 | Y | Infrastructure | S. QUEENS | Safe Routes to Schools - Phase 4C2 | Safe Routes to Schools - Phase 4C2 | Project Scope: Safety improvements at intersections near the following seven schools in Queens, Brooklyn, and Staten Island: 1. P.S. 361, East Flatbush Early Childhood School, Brooklyn 2. P.S. 13, Annex, Clement C. Moore, Queens 3. P.S. 54, Hillside School, Queens 4. P.S. 92, Harry T. Stewart School, Queens 5. P.S. 239, Police Officer Ramon Suarez School, Queens 6. Our Lady's Catholic Academy, Queens 7. Our Lady Queen of Peace School, Staten Island | Citywide |  | Transportation | Construction 0-25% | Street Reconstruction | Critical | In-House/Consultant | Requirements TO | PIMS | FALSE |  | 2015 | 2018 |  | DDC
HWCSCHPBX | HWCSCHPBX | Y | Infrastructure | BRONX & N. QUEENS | SAFE ROUTES TO SCHOOLS BRONX | Construction of pedestrian safety improvements at the following five schools in the Bronx: PS 73; PS 340; St. Luke's School; PS.159; PS.51. The proposed scope of improvements mainly includes curb extensions and pedestrian safety islands. Receiving pedestrian ramps must comply with ADA standards. Also included is related Green Infrastructure work (DEP). | Construction of pedestrian safety improvements at the following five schools in the Bronx: PS 73; PS 340; St. Luke's School; PS.159; PS.51. The proposed scope of improvements mainly includes curb extensions and pedestrian safety islands. Receiving pedestrian ramps must comply with ADA standards. Also included is related Green Infrastructure work (DEP). | Bronx |  | Transportation |  | Street | Critical |  |  | PIMS | FALSE |  | 2018 | 2020 |  | DDC
HWCSCHPKR | HWCSCHPKR | Y | Infrastructure | BROOKLYN | SAFE ROUTES TO SCHOOLS BK & SI | THE SCOPE OF WORK INCLUDES MANAGEMENT OF TOTAL DESIGN, PROCUREMENT AND CONSTRUCTION OF PEDESTRIAN SAFETY IMPROVEMENTS AT THE FOLLOWING EIGHT SCHOOLS IN BK & SI: M.S. 598, PS169, PS156, PS189, PS327 AND PS380 IN BROOKLYN AND PS41-THE NEW DORP SCHOOL IN STATEN ISLAND. THE PROPOSED SCOPE OF IMPROVEMENTS MAINLY INCLUDES SIDEWALKS/CURB EXTENSIONS, BUS PADS AND PEDESTRIAN SAFETY ISLANDS. | Safe Route to School in Brooklyn and Staten Island |  |  | Transportation | [5 empty] | PIMS | FALSE |  |  |  | 2017-10-30 07:00:23.0370000 +00:00
HWCSCHPQN | HWCSCHPQN | Y | Infrastructure | S. QUEENS | SAFE ROUTES TO SCHOOLS, QNS | PEDESTRIAN SAFETY IMPROVEMENTS AT 8 SCHOOLS IN QUEENS: PS 50, PS 71, PS 89, PS 220, IS 125, JHS 210, ST. ELIZABETH SCHOOL, EPIC HIGH SCHOOL NORTH | Pedestrian safety improvements at the following eight schools in Queens: P.S. 50, P.S. 71 – Forest School, P. S 89, P.S. 220, I.S. 125, St. Elizabeth School and JHS 210 and Epic High School North (previously known as Benedict Joseph Labre School) |  |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard |  |  | PIMS | FALSE |  |  |  | 2017-10-30 07:00:24.5200000 +00:00
HWCURB09 | HWCURB09 | Y | Infrastructure | MANHATTAN & CITYWIDE | CURB RECONSTRUCTION | RECONSTRUCTION OF ROADWAY CURBS, CITYWIDE | Reconstruction of Roadway Curbs, Citywide | Citywide |  | Transportation | Construction Procurement | Street Reconstruction | Critical | In-House |  | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HWD005K01 | HWD005K01 | Y | Infrastructure | BROOKLYN | FULTON STREET IMPROVEMENTS | Safety improvement to the intersection of Fulton Street at Green Avenue and gates Avenue. The East and West corners of intersection of Fulton Street/Greene Street/ Hanson Place will see new benches installed as well as upgraded tree pits and new bike racks. The scope also includes the installation or upgrading of sidewalks and pedestrian ramps, particularly around the subway grates, where the sidewalks are uneven and sinking. Street Locations:- STREET FROM TO ============================================== 1-Fulton Street Greene Avenue Hanson Place 2-Fulton Street Hanson Place Cumberland street 3-Gates Avenue Fulton Street Vanderbilt Avenue 4-Greene Avenue Fulton Street Cumberland Street | Fulton Street Safety Improvements, Brooklyn | Brooklyn |  | Transportation | Substantial Completion | Sidewalks | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWD10105 | HWD10105 | Y | Infrastructure | BROOKLYN | ATLANTIC AVENUE SAFETY IMPROVEMENTS, BROOKLYN | ATLANTIC AVENUE SAFETY IMPROVEMENTS, BROOKLYN | ATLANTIC AVENUE SAFETY IMPROVEMENTS, BROOKLYN | Brooklyn |  | Transportation | Construction 0-25% | Street Reconstruction |  | Requirements TO | Requirement Contract | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWD10105A | HWD10105A | Y | Infrastructure | BROOKLYN | ATLANTIC AVE SAFETY IMPROVEMENTS - PH 2, BROOKLYN | ATLANTIC AVE SAFETY IMPROVEMENTS - PH 2, BROOKLYN | PED. SAFETY UPGRADES ON ATLANTIC AVE - PH 2, BROOKLYN | Brooklyn |  | Transportation | Design Development | Street Reconstruction | Critical | Requirements TO | Requirement Contract | PIMS | FALSE |  | 2016 | 2018 |  | DDC
HWD10211 | HWD10211 | Y | Infrastructure | MANHATTAN & CITYWIDE | 185TH STREET - STREETSCAPE IMPROVEMENTS (MED632) | Streetscape improvements on 185th Street from Audubon Ave. to Amsterdam Ave. in Manhattan. Additional work may be required on Amsterdam Ave. from West 184th St. to West 186th St. MED 632 - Water main work at West 185th St. from Audubon Ave. to Amsterdam Ave. | Streetscape improvements on 185th Street from Audubon Ave. to Amsterdam Ave. in Manhattan. | Manhattan |  | Transportation | Construction 75%-Subst. | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2012 | 2016 |  | DDC
HWD104-05 | HWD104-05 | Y | Infrastructure | STATEN ISLAND | ROADWAY IMPROVEMENTS AT THE AMBOY RD & HUGUENOT AV | Roadway improvement at the Amboy road and Huguenot Avenue intersection, Staten Island. | Roadway improvement at the Amboy road and Huguenot Avenue intersection, Staten Island. | Staten Is. |  | Transportation | Substantial Completion | Street Reconstruction | Standard | In-House | DDC Managed/Consultant | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWD10501A-R | HWD10501A | Y | Infrastructure | BRONX & N. QUEENS | HUGH GRANT CIRCLE - METROPOLITAN AV & WESTCHESTER | Hugh Grant Circle located at the Intersection of Metropolitan Ave. and Westchester Avenue. Installation of neckdowns and pedestrian ramps, street lighting, traffic signals, pavement markings, and other related work. | Installation of neckdowns, pedestrian ramps, street lighting, traffic signals, pavement markings, & other related work at Hugh Grant Circle located at the Intersection of Metropolitan Ave. and Westchester Avenue. . | Bronx |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2009 | 2013 |  | DDC
HWD105-03 | HWD105-03 | Y | Infrastructure | BRONX & N. QUEENS | LIBRARY LANE PROJECT | The following road reconstruction: 1. Coles lane from East Kingsbridge Road to Poe place 2. Coles lane from Poe place to Bainbridge Avenue Water Main in: 1. Coles Lane between Bainbridge Avenue & 30-40 feet West from Poe Pl. 2. Poe Place between Coles Lane and Dead End. 3. Briggs Avenue intersection of Coles Lane. 4. E. Kingsbridge Rd. intersection of Briggs Avenue. 5. Bainbridge Avenue intersection of Coles Lane. | The Library Lane project consists of the full reconstruction of Coles lane, a short street between East Kingsbridge Road and Bainbridge Ave in the Fordham section of the Bronx including WM works. | Bronx |  | Transportation | Final Design | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2011 | 2016 |  | DDC
HWHARPER | HWHARPER | Y | Public Buildings | TRANSPORTATION | Asphalt Plant, 30-01 Harper St, Queens Demo/Cons | Demolition and rebuild of the existing structures housing the equipment and related facilities necessary for the production, storage and distribution of asphalt at the NYC Harper Street Asphalt Plant facility. All of the existing equipment, storage facilities, and related buildings (lab, dispatch office, locker rooms, etc.) will be replaced with a new state of the art plant. In addition, the work will involve installing sanitary and storm drainage systems to comply with current government regulatory standard. | Demolition and rebuild of the existing structures housing the equipment and related facilities necessary for the production, storage and distribution of asphalt at the NYC Harper Street Asphalt Plant facility. All of the existing equipment, storage facilities, and related buildings will be replaced with a new state of the art plant. In addition, the work will involve installing sanitary and storm drainage systems to comply with current government regulatory standard | Queens |  | Transportation | Pre-Design/PrgDevelopment | New Construction | Standard | CM | CM-Build | PIMS | FALSE |  |  |  |  | DDC
HWK100BUS | HWK100BUS | Y | Infrastructure | BROOKLYN | UTICA AVENUE SELECT BUS SERVICES (SBS), BROOKLYN | UTICA AVENUE SELECT BUS SERVICES (SBS), BROOKLYN | Utica Avenue Select Bus Services (SBS), Brooklyn. | Brooklyn |  | Transportation | Construction 0-25% | Street Reconstruction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2017 |  | DDC
SEK20051 | SEK20051 | N | Infrastructure | Brooklyn | TRIPLE BARREL STM SEWER OUTFALL - 64 ST AT US BULK | Construction of Triple Barrel Storm Sewer outfall in 64th Street at U.S. Bulkhead Line. | Replace/rehabilitate triple barrel storm sewer outfall, 64th Street at U.S. bulkhead. | Brooklyn |  | Environmental Protection | Completed Project | Sewer | Standard | In-House | Requirements TO |  |  |  |  | 2008 |  | DDC
SEK201A10 | SEK201A10 | N | Infrastructure | Brooklyn | RECON OF VIT CLAY PIPE SEWERS | Reconstruction of Collapsed or Otherwise Defective Sanitary, Storm and Combined Vitrified Clay Pipe Sewers in Various Locations- Brooklyn. | Replacement of defective vitrified clay pipe sewers at various locations in Brooklyn. | Brooklyn |  | Environmental Protection | Completed Project | Sewer | Standard | In-House | DEP Managed |  |  |  |  | 2008 |  | DEP
HWK1048A | HWK1048A | Y | Infrastructure | BROOKLYN | WEST STREET - BROOKLYN WATERFRONT GREENWAY/SE-858 | The reconstruction of West Street from Eagle Street to Quay Street including sewer, watermain, street lighting and traffic signal work together with all work incidental thereto, in Borough of Brooklyn. DEP scope: Installation of High Level Storm Sewer, Combined sewer Replacement, and Water Main Replacement in West Street between Eagle Street and Quay Street, Including reconstruction of 1 outfall, etc. | The reconstruction of West Street from Eagle Street to Quay Street including sewer, watermain, street lighting and traffic signal work together with all work incidental thereto, in Borough of Brooklyn. DEP scope: Installation of High Level Storm Sewer, Combined sewer Replacement, and Water Main Replacement in West Street between Eagle Street and Quay Street, Including reconstruction of 1 outfall, etc. | Brooklyn |  | Transportation | Construction 50-75% | Street Reconstruction | Standard | Requirements TO | Standard Consultant | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HWK1048B | HWK1048B | Y | Infrastructure | BROOKLYN | FLUSHING AVENUE - BROOKLYN WATERFRONT GREENWAY | The reconfiguration of Flushing Avenue from Navy Street to Williamsburg Street will include a two-way, Class 1 separated bike path; a 6' sidewalk extention and improved pavement markings at intersections. | The reconstruction of Flushing Avenue from Navy Street to Williamsburg Street will include a two-way, Class 1 separated bike path; a 6' sidewalk extension and improved pavement markings at intersections. | Brooklyn |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2012 | 2015 |  | DDC
HWK1048C | HWK1048C | Y | Infrastructure | BROOKLYN | KENT AVENUE SOUTH | Pre-Scoping Services for the Kent Avenue South section of the Brooklyn Waterfront Greenway from Clymer Street to Williamsburg Street West. | Reconstruction of Kent Avenue South section of the Brooklyn Waterfront Greenway from Clymer Street to Williamsburg Street West. | Brooklyn |  | Transportation | Compliance | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2017 |  | DDC
HWK1048D | HWK1048D | Y | Infrastructure | BROOKLYN | SUNSET PARK GOWANUS CONNECTOR, BK | BROOKLYN WATERFRONT GREENWAY - SUNSET PARK GOWANUS CONNECTOR IN CONJUNCTION WITH BED-802, WATER MAIN REPLACEMENT IN HAMILTON AVENUE GOWANUS CONNECTOR, BK | Sunset Park Gowanus Connector - Brooklyn Waterfront Greenway. | Brooklyn |  | Transportation | Final Design | Street Reconstruction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2017 |  | DDC
HWK1048G | HWK1048G | Y | Infrastructure | BROOKLYN | Owl's Head - Brooklyn Greenway | This project will construct approximately 12 blocks of the 14-mile Brooklyn Waterfront Greenway. This project establishes the southernmost leg of the Greenway, linking the neighborhoods of Sunset Park and Bay Ridge, where the Greenway will ultimately connect to the Shore Parkway Esplanade. The project will provide safer access to parks and recreational spaces along the waterfront, encourage healthy lifestyles by promoting the use of non-motorized forms of transportation, improve sustainability by capturing storm water, and stimulate economic development by providing connections to employment centers in Downtown Brooklyn and the Sunset Park, Gowanus, and Red Hook neighborhoods. The projects limits include 2nd Avenue from 58th Street to Wakeman Place and Wakeman Place from Ridge Boulevard to Colonial Road. These streets will be reconfigured in order to provide space for the two-way, grade-separated greenway path as well as additional planted areas. This project also includes the rehabilitation (25% replacement & 75% repair) of a retaining wall along the northwest side of 2nd Avenue and between 58th & 65th Streets. | Owl's Head Connector Section of Brooklyn Waterfront Greeway | Brooklyn |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWK1130B | BED-797 | Y | Infrastructure | BROOKLYN | Nostrand Avenue SBS Phase 3/BED-797 | This project will widen sidewalks, add median islands, rationalize street geometry, add street trees, and enhance pedestrian access to and from the bus stops, better knitting the bus plaza into the fabric of the neighborhood. The geometric improvements will reduce pedestrian crossing distances, slow turning vehicles, and improve bus movements, creating a more appealing facility. The business district will benefit from a streetscape that encourages strolling and taps into the bus passenger market. School Safety Locations: From: HWCSCH3H1 Arista Preparatory School and Oholei Torah Elementary School, HWCSCH3E1, P.S. 59 and P.S. 375 Jackie Robinson transferred to HWK1130B. Fabrication and installation of pedestrian wayfinding signage throughout the Nostrand SBS corridor is also included as part of the amended scope of this project. DEP Scope: BED-797 Water Main (WM-1) 1. Roebling Street between Williamsburg Bridge Ramp and S 8th Street 2. Broadway intersection of Roebling Street . 3. Havemeyer Street (E & W) between S 5th Street and Broadway Combined sewer replacement: 1. S 5th Street between Roebling Street and Havemeyer Street 2. Broadway between Roebling Street and Driggs Avenue 3. S 8th Street between Roebling Street and Broadway 4. Roebling Street between Broadway and S 5th Strret Combined sewer spot repair: 1. S 5th Street between Roebling Street and Marcy Avenue 2. Roebling Street between Broadway and S 5th Strret 3. Roebling Street intersection with S 8th Street | Reconstruction of Nostrand Ave Select Bus Service (SBS) - Phase 3, Brooklyn. | Brooklyn |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | TRUE |  | 2014 | 2015 |  | DDC
HWK1130B | HWK1130B | Y | Infrastructure | BROOKLYN | Nostrand Avenue SBS Phase 3/BED-797 | This project will widen sidewalks, add median islands, rationalize street geometry, add street trees, and enhance pedestrian access to and from the bus stops, better knitting the bus plaza into the fabric of the neighborhood. The geometric improvements will reduce pedestrian crossing distances, slow turning vehicles, and improve bus movements, creating a more appealing facility. The business district will benefit from a streetscape that encourages strolling and taps into the bus passenger market. School Safety Locations: From: HWCSCH3H1 Arista Preparatory School and Oholei Torah Elementary School, HWCSCH3E1, P.S. 59 and P.S. 375 Jackie Robinson transferred to HWK1130B. Fabrication and installation of pedestrian wayfinding signage throughout the Nostrand SBS corridor is also included as part of the amended scope of this project. DEP Scope: BED-797 Water Main (WM-1) 1. Roebling Street between Williamsburg Bridge Ramp and S 8th Street 2. Broadway intersection of Roebling Street . 3. Havemeyer Street (E & W) between S 5th Street and Broadway Combined sewer replacement: 1. S 5th Street between Roebling Street and Havemeyer Street 2. Broadway between Roebling Street and Driggs Avenue 3. S 8th Street between Roebling Street and Broadway 4. Roebling Street between Broadway and S 5th Strret Combined sewer spot repair: 1. S 5th Street between Roebling Street and Marcy Avenue 2. Roebling Street between Broadway and S 5th Strret 3. Roebling Street intersection with S 8th Street | Reconstruction of Nostrand Ave Select Bus Service (SBS) - Phase 3, Brooklyn. | Brooklyn |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | TRUE |  | 2014 | 2015 |  | DDC
HWK1173A | BED-785A | Y | Infrastructure | BROOKLYN | ATLANTIC AVENUE FROM GEORGIA AVE TO SCHENCK AVE | Reconstruction of Atlantic Avenue from Georgia Avenue to Schenck Avenue including Sewer, Watermain, Street Lighting and Traffic Signal Work. COMBINED SEWER REPLACEMENT IN: 1. Georgia Avenue bet. Fulton Street and Atlantic Avenue 2. Intersection of Atlantic Avenue(SS) and Georgia Avenue 3. Atlantic Avenue(NS) bet. Pensylvania Avenue and New Jersey Ave including intersection 4. Intersection of Atlantic Avenue(NS) and Vermont Avenue 5. Atlantic Avenue(NS) bet. Wyona Avenue and Bradford Street 6. Intersection of Atlantic Avenue(NS) and Miller Avenue 7. Intersection of Atlantic avenue(NS) and Hendrix street SANITARY SEWER REPLACEMENT IN: 1. Atlantic Avenue(SS) bet. New Jersey Avenue and Van Sicklen Avenue 2. Bradford Avenue bet. Atlantic Avenue and Liberty Avenue 3. Van Sicklen Avenue bet. Atlantic Avenue and Liberty Avenue 4. Bradford Street bet. Atlantic Ave and Liberty Ave SANITARY AND COMBINED SEWERS LINING AND SPOT REPAIR IN:1. Intersection of Atlantic Avenue(SS) and Pensylvania Avenue 2. Atlantic Avenue bet.(NS) Van Sicklen Avenue and Hendrix Street 3. Intersection of Atlantic Avenue(NS) and Wyona Avenue WATER MAIN-6 - TRUNK MAIN 1. Atlantic Avenue between Georgia Avenue and Schenck Avenue WATER MAIN-1 IN: 1. Atlantic Avenue(NS)between Pennsylvania Avenue and Schenck Avenue including intersections 2. Intersectionof Atlantic Avenue and Pennsylvania Avenue 3. Intersection of Atlantic Ave and Schenck Street 4. Atlantic Avenue(NS) bet. George Avenue and Pennsylvania Avenue including intersections 5.Atlantic Avenue(SS) bet. Georgia Avenue and Pennsylvania Avenue(WS) and Schenck Ave including intersections 6. Crossover in intersection of Atlantic Ave. and Sheffield Avenue 7. Crossover in intersection of Atlantic Avenue and Vermont Avenue 8. Crossover in intersection of Atlantic Avenue and Bradford Avenue | Reconstruction of Atlantic Avenue from Georgia Avenue to Schenck Avenue, Brooklyn | Brooklyn |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | TRUE |  | 2021 | 2024 |  | DDC
HWK1668 | HWK1668 | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF WILLOUGHBY ST AREA | Reconstruction of Willoughby Street area. 1) Willoughby Street from Pearl Street to Jay Street 2) Willoughby Street from Lawrence Street to Flatbush Avenue Extension 3) Pearl Street from Willoughby Street to dead end/north of Willoughby Street 4) Lawrence Street from Willoughby Street to Fulton Street 5) Bridge Street from Willoughby Street to Fulton Street 5 ) Duffield Street from Willoughby street to Fulton Street 6) Gold Street from Willoughby Street to Dekalb Avenue | Reconstruction of Willoughby Street area. | Brooklyn |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2021 | 2024 |  | DDC
HWK1669 | HWK1669 | Y | Infrastructure | BROOKLYN | 4TH AVENUE SAFETY IMPROVMENTS, BROOKLYN | 4th Avenue Safety Improvements, Brooklyn This project will mitigate the effects of traffic and enhance pedestrian safety at two contiguous segments along 4th Avenue between 8th to 18th Streets in Park Slope/Gowanus and 33rd to 52nd Street in Sunset Park. The scope includes expanding and raising the existing medians (currently in temporary materials) and includes sidewalk extensions, street trees (where feasible), benches, and wayfinding. | 4th Avenue Safety Improvements, Brooklyn | Brooklyn |  | Transportation | Cancelled Project | Street Reconstruction | Critical | In-House/Consultant | Standard Consultant | PIMS | FALSE |  | 2015 | 2019 |  | DDC
HWK1173A | HWK1173A | Y | Infrastructure | BROOKLYN | ATLANTIC AVENUE FROM GEORGIA AVE TO SCHENCK AVE | Reconstruction of Atlantic Avenue from Georgia Avenue to Schenck Avenue including Sewer, Watermain, Street Lighting and Traffic Signal Work. COMBINED SEWER REPLACEMENT IN: 1. Georgia Avenue bet. Fulton Street and Atlantic Avenue 2. Intersection of Atlantic Avenue(SS) and Georgia Avenue 3. Atlantic Avenue(NS) bet. Pensylvania Avenue and New Jersey Ave including intersection 4. Intersection of Atlantic Avenue(NS) and Vermont Avenue 5. Atlantic Avenue(NS) bet. Wyona Avenue and Bradford Street 6. Intersection of Atlantic Avenue(NS) and Miller Avenue 7. Intersection of Atlantic avenue(NS) and Hendrix street SANITARY SEWER REPLACEMENT IN: 1. Atlantic Avenue(SS) bet. New Jersey Avenue and Van Sicklen Avenue 2. Bradford Avenue bet. Atlantic Avenue and Liberty Avenue 3. Van Sicklen Avenue bet. Atlantic Avenue and Liberty Avenue 4. Bradford Street bet. Atlantic Ave and Liberty Ave SANITARY AND COMBINED SEWERS LINING AND SPOT REPAIR IN:1. Intersection of Atlantic Avenue(SS) and Pensylvania Avenue 2. Atlantic Avenue bet.(NS) Van Sicklen Avenue and Hendrix Street 3. Intersection of Atlantic Avenue(NS) and Wyona Avenue WATER MAIN-6 - TRUNK MAIN 1. Atlantic Avenue between Georgia Avenue and Schenck Avenue WATER MAIN-1 IN: 1. Atlantic Avenue(NS)between Pennsylvania Avenue and Schenck Avenue including intersections 2. Intersectionof Atlantic Avenue and Pennsylvania Avenue 3. Intersection of Atlantic Ave and Schenck Street 4. Atlantic Avenue(NS) bet. George Avenue and Pennsylvania Avenue including intersections 5.Atlantic Avenue(SS) bet. Georgia Avenue and Pennsylvania Avenue(WS) and Schenck Ave including intersections 6. Crossover in intersection of Atlantic Ave. and Sheffield Avenue 7. Crossover in intersection of Atlantic Avenue and Vermont Avenue 8. Crossover in intersection of Atlantic Avenue and Bradford Avenue | Reconstruction of Atlantic Avenue from Georgia Avenue to Schenck Avenue, Brooklyn | Brooklyn |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | TRUE |  | 2021 | 2024 |  | DDC
HWK1173B | HWK1173B | Y | Infrastructure | BROOKLYN | ATLANTIC AVENUE FROM SCHENCK AVE TO ROCKAWAY BLVD | Reconstruction of Atlantic Avenue from Schenck Avenue to Rockaway Boulevard Including Sewer, Watermain, Street Lighting and Traffic Signal Work | Reconstruction of Atlantic Avenue from Schenck Avenue to Rockaway Boulevard Including Sewer, Watermain, Street Lighting and Traffic Signal Work | Brooklyn |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2021 | 2024 |  | DDC
HWK1310 | HWK1310 | Y | Infrastructure | BROOKLYN | BROADWAY JUNCTION ENHANCEMENT PROJECT | The Broadway Junction Enhancement project will create a landscaped intermodal transfer center at the Broadway Junction subway station in Brooklyn on Van Sinderen Avenue between Broadway and Fulton Street. The project includes sidewalk extensions including pavement and curb reconstruction, alterations to the traffic patterns on Van Sinderen Avenue, relocation of street light poles, traffic signals and other bus stop amenities. The design goals include increased pedestrian safety, accommodations for necessary curbside access, and improvements to the streetscape appearance. | The Broadway Junction Enhancement project will create a landscaped intermodal transfer center at the Broadway Junction subway station in Brooklyn on Van Sinderen Avenue between Broadway and Fulton Street. The project includes sidewalk extensions including pavement and curb reconstruction, alterations to the traffic patterns on Van Sinderen Avenue, relocation of street light poles, traffic signals and other bus stop amenities. The design goals include increased pedestrian safety, accommodations for necessary curbside access, and improvements to the streetscape. | Brooklyn |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2014 |  | DDC
HWK1669A | HWK1669A | Y | Infrastructure | BROOKLYN | 4TH AVE. SAFETY IMPROVEMENTS PHASE II-VISION ZERO | 4TH AVENUE SAFETY IMPROVEMENTS PHASE II - VISION ZERO GREAT STREETS Safety Improvements along 4th Avenue from 18th Street to 33rd Street and 52nd Street to 60th Street in Sunset Park section of Brooklyn. | 4TH AVENUE SAFETY IMPROVEMENTS PHASE II - VISION ZERO GREAT STREETS | Brooklyn |  | Transportation | Design Development | New Construction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2016 | 2018 |  | DDC
HWK1670 | HWK1670 | Y | Infrastructure | BROOKLYN | Industry City Safety & Streetscape Improvements | Implement pedestrian safety and streetscape improvements under Gowanus Expressway at the intersection of 36th Street & 3rd Avenue in Sunset Park, Brooklyn. Improvements include sidewalk extensions, citybenches, wayfinding signage, pedestrian ramps, new crosswalks. | Industry City - Sunset Park Pedestrian Safety Improvements | Brooklyn |  | Transportation | Final Design | Street Reconstruction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2016 | 2018 |  | DDC
HWK1672 | HWK1672 | Y | Infrastructure | BROOKLYN | WASHINGTON AVE AND OCEAN AVE SAFETY IMPROVEMENTS | The Washington Ave and Ocean Ave Safety Improvements project will build out a range of pedestrian safety-related small geometric improvements at 4 intersections in Prospect Heights, Crown Heights and Prospect Park. The proposed improvements will build out temporary materials that will soon approach the end of their useful life. They include but are not limited to curb extensions, expanded sidewalks, accessible sidewalks and crossings, and road alignment. | The Washington Ave and Ocean Ave Safety Improvements |  |  | Transportation | [5 empty] | PIMS | FALSE |  |  |  | 2017-10-04 07:00:20.0170000 +00:00
HWK2013GB | HWK2013GB | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF GERRITSEN BEACH AREA, BK | Reconstruction & Resurfacing of Gerritsen Beach Area, including Storm Sewer Installation and Water Main Replacement, Brooklyn. Reconstruction: Beacon Court, Canton Court, Dare Court, and Frank Court from Bartlett Place to Seba Avenue and Eaton Court from Bartlett Place to Cyrus Avenue. Eaton Court from Cyrus Avenue to Seba Avenue, Bartlett Place from Gerritsen Avenue to Plumb Beach Ave, Kay Court from Just Court to End, Noel Avenue from Bartlett Place to Cyrus Avenue, and Post Court from Madoc Avenue to Dead End. Resurfacing: Abbey Court from Bartlett Place to Dead End, Cyrus Avenue from Just Court to Gerritsen Avenue, three sections of Madoc Avenue (from Cyrus Avenue to Lester Court, from Melba Court to Nova Court, from Post Court to Dead End), Noel Avenue from Cyrus Avenue to Lois Avenue and Seba Avenue from Madoc Avenue to Gerritsen Avenue, Channel Ave between Celeste Court and Bevy Court , Channel Ave between Aster Court and Gerritsen Ave . | Reconstruction & Resurfacing of Gerritsen Beach Area, including Storm Sewer Installation and Water Main Replacement, Brooklyn. | Brooklyn |  | Transportation | Scope Development | Street Reconstruction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2018 |  | DDC
HWK2048 | HWK2048 | Y | Infrastructure | BROOKLYN | JAMAICA BAY GREENWAY-PAERDEGAT AVE N CONNECTOR | JAMAICA BAY GREENWAY - PAERDEGAT AVENUE NORTH CONNECTOR | Jamaica Bay Greenway - Paerdegat Avenue North Connector | Brooklyn |  | Transportation | Design Development | Street Reconstruction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2019 | 2021 |  | DDC
HWK300-01 | HWK300-01 | Y | Infrastructure | BROOKLYN | NORTH FLATBUSH AVE - ATLANTIC YARDS AREA | Reconstruction of North Flatbush Avenue/ Atlantic Yards Area Streetscapes. Limits: Street From To 1. 6th Avenue Flatbush Avenue St. Mark's Avenue 2. St. Mark's Avenue 6th Avenue Flatbush Avenue 3. 7th Avenue Flatbush Avenue Park Place 4. Park Place 7th Avenue Carlton Avenue 5. 8th Avenue Flatbush Avenue St. John's Place 6. St. John's Place 8th Avenue Flatbush Avenue Neckdowns 5 and 6 will be removed from HWK300-01 to be done under BED798 as per 9/26/14 meeting. Green Triangles: 1. Intersection Flatbush-Carlton-Park Pl 2. Intersection Flatbush-7th Avenue- Park Pl 3. Intersection Flatbush-6th Avenue-St. Marks Avenue 4. Intersection Flatbush-8th Avenue-St. John's Pl (Removed and to be done under BED798 due to interference as per DOT e-mail dated 6/5/13.) Neckdowns: 1. Intersection Flatbush Avenue and Bergen Street 2. Intersection Carlton Avenue and Park Place 3. Intersection Flatbush Avenue and St. Mark's Avenue 4. Intersection Flatbush Avenue and Prospect Place 5. Intersection Flatbush Avenue and Sterling Place 6. Intersection Flatbush Avenue and St. John's Place 7. Intersection St. John's Place and 8th Avenue | Reconstruction of North Flatbush Avenue/ Atlantic Yards Area Streetscapes. | Brooklyn |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2012 | 2017 |  | DDC
HWK476C | HWK476C | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF MONITOR ST - GREENPOINT AV, ETC | Reconstruction of Monitor Street from Greenpoint Avenue to Norman Street, and six (6) legged intersections at Bedford Avenue/ Lorimer Street/ Nassau avenue, including neckdowns, traffic signals and pavement markings. Also included are the installation of new catch basins and connections, increasing existing curbs reveals, installation of new curbs and sidewalks. | Reconstruction of Monitor Street from Greenpoint Avenue to Norman Street, and six (6) legged intersections at Bedford Avenue/ Lorimer Street/ Nassau avenue, Brooklyn. | Brooklyn |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2022 | 2024 |  | DDC
HWK855 | HWK855 | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF E108TH STREET, BROOKLYN | Reconstruction of East 108th street from Seaview Avenue to Flatlands Avenue. Including curbs and sidewalks. Borough of Brooklyn. | Reconstruction of East 108th street from Seaview Avenue to Flatlands Avenue. Including curbs and sidewalks. Borough of Brooklyn | Brooklyn |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2022 | 2024 |  | DDC
HWK876 | HWK876 | Y | Infrastructure | Brooklyn | RECON WYCKOFF AV-FLUSHING to COOPER AV/SE | Reconstruction of Wyckoff Avenue from Flushing Avenue to Cooper Avenue, in the Boroughs of Brooklyn and Queens. | Reconstruction of Wyckoff Avenue from Flushing Avenue to Cooper Avenue, in the Boroughs of Brooklyn and Queens.. | Brooklyn |  | Trans. & Env. Protection | Final Design | Street Reconstruction | Standard | Requirements TO | Standard Consultant | PIMS | FALSE |  |  |  |  | DDC
HWK614D | HWK614D | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF BERGEN AVE AREA, BKLYN/BED-784 | Reconstruction of Bergen Avenue Area, including Storm Sewers, Water Mains, Street Lighting, Traffic Signal Work, and reconstruction of new outfall at East Mill Basin. Locations: 1. East 66 Street, from Avenue N to Veterans Avenue 2. East 69 Street, from Avenue X to Avenue Y 3. East 70 Street, from Avenue X to Avenue Y 4. East 72 Street, from Avenue W to Avenue Y 5. East73 Street, from Avenue X to Avenue Y 6. East 74 Street, from Avenue U to Avenue Y 7. Avenue N, from East 66 Street to 68th Street. 8. Royce Street, from Avenue T to Avenue U. 9. Royce Street, from Avenue X to Bergen Avenue 10. Avenue T, from East 68 Street to East 72 Street 11. Avenue T, from East 74 Street to Bergen Avenue 12. Avenue U, from East 68 Street to East 71 Street 13. Avenue V, from East 69 Street to East 74 Street 14. Avenue W, from East 71 Street to Bergen Avenue 15. Avenue X, from East 71 Street to Bergen Avenue 16. Avenue Y, from East 69 Street to Bergen Avenue 17. Avenue K, extension from Bergen Ave to East 72nd Street. 18. Veterans Avenue, from East 66 Street to East 71 Street 19. Bergen Avenue, from Avenue K extension to Avenue L 20. Bergen Avenue, from Avenue T to Avenue V 21. Bergen Avenue, from Royce Street to Avenue Y 22. E. 66th Street, from the intersection of Ave. N to 250' ± North of Ave. N (added as per DOT request) | Reconstruction of Bergen Avenue Area, including Storm Sewers, Water Mains, Street Lighting, Traffic Signal Work, and reconstruction of new outfall at East Mill Basin. | Brooklyn |  | Transportation | Compliance | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | FALSE |  | 2012 | 2018 |  | DDC
HWK779W | HWK779W | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF EMPIRE BLVD/BED-796 | Empire Boulevard Safety Improvements Scope of this project includes traffic and pedestrian safety improvements at the western and eastern ends of the street as well as resurfacing of some or all of Empire Blvd in between them. Project Area 1: Intersections of Empire Boulevard, Lefferts Avenue, Utica Avenue, East New York Avenue and Remsen Avenue. Project Area 2: Intersections of Empire Boulevard, Washington Avenue and Franklin Avenue. DEP Scope includes trunk water main, distribution water main and combined sewer work. Trunk Water Main (WM-6): ====================== 1-East New York Ave b/t Utica Ave. & Schenectady Ave. 2-Washington Ave. b/t Lefferts Ave. & Sullivan Pl, Water Main (WM-1) ================ 1-East New York Ave.(NS) b/t Schenectady Ave. & Utica Ave. 2-Empire Blvd b/t Schenectady Ave. & Utica Ave. 3-Lefferts Ave. b/t Schenectady Ave. & Utica Ave. Combined Sewer replacement: ========================= 1-Empire Blvd b/t Schenectady Ave. & Utica Ave. 2-Lefferts Ave. b/t Troy Ave. and Utica Ave. 3-E. New York Ave. b/t Utica Ave. & Schenectady Ave. 4-Washington Ave. b/t Sullivan Pl. & Sterling St. 5-Franklin Ave. b/t Sullivan Pl. & Sterling St. 6-Empire Blvd b/t Washington Blvd & Franklin Ave. Combined Sewer Guniting, Spot Repair: ================================ 1-Empire Blvd b/t franklin Ave. and Mc. Keever Pl. 2-Washington Ave. b/t Empire Blvd & Sterling St. | Empire Boulevard Safety Improvements | Brooklyn |  | Transportation | Final Design | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HWK797W | HWK797W | Y | Infrastructure | BROOKLYN | Reconstruction of Schenck Avenue | Reconstruction of Schenck Avenue | Reconstruction of Schenck Avenue | Brooklyn |  | Transportation | Pre-Preliminary Design | Street Reconstruction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2017 | 2019 |  | DDC
HWK639W | HWK639W | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF TILLARY STREET AREA/BED-782 | Tillary Street Area Reconstruction includes improvements of Tillary Street from Cadman Plaza West to Prince Street, on Adams Street from Red Cross Place to Tech Place, and on Cadman Plaza East from Red Cross Place to Tillary Street. Phase I: Adam Street from Red Cross Place (north of Tillary Street) to tech Place (south of Tillary Street) Phase II: Tillary Street from Cadman Plaza West to Prince Street, and on Cadman Plaza East from Red Cross Place to Tillary Street. The scope of work include: 1-Relocation and reconstruction of medians, with the installation of wideded, planted medians throughout the project area; 2-Widening of sidewalks and the installation of curb extension throughout the project area; 3-Installation of class I (physically separated) bike paths along the north side of Tillary Street, within the expanded center median of Adam Street, and along the West side of Cadman Plaza east;and the 4-Creation of public Plaza space at Cadman Plaza east and at the intersection of Tillary Street and Cadman Plaza west. 5-Water Main WM - 1: 1. Tillary Street (SS) between Adam St and Gold St 2. Tillary Street (nS) between Adam St and Jay St 3. Tillary Street (NS) between Dufield St and Prince St 4. Intersection of Tillary St and Adam St. 5. Intersection of Tillary St and Jay St. 6. Intersection of Tillary St and Bridge St. 7. Intersection of Tillary St and Flatbush Ave. 8. Intersection of Tillary St and Duffield St. 9. Intersection of Tillary St and Gold St. 10. Intersection of Tillary St and Prince St. 6-Combined Sewer Replacement in: 1. Flatbush Ave between Tillary St and Cathredal Pl. 2. intersection of Tillary St and Duffield St. 3. Intersection of Adam St and Red Cross Pl. 4. Intersection of Tillary St and Gold St. 7-Spot Repairs: 1. Adam St between Tillary St and Red Cross Pl 2. Intersection of Tillary St and Flatbush Ave. | Tillary Street Area Reconstruction includes improvements of Tillary Street from Cadman Plaza West to Prince Street, on Adams Street from Red Cross Place to Tech Place, and on Cadman Plaza East from Red Cross Place to Tillary Street. | Brooklyn |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Standard Consultant | Requirements TO | PIMS | FALSE |  | 2013 | 2016 |  | DDC
HWK639WA | HWK639WA | Y | Infrastructure | BROOKLYN | TILLARY STREET - PHASE II, BROOKLYN | TILLARY STREET - PHASE II, BROOKLYN | TILLARY STREET - PHASE II, BROOKLYN | Brooklyn |  | Transportation | Compliance | New Construction | Critical | Standard Consultant | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWMP2012 | HWMP2012 | Y | Infrastructure | Manhattan & Citywide | TIMES & DUFFY SQUARES RECONSTRUCTION (SEN002160) | Reconstruction of streets and implementation of pedestrian spaces in the Times Square and Duffy Square areas, including reconstruction of watermains and sewers as deemed necessary, Borough of Manhattan | Street reconstruction, including sewer and water main work. | Manhattan |  | Transportation | Substantial Completion | Other | Standard | Requirements TO | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWMP2012 | SEN002160 | Y | Infrastructure | Manhattan & Citywide | TIMES & DUFFY SQUARES RECONSTRUCTION (SEN002160) | Reconstruction of streets and implementation of pedestrian spaces in the Times Square and Duffy Square areas, including reconstruction of watermains and sewers as deemed necessary, Borough of Manhattan | Street reconstruction, including sewer and water main work. | Manhattan |  | Transportation | Substantial Completion | Other | Standard | Requirements TO | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWK700B | BED-768B | Y | Infrastructure | Brooklyn | RECONST. OF COLUMBIA ST., PH II/BED-768B/SEK002321 | Roadway reconstruction including new sewers, water main, street lighting and traffic signals on Columbia Street Area south of Hamilton Avenue. Trunk water main connections at shaft 23B in Columbia Street area. Reconstruction of Walcott Street Outfall. Trunk water Main: 1. Van Brunt Street between Hamilton Avenue north bound and Delavan Street 2. delavan Street between Van Brunt Street and Columbia street 3. Nelson Street between Columbia Street and Hicks Street 4. Hicks Steeet between Luquer Street and W. 9th Street 5. W. 9th Street and between Columbia street and Clinton Street ( to connect with water main installed under BED-759) Distribution Water Mains: 1. Van Brunt Street between Hamilton Avenue south bound and Delavan Street 2. Richards Street beween Verona street and Commerce Street 3. Hicks Steeet between Luquer Street and W. 9th Street 4. Huntington Street between Hicks Street and Hamilton Avenue Southbound 5. W. 9th Street and between Columbia street and Clinton Street ( to connect with water main installed under BED-759) Replacement of combined sewers in : 1. Van Brunt Street between Hamilton Avenue south bound and Summit Street 2. Intersection of Van Brunt and Bowne Street 3. Delavan Street between Van Brunt Street and Dwight Street 4. Nelson Street between Columbia Street and Hicks Street 5. Huntington Street between Hicks Street and Hamilton Avenue Southbound 6. W. 9th Street and between Hicks Steeet and Hamilton Avenue Southbound 7. Wolcott Street between Ferris Street and Bulkhead 8. Outfall in Buttermilk Channel Lining of Combined Sewers in: 1. Van Brunt Street between Commerce and Verona Street 2. Intersection of Hicks Street and Nelson Street 3. Hicks Street between Huntington Street and W. 9th Street 4. Hicks Street intersection between Hicks Street and W. 9th Street Guniting of Combined Sewers in: 1. Columbus Street Nelson Street and Huntington Street 2. Richards Street between Commerce Street and Verona Street. | Roadway reconstruction including new sewers, water main, street lighting and traffic signals: Columbia Street south of Hamilton Avenue. | Brooklyn |  | Trans. & Env. Protection | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWMP2012-ER | HWMP2012- | Y | Infrastructure | MANHATTAN & CITYWIDE | URGENT SAFETY IMPROVEMENTS IN TIMES SQUARE | Urgent safety improvements in Times Square between W. 42nd Street and W. 47th Street, Manhattan | Urgent safety improvements in Times Square between W. 42nd Street and W. 47th Street, Manhattan | Manhattan |  | Transportation | Compliance | Other | Critical | Requirements TO |  | PIMS | TRUE |  | 2018 | 2018 |  | DDC
HWMP2017 | HWMP2017 | Y | Infrastructure | MANHATTAN & CITYWIDE | WADSWORTH TERRACE, FAIRVIEW TO W 190TH ST (MED626) | Reconstruction of Wadsworth Terrace from Fairview Avenue to West 190th Street, Manhattan | Reconstruction of Wadsworth Terrace from Fairview Avenue to West 190th Street, Manhattan | Manhattan |  | Transportation | Substantial Completion | Street Reconstruction | Standard | In-House/Consultant | DDC Managed Consultant | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HWMP2019 | HWMP2019 | Y | Infrastructure | Manhattan & Citywide | EAST HOUSTON ST PEDESTRIAN IMPROVEMENTS (MED604) | Street Reconstruction of East Houston St. from Bowery to FDR Drive. Originally scoped to improve pedestrian and bicycle circulation on East Houston, this project will implement watermain and sewer replacement in addition to neckdowns, sidewalk widenings, and median enlargements in Manhattan. | Roadway reconstruction, East Houston Street from the Bowery to the FDR Drive, includes sewer and water main replacement, reconfigured sidewalks, medians and traffic neck downs. | Manhattan |  | Transportation | Construction 75%-Subst. | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWK700B | HWK700B | Y | Infrastructure | Brooklyn | RECONST. OF COLUMBIA ST., PH II/BED-768B/SEK002321 | Roadway reconstruction including new sewers, water main, street lighting and traffic signals on Columbia Street Area south of Hamilton Avenue. Trunk water main connections at shaft 23B in Columbia Street area. Reconstruction of Walcott Street Outfall. Trunk water Main: 1. Van Brunt Street between Hamilton Avenue north bound and Delavan Street 2. delavan Street between Van Brunt Street and Columbia street 3. Nelson Street between Columbia Street and Hicks Street 4. Hicks Steeet between Luquer Street and W. 9th Street 5. W. 9th Street and between Columbia street and Clinton Street ( to connect with water main installed under BED-759) Distribution Water Mains: 1. Van Brunt Street between Hamilton Avenue south bound and Delavan Street 2. Richards Street beween Verona street and Commerce Street 3. Hicks Steeet between Luquer Street and W. 9th Street 4. Huntington Street between Hicks Street and Hamilton Avenue Southbound 5. W. 9th Street and between Columbia street and Clinton Street ( to connect with water main installed under BED-759) Replacement of combined sewers in : 1. Van Brunt Street between Hamilton Avenue south bound and Summit Street 2. Intersection of Van Brunt and Bowne Street 3. Delavan Street between Van Brunt Street and Dwight Street 4. Nelson Street between Columbia Street and Hicks Street 5. Huntington Street between Hicks Street and Hamilton Avenue Southbound 6. W. 9th Street and between Hicks Steeet and Hamilton Avenue Southbound 7. Wolcott Street between Ferris Street and Bulkhead 8. Outfall in Buttermilk Channel Lining of Combined Sewers in: 1. Van Brunt Street between Commerce and Verona Street 2. Intersection of Hicks Street and Nelson Street 3. Hicks Street between Huntington Street and W. 9th Street 4. Hicks Street intersection between Hicks Street and W. 9th Street Guniting of Combined Sewers in: 1. Columbus Street Nelson Street and Huntington Street 2. Richards Street between Commerce Street and Verona Street. | Roadway reconstruction including new sewers, water main, street lighting and traffic signals: Columbia Street south of Hamilton Avenue. | Brooklyn |  | Trans. & Env. Protection | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWK700B | SEK002321 | Y | Infrastructure | Brooklyn | RECONST. OF COLUMBIA ST., PH II/BED-768B/SEK002321 | Roadway reconstruction including new sewers, water main, street lighting and traffic signals on Columbia Street Area south of Hamilton Avenue. Trunk water main connections at shaft 23B in Columbia Street area. Reconstruction of Walcott Street Outfall. Trunk water Main: 1. Van Brunt Street between Hamilton Avenue north bound and Delavan Street 2. delavan Street between Van Brunt Street and Columbia street 3. Nelson Street between Columbia Street and Hicks Street 4. Hicks Steeet between Luquer Street and W. 9th Street 5. W. 9th Street and between Columbia street and Clinton Street ( to connect with water main installed under BED-759) Distribution Water Mains: 1. Van Brunt Street between Hamilton Avenue south bound and Delavan Street 2. Richards Street beween Verona street and Commerce Street 3. Hicks Steeet between Luquer Street and W. 9th Street 4. Huntington Street between Hicks Street and Hamilton Avenue Southbound 5. W. 9th Street and between Columbia street and Clinton Street ( to connect with water main installed under BED-759) Replacement of combined sewers in : 1. Van Brunt Street between Hamilton Avenue south bound and Summit Street 2. Intersection of Van Brunt and Bowne Street 3. Delavan Street between Van Brunt Street and Dwight Street 4. Nelson Street between Columbia Street and Hicks Street 5. Huntington Street between Hicks Street and Hamilton Avenue Southbound 6. W. 9th Street and between Hicks Steeet and Hamilton Avenue Southbound 7. Wolcott Street between Ferris Street and Bulkhead 8. Outfall in Buttermilk Channel Lining of Combined Sewers in: 1. Van Brunt Street between Commerce and Verona Street 2. Intersection of Hicks Street and Nelson Street 3. Hicks Street between Huntington Street and W. 9th Street 4. Hicks Street intersection between Hicks Street and W. 9th Street Guniting of Combined Sewers in: 1. Columbus Street Nelson Street and Huntington Street 2. Richards Street between Commerce Street and Verona Street. | Roadway reconstruction including new sewers, water main, street lighting and traffic signals: Columbia Street south of Hamilton Avenue. | Brooklyn |  | Trans. & Env. Protection | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWK732B | BED-780 | Y | Infrastructure | BROOKLYN | Reconstruction of 5 Av from 34 to 65 St/ BED780 | Reconstruction of 5th Avenue from 34 to 65 street along with reconstruction of Trunk and Distribution water mains and combined sewer | Reconstruction of 5th Avenue from 34 Street to 65 Street , Brooklyn. | Brooklyn |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  | 2022 | 2024 |  | DDC
HWK732B | HWK732B | Y | Infrastructure | BROOKLYN | Reconstruction of 5 Av from 34 to 65 St/ BED780 | Reconstruction of 5th Avenue from 34 to 65 street along with reconstruction of Trunk and Distribution water mains and combined sewer | Reconstruction of 5th Avenue from 34 Street to 65 Street , Brooklyn. | Brooklyn |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  | 2022 | 2024 |  | DDC
HWK900 | HWK900 | Y | Infrastructure | BROOKLYN | BROWNSVILLE PEDESTRIAN SAFETY IMPROVEMENTS | THIS PROJECT IS LOCATED IN THE BROWNSVILLE NEIGHBORHOOD OF EAST BROOKLYN AND IS BOUNDED BY SUTTER AVE, JUNIUS STREET, LIVONIA AVE AND ROCKAWAY AVE. THIS AREA IS A NYC DOT TOP PRIORITY OF SAFETY IMPROVEMENTS AND RANKS IN THE TOP THIRD OF BROOKLYN CORRIDORS. IT HAS A RATE OF 11.2 KSI PER MILES WITH 2 PEDESTRIAN AND BICYCLIST FATALITIES SINCE 2010. THIS PROJECT CONSISTS OF THE INSTALLATION OF 13 CURB EXTENSIONS, 1 SIDEWALK EXTENSION, 1 BUS BULB AND BUS PAD, 2 RAISED CROSSWALKS AND 2 MEDIAN RECONSTRUCTION. THE PURPOSE OF THIS PROJECT IS TO CALM TRAFFIC, PROVIDE SAFER PEDESTRIAN CROSSINGS AND IMPROVE THE PUBLIC REALM IN A MAINLY RESIDENTIAL NEIGHBORHOOD. THE CURB EXTENSION WILL SHORTEN CROSSING DISTANCE FOR PEDESTRIANS AND REDUCE THE SPEED OF VEHICLES APPROACHING AND TURNING ON SCHOOL CROSSWALKS. | Brownsville Pedestrian Safety Improvements |  |  | Transportation | Pre-Design/PrgDevelopment | New Construction | Standard | Requirement Contract | Requirement Contract | PIMS | FALSE |  |  |  | 2017-12-11 13:00:20.9170000 +00:00
HWKF029B | HWKF029B | Y | Public Buildings | Transportation | 424 Wythe Ave. | Relocate DOT Paint Warehouse from 121 Plymouth Street, brooklyn to 424 Wythe Avenue, Brooklyn and housed in new explosion metal containers and building of a new pre-fab building | Relocate DOT Paint Warehouse from 121 Plymouth Street to a new, pre-fab building at 424 Wythe Avenue, Brooklyn. |  |  | Transportation | Substantial Completion | New Construction | Mayoral In | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HWKF2007A | HWKF2007 | Y | Public Buildings | Transportation | Hamilton Avenue Asphalt Plant Control Tower Renov | Renovation of the control tower building and the installation of a new fire supression shed | Renovate the control tower building and install a new fire supression shed. |  |  | Transportation | Acceptance/Final Completion | Renovation | Critical | CM-Build | CM-Build | Project Info | FALSE |  |  |  |  | DDC
HWKF488R | HWKF488R | Y | Public Buildings | TRANSPORTATION | Hamilton Asphalt roof Replacement | The scope of work includes replacement of roof and upgrades to the building façade. In addition, the consultant shall examine plumbing and electrical modifications that may be required to facilitate the building envelope rehabilitation. | The scope of work includes replacement of roof and upgrades to the building façade. In addition, the consultant shall examine plumbing and electrical modifications that may be required to facilitate the building envelope rehabilitation. | Brooklyn |  | Transportation | Schematic Design | Renovation | Standard | DDC Managed |  | PIMS | FALSE |  |  |  |  | DDC
HWKKP005 | BED-794 | Y | Infrastructure | BROOKLYN | DUMBO / VINEGAR HILL AREA-Phase II / BED-794 | Reconstruction and restoration of Belgian block roadways in the DUMBO (Down under the Manhattan Bridge overpass) and Vinegar Hill communities and the permanently build out the Pearl Street Triangle Plaza. Trunk Water Main (WM-6) Replacement In: 1. Water Street between Adams Street and Gold Street Water Main (WM-1) Replacement In: 1. Plymouth Street between Main Street and Adams Street 2. Water Street between Adams Street and Gold Street 3. Anchorage Pl between Plymouth Street and Water Street 4. Main Street between Plymouth Street and Water Street 5. Main Street between Water Street and Front Street 6. Adams Street between John Street and Plymouth Street 7. Pearl Street between Plymouth Street and Front Street 8. Jay Street intersection of Water Street 9. Bridge Street intersection of Water Street Combined Sewer Replacement In: 1. Anchorage Pl between Plymouth Street and Water Street 2. Water Street between Pearl Street and Gold Street High Level Storm Sewer Extention: 1. John Street between Adams Street and Pearl Street 2. Pearl Street between John Street and Front Street 3. Water Street between Pearl Street and Gold Street 4. Adams Street between John Street and Plymouth Street 5. Anchorage Pl between Plymouth Street and Water Stree . | Reconstruction DUMBO/Vinegar Hill Area including Trunk and Distribution water main replacement; Installation of HLSS and Combined Sewer replacement; Restoration of Belgian block in Water Street; Street lighting and Traffic Signal work. | Brooklyn |  | Transportation | Final Design | Street Reconstruction | Standard | Standard Consultant | Requirements TO | PIMS | TRUE |  | 2014 | 2018 |  | DDC
HWKKP005 | HWKKP005 | Y | Infrastructure | BROOKLYN | DUMBO / VINEGAR HILL AREA-Phase II / BED-794 | Reconstruction and restoration of Belgian block roadways in the DUMBO (Down under the Manhattan Bridge overpass) and Vinegar Hill communities and the permanently build out the Pearl Street Triangle Plaza. Trunk Water Main (WM-6) Replacement In: 1. Water Street between Adams Street and Gold Street Water Main (WM-1) Replacement In: 1. Plymouth Street between Main Street and Adams Street 2. Water Street between Adams Street and Gold Street 3. Anchorage Pl between Plymouth Street and Water Street 4. Main Street between Plymouth Street and Water Street 5. Main Street between Water Street and Front Street 6. Adams Street between John Street and Plymouth Street 7. Pearl Street between Plymouth Street and Front Street 8. Jay Street intersection of Water Street 9. Bridge Street intersection of Water Street Combined Sewer Replacement In: 1. Anchorage Pl between Plymouth Street and Water Street 2. Water Street between Pearl Street and Gold Street High Level Storm Sewer Extention: 1. John Street between Adams Street and Pearl Street 2. Pearl Street between John Street and Front Street 3. Water Street between Pearl Street and Gold Street 4. Adams Street between John Street and Plymouth Street 5. Anchorage Pl between Plymouth Street and Water Stree . | Reconstruction DUMBO/Vinegar Hill Area including Trunk and Distribution water main replacement; Installation of HLSS and Combined Sewer replacement; Restoration of Belgian block in Water Street; Street lighting and Traffic Signal work. | Brooklyn |  | Transportation | Final Design | Street Reconstruction | Standard | Standard Consultant | Requirements TO | PIMS | TRUE |  | 2014 | 2018 |  | DDC
HWKP2027 | HWKP2027 | Y | Infrastructure | BROOKLYN | CHURCH AVENUE SIDEWALKS AND NECKDOWNS | Replacement and Reconstruction of Sidewalks and Neckdowns on Church Avenue Area, Brooklyn. The scope of the project also includes full reconstruction of the intersection at Church Avenue and McDonald Avenue. | Replacement and Reconstruction of Sidewalks and Neckdowns on Church Avenue Area, Brooklyn. | Brooklyn |  | Transportation | Construction 0-25% | Sidewalks | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWKP2029 | HWKP2029 | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF PUTNAM PLAZA TRIANGLE | Putnam Plaza is an existing plaza implemented in temporary materials that also includes an existing Department of Parks and Recreation (DPR) Green street triangle with trees and a landscape area. This project will create a large, permanent public space for the Clinton Hill and Bedford-Stuyvesant neighborhoods by permanently pedestrianizing Putnam Avenue from Grand Avenue to Fulton Street, increasing the amount of open space for the local residents, shoppers, and transit users. The design will incorporate the existing Green street and will likely include additional trees, benches, movable tables and chairs, trash receptacles, green infrastructure elements, pedestrian Wayfinding signage and an NYC Bike Share station. | Putnam Plaza is an existing plaza implemented in temporary materials that also includes an existing Department of Parks and Recreation (DPR) Green street triangle with trees and a landscape area. This project will create a large, permanent public space for the Clinton Hill and Bedford-Stuyvesant neighborhoods by permanently pedestrianizing Putnam Avenue from Grand Avenue to Fulton Street, increasing the amount of open space for the local residents, shoppers, and transit users. The design will incorporate the existing Green street and will likely include additional trees, benches, movable tables and chairs, trash receptacles, green infrastructure elements, pedestrian Wayfinding signage and an NYC Bike Share station. | Brooklyn |  | Transportation | Construction 0-25% | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2017 |  | DDC
HWM1163 | HWM1163 | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF 7TH AVENUE (SEN002164) | Street Reconstruction of 7th Avenue between West 31st and West 34th Streets. | Street Reconstruction of 7th Avenue between West 31st and West 34th Streets. |  |  | Transportation | Cancelled Project | Street Reconstruction | Standard | In-House/Consultant | Requirements TO | PIMS | FALSE
HWM1683 | HWM1683 | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF W 33RD ST (SEN002165) | Full Reconstruction of West 33rd Street between 10th Avenue and 11th Avenue, including sewer and water main replacement, Manhattan As of 10/21/09 The Scope of work has changed Phase 1 & 2 is the construction of the north retaining wall, The MPT and street reconstruction up to the viaduct (abutment) Phase 3 is the South retaining wall Phase 4 is the bridge from the abutment wall to the intersection of 11 St | Reconstruction of West 33rd Street between 10th Avenue and 11th Avenue, Borough of Manhattan | Manhattan |  | Transportation | Construction 50-75% | Street Reconstruction | Mayoral In | Standard Consultant | Requirements TO | PIMS | FALSE |  |  | 2016 |  | DDC
HWM2025 | HWM2025 | Y | Infrastructure | MANHATTAN & CITYWIDE | DELANCEY STREET SAFETY IMPROVEMENTS | DELANCEY STREET SAFETY IMPROVEMENTS | DELANCEY STREET SAFETY IMPROVEMENTS | Manhattan |  | Transportation | Design Development | Other | Critical | Requirement Contract |  | PIMS | FALSE |  | 2017 | 2020 |  | DDC
HWM215 | HWM215 | Y | Infrastructure | MANHATTAN & CITYWIDE | STEP RECONSTRUCTION OF WEST 215 ST, MANHATTAN | STEP RECONSTRUCTION OF W 215 ST, MANHATTAN | STEP RECONSTRUCTION OF W 215 ST, MANHATTAN | Manhattan |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2009 | 2013 |  | DDC
HWMBRT5A | HWMBRT5A | Y | Infrastructure | MANHATTAN & CITYWIDE | 34th STREET TRANSITWAY - Phase I | As part of the 34th Street Select Bus Service project, work includes installation of pavement markings on 34th St. from FDR Drive to First Ave. and installation of bus bulbs & pavement markings on 34th St. from First Ave. to Lexington Ave. DEP Work: Trunk and Distribution Watermains replacement in E34th St. between 1st Ave. & 3rd Ave. | As part of the 34th Street Select Bus Service project, work includes installation of pavement markings on 34th St. from FDR Drive to First Ave. and installation of bus bulbs & pavement markings on 34th St. from First Ave. to Lexington Ave. DEP Work: Trunk and Distribution Watermains replacement in E34th St. between 1st Ave. & 3rd Ave. | Manhattan |  | Transportation | Substantial Completion | Street Reconstruction | Mayoral In | In-House/Consultant | Requirements TO | PIMS | FALSE |  | 2012 | 2014 |  | DDC
HWMM008 | HWMM008 | Y | Infrastructure | MANHATTAN & CITYWIDE | E. 86TH SAFETY & STREETSCAPE IMPROVEMENTS (MED633) | Replacement of curbs and first five feet of sidewalk and street enhancements on East 86th Street from Park Avenue to Second Avenue in Manhattan. In addition, the project includes DOT School Safety neckdowns and DOT Transit Development bus bulbs and neckdowns at the following locations in Manhattan: School Safety neckdowns: 1. Type II Neckdown @ NW and SE corners of E. 86th/ Park Ave. for Ramaz Lower School 2. Type II Neckdown @ SW corner of E. 85th/Madison Ave. for Park Ave. Christian Church Day School 3. Type I Neckdown @ NW and SW corners of E. 84th/Madison Ave. for Park Ave. Christian Church Day School Transit Development bus bulbs and neckdowns along E. 86th St. and: 1. Northwest corner with Lexington Ave. (bus bulb) 2. Northeast corner with Lexington Ave. (Type II neckdown) 3. Southeast corner with Lexington Ave. (bus bulb) 4. Northwest corner with Third Ave. (bus bulb) 5. Southwest corner with Third Ave. (Type II neckdown) 6. Southeast corner with Third Ave. (bus bulb) Water Main (WM-1) in: 1. E. 86th Street between Park Avenue and 2nd Avenue. 2. Madison Avenue between E. 84th Street and E. 85th Street. 3. Park Avenue intersection with E. 86th Steert 4. Lexington Avenue intersection with E. 86th Steert 5. 3rd Avenue intersection with E. 86th Steert 6. 2nd Avenue intersection with E. 86th Steert. This is an FTA-funded project. | Replacement of curbs and first five feet of sidewalk and street enhancements on East 86th Street from Park Avenue to Second Avenue in Manhattan. In addition, the project includes DOT School Safety neckdowns and DOT Transit Development bus bulbs and neckdowns. | Manhattan |  | Transportation | Construction 25-50% | Other | Standard | Requirement Contract | Requirements TO | PIMS | TRUE |  | 2013 | 2016 |  | DDC
HWMM008 | MED-633 | Y | Infrastructure | MANHATTAN & CITYWIDE | E. 86TH SAFETY & STREETSCAPE IMPROVEMENTS (MED633) | Replacement of curbs and first five feet of sidewalk and street enhancements on East 86th Street from Park Avenue to Second Avenue in Manhattan. In addition, the project includes DOT School Safety neckdowns and DOT Transit Development bus bulbs and neckdowns at the following locations in Manhattan: School Safety neckdowns: 1. Type II Neckdown @ NW and SE corners of E. 86th/ Park Ave. for Ramaz Lower School 2. Type II Neckdown @ SW corner of E. 85th/Madison Ave. for Park Ave. Christian Church Day School 3. Type I Neckdown @ NW and SW corners of E. 84th/Madison Ave. for Park Ave. Christian Church Day School Transit Development bus bulbs and neckdowns along E. 86th St. and: 1. Northwest corner with Lexington Ave. (bus bulb) 2. Northeast corner with Lexington Ave. (Type II neckdown) 3. Southeast corner with Lexington Ave. (bus bulb) 4. Northwest corner with Third Ave. (bus bulb) 5. Southwest corner with Third Ave. (Type II neckdown) 6. Southeast corner with Third Ave. (bus bulb) Water Main (WM-1) in: 1. E. 86th Street between Park Avenue and 2nd Avenue. 2. Madison Avenue between E. 84th Street and E. 85th Street. 3. Park Avenue intersection with E. 86th Steert 4. Lexington Avenue intersection with E. 86th Steert 5. 3rd Avenue intersection with E. 86th Steert 6. 2nd Avenue intersection with E. 86th Steert. This is an FTA-funded project. | Replacement of curbs and first five feet of sidewalk and street enhancements on East 86th Street from Park Avenue to Second Avenue in Manhattan. In addition, the project includes DOT School Safety neckdowns and DOT Transit Development bus bulbs and neckdowns. | Manhattan |  | Transportation | Construction 25-50% | Other | Standard | Requirement Contract | Requirements TO | PIMS | TRUE |  | 2013 | 2016 |  | DDC
HWMNYPL | HWMNYPL | Y | Infrastructure | MANHATTAN & CITYWIDE | New York Public Library Pedestrian Improvements | New York Public Library Pedestrian Improvements at the following locations in Manhattan: - Southern sidewalk and curb of West 42nd Street between 5th Avenue and 6th Avenue - Northern sidewalk and curb of West 40th Street between 5th Avenue and 6th Avenue - Curb extension at 6th Avenue on West 40th Street | New York Public Library Pedestrian Improvements at the following locations in Manhattan: - Southern sidewalk and curb of West 42nd Street between 5th Avenue and 6th Avenue - Northern sidewalk and curb of West 40th Street between 5th Avenue and 6th Avenue - Curb extension at 6th Avenue on West 40th Street | Manhattan |  | Transportation | Pre-Design/PrgDevelopment | Upgrade | Critical | Requirements TO |  | PIMS | FALSE |  | 2017 | 2020 |  | DDC
HWMP116 | HWMP116 | Y | Infrastructure | Manhattan & Citywide | RECONST OF ASTOR PL (SEN002163) | The creation of new pedestrian public spaces and improvement of Cooper Park. The Resurfacing of East 4th Street between Bowery and Lafayette Street, Lafayette Street and Broadway. And the reconstruction of the following Street segments: Lafayette Street between Astor Place and East 9th Street, East 8th Street between Lafayette and 3rd Avenue, East 4th Street between Bowery and 2nd Avenue, Astor Place between Lafayette Street and 3rd Avenue, 3rd Avenue between East 5th Street and East 9th Street, Fourth Avenue/ Cooper Square/ Bowery between East 4th Street and East 9th Street, and Median construction on Third Ave b/t East 4th Street and East 9th Street. | Street reconstruction and reconfiguration, includes the expansion of Cooper Park and creation of new pedestrian plazas. |  |  | Transportation | Substantial Completion | Other | Standard | In-House/Consultant | Requirements TO | PIMS | FALSE
HWMP2019 | MED-604 | Y | Infrastructure | Manhattan & Citywide | EAST HOUSTON ST PEDESTRIAN IMPROVEMENTS (MED604) | Street Reconstruction of East Houston St. from Bowery to FDR Drive. Originally scoped to improve pedestrian and bicycle circulation on East Houston, this project will implement watermain and sewer replacement in addition to neckdowns, sidewalk widenings, and median enlargements in Manhattan. | Roadway reconstruction, East Houston Street from the Bowery to the FDR Drive, includes sewer and water main replacement, reconfigured sidewalks, medians and traffic neck downs. | Manhattan |  | Transportation | Construction 75%-Subst. | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWMP2020 | HWMP2020 | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF GANSEVOORT AREA | Street Reconstruction and Pedestrian Space improvement within the following limits: - Ninth Avenue from Gansevoort Street to West 16 th Street -Gansevoort Street from Ninth Ave to Hudson Street -Hudson Street from West 14th Street to a point approximately 100' south of West 14th Street The project corridor is bordered by Chelsea and Gansevoort Market Historic District on the north and south, respectively. DEP Scope:Trunk Water Main in W. 13th St. and in following locations to connect Shaft 27B of City Water Tunnel #3 to the water distribution system, Phase 2, Borough of Manhattan: | Street Reconstruction and Pedestrian Space improvement within the following limits: - Ninth Avenue from Gansevoort Street to West 16th Street - Gansevoort Street from Ninth Avenue to Hudson Street - Hudson Street from West 14th Street to a point approximately 100' south of West 14th Street | Manhattan |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | In-House/Consultant | Standard Consultant | PIMS | FALSE |  | 2011 | 2015 |  | DDC
HWMWTCA6A | HWMWTCA6A | Y | Infrastructure | Manhattan & Citywide | RECONSTRUCTION OF BROADWAY, ETC (SEN002146) | Street reconstruction, water main replacement and sewer rehabilitation on the following streets: Broadway from Ann St. to Cortlandt St. (ADD as per 8/19/10 LMBCO's letter) Broadway from Cortlandt St. to Rector St. DELETED LOCATIONS: Broadway from Beaver St. to Stone St. (DELETE as per 11/29/10 LMBCO's email) Broadway from Morris St. to Battery Pl. (sewer work only) (DELETE as per 11/29/10 LMBCO's email) John St. from Broadway to William St. (DELETE as per 3/18/04 Lower Manhattan Executive Meeting) Morris St. from West St. to Washington St. (DELETE as per 6/9/03 memo) Morris St. from Greenwich St. to Broadway (DELETE as per 6/9/03 memo) | Reconstruct roadway; replace water main; rehabilitate sewers: sections of Broadway and adjoining streets south of Fulton. |  |  | Trans. & Env. Protection | Substantial Completion | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE
HWMWTCA6A | SEN002146 | Y | Infrastructure | Manhattan & Citywide | RECONSTRUCTION OF BROADWAY, ETC (SEN002146) | Street reconstruction, water main replacement and sewer rehabilitation on the following streets: Broadway from Ann St. to Cortlandt St. (ADD as per 8/19/10 LMBCO's letter) Broadway from Cortlandt St. to Rector St. DELETED LOCATIONS: Broadway from Beaver St. to Stone St. (DELETE as per 11/29/10 LMBCO's email) Broadway from Morris St. to Battery Pl. (sewer work only) (DELETE as per 11/29/10 LMBCO's email) John St. from Broadway to William St. (DELETE as per 3/18/04 Lower Manhattan Executive Meeting) Morris St. from West St. to Washington St. (DELETE as per 6/9/03 memo) Morris St. from Greenwich St. to Broadway (DELETE as per 6/9/03 memo) | Reconstruct roadway; replace water main; rehabilitate sewers: sections of Broadway and adjoining streets south of Fulton. |  |  | Trans. & Env. Protection | Substantial Completion | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE
HWMWTCA7B | HWMWTCA7B | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF BROADWAY, PHASE II (SEN002161) | Street Reconstruction of Broadway from Leonard St. to Cortlandt St. and Leonard Street from Church Street to Broadway. | Street Reconstruction of Broadway from Leonard St. to Cortlandt St. and Leonard Street from Church Street to Broadway. | Manhattan |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWMWTCA7B | SEN002161 | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF BROADWAY, PHASE II (SEN002161) | Street Reconstruction of Broadway from Leonard St. to Cortlandt St. and Leonard Street from Church Street to Broadway. | Street Reconstruction of Broadway from Leonard St. to Cortlandt St. and Leonard Street from Church Street to Broadway. | Manhattan |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWMWTCA7E | HWMWTCA7E | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF WORTH STREET (SEN002152) | Reconstruction of Worth Street from Hudson Street to Park Row in Manhattan, including roadways, sidewalks, curbs, sewers and watermain work. | Reconstruction of Worth Street from Hudson Street to Park Row, Borough of Manhattan | Manhattan |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  | 2016 |  | DDC
HWMWTCA7E | SEN002152 | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF WORTH STREET (SEN002152) | Reconstruction of Worth Street from Hudson Street to Park Row in Manhattan, including roadways, sidewalks, curbs, sewers and watermain work. | Reconstruction of Worth Street from Hudson Street to Park Row, Borough of Manhattan | Manhattan |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  | 2016 |  | DDC
HWMWTCA7F | HWMWTCA7F | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF WARREN & JOHN STS. (SEN002156) | Street Reconstruction of Warren St. from West St. to Broadway and John St. from Broadway to William St. | Street Reconstruction of Warren St. from West St. to Broadway and John St. from Broadway to William St. | Manhattan |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  | 2017 |  | DDC
HWMWTCA7F | SEN002156 | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF WARREN & JOHN STS. (SEN002156) | Street Reconstruction of Warren St. from West St. to Broadway and John St. from Broadway to William St. | Street Reconstruction of Warren St. from West St. to Broadway and John St. from Broadway to William St. | Manhattan |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  | 2017 |  | DDC
HWMWTCA7G | HWMWTCA7G | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF JOHN STREET (SEN002162) | Street reconstruction of John Street from Broadway to William Street, including sewer reconstruction. | Street reconstruction of John Street from Broadway to William Street, including sewer reconstruction |  |  | Transportation | Cancelled Project | Street Reconstruction | Standard | In-House | DDC Managed | PIMS | FALSE
HWMWTCA7G | SEN002162 | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF JOHN STREET (SEN002162) | Street reconstruction of John Street from Broadway to William Street, including sewer reconstruction. | Street reconstruction of John Street from Broadway to William Street, including sewer reconstruction |  |  | Transportation | Cancelled Project | Street Reconstruction | Standard | In-House | DDC Managed | PIMS | FALSE
HWMWTCA9 | HWMWTCA9 | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF DOVER and SOUTH ST., MANHATTAN | Reconstruction of Dover Street from Pearl Street to South Street, and South Street from Dover Street to Fulton Street. | Reconstruction of Dover Street from Pearl Street to South Street, and South Street from Dover Street to Fulton Street. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE
HWMWTCB1 | HWMWTCB1 | Y | Infrastructure | MANHATTAN & CITYWIDE | NASSAU STRET RECONSTRUCTION | The proposed project will reconstruct 3 blocks of Nassau Street, from Pine St to Maiden Ln. Vaults will be reinforced and filled. The sidewalks and curbs will be upgraded to the Lower Manhattan standards of 6" wide granite curbs and dark pigmented concrete sidewalks. Street lights, signals and curb ramps will be upgraded. This project is part of the WTC Emergency Relief fund from FHWA to reconstruct resources damaged during the events 9/11. The following work will be included: Sidewalks and curbs; Roadway; Vaults; Pedestrian Ramps; Street Lights; Street Signals; Tree Planting; Street Markings; Wayfinding Considerations | Reconstruction of Nassau Street from Pine Street to Maiden Lane, Manhattan | Manhattan |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Critical | Requirements TO |  | PIMS | FALSE |  | 2018 | 2020 |  | DDC
HWMWTCB2 | HWMWTCB2 | Y | Infrastructure | MANHATTAN & CITYWIDE | GREENWICH STREET RECONSTRUCTION | The proposed project will reconstruct 4 blocks of Greenwich St, from Barclay St to Chambers St. Any vaults encountered will be reinforced and filled. South of Murray St, the sidewalks and curbs will be upgraded to the Lower Manhattan standards of 6" wide granite curbs and dark pigmented concrete sidewalks. North of Murray St. the typical city standards will be used. Street lights, signals, and curb ramps will be upgraded. This project is part of the WTC Emergency Relief fund from FHWA to reconstruct resources damaged during 9/11. The scope includes the following: Roadway work; sidewalks and curbs; vaults; pedestrian ramps; street lights and signals; street tree plantings; greenstreet; street markings and wayfinding considerations | RECONSTRUCTION OF GREENWICH STREET FROM BARCLAY STREET TO CHAMBERS STREET, MANHATTAN | Manhattan |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Critical | Requirements TO |  | PIMS | FALSE |  | 2018 | 2020 |  | DDC
HWMWTCB5A | HWMWTCB5A | Y | Infrastructure | MANHATTAN & CITYWIDE | LIBERTY STREET WEST RECONSTRUCTION | THIS PROJECT WILL RECONSTRUCT ONE BLOCK OF LIBERTY STREET BETWEEN GREENWICH STREET AND CHURCH STREET. THE INTERSECTION OF LIBERTY STREET WITH CHURCH STREET WILL BE RESURFACED. THE SOUTHERN SIDEWALK AND CURB LINE WILL BE RECONSTRUCTED TO MEET GRADES AND ADA ACCESSIBILITY STANDARDS. THE NEW SIDEWALK WILL MEET LOWER MANHATTAN STANDARDS OF GRANITE CURBING AND DARK PIGMENTED CONCRETE. SECURITY DEVICES WILL BE INSTALLED BY THE PORT AUTHORITY OF NY/NJ ON THE WESTERN END OF THE BLOCK, AND ARE OUTSIDE OF THE SCOPE OF THIS PROJECT. | Reconstruction of Liberty Street between Greenwich Street and Church Street |  |  | Transportation | Design Development | Street Reconstruction | Critical | In-House |  | PIMS | FALSE |  |  |  | 2017-11-01 13:00:20.3100000 +00:00
HWMWTCB6 | HWMWTCB6 | Y | Infrastructure | MANHATTAN & CITYWIDE | VESEY STREET RECONSTRUCTION | The proposed scope will reconstruct one block of Vesey St from Church to Broadway. Vaults will be reinforced and back-filled. The sidewalks and curbs will be upgraded to the Lower Manhattan standards of 6" wide granite curbs and dark pigmented concrete sidewalks. Street lights, signals, and curb ramps will be upgraded where necessary. This project is part of the WTC Emergency Relief fund from FHWA (80/20) to reconstruct resources damaged during the events of 9/11. | Reconstruction of Vesey Street from Church Street to Broadway, Borough of Manhattan |  |  | Transportation | [5 empty] | PIMS | FALSE |  |  |  | 2017-10-12 13:00:19.2200000 +00:00
HWMWTCB7 | HWMWTCB7 | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF TRINITY PL | The proposed scope will reconstruct 4 blocks of Trinity Place, from Morris St to Cedar St. Any vaults encountered will be reinforced and filled. The sidewalks and curbs will be upgraded to the Lower Manhattan standards of 6" wide granite curbs and dark pigmented concrete sidewalks. Street lights, signals and curb ramps will be upgraded to modern safety standards where necessary. This project is part of the WTC Emergency Relief fund from FHWA to reconstruct resources damaged during the events of 9/11. | Reconstruction of Trinity Place from Morris Street to Cedar Street, Borough of Manhattan |  |  | Transportation | [5 empty] | PIMS | FALSE |  |  |  | 2017-10-12 13:00:20.4730000 +00:00
HWP14MLM | HWP14MLM | Y | Infrastructure | MANHATTAN & CITYWIDE | COMPLEX PED RAMPS (LANDMARK) - MANHATTAN | Design of complex pedestrian ramps adjacent to historic and/or landmark facilities within the borough of Manhattan. Locations of the pedestrian ramps will be provided by the NYCDOT Division of Sidewalks and Inspection Management. Since, We still have left over ramp locations for Manhattan from a list we received last year for LM locations. We will continue to use that list until it is completed. | Complex pedestrian ramps adjacent to historic and/or landmark facilities within the Borough of Manhattan | Manhattan |  | Transportation | Construction 0-25% | Ped Ramps | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWP14MTA | HWP14MTA | Y | Infrastructure | MANHATTAN & CITYWIDE | COMPLEX PED RAMPS (TRANSIT AUTHORITY) - MANHATTAN | Design of complex pedestrian ramps adjacent to transit facilities within the borough of Manhattan. Locations of the pedestrian ramps will be provided by the NYCDOT Division of Sidewalks and Inspection Management. Since, We still have left over ramp locations for Manhattan from a list we received last year TA locations. We will continue to use that list until it is completed. | Complex pedestrian ramps adjacent to transit facilities within the borough of Manhattan. | Manhattan |  | Transportation | Construction 0-25% | Ped Ramps | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2016 |  | DDC
HWP14QC | HWP14QC | Y | Infrastructure | S. QUEENS | COMPLEX PED RAMPS - QUEENS | Installation of complex pedestrian ramps at designated locations in the Borough of Queens. | Installation of complex pedestrian ramps at various locations. | Queens |  | Transportation | Construction 50-75% | Ped Ramps | Standard | In-House/Consultant | DDC Managed | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HWP14QLM | HWP14QLM | Y | Infrastructure | BRONX & N. QUEENS | COMPLEX PED RAMPS (LANDMARK) - QUEENS | Installation of complex pedestrian ramps adjacent to historic and/or landmark facilities at designated locations in the Borough of Queens. | Installation of complex pedestrian ramps adjacent to historic and/or landmark facilities at designated locations in the Borough of Queens. | Queens |  | Transportation | Substantial Completion | Ped Ramps | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HWP14QTA | HWP14QTA | Y | Infrastructure | BRONX & N. QUEENS | COMPLEX PED RAMPS (TRANSIT AUTHORITY) - QUEENS | Design of complex pedestrian ramps adjacent to transit facilities within the Borough of Queens. | Complex pedestrian ramps adjacent to transit facilities at various locations. | Queens |  | Transportation | Substantial Completion | Ped Ramps | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HWP14RLM | HWP14RLM | Y | Infrastructure | STATEN ISLAND | COMPLEX PED RAMPS (LANDMARK) - SI | Design of Complex Pedestrian Ramps adjacent to historic and/or landmark facilities within the Borough of Staten Island. Locations of the Pedestrian Ramps will be provided by the Department of Transportation's (DOT) Division of Sidewalks and Inspection Management, Pedestrian Ramps Unit. | Design of Complex Pedestrian Ramps adjacent to historic and/or landmark facilities within the Borough of Staten Island. | Staten Is. |  | Transportation | Substantial Completion | Ped Ramps | Standard | Requirements TO | None | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWP14RTA | HWP14RTA | Y | Infrastructure | STATEN ISLAND | CITYWIDE COMPLEX PED RAMPS (TA) - SI | Design of Complex Pedestrian Ramps adjacent to Transit Authority's (TA) facilities within the Borough of Staten Island. Locations of the Pedestrian Ramps will be provided by the Department of Transportation's (DOT) Division of Sidewalks and Inspection Management, Pedestrian Ramps Unit. | Design of Complex Pedestrian Ramps adjacent to Transit Authority's (TA) facilities within the Borough of Staten Island. | Staten Is. |  | Transportation | Construction 0-25% | Ped Ramps | Standard | In-House | DDC Managed | PIMS | FALSE |  | 2013 | 2016 |  | DDC
HWP15KCL | HWP15KCL | Y | Infrastructure | BROOKLYN | SIMPLE, COMPLEX & LANDMARK PED. RAMPS, BK | SIMPLE, COMPLEX & LANDMARK PED. RAMPS, BK | Simple, Complex & Landmark Pedestrian Ramps in Brooklyn. | Brooklyn |  | Transportation | Construction 0-25% | Ped Ramps | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWP15KTA | HWP15KTA | Y | Infrastructure | BROOKLYN | COMPLEX PED. RAMPS - TRANSIT AUTHORITY, BK | COMPLEX PED. RAMPS - TRANSIT AUTHORITY, BK | COMPLEX PED. RAMPS - TRANSIT AUTHORITY, BK | Brooklyn |  | Transportation | Construction 0-25% | Ped Ramps | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWP15QLA | HWP15QLA | Y | Infrastructure | S. QUEENS | COMPLEX PED. RAMPS - LANDMARKS, QNS | COMPLEX PED. RAMPS - LANDMARKS, QNS | COMPLEX PED. RAMPS - LANDMARKS, QNS |  |  | Transportation |  | Ped Ramps | Critical |  |  | PIMS | FALSE
HWP15QTA | HWP15QTA | Y | Infrastructure | BROOKLYN | COMPLEX PED. RAMPS - TRANSIT AUTHORITY, QNS | COMPLEX PED. RAMPS - TRANSIT AUTHORITY, QNS | COMPLEX PED. RAMPS - TRANSIT AUTHORITY, QNS | Queens |  | Transportation | Construction 0-25% | Ped Ramps | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWP15RSC | HWP15RSC | Y | Infrastructure | STATEN ISLAND | SIMPLE & COMPLEX PED. RAMPS, SI | SIMPLE & COMPLEX PED. RAMPS, SI | SIMPLE & COMPLEX PED. RAMPS, SI | Staten Is. |  | Transportation | Construction 0-25% | Ped Ramps | Standard | Requirement Contract | DDC Managed Consultant | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWP15XMCL | HWP15XMCL | Y | Infrastructure | MANHATTAN & CITYWIDE | SIMPLE, COMPLEX & LANDMARKS PED. RAMPS, MN | SIMPLE, COMPLEX & LANDMARKS PED. RAMPS, BX & MN | SIMPLE, COMPLEX & LANDMARKS PED. RAMPS, BX & MN | Manhattan |  | Transportation | Construction 0-25% | Ped Ramps | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWP15XMTA | HWP15XMTA | Y | Infrastructure | MANHATTAN & CITYWIDE | COMPLEX PED. RAMPS - TRANSIT AUTHORITY, BX & MN | COMPLEX PED. RAMPS - TRANSIT AUTHORITY, BX & MN | COMPLEX PED. RAMPS - TRANSIT AUTHORITY, BX & MN | Manhattan |  | Transportation | Construction 0-25% | Ped Ramps | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWP16KC | HWP16KC | Y | Infrastructure | BROOKLYN | CITYWIDE COMPLEX PED RAMPS - BROOKLYN | RECONSTRUCTION OF CITYWIDE COMPLEX PED RAMPS - BROOKLYN | RECONSTRUCTION OF COMPLEX PED RAMPS - BROOKLYN | Brooklyn |  | Transportation | Construction 0-25% | Ped Ramps | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWP16MTAL | HWP16MTAL | Y | Infrastructure | MANHATTAN & CITYWIDE | COMPLEX PEDESTRIAN RAMP-MTA & LANDMARK PHASE II MA | COMPLEX PEDESTRIAN RAMPS ADJACENT TO TRANSIT AND LANDMARK FACILITIES WITHIN LOWER MANHATTTAN COMMUNITY BOARDS 1, 2 AND 3. | COMPLEX PEDESTRIAN RAMPS ADJACENT TO TRANSIT AND LANDMARK FACILITIES WITHIN LOWER MANHATTTAN COMMUNITY BOARDS 1, 2 AND 3. | Manhattan |  | Transportation | Construction 0-25% | Ped Ramps | Critical | Requirement Contract | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWP16XTA | HWP16XTA | Y | Infrastructure | BRONX & N. QUEENS | COMPLEX PED RAMPS - TRANSIT AUTHORITY - BRONX | RECONSTRUCTION OF COMPLEX PEDESTRIAN RAMPS AT TRANSIT AUTHORITY LOCATIONS IN THE BOROUGH OF THE BRONX | RECONSTRUCTION OF COMPLEX PEDESTRIAM RAMPS AT TRANSIT AUTHORITY LOCATIONS IN THE BOROUGH OF THE BRONX | Bronx |  | Transportation | Final Design | Ped Ramps | Critical |  |  | PIMS | FALSE |  | 2015 |  |  | DDC
HWP2010R | HWP2010R | Y | Infrastructure | STATEN ISLAND | STATEN ISLAND COMPLEX PED RAMPS | Installation of Complex Pedestrian Ramps at Designated Locations in Borough of Staten Island | Installation of Complex Pedestrian Ramps at Designated Locations in Borough of Staten Island |  |  | Transportation | Substantial Completion | Ped Ramps | Standard | In-House/Consultant | Standard Consultant | PIMS | FALSE
HWP2012QC | HWP2012QC | Y | Infrastructure | S. QUEENS | CONSTRUCTION OF COMPLEX PED RAMPS, QUEENS | Project Limit/ location Queens Pedestrian Ramps will be provided by the NYCDOT Division of Sidewallks and Inspections Management, Pedestrian Unit upon the Community Boards Schedule for construction.Various locations, Borough of Queens. | Project Limit/ location Queens Pedestrian Ramps will be provided by the NYCDOT Division of Sidewallks and Inspections Management, Pedestrian Unit upon the Community Boards Schedule for construction.Various locations, Borough of Queens. | Queens |  | Transportation | Completed Project | Ped Ramps | Standard | In-House | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HWP2012R | HWP2012R | Y | Infrastructure | STATEN ISLAND | SIMPLE PEDESTRIAN RAMPS - STATEN ISLAND | SIMPLE PEDESTRIAN RAMPS - STATEN ISLAND | SIMPLE PEDESTRIAN RAMPS - STATEN ISLAND |  |  | Transportation | Acceptance/Final Completion | Ped Ramps | Standard |  |  | PIMS | FALSE
HWP2013LM | HWP2013LM | Y | Infrastructure | MANHATTAN & CITYWIDE | COMPLEX PED RAMPS AT LAND MARK LOCATIONS, BK & MAN | Complex Pedestrian Ramps adjacent to Historic and /or Landmark facilities within the Boroughs of Brooklyn & Manhattan. 09/04/2013 - Origianl list of locations 108 corners. 4 corners were added when performing preliminary investigation. There is a total 112 corners. Out of the 112 corners, 63 corners (38 intersections) require detailed design, 7 corners require vault investigation, 1 corner is a simple corner/not in historic district and 41 corners do not required work. | Complex Pedestrian Ramps adjacent to Historic and/or Landmark facilities within the Borough of Brooklyn & Manhattan | Manhattan |  | Transportation | Construction 25-50% | Ped Ramps | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2016 |  | DDC
HWP2013MX | HWP2013MX | Y | Infrastructure | BRONX & N. QUEENS | COMPLEX PED RAMPS - BRONX AND MANHATTAN | Construction of Complex Ped Ramps within the boroughs of Bronx and Manhattan. Locations of Ped Ramps will be provided by the NYCDOT Division of Sidewalks and Inspections. | Construction of Complex Ped Ramps within the boroughs of Bronx and Manhattan. Locations of Ped Ramps will be provided by the NYCDOT Division of Sidewalks and Inspections. | Citywide |  | Transportation | Construction 50-75% | Ped Ramps | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2012 | 2013 |  | DDC
HWP2013TA | HWP2013TA | Y | Infrastructure | MANHATTAN & CITYWIDE | CONSTRUCTION OF COMPLEX PED RAMPS(MTA), BK & MANS | Construction of complex ped ramps (MTA) in Brooklyn & Manhattan. | Construction of complex ped ramps (MTA) in Brooklyn & Manhattan. | Manhattan |  | Transportation | Substantial Completion | Ped Ramps | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2016 |  | DDC
HWP2016M1 | HWP2016M1 | Y | Infrastructure | MANHATTAN & CITYWIDE | REHABILITATION OF PEDESTRIAN RAMPS - MANHATTAN | REHABILITATION OF PEDESTRIAN RAMPS - MANHATTAN (CB1) | Rehabilitation of existing pedestrian ramps, Manhattan Community Board No.1 |  |  | Transportation | Cancelled Project | Ped Ramps | Critical | In-House | Requirements TO | PIMS | FALSE
HWP2016M2 | HWP2016M2 | Y | Infrastructure | MANHATTAN & CITYWIDE | REHABILITATION OF PEDESTRIAN RAMPS - MANHATTAN | REHABILITATION OF PEDESTRIAN RAMPS - MANHATTAN (CB2) | Rehabilitation of Existing Pedestrian Ramps, Manhattan CB#2 |  |  | Transportation | Cancelled Project | Ped Ramps | Critical | In-House |  | PIMS | FALSE
HWP2016M3 | HWP2016M3 | Y | Infrastructure | MANHATTAN & CITYWIDE | REHABILITATION OF PEDESTRIAN RAMPS - MANHATTAN | REHABILITATION OF PEDESTRIAN RAMPS - MANHATTAN (CB3) | Rehabilitation of Pedestrian Ramps- Manhattan CB3 |  |  | Transportation | Cancelled Project | Ped Ramps | Critical | In-House |  | PIMS | FALSE
HWPEDSF1 | HWPEDSF1 | Y | Infrastructure | BRONX & N. QUEENS | MULTI - SITE PEDESTRIAN SAFETY | Construction of curb extensions (bus bulbs) for bus stops at subway located underneath elevated subway structures. 31 St and Broadway (from HWSRT2009) 31 St and 36 Ave 31 St and 39 Ave | Construction of curb extensions (bus bulbs) for bus stops at subway located underneath elevated subway structures. 31 St and Broadway (from HWSRT2009) 31 St and 36 Ave 31 St and 39 Ave | Queens |  | Transportation | Construction 25-50% | Street Reconstruction | Standard | Requirements TO | DDC Managed/Consultant | PIMS | FALSE |  |  |  |  | DDC
HWPEDSF3A | HWPEDSF3A | Y | Infrastructure | MANHATTAN & CITYWIDE | MULTI-SITE PEDESTRIAN SAFETY - 5 LOCATIONS | Construction of roadway and sidewalk treatments to enhance pedestrian safety in the locations listed below, Citywide. These locations and funding were transferred from original contract # HWPEDSF3. Manhattan: 1 - E. 14th Street & 1st Avenue (Reso-A - $165,000) - Design deleted location due to utility manholes. - NYCT 2 - Lexington Ave and E. 59th St. / E. 60th St. (Reso-A - $300,000/2) - NYCT 3 - E. 84th St./Transverse # 3 and 5th Ave. (Reso-A - $300,000/2) - Historic District/Scenic Landmark 13 - W. 71st St. and Broadway/Amsterdam Ave. - NYCT & Historic District 14 - Nagle Ave. and Hillside Ave./Broadway/Bennett Ave. (Additional location from revised CPI 8/31/11) 16 – West 70th and West End. (Additional location from revised CPI dated 08/30/13) - NYCT One block & Historic District Brooklyn: 5 - York St. & Navy St//Hudson Avenue Queens: 8 - Hempstead Ave. and Springfield Blvd. 17 – Parsons Blvd./ 84th Ave./ Hoover Ave. (Additional location from revised CPI dated 08/30/13). | Construction of roadway and sidewalk treatments to enhance pedestrian safety at various location, Citywide. | Citywide |  | Transportation | Construction 0-25% | Other | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2013 | 2017 |  | DDC
HWPEDSF3-R | HWPEDSF3 | Y | Infrastructure | BROOKLYN | MULTI-SITE PEDESTRIAN SAFETY | Construction of roadway and sidewalk treatments to enhance pedestrian safety in locations listed below, Citywide This project was transferred from original contract # HWPEDSF3. Manhattan: 1- E. 14th St. and 1st Ave. (Reso-A - $35,000) - NYCT (Reso-A-$95,000 - CM) - Cannot be built due to utility manholes. Bronx: 4- E. 137th St. from Brook Ave. to St. Ann's Ave. (Reso A. - $150,000) - NYCT Brooklyn: 9- Nostrand Ave. & Linden Blvd. - NYCT 10- Nostrand Ave. and Clarkson Ave. - NYCT 11- Ave. P and Ocean Ave. 15- 68th St. and Shore Rd. (Additional location from revised CPI 8/31/11) Queens: 6- 136th St. and 71st Rd. 7- 69th Ave. and 195th Ln. Staten Island: 12- 8th St. and New Dorp Lane - NYCT SI Railroad The Following locations were transferred to Contract # HWPEDSF3A: Manhattan: 2- Lexington Ave. and E. 59th St / E. 60th St. (Reso-A - $300,000/2) - NYCT 3- E. 84th St./Transverse # 3 and 5th Ave. (Reso-A - $300,000/2) - Historic District/Scenic Landmark 13- W. 71st St. and Broadway/Amsterdam Ave. - NYCT & Historic District (Additional location from revised CPI 8/31/11) 14- Nagle Ave. and Hillside Ave./Broadway/Bennett Ave. (Additional location from revised CPI 8/31/11) Brooklyn: 5- York St. & Navy St. /Hudson St. Queens: 8- Hempstead Ave. and Springfield Blvd | Construction of roadway and sidewalk treatments to enhance pedestrian safety in various locations, Citywide | Citywide |  | Transportation | Completed Project | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2014 |  | DDC
HWPEDSF4 | HWPEDSF4 | Y | Infrastructure | MANHATTAN & CITYWIDE | MULTI-SITE PEDESTRIAN SAFETY | MULTI-SITE PEDESTRIAN SAFETY, CITYWIDE PROJECT SCOPE AND LOCATIONS: BRONX- Loc.#1- Bruckner Blvd. (Body of water by Concrete Plant Park) BROOKLYN - Loc.# 2 -8th Ave./57th St.; Loc. #3 -92nd St. /Ft. Hamilton Parkway (Removed).; Loc.#4 Cortelyou Rd./Rugby Rd.;Loc.#5 -Linden Blvd./E. 51st St.; Loc.#6 -Linden Blvd./E. 52nd St.; Loc.#7 -Ocean Parkway N./In front of Coney Island Hosp.(Pending S.G.D) MANHATTAN- Loc.#8 -E. 125th St/Lexington Ave.; Loc.#9 -W. 125th St./Amsterdam Ave.; Loc.#10-W. 181st St./Broadway; Loc.#11-W. 181st St./St. Nicholas Ave.; Loc.#12-W. 181st St./Amsterdam Ave.; Loc. (Removed).#13-Delancey St./Orchard St.; (Removed) Loc.#14-Delancey St./Essex St. (Removed) ADDED Location in Manhattan #18 NW corner of W34th St and 8th AVE. QUEENS- Loc.#15 -Hoyt Ave. South/Columbus Triangle (Will be given to NYCT to bid) STATEN ISLAND - Loc.#16-Amundsen Circle Roads/Amboy Rd, Riedel Ave., Clark Ave., Savoy St.; (ROW Issues) Loc. #17-Richmond Ave./300' N. from N. Leg of Yukon Ave. to 310' S. of S. leg of Yukon Ave. | Multi-Site Pedestrian Safety, Citywide | Citywide |  | Transportation | Final Design | Street Reconstruction | Standard | In-House/Consultant | Requirements TO | PIMS | FALSE |  | 2014 | 2018 |  | DDC
HWPEDSF5 | HWPEDSF5 | Y | Infrastructure | Miscellaneous | MULTI-SITE PEDESTRIAN SAFETY PHASE 5 | CONSTRUCT A RANGE OF PEDESTRIAN SAFETY GEOMETRIC IMPROVEMENTS AT VARIOUS SPECIFIED LOCATIONS, CITYWIDE. | PEDESTRIAN SAFETY GEOMETRIC IMPROVEMENTS AT VARIOUS SPECIFIED LOCATIONS, CITYWIDE | Citywide |  | Transportation | Design Development | Street Reconstruction | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2017 | 2019 |  | DDC
HWPLZ001K | HWPLZ001K | Y | Infrastructure | BROOKLYN | Myrtle Ave. Plaza & Street Reconstruction/BED-792 | Construction of Myrtle Avenue Plaza and Streetscape in the Borough of Brooklyn. This project will fully reconstruct the street on Myrtle Avenue from Hall Street to Emerson Place, in the Clinton Hill neighborhood of Brooklyn. The project will provide many pedestrian improvements to make crossing Myrtle Avenue safer, including bulb outs at Hall Street, Grand Street and Emerson Place; a new signalized crossing at Grand St; an expanded center median; the consolidation of bus stops; and conversion of two blocks of the service road to pedestrian plaza. Amenities to be added including seating, lighting, trees/plants, decorative paving, drinking fountain(s), bike racks, public art, etc. | Construction of Myrtle Avenue Plaza and Streetscape in the Borough of Brooklyn. | Brooklyn |  | Transportation | Substantial Completion | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2012 | 2014 |  | DDC
HWPLZ003M | HWPLZ003M | Y | Infrastructure | MANHATTAN & CITYWIDE | Montefiore Park & Plaza Improvement (MED-629) | Reconstruction of Montefiore Park bounded by Broadway, Hamilton Place, & 138th Street, including expansion onto Hamilton Place to create a pedestrian plaza MED-629-Trunk water main and distribution water main replacement in Broadway bet. W. 136th and W. 138th Sts. and W. 138th St. bet. Broadway and Hamilton Place. | Reconstruction of Montefiore Park bounded by Broadway, Hamilton Place, & 138th Street, including expansion onto Hamilton Place to create a pedestrian plaza | Manhattan |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2016 |  | DDC
HWPLZ004M | HWPLZ004M | Y | Infrastructure | MANHATTAN & CITYWIDE | Pershing Sq Plaza/Streetscape (MED-622) | Roadway reconstruction, in conjunction with water main replacement, to create a pedestrian plaza on the west side of Park Avenue between 41st and 42nd Streets, adjacent to the viaduct. | Roadway reconstruction, in conjunction with water main replacement, to create a pedestrian plaza on the west side of Park Avenue between 41st and 42nd Streets, adjacent to the viaduct. | Manhattan |  | Transportation | Construction 25-50% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2010 | 2014 |  | DDC
HWPLZ004X | HWPLZ004X | Y | Infrastructure | BRONX & N. QUEENS | MORRISON AVENUE PLAZA, BX | RECONSTRUCTION OF MORRISON AVE PLAZA, BRONX | RECONSTRUCTION OF MORRISON AVE PLAZA, BRONX | Bronx |  | Transportation | Final Design | Street Reconstruction | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HWPLZ008M | HWPLZ008M | Y | Infrastructure | MANHATTAN & CITYWIDE | Forsyth Streetscape and Plaza Reconstruction | Plaza Construction along Forsyth Street from Canal Street to Division Street, and Creation of Plaza on Upper Portion of Manhattan Bridge, Manhattan | Plaza Construction along Forsyth Street from Canal Street to Division Street, and Creation of Plaza on Upper Portion of Manhattan Bridge, Manhattan | Manhattan |  | Transportation | Construction 50-75% | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2010 | 2014 |  | DDC
HWPLZ008Q | HWPLZ008Q | Y | Infrastructure | S. QUEENS | MYRTLE AVE-COOPER PLAZA | Myrtle/Cooper Plaza: 1. Myrtle Avenue from 70th Street to 71st Street. 2. Cooper Avenue from 70th Street to 71st Street. 3. 70th Street from Cooper Avenue to Myrtle Avenue. | Myrtle/Cooper Plaza: 1. Myrtle Avenue from 70th Street to 71st Street. 2. Cooper Avenue from 70th Street to 71st Street. 3. 70th Street from Cooper Avenue to Myrtle Avenue. | Queens |  | Transportation | Substantial Completion | Street Reconstruction | Standard | DDC Managed/Consultant | DDC Managed/Consultant | PIMS | FALSE |  |  | 2016 |  | DDC
HWPLZ009K | HWPLZ009K | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF NEW LOTS PLAZA | Reconstruction and expansion of New Lots Triangle LOCATION FROM TO =================================================== New Lots Avenue Ashford Stret Livonia Avenue Livonia Avenue Ashford Street New Lots Avenue Ashford Street Livonia Avenue New Lots Street | Reconstruction and expansion of New Lots Triangle | Brooklyn |  | Transportation | Construction 25-50% | Other |  | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2016 |  | DDC
HWPLZ009M | HWPLZ009M | Y | Infrastructure | MANHATTAN & CITYWIDE | Plaza De Las Americas Reconstruction (MED-621) | Street reconstruction of 175th Street between Broadway and Wadsworth Avenue, to create a pedestrian plaza with amenities including trees, plantings, lighting and benches. - Water Main Replacement in West 175th St. between Broadway and St. Nicholas Ave. - Broadway bet. West 175th & West 176th Streets; - Intersection of West 175th Street and Wadsworth Ave. Together with all work incidental thereto, Borough of Manhattan. | Street reconstruction of 175th Street between Broadway and Wadsworth Avenue, to create a pedestrian plaza with amenities including trees, plantings, lighting and benches. - Water Main Replacement in West 175th St. between Broadway and St. Nicholas Ave. - Broadway bet. West 175th & West 176th Streets; - Intersection of West 175th Street and Wadsworth Ave. Together with all work incidental thereto, Borough of Manhattan. | Manhattan |  | Transportation | Substantial Completion | Other | Mayoral In | Requirements TO | Requirements TO | PIMS | FALSE |  |  | 2014 |  | DDC
HWPLZ009Q | HWPLZ009Q | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF 71 AVENUE PLAZA | 71st Avenue Plaza: Midblock at Myrtle Avenue and 71 Avenue in Ridgewood, Queens. | The project will upgrade and expand the existing plaza along 71st Avenue and Myrtle Avenue. The Project will reconfigure traffic circulation, enhance pedestrian safety in the project area and improve a community public Space. | Queens |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirement Contract | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWPLZ010K | HWPLZ010K | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF FOWLER SQUARE | Reconstruct pedestrians plaza with resting/sitting area, walkways/sidewalks and landscaping (grass/planting spaces), drinking fountain. The scope of work also involves the reconstruction, re-configuration and re-grading of Fowler Square (bounded by Lafayette Ave, Fulton St and South Elliott Place) and S. Elliot Place, expanding the public space into Lafayette Ave by approximately 6 feet, plus10' width roadways (around the public plaza) including all related works (street lighting, traffic signals & marking, catch basin installation); build ADA ramps and sidewalk. | Reconstruction of Fowlr Square Plaza | Brooklyn |  | Transportation | Construction 0-25% | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2013 | 2016 |  | DDC
HWPLZ010M | HWPLZ010M | Y | Infrastructure | MANHATTAN & CITYWIDE | RECONSTRUCTION OF FLATIRON PLAZA, MN | RECONSTRUCTION OF FLATIRON PLAZA, MANHATTAN | RECONSTRUCTION OF FLATIRON PLAZA, MANHATTAN | Manhattan |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Critical | In-House |  | PIMS | FALSE |  | 2017 | 2019 |  | DDC
HWPLZ010Q | HWPLZ010Q | Y | Infrastructure | BRONX & N. QUEENS | RECONSTRUCTION OF CORONA PLAZA | Reconstruction of a pedestrian plaza to include new landscaping, infrastructure. Reconstruction and re-configuration of Corona Plaza (bounded by National Street and 104th Street), expanding the public space into Roosevelt Avenue, build ADA ramps and sidewalks. | Reconstruction of a pedestrian plaza to include new landscaping, infrastructure. Reconstruction and re-configuration of Corona Plaza (bounded by National Street and 104th Street), expanding the public space into Roosevelt Avenue, build ADA ramps and sidewalks. | Queens |  | Transportation | Construction 25-50% | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 |  |  | DDC
HWPLZ011K | HWPLZ011K | Y | Infrastructure | BROOKLYN | RECONSTRUCTION OF ZION TRIANGLE/BED804 | Reconstruction and expansion of Zion Triangle. Also, water main work in the project area. Zion Triangle lies at the intersection of Pitkin and East New York Avenues and Legion Street in Brownsville, Brooklyn. The scope includes: Reconstruct pedestrian plaza with resting/sitting area, walkways/sidewalks and landscaping (grass/planting spaces), drinking fountain, & refurbishing of war memorial. The scope of work also involves the reconstruction and re-configuration of Zion Triangle bounded by Pitkin Ave, East NY Ave, and Legion St, expanding the public space into East New York Ave by approximately 6 feet, plus 10' width roadways (around the public plaza) including all related works (street lighting, traffic signals & marking, catch basin installation); build ADA ramps and sidewalk. Legion Street will be closed to vehicular traffic and incorporate that street into the enhanced public space. WM - 1 1. East New York Avenue between Howard Avenue and Legion St. 2. Intersection of East New York Ave and Pikin Avenue. WM - 6 1. East New York Avenue between Howard Avenue and Legion St. BED804 Water Main work is cancelled and this work will now be done under BED776 and in conjunction with HWPLZ011K | Reconstruction and expansion of Zion Triangle. | Brooklyn |  | Transportation | Construction Procurement | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWPLZ012M | HWPLZ012M | Y | Infrastructure | MANHATTAN & CITYWIDE | BOGARDUS PLAZA | To make permanent improvements to the temporary plaza on Hudson Street from Reade Street to Chambers Street. The Bogardus Garden Park will also be incorporated into the plaza design. | To make permanent improvements to the temporary plaza on Hudson Street from Reade Street to Chambers Street. The Bogardus Garden Park will also be incorporated into the plaza design. | Manhattan |  | Transportation | Construction 0-25% | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWPLZ014Q | HWPLZ014Q | Y | Infrastructure | BRONX & N. QUEENS | 37TH ROAD PLAZA | Creating a permanent pedestrian plaza, on 37th Road from 73rd Street to 74th Street and from 37th Road to Roosevelt Avenue. | Creating a permanent pedestrian plaza, on 37th Road from 73rd Street to 74th Street and from 37th Road to Roosevelt Avenue. | Queens |  | Transportation | Construction 0-25% | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HWPLZ016K | HWPLZ016K | Y | Infrastructure | BROOKLYN | BROADWAY BEDFORD PLAZA, BROOKLYN | To construct a pedestrian plaza on Broadway at South 6th Street and Bedford Avenue in Brooklyn. This project will reconfigure traffic circulation, enhance pedestrian safety in the project area and create a new public space. Also, water main work in the project area. | Construction of Broadway-Bedford Plaza, Brooklyn | Brooklyn |  | Transportation | Construction 0-25% | New Construction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWPR16M | HWPR16M | Y | Infrastructure | MANHATTAN & CITYWIDE | Rehabilitation of Pedestrian Ramps, Manhattan | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in Manhattan. | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in Manhattan | Manhattan |  | Transportation | Construction 25-50% | Ped Ramps | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWPR17CW | HWPR17CW | Y | Infrastructure | MANHATTAN & CITYWIDE | Rehabilitation of Pedestrian Ramps, Citywide | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps Citywide. The list of final locations for this contract will be provided by CPM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps Citywide. The list of final locations for this contract will be provided by CPM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Citywide |  | Transportation | Construction 0-25% | Ped Ramps | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2017 | 2017 |  | DDC
HWPR17K | HWPR17K | Y | Infrastructure | BROOKLYN | Pedestrian Ramp Rehabilitation, Brooklyn | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of Brooklyn. The list of final locations for this contract will be provided by CPM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of Brooklyn. | Brooklyn |  | Transportation | Construction 0-25% | Ped Ramps | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWPR17M | HWPR17M | Y | Infrastructure | MANHATTAN & CITYWIDE | Pedestrian Ramp Rehabilitation, Manhattan | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of Manhattan. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of Manhattan. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Manhattan |  | Transportation | Construction 0-25% | Ped Ramps | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2017 | 2017 |  | DDC
HWPR17Q | HWPR17Q | Y | Infrastructure | S. QUEENS | Pedestrian Ramp Rehabilitation, Queens | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of Queens. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of Queens. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. This contract shall be established for one year with an option to renew for a second year. | Citywide |  | Transportation | Construction 0-25% | Ped Ramps | Critical | In-House | DDC Managed/Consultant | PIMS | FALSE |  |  | 2017 |  | DDC
HWPR17R | HWPR17R | Y | Infrastructure | STATEN ISLAND | Pedestrian Ramp Rehabilitation, Staten Island | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of Staten Island. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of Staten Island. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Staten Is. |  | Transportation | Construction 0-25% | Ped Ramps | Standard | Requirements TO |  | PIMS | FALSE |  | 2017 | 2017 |  | DDC
HWPR17X | HWPR17X | Y | Infrastructure | BRONX & N. QUEENS | Pedestrian Ramp Rehabilitation, Bronx | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of the Bronx. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Rehabilitation (repair and upgrade to ADA specifications) of existing pedestrian ramps in the borough of the Bronx. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. | Bronx |  | Transportation | Construction 0-25% | Ped Ramps | Critical | In-House |  | PIMS | FALSE |  |  |  |  | DDC
HWPR18K1 | HWPR18K1 | Y | Infrastructure | BROOKLYN | REHABILITATION OF PEDESTRIAN RAMPS | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Brooklyn. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. Any upgrades to the ramps must also rehabilitate the receiving corner where possible. Any deviation will require DOT's approval. This contract will be addressing simple pedestrian ramps upgrades. | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Brooklyn. | Brooklyn |  | Transportation | Compliance | Ped Ramps | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2018 | 2018 |  | DDC
HWPR18K2 | HWPR18K2 | Y | Infrastructure | BROOKLYN | REHABILITATION OF PEDESTRIAN RAMPS | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Brooklyn. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. Any upgrades to the ramps must also rehabilitate the receiving corner where possible. Any deviation will require DOT's approval. This contract will be addressing simple pedestrian ramps upgrades. | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Brooklyn. | Brooklyn |  | Transportation | Compliance | Ped Ramps | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2018 | 2018 |  | DDC
HWPR18M | HWPR18M | Y | Infrastructure | MANHATTAN & CITYWIDE | REHABILITATION OF PEDESTRIAN RAMPS | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Manhattan. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. Any upgrades to the ramps must also rehabilitate the receiving corner where possible. Any deviation will require DOT's approval. This contract will be addressing simple pedestrian ramps upgrades. | Rehabilitation of existing pedestrian ramps in the Borough of Manhattan | Manhattan |  | Transportation | Compliance | Ped Ramps | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2018 | 2018 |  | DDC
HWPR18Q1 | HWPR18Q1 | Y | Infrastructure | S. QUEENS | REHABILITATION OF PEDESTRIAN RAMPS | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Queens. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. Any upgrades to the ramps must also rehabilitate the receiving corner where possible. Any deviation will require DOT's approval. This contract will be addressing simple pedestrian ramps upgrades. | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Queens. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. Any upgrades to the ramps must also rehabilitate the receiving corner where possible. Any deviation will require DOT's approval. This contract will be addressing simple pedestrian ramps upgrades. | Queens |  | Transportation | Construction Procurement | Ped Ramps | Critical | In-House |  | PIMS | FALSE |  |  |  |  | DDC
HWPR18Q2 | HWPR18Q2 | Y | Infrastructure | S. QUEENS | REHABILITATION OF PEDESTRIAN RAMPS | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Queens. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. Any upgrades to the ramps must also rehabilitate the receiving corner where possible. Any deviation will require DOT's approval. This contract will be addressing simple pedestrian ramps upgrades. | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Queens. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. Any upgrades to the ramps must also rehabilitate the receiving corner where possible. Any deviation will require DOT's approval. This contract will be addressing simple pedestrian ramps upgrades. | Queens |  | Transportation | Construction Procurement | Ped Ramps | Critical | In-House |  | PIMS | FALSE |  |  | 2018 |  | DDC
HWPR18R | HWPR18R | Y | Infrastructure | STATEN ISLAND | REHABILITATION OF PEDESTRIAN RAMPS | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Staten Island. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. Any upgrades to the ramps must also rehabilitate the receiving corner where possible. Any deviation will require DOT's approval. This contract will be addressing simple pedestrian ramps upgrades. | Rehabilitation of Pedestrian Ramps, Borough of Staten Island | Staten Is. |  | Transportation | Compliance | Ped Ramps | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2018 | 2018 |  | DDC
HWPR18X | HWPR18X | Y | Infrastructure | BRONX & N. QUEENS | REHABILITATION OF PEDESTRIAN RAMPS | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Bronx. The list of final locations for this contract will be provided by SIM at a later date. The pedestrian ramp repairs will follow resurfacing schedules. Any upgrades to the ramps must also rehabilitate the receiving corner where possible. Any deviation will require DOT's approval. This contract will be addressing simple pedestrian ramps upgrades. | Rehabilitation (repair and upgrade to ADA specifications to the maximum extent feasible) of existing pedestrian ramps in the borough of Bronx. | Bronx |  | Transportation | Final Design | Ped Ramps | Critical |  | Individual Contract(s) | PIMS | FALSE |  |  | 2018 |  | DDC
HWPS199 | HWPS199 | Y | Infrastructure | BRONX & N. QUEENS | SAFETY IMPROVEMENTS - PS199, QNS | SAFETY IMPROVEMENTS - PS199, QUEENS | SAFETY IMPROVEMENTS - PS199, QUEENS | Queens |  | Transportation | Construction 50-75% | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWQ100FJM | HWQ100FJM | Y | Infrastructure | BRONX & N. QUEENS | FLUSHING - JAMAICA (MAIN ST) SBS | FLUSHING - JAMAICA (MAIN ST) SBS | Main Street (Flushing-Jamaica-Bronx) Select Bus Service | Queens |  | Transportation | Final Design | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2016 | 2018 |  | DDC
HWQ100SBA | HWQ100SBA | Y | Infrastructure | S. QUEENS | WOODHAVEN BLVD SBS, SEGMENT A | The Woodhaven Boulevard Select Bus Service (SBS) will follow the Q52/Q53 Limited bus routes, connecting the Woodside neighborhood to the Rockaway Peninsula in Central Queens. This project is a top priority for the City and major goals are to increase the speed, reliability and customer satisfaction of bus service. SBS projects not only improve bus efficiency, but also strive to improve intermodal connections and pedestrian safety along adjacent streets. | The Woodhaven Boulevard Select Bus Service (SBS) will follow the Q52/Q53 Limited bus routes, connecting the Woodside neighborhood to the Rockaway Peninsula in Central Queens. Segment A of this project will follow the Q52/Q53 along Cross Bay Boulevard between 107th Avenue and West 5th Road. The Segment A portion will improve poor curb and sidewalk conditions, build four (4) new bus bulbs, 12 new bus pads, three (3) median extensions, two (2) pedestrian safety islands and 19 curb extensions meant to improve both bus efficiency and pedestrian safety and access. This project is a top priority for the City and major goals are to increase the speed, reliability and customer satisfaction of bus service. SBS projects not only improve bus efficiency, but also strive to improve intermodal connections and pedestrian safety along adjacent streets. | Queens |  | Transportation | Design Development | Street Reconstruction | Critical | DDC Managed/Consultant |  | PIMS | FALSE |  |  |  |  | DDC
HWQ100SBS | HWQ100SBS | Y | Infrastructure | S. QUEENS | WOODHAVEN BLVD SBS, QNS | WOODHAVEN BLVD SBS, QNS | Reconstrction for implementation of SBS service on on Woodhaven and Cross Bay Boulevards | Queens |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HWQ1079 | HWQ1079 | Y | Infrastructure | S. QUEENS | FAR ROCKAWAY IMPROVEMENTS BUSINESS DISTRICT, QNS | FAR ROCKAWAY IMPROVEMENTS BUSINESS DISTRICT, QNS | For the reconstruction os Storm and Sanitary Sewer in Mott Avenue, Queens | Queens |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HWQ1126B | HWQ1126B | Y | Infrastructure | S. QUEENS | RECONS BEACH CHANNEL DR & BEACH 54 ST, ETC | Project limit/locations: Reconstruction of Streets, sanitary sewers, storm sewers and Water main in Arverne/Edgemere Hope VI, Neighborhood Revitalization Area(NYCHA) Sreets includes: 1. Beach Channel Dr. from Beach 62 St. to Beach 49 St. 2. Beach 54 St. from Almeda Ave. to Rockaway Beach Blvd. | Street reconstruction to include new sewers and water mains. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | DDC Managed | PIMS | FALSE
HWQ1126B | SEQ002527 | Y | Infrastructure | S. QUEENS | RECONS BEACH CHANNEL DR & BEACH 54 ST, ETC | Project limit/locations: Reconstruction of Streets, sanitary sewers, storm sewers and Water main in Arverne/Edgemere Hope VI, Neighborhood Revitalization Area(NYCHA) Sreets includes: 1. Beach Channel Dr. from Beach 62 St. to Beach 49 St. 2. Beach 54 St. from Almeda Ave. to Rockaway Beach Blvd. | Street reconstruction to include new sewers and water mains. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | DDC Managed | PIMS | FALSE
HWQ1126B | SEQ002583 | Y | Infrastructure | S. QUEENS | RECONS BEACH CHANNEL DR & BEACH 54 ST, ETC | Project limit/locations: Reconstruction of Streets, sanitary sewers, storm sewers and Water main in Arverne/Edgemere Hope VI, Neighborhood Revitalization Area(NYCHA) Sreets includes: 1. Beach Channel Dr. from Beach 62 St. to Beach 49 St. 2. Beach 54 St. from Almeda Ave. to Rockaway Beach Blvd. | Street reconstruction to include new sewers and water mains. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | DDC Managed | PIMS | FALSE
HWQ1126B | SEQ200386 | Y | Infrastructure | S. QUEENS | RECONS BEACH CHANNEL DR & BEACH 54 ST, ETC | Project limit/locations: Reconstruction of Streets, sanitary sewers, storm sewers and Water main in Arverne/Edgemere Hope VI, Neighborhood Revitalization Area(NYCHA) Sreets includes: 1. Beach Channel Dr. from Beach 62 St. to Beach 49 St. 2. Beach 54 St. from Almeda Ave. to Rockaway Beach Blvd. | Street reconstruction to include new sewers and water mains. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | DDC Managed | PIMS | FALSE
HWQ1126B | SEQ200426 | Y | Infrastructure | S. QUEENS | RECONS BEACH CHANNEL DR & BEACH 54 ST, ETC | Project limit/locations: Reconstruction of Streets, sanitary sewers, storm sewers and Water main in Arverne/Edgemere Hope VI, Neighborhood Revitalization Area(NYCHA) Sreets includes: 1. Beach Channel Dr. from Beach 62 St. to Beach 49 St. 2. Beach 54 St. from Almeda Ave. to Rockaway Beach Blvd. | Street reconstruction to include new sewers and water mains. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | DDC Managed | PIMS | FALSE
HWQ1126C | HWQ1126C | Y | Infrastructure | S. QUEENS | RECONS ARVERNE BLVD/RCKWY BEACH BLVD, ETC, ARVERNE | Project limit/locations Reconstruction of Streets, sanitary sewers, storm sewers and Water main in Arverne/Edgemere Hope VI, Neighborhood Revitalization Area(NYCHA) Streets includes: 1. Rockaway Beach Blvd. Between Beach 49 St. & Beach 54 St. * 2. Arverne Blvd. Between Beach 54 St. & Beach 59 St 3. Beach 56 St. between Beach Channel Dr. and Arverne Blvd. 4. Beach 57 St. Between Beach Channel Dr. and Arverne Blvd. | Reconstruct streets, sewers and water mains. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | DDC Managed | PIMS | FALSE
HWQ1126C | QED-974 | Y | Infrastructure | S. QUEENS | RECONS ARVERNE BLVD/RCKWY BEACH BLVD, ETC, ARVERNE | Project limit/locations Reconstruction of Streets, sanitary sewers, storm sewers and Water main in Arverne/Edgemere Hope VI, Neighborhood Revitalization Area(NYCHA) Streets includes: 1. Rockaway Beach Blvd. Between Beach 49 St. & Beach 54 St. * 2. Arverne Blvd. Between Beach 54 St. & Beach 59 St 3. Beach 56 St. between Beach Channel Dr. and Arverne Blvd. 4. Beach 57 St. Between Beach Channel Dr. and Arverne Blvd. | Reconstruct streets, sewers and water mains. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | DDC Managed | PIMS | FALSE
HWQ1182A | HWQ1182A | Y | Infrastructure | S. QUEENS | CONSTR. OF BULKHEADS AT BROAD CHANNEL AREA, PH I | 1. West 11th Rd. from Cross Bay Blvd. to Dead end (water side) 2. West 12th Rd. from Cross Bay Blvd. to Dead end (water side) 3. West 13th Rd. from Cross Bay Blvd. to Dead end (water side) 4. Cross Bay Blvd. from W13th Road(200th Ave.) to W11th Road(198th Ave.) | 1. West 11th Rd. from Cross Bay Blvd. to Dead end (water side) 2. West 12th Rd. from Cross Bay Blvd. to Dead end (water side) 3. West 13th Rd. from Cross Bay Blvd. to Dead end (water side) 4. Cross Bay Blvd. from W13th Road(200th Ave.) to W11th Road(198th Ave.) | Queens |  | Transportation | Construction 75%-Subst. | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HWQ1182B | HWQ1182B | Y | Infrastructure | S. QUEENS | BROAD CHANNEL BULKHEADS - PH II | BROAD CHANNEL STREET AND BULKHEADS RECONSTRUCTION - PHASE 2 | West 14th Rd. from Cross Bay Blvd. to Dead end (water side) West 15th Rd. from Cross Bay Blvd. to Dead end (water side) West 16th Rd. from Cross Bay Blvd. to Dead end (water side) West 17th Rd. from Cross Bay Blvd. to Dead end (water side) West 18th Rd. from Cross Bay Blvd. to Dead end (water side) West 19th Rd. from Cross Bay Blvd. to Dead end (water side) | Queens |  | Transportation | Design Development | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWQ1184A | HWQ1184A | Y | Infrastructure | S. QUEENS | JAMES COURT ROADWAY AND BULKHEAD | Reconstruction of the bulkhead on the west end of James Court at Hawtree Basin and the roadway and sidewalks from the bulkhead to 104 Street. | Reconstruction of the bulkhead on the west end of James Court at Hawtree Basin and the roadway and sidewalks from the bulkhead to 104 Street. | Queens |  | Transportation | Final Design | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HWQ1187 | HWQ1187 | Y | Infrastructure | S. QUEENS | WESTBOURNE - DUNBAR ROADWAYS/BULKHEADS, QNS | RECONSTRUCTION OF WESTBOURNE - DUNBAR ROADWAYS/BULKHEADS, QUEENS | PRELIMINARY AND FINAL DESIGN SERVICES FOR RECONSTRUCTION OF WESTBOURNE NORTON DRIVE. BOROUGH OF QUEENS | Queens |  | Transportation | Design Development | Street Reconstruction | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HWQ1188 | HWQ1188 | Y | Infrastructure | BRONX & N. QUEENS | COLLEGE POINT PERMEABLE PAVEMENT, QUEENS This pro | COLLEGE POINT PERMEABLE PAVEMENT, QUEENS This project will implement permeable pavement within four street segments in the Flushing Bay Priority Watershed in College Point, Queens in the areas bounded by 14th Avenue to the north, 23rd Avenue to the south, 126th Street to the east and 116th Street to the west. This area has high levels of combined sewer overflows and pollutants and the project will be used as a case study to evaluate different design and construction methods to determine the best approach to reduce storm water runoff volume and velocity while improving water quality. | COLLEGE POINT PERMEABLE PAVEMENT, QUEENS This project will implement permeable pavement within four street segments in the Flushing Bay Priority Watershed in College Point, Queens in the areas bounded by 14th Avenue to the north, 23rd Avenue to the south, 126th Street to the east and 116th Street to the west. This area has high levels of combined sewer overflows and pollutants and the project will be used as a case study to evaluate different design and construction methods to determine the best approach to reduce storm water runoff volume and velocity while improving water quality. | Queens |  | Transportation | Cancelled Project | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWQ1190 | HWQ1190 | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF QUEENS BLVD, QNS | RECONSTRUCTION OF QUEENS BLVD - PHASE 1, QUEENS | RECONSTRUCTION OF QUEENS BLVD - PHASE 1, QUEENS | Queens |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2016 | 2018 |  | DDC
HWQ1190A | HWQ1190A | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF QUEENS BLVD - PHASE 1 | Vision Zero - Queens Boulevard - Segment 1: Roosevelt Avenue to 73rd Street. Variety of safety and streetscape improvements including partial street reconstruction and resurfacing to address roadway conditions | Vision Zero - Queens Boulevard - Segment 1: Roosevelt Avenue to 73rd Street. Variety of safety and streetscape improvements including partial street reconstruction and resurfacing to address roadway conditions | Queens |  | Transportation | Design Development | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2016 | 2019 |  | DDC
HWQ1190B | HWQ1190B | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF QUEENS BLVD - PHASE 2 | Vision Zero - Queens Boulevard - Segment 2: 73rd Street to Eliot Avenue. Variety of safety and streetscape improvements including partial street reconstruction and resurfacing to address roadway conditions | Vision Zero - Queens Boulevard - Segment 2: 73rd Street to Eliot Avenue. Variety of safety and streetscape improvements including partial street reconstruction and resurfacing to address roadway conditions | Queens |  | Transportation | Design Development | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2017 | 2020 |  | DDC
HWQ1190C | HWQ1190C | Y | Infrastructure | S. QUEENS | RECON OF QUEENS BLVD PHASE 3 | Vision Zero - Queens Boulevard - Segment 3: Eliot Avenue to Yellowstone Boulevard. Variety of safety and streetscape improvements including partial street reconstruction and resurfacing to address roadway conditions | Vision Zero - Queens Boulevard - Segment 3: Eliot Avenue to Yellowstone Boulevard. Variety of safety and streetscape improvements including partial street reconstruction and resurfacing to address roadway conditions |  |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | Requirements TO |  | PIMS | FALSE |  |  |  | 2017-11-28 07:00:21.1800000 +00:00
HWQ1197 | HWQ1197 | Y | Infrastructure | BRONX & N. QUEENS | Pre-Scoping-College Point Subsidence, Queens | Pre-Scoping services for College Point Subsidence, Queens | Pre-Scoping services for College Point Subsidence, Queens |  |  | Transportation | Scope Development | Feasibility Study | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  | 2017-09-09 15:33:14.4070000 +00:00
HWQ121B3 | HWQ121B3 | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200562) | Project Limit/ location stage1: Reconstruction of the following streets: - 115 Rd. b/n 157th Street and Bedell Street; - 116 Ave. b/n 157th Street and Bedell Street; - Meyer Ave b/n 157th Street and Bedell Street; - 158 St. b/n 116th Ave. and DE N/O 111 th Ave.; - 159 St b/n 116th Ave. and 111th Ave.; - Beddell St. b/n 116th Ave. and Meyer Ave. - SEQ200332 Project Limit/ location stage2: - 113 Ave. b/n Sutphin Blvd. and 155th St.; - 122th Ave. b/n Sutphin Blvd. and 155th St.; - 111th Rd. b/n Sutphin Blvd. and 155th St.; 111th Ave. b/n Sutphin Blvd. and 155th St.; - 110 Rd. b/n Sutphin Blvd. and 155th St.; - 109th Rd. b/n Sutphin Blvd. and 155th St.; - 109th Drive b/n Sutphin Blvd. and 155th St.; - 109 Ave. b/n Sutphin Blvd. and 155th St.; - 153rd Street b/n 112th Ave. and DE N/O 109 Ave.; - 155th Street b/n Linden Blvd. and 114th Rd. | otal reconstruction of two street grids in South Jamaica approximately bounded by Sutphin Boulevard, 109th Avenue, 155th Street and Linden Boulevard, and by 157th Street, 111th Avenue, Beddell Street and 116th Avenue. | Queens |  | Transportation | Final Design | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | TRUE |  | 2016 | 2019 |  | DDC
HWQ121B4 | HWQ121B4 | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200436) | Project Limit/ locations: Reconstruction of the following streets: -118th Ave. from Long Street to Lakeview Blvd. East - 122 Ave. from Lakeview Lane to Lakeview Blvd. East - Lakeview Blvd. East from 118th Ave. to 122nd Ave. - Lakeview Lane from 122nd Ave. to Baisley Blvd. Storm Sewer (Extension.) with BMP: - 164 Street from 119th Ave to 120th e - 119 Ave. from Long Street to 164th Street - 122 Ave. from Lakeview Lane to Lakeview Blvd. East - Lakeview Blvd. East from 118th Ave. to 122nd Ave. - Lakeview Lane from 122nd Ave. to Baisley Blvd. - 119th Rd. between 180th St. and 178th Pl. - canselled Sanitary Sewer (Replacement) - Lakeview Blvd. East from 118th Rd to 119 Rd. - 122 Ave. from Lakeview Lane to Lakeview Blvd. East - 119th Rd. between 180th St. and 178th Pl. - - 119 Ave. from Long Street to Guy Brewer Blvd. - - 164 Street from 119th Ave to 120th Ave Water Main Work: - 118 Ave. between Lakeview Blvd. East and Long St. - Lakeview Blvd. East from 118th Ave. to 122nd Ave. | Street reconstruction with sewer and water main work--multiple locations including Lakeview Boulevard East and portions of 118th, 119th and 122nd Avenues; Lakeview Lane; 164th Street and 119th Road | Queens |  | Transportation | Construction 75%-Subst. | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | TRUE |  |  | 2016 |  | DDC
HWQ121B4 | SEQ200436 | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF SOUTH JAMAICA AREA (SEQ200436) | Project Limit/ locations: Reconstruction of the following streets: -118th Ave. from Long Street to Lakeview Blvd. East - 122 Ave. from Lakeview Lane to Lakeview Blvd. East - Lakeview Blvd. East from 118th Ave. to 122nd Ave. - Lakeview Lane from 122nd Ave. to Baisley Blvd. Storm Sewer (Extension.) with BMP: - 164 Street from 119th Ave to 120th e - 119 Ave. from Long Street to 164th Street - 122 Ave. from Lakeview Lane to Lakeview Blvd. East - Lakeview Blvd. East from 118th Ave. to 122nd Ave. - Lakeview Lane from 122nd Ave. to Baisley Blvd. - 119th Rd. between 180th St. and 178th Pl. - canselled Sanitary Sewer (Replacement) - Lakeview Blvd. East from 118th Rd to 119 Rd. - 122 Ave. from Lakeview Lane to Lakeview Blvd. East - 119th Rd. between 180th St. and 178th Pl. - - 119 Ave. from Long Street to Guy Brewer Blvd. - - 164 Street from 119th Ave to 120th Ave Water Main Work: - 118 Ave. between Lakeview Blvd. East and Long St. - Lakeview Blvd. East from 118th Ave. to 122nd Ave. | Street reconstruction with sewer and water main work--multiple locations including Lakeview Boulevard East and portions of 118th, 119th and 122nd Avenues; Lakeview Lane; 164th Street and 119th Road | Queens |  | Transportation | Construction 75%-Subst. | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | TRUE |  |  | 2016 |  | DDC
HWQ1682 | HWQ1682 | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF SHORE FRONT PKWY | Project Limit/ locations Improvements/ Reconsruction of Shore Front Parkway from Beach 73 to Beach 108 Streets. | Improvements/Reconstruction of Shore Front Parkway from Beach 73 to Beach 108 Streets. | Queens |  | Transportation | On-Hold | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | FALSE |  |  | 2022 |  | DDC
HWQ213C | HWQ213C | Y | Infrastructure | BRONX & N. QUEENS | RECON OF MAIN ST WITH WIDENED SIDEWALK X772.66 | Reconstruction of Main Street with wider sidewalks from 38th Avenue to LIRR Port Washington Line in downtown Flushing, enhancing the movement of pedestrians together with the relocation of bus stops and change in lane assignment and traffic controls. Project limit. Main Street 38 Avenue 39 Avenue Main Street 39 Avenue Roosevelt Avenue Main Street Roosevelt Avenue 40 Road Main Street 40 Road 41 Avenue Also include combined sewer in Main Street between 40 Road and 41 Avenue etc. | Reconstruction of Main Street with wider sidewalks from 38th Avenue to LIRR Port Washington Line in downtown Flushing, | Queens |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Standard Consultant | PIMS | FALSE |  | 2013 | 2016 |  | DDC
HWQ233 | HWQ233 | Y | Infrastructure | BRONX & N. QUEENS | RECONSTRUCTION OF BARNETT AVE | Reconstruction of Barnett Avenue from 48th Street to Woodside Avenue. DEP Scope under ID SEQ002689: Combined Sewer: Barnett Avenue from 48th Street to 50th Street. Water Main: Barnett Avenue from 48th Street to Woodside Avenue. | Reconstruction of Barnett Avenue from 48th Street to Woodside Avenue. DEP Scope under ID SEQ002689: Combined Sewer: Barnett Avenue from 48th Street to 50th Street. Water Main: Barnett Avenue from 48th Street to Woodside Avenue. | Queens |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | DDC Managed/Consultant | PIMS | FALSE |  |  |  |  | DDC
HWQ242CW | HWQ242CW | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF FRANCIS LEWIS BLVD. | Project limit/locations: Reconstruct Francis Lewis Blvd. from Springfield Blvd to Merrick Blvd., Laurelton/Cambria Heights. The Blvd. is to be redesigned with a new 20' landscaped median for most of the length. | Reconstruct roadway; new landscaped median. | Queens |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | FALSE |  |  | 2022 |  | DDC
HWQ274F1 | HWQ274F1 | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF STREETS IN THE ROSEDALE AREA | DOT Project Limit / Locations (Phase I): Reconstruction of Francis Lewis Blvd from 254 Street to 257 Street Hook Creek Blvd from 253 Street to 257 Street 139 Ave from 254 Street to Hook Creek Blvd 255, 256, & 257 Streets from Francis Lewis Blvd to the Nassau County Border. NOTE:WM 8" on 259th Street b/n 148th Avenue and 148th Drive was done in 2005 under project HWQ274F-R. | Reconstruction of Francis Lewis Blvd, Hook Creek Blvd,etc. (DOT scope),Rosedale area. | Queens |  | Transportation | Final Design | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  | 2015 | 2018 |  | DDC
HWQ274F1 | SEQ002606 | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF STREETS IN THE ROSEDALE AREA | DOT Project Limit / Locations (Phase I): Reconstruction of Francis Lewis Blvd from 254 Street to 257 Street Hook Creek Blvd from 253 Street to 257 Street 139 Ave from 254 Street to Hook Creek Blvd 255, 256, & 257 Streets from Francis Lewis Blvd to the Nassau County Border. NOTE:WM 8" on 259th Street b/n 148th Avenue and 148th Drive was done in 2005 under project HWQ274F-R. | Reconstruction of Francis Lewis Blvd, Hook Creek Blvd,etc. (DOT scope),Rosedale area. | Queens |  | Transportation | Final Design | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  | 2015 | 2018 |  | DDC
HWQ274F1 | SEQ200446 | Y | Infrastructure | S. QUEENS | RECONSTRUCTION OF STREETS IN THE ROSEDALE AREA | DOT Project Limit / Locations (Phase I): Reconstruction of Francis Lewis Blvd from 254 Street to 257 Street Hook Creek Blvd from 253 Street to 257 Street 139 Ave from 254 Street to Hook Creek Blvd 255, 256, & 257 Streets from Francis Lewis Blvd to the Nassau County Border. NOTE:WM 8" on 259th Street b/n 148th Avenue and 148th Drive was done in 2005 under project HWQ274F-R. | Reconstruction of Francis Lewis Blvd, Hook Creek Blvd,etc. (DOT scope),Rosedale area. | Queens |  | Transportation | Final Design | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  | 2015 | 2018 |  | DDC
HWQ411B | HWQ411B | Y | Infrastructure | S. QUEENS | Albert Road Area - Ozone Park Streets (SEQ002568) | Project Limit / locations: Albert Road Area / Reconstruction 1. 94th Street from Albert Road to Linden Boulevard. 2. 95th Street from 150th Road to Albert Road. 3. 95th Street from Linden Boulevard to Albert Road. 4. 96th Place from Linden Boulevard to Dead-End (South of 149th Avenue). 5. 96th Street from Albert Road to Linden Boulevard. 6. 97th Street from 149th Avenue to Linden Boulevard. 7. 99th Place from Albert Road to Hawtree Street. 8. 135 Road from 97th Street to Hawtree Street. 9. 135th Drive from Centerville Street to Dead-End (East of Centerville Street). 10. 149th Avenue from Cross Bay Boulevard to Centerville Street. 11. 150th Road from 95th Street to Centerville Street. 12. Albert Road from Cross-Bay Boulevard to North Conduit Avenue. 13. Bristol Avenue from Centerville Street to Dead-End (East of Centerville Street). 14. Bristol Avenue from Dead-End (East of Centerville Street) to Hawtree Street. 15. Centerville Street from North Conduit Avenue to Pitkin Avenue. 16. Cohancy Street from North Conduit Avenue to Hawtree Street. 17. Eckford Avenue from Centerville Street to Hawtree Street. 18. Hawtree Street from Cohancy Street to Bristol Avenue. 19. Hawtree Street from Pitkin Avenue to Linden Blvd. 20. Huron Street from Albert Road to Ecford Avenue. 21. Linden Boulevard from Cross-Bay Boulevard to Hawtree Street. 22. North Conduit Avenue from Raliegh Street to Tahoe Street. 23. Pitkin Avenue from Cross-Bay Boulevard to Centerville Street. 24. Pitkin Avenue from intersection of Hawtree Street to Dead-End – East of Hawtree Street (Side Entrance Aqueduct). 25. Raleigh Street from Albert Road to Ecford Avenue. 26. Raleigh Street from North Conduit Avenue to (Dead-End) Albert Road. 27. Tahoe Street from North Conduit Avenue to Albert Road. 28. Tahoe Street from Albert Road to Ecford Avenue. | Street reconstruction in the area bounded by Linden Boulevard on the north, North Conduit Avenue on the south, Cross Bay Boulevard to the west and the rail road right-of-way along Aqueduct Race Track to the east. | Queens |  | Transportation | Construction 25-50% | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  | 2014 |  | DDC
HWQ411B | SEQ002568 | Y | Infrastructure | S. QUEENS | Albert Road Area - Ozone Park Streets (SEQ002568) | Project Limit / locations: Albert Road Area / Reconstruction 1. 94th Street from Albert Road to Linden Boulevard. 2. 95th Street from 150th Road to Albert Road. 3. 95th Street from Linden Boulevard to Albert Road. 4. 96th Place from Linden Boulevard to Dead-End (South of 149th Avenue). 5. 96th Street from Albert Road to Linden Boulevard. 6. 97th Street from 149th Avenue to Linden Boulevard. 7. 99th Place from Albert Road to Hawtree Street. 8. 135 Road from 97th Street to Hawtree Street. 9. 135th Drive from Centerville Street to Dead-End (East of Centerville Street). 10. 149th Avenue from Cross Bay Boulevard to Centerville Street. 11. 150th Road from 95th Street to Centerville Street. 12. Albert Road from Cross-Bay Boulevard to North Conduit Avenue. 13. Bristol Avenue from Centerville Street to Dead-End (East of Centerville Street). 14. Bristol Avenue from Dead-End (East of Centerville Street) to Hawtree Street. 15. Centerville Street from North Conduit Avenue to Pitkin Avenue. 16. Cohancy Street from North Conduit Avenue to Hawtree Street. 17. Eckford Avenue from Centerville Street to Hawtree Street. 18. Hawtree Street from Cohancy Street to Bristol Avenue. 19. Hawtree Street from Pitkin Avenue to Linden Blvd. 20. Huron Street from Albert Road to Ecford Avenue. 21. Linden Boulevard from Cross-Bay Boulevard to Hawtree Street. 22. North Conduit Avenue from Raliegh Street to Tahoe Street. 23. Pitkin Avenue from Cross-Bay Boulevard to Centerville Street. 24. Pitkin Avenue from intersection of Hawtree Street to Dead-End – East of Hawtree Street (Side Entrance Aqueduct). 25. Raleigh Street from Albert Road to Ecford Avenue. 26. Raleigh Street from North Conduit Avenue to (Dead-End) Albert Road. 27. Tahoe Street from North Conduit Avenue to Albert Road. 28. Tahoe Street from Albert Road to Ecford Avenue. | Street reconstruction in the area bounded by Linden Boulevard on the north, North Conduit Avenue on the south, Cross Bay Boulevard to the west and the rail road right-of-way along Aqueduct Race Track to the east. | Queens |  | Transportation | Construction 25-50% | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  | 2014 |  | DDC
HWQ631B2 | HWQ631B2 | Y | Infrastructure | S. Queens | RECONSTRUCTION OF THURSBY AVE AND AREA (PHASE B2) | Project Limit/locations: Storm & Sanitary Sewers in: 1. B. 69th St. between Bayfield Ave. & Almeda Ave.; 2. B. 72 St. between Bayfield Ave. & Thursby Ave; 3. Barbadoes Drive between Hillmeyer Ave. & Burchell Ave.; 4. Bayfield Ave. between B. 69th St. & B. 72nd St.; 5. Decosta Ave. between B. 69 St. & B. 72nd St.; 6. Hillmeyer Ave. between B.69 St. & DE near Jamaica Bay; 7. Almeda Ave. between B.69th St. & outlet in Jamaica Bay; 8. Burchell Ave. between Barbadoes Drive & B.69th St.; 9. Elizabeth Ave. between B. 69th St. & U.S. Bulkhead Line; 10. Thursby Ave. between B. 69th St. & U.S. Bulkhead Line; Sanitary Sewers in: 1. B. 69th St. between Bayfield Ave. & Thursby Ave.; 2. B. 72 St. between Bayfield Ave. & Thursby Ave; 3. Barbadoes Drive between Hillmeyer Ave. & Burchell Ave.; 4. Bayfield Ave. between B. 69th St. & B. 72nd St.; 5. Decosta Ave. between B. 69 St. & B. 72nd St.; 6. Hillmeyer Ave. between B.69 St. & DE near Jamaica Bay; 7. Almeda Ave. between B.69th St. & outlet in Jamaica Bay; 8. Burchell Ave. between Barbadoes Drive & B.69th St.; 9. Elizabeth Ave. between B. 69th St. & U.S. Bulkhead Line; 10. Thursby Ave. between B. 69th St. & U.S. Bulkhead Line; Water Main in: 1. Bayfield Ave between B. 69th St. & DE; 2. Hillmeyer Ave. between B.72 St. & DE; 3. Almeda Ave. between Barbadoes Drive & DE; 4. Almeda Ave. between B. 72nd St. & B. 69th St.; 5. Burchell Ave. between Barbadoes Drive & B. 69th Street; 6. Elizabeth Ave. between DE & B. 69th St.; 7. Barbadoes Dr. between Hillmeyer Ave. & Thursby Ave.; 8. B. 72 St.between Almeda Ave. & Thursby Ave. | Reconstruct roadway, replace sanitary sewers and water main, install new storm sewers: Rockaway Peninsula area bounded by Bayfield Avenue to the north, Thursby Avenue to the south, Beach 69th Street to the east and Jamaica Bay to the west. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE
HWQF027D | HWQF027C | Y | Public Buildings | TRANSPORTATION | Harper Street Yard Full Capture Exhaust | Iinstallation of a full capture exhaust system | Installation of a full capture exhaust system at Harper Street Yard | Queens |  | Transportation | Acceptance/Final Completion | Upgrade | Standard | DDC Managed | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HWQF030 | HWQF030 | Y | Public Buildings | TRANSPORTATION | Harper Street Roof & Wastewater Conveyances | 1. Install of a new roof including the replacement of existing skylights. Replace or upgrade sub roof as necessary. New roof should be ready to easily accept solar panels. 2. Design and install a new waste water conveyance system that will transfer waste into a collection tank or tanks. The design should also allow for future connection to the City's sewer system when available. | CP request will be send to our Budget personnel for processing. We are requesting OMB to approve for the Pre-preliminary Design phase is $187,787 | Queens |  | Transportation | Pre-Design/PrgDevelopment | Renovation | Standard | DDC Managed |  | PIMS | FALSE |  |  |  |  | DDC
HWR00504 | HWR00504 | Y | Infrastructure | STATEN ISLAND | INTERSECTION IMPROVEMENT VICTORY BLVD & CLOVE ROAD | Roadway improvement at the Victory Blvd and Clove Road intersection. Borough of Staten Island | Roadway improvement at the Victory Blvd and Clove Road intersection. Borough of Staten Island | Staten Is. |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | In-House/Consultant | DDC Managed/Consultant | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWR00505 | HWR00505 | Y | Infrastructure | STATEN ISLAND | VICTORY BLVD & MANOR ROAD INTERSECTION IMPROVEMENT | Roadway improvement at the Victory Boulevard and Manor Road Intersection, Staten Island | Roadway improvement at the Victory Boulevard and Manor Road Intersection, Staten Island | Staten Is. |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | In-House/Consultant | DDC Managed/Consultant | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWQ631B2 | SE-789B2 | Y | Infrastructure | S. Queens | RECONSTRUCTION OF THURSBY AVE AND AREA (PHASE B2) | Project Limit/locations: Storm & Sanitary Sewers in: 1. B. 69th St. between Bayfield Ave. & Almeda Ave.; 2. B. 72 St. between Bayfield Ave. & Thursby Ave; 3. Barbadoes Drive between Hillmeyer Ave. & Burchell Ave.; 4. Bayfield Ave. between B. 69th St. & B. 72nd St.; 5. Decosta Ave. between B. 69 St. & B. 72nd St.; 6. Hillmeyer Ave. between B.69 St. & DE near Jamaica Bay; 7. Almeda Ave. between B.69th St. & outlet in Jamaica Bay; 8. Burchell Ave. between Barbadoes Drive & B.69th St.; 9. Elizabeth Ave. between B. 69th St. & U.S. Bulkhead Line; 10. Thursby Ave. between B. 69th St. & U.S. Bulkhead Line; Sanitary Sewers in: 1. B. 69th St. between Bayfield Ave. & Thursby Ave.; 2. B. 72 St. between Bayfield Ave. & Thursby Ave; 3. Barbadoes Drive between Hillmeyer Ave. & Burchell Ave.; 4. Bayfield Ave. between B. 69th St. & B. 72nd St.; 5. Decosta Ave. between B. 69 St. & B. 72nd St.; 6. Hillmeyer Ave. between B.69 St. & DE near Jamaica Bay; 7. Almeda Ave. between B.69th St. & outlet in Jamaica Bay; 8. Burchell Ave. between Barbadoes Drive & B.69th St.; 9. Elizabeth Ave. between B. 69th St. & U.S. Bulkhead Line; 10. Thursby Ave. between B. 69th St. & U.S. Bulkhead Line; Water Main in: 1. Bayfield Ave between B. 69th St. & DE; 2. Hillmeyer Ave. between B.72 St. & DE; 3. Almeda Ave. between Barbadoes Drive & DE; 4. Almeda Ave. between B. 72nd St. & B. 69th St.; 5. Burchell Ave. between Barbadoes Drive & B. 69th Street; 6. Elizabeth Ave. between DE & B. 69th St.; 7. Barbadoes Dr. between Hillmeyer Ave. & Thursby Ave.; 8. B. 72 St.between Almeda Ave. & Thursby Ave. | Reconstruct roadway, replace sanitary sewers and water main, install new storm sewers: Rockaway Peninsula area bounded by Bayfield Avenue to the north, Thursby Avenue to the south, Beach 69th Street to the east and Jamaica Bay to the west. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE
HWR00508 | HWR00508 | Y | Infrastructure | STATEN ISLAND | AMBOY ROAD IMPROVEMENTS AT ELTINGVILLE CORRIDOR | Roadway widening and related work on Amboy Road between Richmond Ave. and Armstrong Ave., Borough of Staten Island | Roadway widening and related work on Amboy Road between Richmond Ave. and Armstrong Ave., Borough of Staten Island | Staten Is. |  | Transportation | Design Development | Street Reconstruction | Standard | In-House/Consultant | DDC Managed | PIMS | FALSE |  | 2015 | 2018 |  | DDC
HWR00510 | HWR00510 | Y | Infrastructure | STATEN ISLAND | WOODROW ROAD CONNECTION AT VETERAN'S ROAD EAST | WOODROW ROAD CONNECTION AT VETERAN'S ROAD EAST | WOODROW ROAD CONNECTION AT VETERAN'S ROAD EAST | Staten Is. |  | Transportation | On-Hold | Street Reconstruction | Standard | Requirements TO | DDC Managed/Consultant | PIMS | FALSE |  | 2014 | 2018 |  | DDC
HWR00511 | HWR00511 | Y | Infrastructure | STATEN ISLAND | TRAVIS AVENUE WIDENING | TRAVIS AVENUE WIDENING | TRAVIS AVENUE WIDENING | Staten Is. |  | Transportation | Design Development | Street Reconstruction | Standard | Requirements TO | DDC Managed Consultant | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWR00512 | HWR00512 | Y | Infrastructure | STATEN ISLAND | RICHMOND VALLEY ROAD, SI | RECONSTRUCTION OF RICHMOND VALLEY ROAD, SI | Richmond Valley Road Between Arthur Kill Road and Page Avenue | Staten Is. |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | DDC Managed Consultant |  | PIMS | FALSE |  |  |  |  | DDC
HWR005B | HWR005B | Y | Infrastructure | STATEN ISLAND | TODT HILL ROAD CURVE REHAB | Reconstruction of Todt Hill Road from St. Francis Seminary Exit Road to approximately 260' south of Circle Road; and Willow Pond Road from Todt Hill Road to Buttonwood Road, Borough of Staten Island | Reconstruction of Todt Hill Road from St. Francis Seminary Exit Road to approximately 260' south of Circle Road; and Willow Pond Road from Todt Hill Road to Buttonwood Road, Borough of Staten Island | Staten Is. |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House/Consultant | DDC Managed/Consultant | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWQ631B2 | SEQ002681 | Y | Infrastructure | S. Queens | RECONSTRUCTION OF THURSBY AVE AND AREA (PHASE B2) | Project Limit/locations: Storm & Sanitary Sewers in: 1. B. 69th St. between Bayfield Ave. & Almeda Ave.; 2. B. 72 St. between Bayfield Ave. & Thursby Ave; 3. Barbadoes Drive between Hillmeyer Ave. & Burchell Ave.; 4. Bayfield Ave. between B. 69th St. & B. 72nd St.; 5. Decosta Ave. between B. 69 St. & B. 72nd St.; 6. Hillmeyer Ave. between B.69 St. & DE near Jamaica Bay; 7. Almeda Ave. between B.69th St. & outlet in Jamaica Bay; 8. Burchell Ave. between Barbadoes Drive & B.69th St.; 9. Elizabeth Ave. between B. 69th St. & U.S. Bulkhead Line; 10. Thursby Ave. between B. 69th St. & U.S. Bulkhead Line; Sanitary Sewers in: 1. B. 69th St. between Bayfield Ave. & Thursby Ave.; 2. B. 72 St. between Bayfield Ave. & Thursby Ave; 3. Barbadoes Drive between Hillmeyer Ave. & Burchell Ave.; 4. Bayfield Ave. between B. 69th St. & B. 72nd St.; 5. Decosta Ave. between B. 69 St. & B. 72nd St.; 6. Hillmeyer Ave. between B.69 St. & DE near Jamaica Bay; 7. Almeda Ave. between B.69th St. & outlet in Jamaica Bay; 8. Burchell Ave. between Barbadoes Drive & B.69th St.; 9. Elizabeth Ave. between B. 69th St. & U.S. Bulkhead Line; 10. Thursby Ave. between B. 69th St. & U.S. Bulkhead Line; Water Main in: 1. Bayfield Ave between B. 69th St. & DE; 2. Hillmeyer Ave. between B.72 St. & DE; 3. Almeda Ave. between Barbadoes Drive & DE; 4. Almeda Ave. between B. 72nd St. & B. 69th St.; 5. Burchell Ave. between Barbadoes Drive & B. 69th Street; 6. Elizabeth Ave. between DE & B. 69th St.; 7. Barbadoes Dr. between Hillmeyer Ave. & Thursby Ave.; 8. B. 72 St.between Almeda Ave. & Thursby Ave. | Reconstruct roadway, replace sanitary sewers and water main, install new storm sewers: Rockaway Peninsula area bounded by Bayfield Avenue to the north, Thursby Avenue to the south, Beach 69th Street to the east and Jamaica Bay to the west. |  |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE
HWQ631B3 | HWQ631B3 | Y | Infrastructure | S. QUEENS | SOMERVILLE AREA (N/E Section) | Project Limit/locations: The North-East part of Somerville area bonded: -- from Bayfield Ave (North) to Thursby Ave (South); --from B.69 St. (East) to B.72 St. ( West, included partially) | Reconstruct roadway, replace sanitary sewers and water main, install new storm sewers:The North-East part of Somerville area bonded: from Bayfield Ave (North) to Thursby Ave (South); from B.69 St. (East) to B.72 St. ( West, included partially) | Queens |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWQ631B3 | SE-789B3 | Y | Infrastructure | S. QUEENS | SOMERVILLE AREA (N/E Section) | Project Limit/locations: The North-East part of Somerville area bonded: -- from Bayfield Ave (North) to Thursby Ave (South); --from B.69 St. (East) to B.72 St. ( West, included partially) | Reconstruct roadway, replace sanitary sewers and water main, install new storm sewers:The North-East part of Somerville area bonded: from Bayfield Ave (North) to Thursby Ave (South); from B.69 St. (East) to B.72 St. ( West, included partially) | Queens |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | TRUE |  |  |  |  | DDC
HWQ708 | HWQ708 | Y | Infrastructure | S. Queens | RECONSTRUCTION OF THE 73 PLACE AREA | Project Limit/ locations: Reconstruction of 73rd Place Area On Street From To 73rd Pl. Metropolitan Ave. Dead End S/O 70th Ave 75th St. Metropolitan Ave. 71st Ave. 74th St. 69th Road 70th Ave. 74th St. 70th Ave. 71st Ave. 76th St. 68th Ave. Cooper Ave. 78th St. Metropolitan Ave. Cooper Ave. 79th St. Metropolitan Ave. Cooper Ave. 67th Road 73rd Pl. 80th St. 67th Dr. 73rd Pl. 80 St. 68th Ave. 73rd Pl. 80St. 68th Road 73rd Pl. 75th St. 68th Road 78th St. 80th St. 69th Ave. 73rd Pl. 75th St. 69th Ave 78th St. 80th St. Cook Ave. 73rd Pl. 75th St. 69th road 73rdPl. Cooper Ave. 69th Dr. 79th St. Cooper Ave. 70th Ave. 73rd Pl. 74th St. 71st Ave. 74th St. Cooper Ave. Cooper Ave. NSR 71st Ave. 69 Dr.4 | Roadway reconstruction, 73rd Place from Metropolitan Avenue to the dead end below 70th Avenue, including most streets in the area bounded by Metropolitan Avenue, 73rd Place, 80th Street and Cooper Avenue. | Queens |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE |  |  |  |  | DDC
HWQ724B | HWQ724B | Y | Infrastructure | S. QUEENS | Brookville Blvd and Edgewood Triangle (SEQ200519) | Project Limit / locations: Reconstruction of Streets - Brookville Boulevard Area 1. Bentley Road between 235th Street and Brookville Boulevard. 2. Brookville Boulevard between Newhall Avenue and Dead-End south of 149th Avenue. 3. Edgewood Street between 147th Avenue and Brookville Boulevard. 4. 146th Avenue between Brookville Boulevard and Edgewood Street. 5. 147th Avenue between 230th Place & 200' east of Edgewood Street. 6. 147th Drive between 235th Street and Brookville Boulevard to 241st Street. 7. 147th Road between 235th Street and Brookville Blvd. to 241st Street. 8. 148th Avenue between 235th Street and Brookville Boulevard to 241st Street. 9. 148th Drive between 235th Street and Brookville Boulevard to 241st Street. 10. 148th Road between 235th Street and Brookville Boulevard to 241st Street. 11. 149th Avenue between Brookville Boulevard and 241st Street. 12. 235th Street between 147th Avenue and 148th Avenue. 13. 235th Street between Bentley Rd. and DE SO Bentley Rd. 14. 236th Street between Bentley Road and 148th Drive. 15. 240th Street between 147th Avenue and 147th Road. 16. 232nd Street between 147th Ave. and Dead End. 17. 231st Street between 145th Ave. and 146th Ave. 18. 231st Street between 148th Ave. & Dead End. 19. 148th Ave. between 231st Street and Brookville Park | Reconstruct roadway and extend storm and sanitary sewers in portions of Brookville Boulevard, Edgewood Street, 147th Avenue, and adjacent streets west of 241st Street. | Queens |  | Transportation | Final Design | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | TRUE |  |  | 2019 |  | DDC
HWQ724B | SEQ200519 | Y | Infrastructure | S. QUEENS | Brookville Blvd and Edgewood Triangle (SEQ200519) | Project Limit / locations: Reconstruction of Streets - Brookville Boulevard Area 1. Bentley Road between 235th Street and Brookville Boulevard. 2. Brookville Boulevard between Newhall Avenue and Dead-End south of 149th Avenue. 3. Edgewood Street between 147th Avenue and Brookville Boulevard. 4. 146th Avenue between Brookville Boulevard and Edgewood Street. 5. 147th Avenue between 230th Place & 200' east of Edgewood Street. 6. 147th Drive between 235th Street and Brookville Boulevard to 241st Street. 7. 147th Road between 235th Street and Brookville Blvd. to 241st Street. 8. 148th Avenue between 235th Street and Brookville Boulevard to 241st Street. 9. 148th Drive between 235th Street and Brookville Boulevard to 241st Street. 10. 148th Road between 235th Street and Brookville Boulevard to 241st Street. 11. 149th Avenue between Brookville Boulevard and 241st Street. 12. 235th Street between 147th Avenue and 148th Avenue. 13. 235th Street between Bentley Rd. and DE SO Bentley Rd. 14. 236th Street between Bentley Road and 148th Drive. 15. 240th Street between 147th Avenue and 147th Road. 16. 232nd Street between 147th Ave. and Dead End. 17. 231st Street between 145th Ave. and 146th Ave. 18. 231st Street between 148th Ave. & Dead End. 19. 148th Ave. between 231st Street and Brookville Park | Reconstruct roadway and extend storm and sanitary sewers in portions of Brookville Boulevard, Edgewood Street, 147th Avenue, and adjacent streets west of 241st Street. | Queens |  | Transportation | Final Design | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | TRUE |  |  | 2019 |  | DDC
HWQ787B3 | HWQ787B3 | Y | Infrastructure | S. QUEENS | SUTTER AVE, ETC - PHASE V (B3) | 142nd Street from 135th Avenue to North Conduit Avenue | Roadway reconstruction, Sutter Avenue and vicinity including 142nd Street from 135th Avenue to North Conduit Avenue. | Queens |  | Transportation | Construction Procurement | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | FALSE |  |  | 2015 |  | DDC
HWQ788 | HWQ788 | Y | Infrastructure | BRONX & N. QUEENS | RECON 11TH ST: 44TH DRIVE TO JACKSON AVE | Long Island City/Hunters Point Area-wide Reconstruction: Bounded by 44th Drive, Jackson Ave, Borden Ave and 5th Street, Borough of Queens | Long Island City/Hunters Point Area-wide Reconstruction: Bounded by 44th Drive, Jackson Ave, Borden Ave and 5th Street, Borough of Queens | Queens |  | Transportation | Schematic Design | Street Reconstruction | Standard | Standard Consultant | Requirements TO | PIMS | FALSE |  | 2015 |  |  | DDC
HWQ985 | HWQ985 | Y | Infrastructure | BRONX & N. QUEENS | SHORE ROAD RECONSTRUCTION | Engineered resurfacing of Shore Road from West Drive to 36th Ave in Douglas Manor, Douglaston, Queens. | Engineered resurfacing of Shore Road from West Drive to 36th Ave in Douglas Manor, Douglaston, Queens. | Queens |  | Transportation | Construction 50-75% | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2010 | 2015 |  | DDC
HWQF027C | HWQF027C | Y | Public Buildings | Transportation | Construction of New Diesel Station, Harper St. Yd. | Phase 1:Construction of a new diesel fueling station plus installation of an exhaust capture system, upgrades to electrical equipment, floor leveling and roof replacement. Buildings 4,5, and yard. Phase 2: Asphalt Plant Electrical upgrade and new Block House. | Construction of a new diesel fueling station plus installation of an exhaust capture system, upgrades to electrical equipment, floor leveling and roof replacement. |  |  | Transportation | Construction 75%-Subst. | Renovation |  | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HWR005B1 | HWR005B1 | Y | Infrastructure | Staten Island | TODT HILL ROAD - CIRCLE ROAD (SER200285) | Intersection improvement of Todt Hill Road and Circle Road and Installation of new storm sewer and water main replasement in Todt Hill Road between willow Pond RD and Four Corners Rd Sataten Island | Implement measures to improve traffic flow: Intersection of Todt Hill and Circle Roads. | Staten Is. |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HWR100PAD | HWR100PAD | Y | Infrastructure | STATEN ISLAND | HYLAN BLVD SBS BUS PADS | HYLAN BOULEVARD BUS PADS FOR SELECT BUS SERVICES | HYLAN BOULEVARD BUS PADS FOR SELECT BUS SERVICES | Staten Is. |  | Transportation | Construction 75%-Subst. | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWR1132B | HWR1132B | Y | Infrastructure | Staten Island | Reconstruction of South Beach Area (SE-793) | Reconstruction of the following streets in South Beach area, including street grading, installation of new storm sewers and the replacement of existing sanitary sewers and water mains as required. 1- McClean Ave b/t Norway Ave & Hickory Ave. 2- Foch Ave. b/t Norway Ave & Hickory Ave. 3- Olympia Blvd. b/t Quintard St.& Hickory Ave. 4- Cameron Ave b/t Norway Ave & Quintard Street. 5- Scott Ave b/t Norway Ave & Quintard Street 6- Appleby Ave b/t Norway Ave & Quintard Street. 7- Nugent Ave b/t Norway Ave & Quintard St. 8- Norway Ave b/t McClean Ave & Olympia Blvd. 9- Mallory Ave b/t McClean Ave & Olympia Blvd. 10- Lamport Blvd b/t McClean Ave & Olympia Blvd. 11- Kensington Ave b/t McClean Ave & Olympia Blvd. 12- Jerome Ave b/t McClean Ave & Olympia Blvd. 13- Bionia Ave b/t McClean Ave & Olympia Blvd. 14- Vulcan St. b/t Nugent Ave & Olympia Blvd. 15- Winfield St. b/t Nugent Ave & Olympia Blvd. 16. Patterson b/t Quintard Street & Vulcan Street. | Roadway reconstruction including new storm and sanitary sewers, and water main: South Beach area defined by McClean Avenue to the north, Olympia Boulevard to the south and Hickory Avenue and Quintard Street to the east and west. | Staten Is. |  | Trans. & Env. Protection | Construction 25-50% | Street Reconstruction | Standard | Standard Consultant | DDC Managed Consultant | PIMS | TRUE |  |  | 2017 |  | DDC
HWR1132B | SE-793 | Y | Infrastructure | Staten Island | Reconstruction of South Beach Area (SE-793) | Reconstruction of the following streets in South Beach area, including street grading, installation of new storm sewers and the replacement of existing sanitary sewers and water mains as required. 1- McClean Ave b/t Norway Ave & Hickory Ave. 2- Foch Ave. b/t Norway Ave & Hickory Ave. 3- Olympia Blvd. b/t Quintard St.& Hickory Ave. 4- Cameron Ave b/t Norway Ave & Quintard Street. 5- Scott Ave b/t Norway Ave & Quintard Street 6- Appleby Ave b/t Norway Ave & Quintard Street. 7- Nugent Ave b/t Norway Ave & Quintard St. 8- Norway Ave b/t McClean Ave & Olympia Blvd. 9- Mallory Ave b/t McClean Ave & Olympia Blvd. 10- Lamport Blvd b/t McClean Ave & Olympia Blvd. 11- Kensington Ave b/t McClean Ave & Olympia Blvd. 12- Jerome Ave b/t McClean Ave & Olympia Blvd. 13- Bionia Ave b/t McClean Ave & Olympia Blvd. 14- Vulcan St. b/t Nugent Ave & Olympia Blvd. 15- Winfield St. b/t Nugent Ave & Olympia Blvd. 16. Patterson b/t Quintard Street & Vulcan Street. | Roadway reconstruction including new storm and sanitary sewers, and water main: South Beach area defined by McClean Avenue to the north, Olympia Boulevard to the south and Hickory Avenue and Quintard Street to the east and west. | Staten Is. |  | Trans. & Env. Protection | Construction 25-50% | Street Reconstruction | Standard | Standard Consultant | DDC Managed Consultant | PIMS | TRUE |  |  | 2017 |  | DDC
HWR1140A | HWR1140A | Y | Infrastructure | Staten Island | Reconstruction of Arthur Kill Road, Phase I | HWR1140A: Reconstruction of Arthur Kill Rd from Clark Avenue to Richmond Avenue including widening of roadway | Reconstruction of Arthur Kill Rd from Clark Avenue to Richmond Avenue including widening of roadway | Staten Is. |  | Transportation | Schematic Design | Street Reconstruction | Mayoral Initiative | In-House/Consultant | Standard Consultant | PIMS | TRUE |  |  | 2024 |  | DDC
HWR1140A | RED-366 | Y | Infrastructure | Staten Island | Reconstruction of Arthur Kill Road, Phase I | HWR1140A: Reconstruction of Arthur Kill Rd from Clark Avenue to Richmond Avenue including widening of roadway | Reconstruction of Arthur Kill Rd from Clark Avenue to Richmond Avenue including widening of roadway | Staten Is. |  | Transportation | Schematic Design | Street Reconstruction | Mayoral Initiative | In-House/Consultant | Standard Consultant | PIMS | TRUE |  |  | 2024 |  | DDC
HWR200-01 | HWR200-01 | Y | Infrastructure | STATEN ISLAND | BLOOMINGDALE PARKS SIDEWALKS, SI | BLOOMINGDALE PARKS SIDEWALKS, SI | BLOOMINGDALE PARKS SIDEWALKS, SI | Staten Is. |  | Transportation | Cancelled Project | Sidewalks | Standard |  |  | PIMS | TRUE |  | 2014 | 2017 |  | DDC
HWR300-03 | HWR300-03 | Y | Infrastructure | STATEN ISLAND | ROAD IMPROVEMENT AT SOUTH AVENUE AND FOREST AVENUE | Road Improvement at South Avenue and Forest Avenue Intersection . Borough of Staten Island | Proposed improvement is 300SY 2 the intersection of Sout avenue and Forest Avenue. Borough of Staten Island | Staten Is. |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | In-House/Consultant | DDC Managed/Consultant | PIMS | FALSE |  | 2014 | 2016 |  | DDC
HWR669C | HWR669C | Y | Infrastructure | Staten Island | ROMA & HETT AVENUE, STATEN IS (W/SE-413A/SE-414A) | Installation of Storm, Sanitary Sewers in the following Streets: ================================= 1- Cedar Grove Avenue between Ebbitts Street and new Dorp Lane. 2- Milton Avenue between Ebbitts Street and new Dorp Lane. 3- Finley Avenue between Ebbitts Street and new Dorp Lane. 4- Roma Avenue between Ebbitts Street and new Dorp Lane. 5- Hett Avenue between Ebbitts Street and new Dorp Lane. 6- Marine Way between Cedar Grove and Milton Avenue 7- Beacon Avenue between Roma Avenue and Milton Avenue. 8- Dustan Avenue between Marine way and Milton Avenue. 9- Garibaldi Avenue between Roma Avenue and Cedar Grove Avenue. 10- Cedar Grove Court between Cedar Grove Avenue and Dustan Street. 11- Topping Street between Cedar Grove Avenue and Dustan Street. 12- Center Way between Cedar Grove Avenue and Dustan Street. 13- Neptune Street between Cedar Grove Avenue and Dustan Street. 14- Seafoam Street between Cedar Grove Avenue and Dustan Street. 15- Waterside Street between Cedar Grove Avenue and Dustan Street. 16- Maple Terrace between Cedar Grove Avenue and Dustan Street. 17- Herman Street between Cedar Grove Avenue and Dustan Street. 18- Neutral Avenue between Cedar Grove Avenue and Dustan Street. 19- Milbank Drive between Cedar Grove Avenue and Dustan Street. | Install storm and sanitary sewers at multiple locations. | Staten Is. |  | Trans. & Env. Protection | Final Design | Street Reconstruction | Standard | Requirements TO | DDC Managed/Consultant | PIMS | TRUE |  | 2017 | 2018 |  | DDC
HWR919 | SER200241 | Y | Infrastructure | STATEN ISLAND | RECONSTRUCTION OF BLOOMINGDALE ROAD (SER200241) | Total reconstruction of Bloomingdale Road from Arthur Kill Road and Amboy Road, including installation of Storm & Sanitary sewers, watermains and widening of the roadway at various locations within the project limits. Staten Island | Total reconstruction of Bloomingdale Road from Arthur Kill Road and Amboy Road, including installation of Storm & Sanitary sewers, watermains and widening of the roadway at various locations within the project limits. Staten Island | Staten Is. |  | Transportation | Design Development | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | TRUE |  | 2015 | 2017 |  | DDC
HWR669C | SE-413A | Y | Infrastructure | Staten Island | ROMA & HETT AVENUE, STATEN IS (W/SE-413A/SE-414A) | Installation of Storm, Sanitary Sewers in the following Streets: ================================= 1- Cedar Grove Avenue between Ebbitts Street and new Dorp Lane. 2- Milton Avenue between Ebbitts Street and new Dorp Lane. 3- Finley Avenue between Ebbitts Street and new Dorp Lane. 4- Roma Avenue between Ebbitts Street and new Dorp Lane. 5- Hett Avenue between Ebbitts Street and new Dorp Lane. 6- Marine Way between Cedar Grove and Milton Avenue 7- Beacon Avenue between Roma Avenue and Milton Avenue. 8- Dustan Avenue between Marine way and Milton Avenue. 9- Garibaldi Avenue between Roma Avenue and Cedar Grove Avenue. 10- Cedar Grove Court between Cedar Grove Avenue and Dustan Street. 11- Topping Street between Cedar Grove Avenue and Dustan Street. 12- Center Way between Cedar Grove Avenue and Dustan Street. 13- Neptune Street between Cedar Grove Avenue and Dustan Street. 14- Seafoam Street between Cedar Grove Avenue and Dustan Street. 15- Waterside Street between Cedar Grove Avenue and Dustan Street. 16- Maple Terrace between Cedar Grove Avenue and Dustan Street. 17- Herman Street between Cedar Grove Avenue and Dustan Street. 18- Neutral Avenue between Cedar Grove Avenue and Dustan Street. 19- Milbank Drive between Cedar Grove Avenue and Dustan Street. | Install storm and sanitary sewers at multiple locations. | Staten Is. |  | Trans. & Env. Protection | Final Design | Street Reconstruction | Standard | Requirements TO | DDC Managed/Consultant | PIMS | TRUE |  | 2017 | 2018 |  | DDC
HWR703 | HWR703 | Y | Infrastructure | STATEN ISLAND | BAY STREET AREA SAFETY IMPROVEMENT | In 2016, EDC in collaboration with DCP and the other City agencies released the North Shore Transportation Improvement Strategy report with recommendations for transportation improvements in the neighborhoods. This project will enhance pedestrian safety through safety and streetscape improvements to the medians and/or sidewalks and crosswalks around some of the congested intersections (listed above) within Vision Zero Priority Area of Bay Street area corridor. The project scope of work includes median extensions, street trees (where feasible), sidewalks/curbs extensions, crossing distance(s) reductions and Wayfinding signs installations within expanded sidewalks. |  |  |  | Transportation | Scope Development | Street Reconstruction | Standard | In-House/Consultant | DDC Managed | Project Info | FALSE |  |  |  | 2017-10-10 13:00:21.1100000 +00:00
HWR890 | HWR890 | Y | Infrastructure | STATEN ISLAND | RECONSTRUCTION OF WOODROW ROAD | RECONSTRUCTION OF WOODROW ROAD | RECONSTRUCTION OF WOODROW ROAD | Staten Is. |  | Transportation | On-Hold | Street Reconstruction | Standard | In-House | Requirements TO | PIMS | FALSE |  |  | 2018 |  | DOT
HWR919 | HWR919 | Y | Infrastructure | STATEN ISLAND | RECONSTRUCTION OF BLOOMINGDALE ROAD (SER200241) | Total reconstruction of Bloomingdale Road from Arthur Kill Road and Amboy Road, including installation of Storm & Sanitary sewers, watermains and widening of the roadway at various locations within the project limits. Staten Island | Total reconstruction of Bloomingdale Road from Arthur Kill Road and Amboy Road, including installation of Storm & Sanitary sewers, watermains and widening of the roadway at various locations within the project limits. Staten Island | Staten Is. |  | Transportation | Design Development | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | TRUE |  | 2015 | 2017 |  | DDC
HWRC054-R | HWRC054-R | Y | Infrastructure | STATEN ISLAND | HYLAN BOULEVARD INTERSECTION IMPROVEMENT (RE-BID) | HYLAN BOULEVARD INTERSECTION IMPROVEMENTS at the following location: (1) HYLAN BLVD. BETWEEN TARLEE PLACE AND WHITMAN AVENUE (Cleveland Avenue Intersection); (2) HYLAN BLVD. BETWEEN WATERSIDE PARKWAY AND FAIRLAWN AVENUE (Fieldway Avenue Inersection); (3) & (4) HYLAN BLVD. BETWEEN HOPKINS AVENUE AND MONTREAL AVENUE (Buffalo Street & Chesterton Avenue Intersection). | HYLAN BOULEVARD INTERSECTION IMPROVEMENTS at the following location: Cleveland Avenue Intersection; Fieldway Avenue Intersection; Buffalo Street Intersection & Chesterton Avenue Intersection. | Staten Is. |  | Transportation | Acceptance/Final Completion | Street Reconstruction | Standard | In-House | Standard Consultant | PIMS | FALSE |  | 2011 | 2012 |  | DDC
HWRC055 | HWRC055 | Y | Infrastructure | STATEN ISLAND | HYLAN BOULEVARD AT NEW DORP LANE | HYLAN BOULEVARD INTERSECTION IMPROVEMENTS: Hylan Boulevard at New Dorp Lane. | IMPROVEMENTS OF THE INTERSECTION OF HYLAN BOULEVARD @ NEW DORP LANE | Staten Is. |  | Transportation | Pre-Design/PrgDevelopment | Street Resurfacing | Standard | In-House | DDC Managed | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWRF05R | HWRF05R | Y | Public Buildings | TRANSPORTATION | Replacement of roof , sprinkler & related repairs | Roof replacement and related repairs caused by water damage. Replace wet sprinkler system with dry system. | Roof replacement and related repairs caused by water damage. Replace wet sprinkler system with dry system. | Staten Is. |  | Transportation | Design Development | Renovation | Standard | Requirement Contract |  | PIMS | FALSE |  |  |  |  | DDC
HWS16CW1 | HWS16CW1 | Y | Infrastructure | BRONX & N. QUEENS | PRIOR NOTICE SIDEWALKS - CITYWIDE | PRIOR NOTICE SIDEWALKS - CITYWIDE (BROOKLYN & QUEENS) | PRIOR NOTICE SIDEWALKS - CITYWIDE (BROOKLYN & QUEENS) | Citywide |  | Transportation | Construction 0-25% | Sidewalks | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWS16CW2 | HWS16CW2 | Y | Infrastructure | BRONX & N. QUEENS | PRIOR NOTICE SIDEWALKS - CITYWIDE (BX, MN & SI) | PRIOR NOTICE SIDEWALKS - CITYWIDE (BRONX, MANHATTAN & STATEN ISLAND) | PRIOR NOTICE SIDEWALKS - CITYWIDE (BRONX, MANHATTAN & STATEN ISLAND) | Citywide |  | Transportation | Construction 0-25% | Sidewalks | Critical | In-House | Requirement Contract | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWS16XCW2 | HWS16XCW2 | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS - MANHATTAN & STATEN ISLAND | PRIOR NOTICE SIDEWALKS - BRONX, MANHATTAN & STATEN ISLAND | PRIOR NOTICE SIDEWALKS - BRONX, MANHATTAN & STATEN ISLAND |  |  | Transportation |  | New Construction | Critical |  |  | PIMS | FALSE
HWS17CW1 | HWS17CW1 | Y | Infrastructure | BROOKLYN | PRIOR NOTICE SIDEWALKS FY17 - CITYWIDE (BK & QU) | PRIOR NOTICE SIDEWALKS FY17 - CITYWIDE (BK & QU) | PRIOR NOTICE SIDEWALKS FY17 - CITYWIDE (BK & QU) | Citywide |  | Transportation | Construction Procurement | Sidewalks | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2017 | 2017 |  | DDC
HWS17CW2 | HWS17CW2 | Y | Infrastructure | STATEN ISLAND | PRIOR NOTICE SIDEWALKS FY17 - CITYWIDE (BX,MN,SI) | PRIOR NOTICE SIDEWALKS FY17 - CITYWIDE (BX,MN,SI) | PRIOR NOTICE SIDEWALKS FY17 - CITYWIDE (BX,MN,SI) | Citywide |  | Transportation | Cancelled Project | Sidewalks | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
HWS18CW1 | HWS18CW1 | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS CITYWIDE | PRIOR NOTICE SIDEWALKS, CITYWIDE | PRIOR NOTICE SIDEWALKS, CITYWIDE | Citywide |  | Transportation | Design Development | Sidewalks | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HWS18CW2 | HWS18CW2 | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS CITYWIDE | PRIOR NOTICE SIDEWALKS, CITYWIDE | PRIOR NOTICE SIDEWALKS, CITYWIDE | Citywide |  | Transportation | Design Development | Sidewalks | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HWS2011R | HWS2011R | Y | Infrastructure | STATEN ISLAND | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | Replacement of Sidewalks that have violations for which property owners have received prior notices. NYCDOT, Division of Sidewalks and Inspection Management, will identify the actual locations. | Replacement of Sidewalks that have violations for which property owners have received prior notices. NYCDOT, Division of Sidewalks and Inspection Management, will identify the actual locations. |  |  | Transportation | Completed Project | Sidewalks | Standard | In-House | Standard Consultant | PIMS | FALSE
HWS2013CW | HWS2013CW | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS - CITYWIDE | Replacement of sidewalks that have violations in which property owners have received prior notice, citywide. Locations for prior notice sidewalks will be determined by NYC DOT Divison of Sidewalks and Inspections Managements. This project is privately funded. Chelmsford Contracting Co. | Replacement of sidewalks that have violations in which property owners have received prior notice, citywide. Locations for prior notice sidewalks will be determined by NYC DOT Divison of Sidewalks and Inspections Managements. | Citywide |  | Transportation | Substantial Completion | Sidewalks | Standard | In-House | Requirements TO | PIMS | FALSE |  |  | 2014 |  | DDC
HWS2013M | HWS2013M | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS - MANHATTAN | Replacement of sidewalks that have violations in which property owners have received prior notice, Manhattan. Locations for prior notice sidewalks will be determined by NYC DOT, Division of Sidewalks and Inspections Managements. This project has $1,419,000 in city funding and $400,000 for construction in private funding. | Replacement of sidewalks that have violations in which property owners have received prior notice, Borough of Manhattan | Manhattan |  | Transportation | Completed Project | Sidewalks | Standard | In-House | Standard Consultant | PIMS | FALSE |  | 2013 | 2014 |  | DDC
HWS2013Q | HWS2013Q | Y | Infrastructure | S. QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | Replacement of sidewalks that have violations in which property owners have received prior notice. Locations for prior notice sidewalks will be determined by New York City Department of Transportation, Division of Sidewalks and Inspections Management. | Replacement of sidewalks that have violations in which property owners have received prior notice. Locations for prior notice sidewalks will be determined by New York City Department of Transportation, Division of Sidewalks and Inspections Management. | Queens |  | Transportation | Completed Project | Sidewalks | Standard | In-House | Standard Consultant | PIMS | FALSE |  |  | 2013 |  | DDC
HWS2013R | HWS2012R | Y | Infrastructure | STATEN ISLAND | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | Replacement of Sidewalks that have violations for which property owners have received prior notices. NYCDOT, Division of Sidewalks and Inspection Management, will identify the actual locations. | Replacement of Sidewalks that have violations for which property owners have received prior notices. |  |  | Transportation | Completed Project | Sidewalks | Standard | In-House | Standard Consultant | PIMS | FALSE
HWS2013R | HWS2013R | Y | Infrastructure | STATEN ISLAND | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | Replacement of Sidewalks that have violations for which property owners have received prior notices. NYCDOT, Division of Sidewalks and Inspection Management, will identify the actual locations. | Replacement of Sidewalks that have violations for which property owners have received prior notices. |  |  | Transportation | Completed Project | Sidewalks | Standard | In-House | Standard Consultant | PIMS | FALSE
HWS2014CW | HWS2014CW | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS - CITYWIDE | Replacement of Sidewalks that Have Violations and for Which Property Owners Have Received Prior Notice, Citywide | Prior Notice Sidewalks - Citywide | Citywide |  | Transportation | Substantial Completion | Sidewalks | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HWS2014K | HWS2014K | Y | Infrastructure | BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | Installation of sidewalks, adjacent curbs and pedestrian ramps as necessary in various locations. Replacement of Sidewalks that have violations for which property owner has received prior notice. | Installation of sidewalks, adjacent curbs and pedestrian ramps as necessary in various locations. Brooklyn |  |  | Transportation | Substantial Completion | Sidewalks | Standard | In-House | Requirements TO | PIMS | FALSE
HWS2014M | HWS2014M | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS - MANHATTAN | Replacement of Sidewalks that Have Violations and for Which Property Owners Have Received Prior Notice, Manhattan | Replacement of Sidewalks with Prior Notice violation in Manhattan | Manhattan |  | Transportation | Substantial Completion | Sidewalks | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2013 | 2014 |  | DDC
HWS2014Q | HWS2014Q | Y | Infrastructure | S. QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | Replacement of sidewalks that have violations for which property owners have received prior notice. Locations for prior notice sidewalks will be determined by New York City Department of Transportation, Division of Sidewalks and Inspections Management. | Replacement of sidewalks that have violations for which property owners have received prior notice. Locations for prior notice sidewalks will be determined by New York City Department of Transportation, Division of Sidewalks and Inspections Management. | Queens |  | Transportation | Substantial Completion | Sidewalks | Standard | In-House | Standard Consultant | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HWS2014R | HWS2014R | Y | Infrastructure | STATEN ISLAND | PRIOR NOTICE SIDEWALKS, STATEN ISLAND | Replacement of Sidewalks that have violations for which property owners have received prior notices. NYCDOT, Division of Sidewalks and Inspection Management, will identify the actual locations. | Replacement of Sidewalks that have violations for which property owners have received prior notices. | Staten Is. |  | Transportation | Substantial Completion | Sidewalks | Standard |  |  | PIMS | FALSE |  | 2014 | 2014 |  | DDC
HWS2014X | HWS2014X | Y | Infrastructure | BRONX & N. QUEENS | PRIOR NOTICE SIDEWALKS - BRONX | Replacement of Various locations of sidewalks in Bronx that have violation which property owners have received prior notice | Repair/replacement of sidewalks at various locations of Bronx with violations for which property owners have received prior notice. | Bronx |  | Transportation | Substantial Completion | Sidewalks | Standard | In-House | DDC Managed Consultant | PIMS | FALSE |  | 2013 | 2014 |  | DDC
HWS2015CW | HWS2015CW | Y | Infrastructure | BROOKLYN | PRIOR NOTICE SIDEWALKS - CITYWIDE | PRIOR NOTICE SIDEWALKS - CITYWIDE | Prior Notice Sidewalks - Citywide | Brooklyn |  | Transportation | Substantial Completion | Sidewalks | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2015 |  | DDC
HWS2015K | HWS2015K | Y | Infrastructure | BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | Prior Notice Sidewalks, Brooklyn. | Brooklyn |  | Transportation | Substantial Completion | Sidewalks | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2015 |  | DDC
HWS2015M | HWS2015M | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS - MANHATTAN | PRIOR NOTICE SIDEWALKS - MANHATTAN | Prior Notice Sidewalks - Manhattan | Manhattan |  | Transportation | Substantial Completion | Sidewalks | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2015 | 2015 |  | DDC
HWS2015Q | HWS2015Q | Y | Infrastructure | S. QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS |  | Queens |  | Transportation | Substantial Completion | Sidewalks | Critical |  |  | PIMS | FALSE |  | 2015 | 2015 |  | DDC
HWS2015R | HWS2015R | Y | Infrastructure | STATEN ISLAND | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | PRIOR NOTICE SIDEWALKS - STATEN ISLAND | PRIOR NOTICE SIDEWALKS - STATEN ISLAND |  |  | Transportation | Substantial Completion | Sidewalks | Standard | In-House | Requirements TO | PIMS | FALSE
HWS2015X | HWS2015X | Y | Infrastructure | BRONX & N. QUEENS | PRIOR NOTICE SIDEWALKS - BRONX | PRIOR NOTICE SIDEWALKS - BRONX | PRIOR NOTICE SIDEWALKS - BRONX | Bronx |  | Transportation | Substantial Completion | Sidewalks | Critical |  |  | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HWS2016CW1 | HWS2016CW | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS - CITYWIDE | PRIOR NOTICE SIDEWALKS - CITYWIDE (BROOKLYN & QUEENS) | PRIOR NOTICE SIDEWALKS - CITYWIDE (BROOKLYN & QUEENS) |  |  | Transportation | Cancelled Project | New Construction | Critical | In-House |  | PIMS | FALSE
HWS2016K1 | HWS2016K1 | Y | Infrastructure | BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | Brooklyn |  | Transportation | Construction 0-25% | New Construction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWS2016K2 | HWS2016K2 | Y | Infrastructure | BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | PRIOR NOTICE SIDEWALKS - BROOKLYN | Brooklyn |  | Transportation | Construction 0-25% | New Construction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2015 | 2016 |  | DDC
HWS2016M | HWS2016M | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS - MANHATTAN | PRIOR NOTICE SIDEWALKS - MANHATTAN | PRIOR NOTICE SIDEWALKS - MANHATTAN | Manhattan |  | Transportation | Construction 0-25% | Sidewalks | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWS2016Q1 | HWS2016Q1 | Y | Infrastructure | S. QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | INSTALLATION OF SIDEWALKS, ADJACENT CURBS AND PEDESTRIAN RAMPS AS NECESSARY IN VARIOUS LOCATIONS - BOROUGH OF QUEENS | Queens |  | Transportation | Construction 0-25% | New Construction | Critical | In-House |  | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWS2016Q2 | HWS2016Q2 | Y | Infrastructure | S. QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | PRIOR NOTICE SIDEWALKS - BOROUGH OF QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | Queens |  | Transportation | Construction 0-25% | New Construction | Critical |  |  | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWS2016R1 | HWS2016R1 | Y | Infrastructure | STATEN ISLAND | PRIOR NOTICE SIDEWALKS- STATEN ISLAND | PRIOR NOTICE SIDEWALKS- STATEN ISLAND | PRIOR NOTICE SIDEWALKS- STATEN ISLAND | Staten Is. |  | Transportation | Construction 0-25% | Sidewalks | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWS2016R2 | HWS2016R2 | Y | Infrastructure | STATEN ISLAND | PRIOR NOTICE SIDEWALKS- STATEN ISLAND | PRIOR NOTICE SIDEWALKS- STATEN ISLAND | PRIOR NOTICE SIDEWALKS- STATEN ISLAND | Staten Is. |  | Transportation | Construction 0-25% | Sidewalks | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWS2016X | HWS2016X | Y | Infrastructure | BRONX & N. QUEENS | PRIOR NOTICE SIDEWALKS - BRONX | PRIOR NOTICE SIDEWALKS - BRONX | PRIOR NOTICE SIDEWALKS - BRONX | Bronx |  | Transportation | Construction 0-25% | New Construction | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HWS2016XM | HWS2016XM | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS-BRONX & MANHATTAN | PRIOR NOTICE SIDEWALKS - BRONX & MANHATTAN | PRIOR NOTICE SIDEWALKS - BRONX & MANHATTAN | Citywide |  | Transportation | Construction 0-25% | Sidewalks | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2016 | 2017 |  | DDC
HWS2017M | HWS2017M | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS FY17 - MANHATTAN | PRIOR NOTICE SIDEWALKS FY17 - MANHATTAN | PRIOR NOTICE SIDEWALKS - MANHATTAN | Manhattan |  | Transportation | Construction Procurement | Sidewalks | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2017 | 2017 |  | DDC
HWS2017Q1 | HWS2017Q1 | Y | Infrastructure | S. QUEENS | PRIOR NOTICE SIDEWALKS FY17 - QUEENS1 | PRIOR NOTICE SIDEWALKS - QUEENS1 | Replacement of Sidewalks that have violations where property owners received prior notice. Borough of Queens. | Queens |  | Transportation | Construction 0-25% | Sidewalks | Standard | In-House | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HWS2017Q2 | HWS2017Q2 | Y | Infrastructure | S. QUEENS | PRIOR NOTICE SIDEWALKS FY17 - QUEENS2 | PRIOR NOTICE SIDEWALKS FY17 - QUEENS2 | Replacement of Sidewalk that have violations where property owners received prior notice. | Queens |  | Transportation | Construction Procurement | Sidewalks | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HWS2017X | HWS2017X | Y | Infrastructure | BRONX & N. QUEENS | PRIOR NOTICE SIDEWALKS FY17 - BRONX | PRIOR NOTICE SIDEWALKS FY17 - BRONX | PRIOR NOTICE SIDEWALKS FY17 - BRONX | Bronx |  | Transportation |  | Sidewalks | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HWS2018M | HWS2018M | Y | Infrastructure | MANHATTAN & CITYWIDE | PRIOR NOTICE SIDEWALKS FY18 MANHATTAN | PRIOR NOTICE SIDEWALKS - MANHATTAN | PRIOR NOTICE SIDEWALKS - MANHATTAN | Manhattan |  | Transportation | Final Design | Sidewalks | Critical | In-House | Requirements TO | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HWS2018Q1 | HWS2018Q1 | Y | Infrastructure | S. QUEENS | PRIOR NOTICE SIDEWALKS FY18 QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | INSTALLATON OF SIDEWALKS, ADJACENT CURBS AND PEDESTRIAN RAMPS AS NECESSARY IN VARIOUS LOCATIONS ~ BOROUGH OF QUEENS | Queens |  | Transportation | Construction Procurement | Sidewalks | Critical | In-House |  | PIMS | FALSE |  |  |  |  | DDC
HWS2018Q2 | HWS2018Q2 | Y | Infrastructure | S. QUEENS | PRIOR NOTICE SIDEWALKS FY18 QUEENS | PRIOR NOTICE SIDEWALKS - QUEENS | INSTALLATION OF SIDEWALKS, ADJACENT CURBS AND RAMPS AS NECESSARY IN VARIOUS LOCATIONS ~ BOROUGH OF QUEENS | Queens |  | Transportation | Construction Procurement | Sidewalks | Critical | In-House | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HWS2018X | HWS2018X | Y | Infrastructure | BRONX & N. QUEENS | PRIOR NOTICE SIDEWALKS FY18 BRONX | PRIOR NOTICE SIDEWALKS - BRONX | PRIOR NOTICE SIDEWALKS - BRONX | Bronx |  | Transportation | Final Design | Sidewalks | Standard | DDC Managed Consultant |  | PIMS | FALSE |  |  |  |  | DDC
HWSRT2009 | HWSRT2009 | Y | Infrastructure | BRONX & N. QUEENS | SAFE ROUTES TO TRANSIT | The intent of this project is to install sidewalk extensions (bus bulbs) to the inner travel lane of streets under elevated transit lines. These extensions will be located at existing bus stops and will eliminate mid-roadway bus loading. 1) White Plains Rd at Allerton Ave (CB 11) 2) White Plains Rd at 219 Street (12) 31st St at Broadway, Queens (No FTA Funding). Location removed and incorporated into School Safety project HWCSCH3B-3. To be bid under HWPEDSF1 with two additional Queens locations. | Installation of sidewalk extensions (bus bulbs) to the inner travel lane of streets under elevated transit lines. These extensions will be at existing bus stops at 2 locations and will eliminate mid-roadway bus loading. | Bronx |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2009 | 2014 |  | DDC
HWSRT200A | HWSRT200A | Y | Infrastructure | BRONX & N. QUEENS | SAFE ROUTES TO TRANSIT FTA-NF | The intent of this project is to install sidewalk extensions (bus bulbs) to the inner travel lane of streets under elevated transit lines. These extensions will be located at existing bus stops and will eliminate mid-roadway bus loading. FTA Funded Locations: 1) Westchester Ave at Middletown Rd (CB # 10) 2) Westchester Ave at Castle Hill (CB # 9 & 10) 3) Westchester Ave at Zerega (CB # 10) (TA WORKING AT SITE) 4) Westchester Ave at St Lawrence Ave (CB # 9) Westchester Ave at Buhre/Edison Aves (CB # 10) (REMOVED - FUNDING SHORTAGE) | Installation of sidewalk extensions (bus bulbs) to the inner travel lane of streets under elevated transit lines. These extensions will be at existing bus stops at 4 locations and will eliminate mid-roadway bus loading. | Bronx |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  | 2014 |  | DDC
HWSRT200B | HWSRT200B | Y | Infrastructure | BRONX & N. QUEENS | SAFE ROUTES TO TRANSIT - CMAQ X501.85 | The intent of this project is to install sidewalk extensions (bus bulbs) to the inner travel lane of streets under elevated transit lines. These extensions will be located at existing bus stops and will eliminate mid-roadway bus loading CMAQ Funded Locations: 1) Broadway and 231st St (CB # 8) 2) Broadway and 238tht St (CB # 8) 3) Broadway at w242nd St (CB # 8) (Loc. # 3 removed per DOT e-mail) | Installation of sidewalk extensions (bus bulbs) to the inner travel lane of streets under elevated transit lines. These extensions will be at existing bus stops at 2 locations and will eliminate mid-roadway bus loading. | Bronx |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  | 2014 |  | DDC
HWSRT200C | HWSRT200C | Y | Infrastructure | BRONX & N. QUEENS | SAFE ROUTES TO TRANSIT FTA-NF X767.03 | The intent of this project is to install sidewalk extensions (bus bulbs) to the inner travel lane of streets under elevated transit lines. These extensions will be located at existing bus stops and will eliminate mid-roadway bus loading. 1) Westchester Ave at Simpson Street (CB 2) 2) Westchester ave at Elder Ave (CB 9) 3) Westchester Ave at Morrison Ave (CB 9) 4) White Plains Rd at 233 Street (CB 12) 5) White Plains Rd at Nereid Ave (CB 12) 6) White Plains Rd at 241 Street (CB 12) 7) Jerome Ave at E 183rd Street (CB 5) 8) Jerome Ave at E 176th Street (CB 5) 9) Jerome Ave at Kingsbridge Ave (CB 7) 10) Jerome Ave at Bainbridge Ave (CB 7) | Installation of sidewalk extensions (bus bulbs) to the inner travel lane of streets under elevated transit lines. These extensions will be at existing bus stops at 10 locations and will eliminate mid-roadway bus loading. | Bronx |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  | 2015 |  | DDC
HWSRT200D | HWSRT200D | Y | Infrastructure | BROOKLYN | SAFE ROUTES TO TRANSIT -86TH ST | Safe Routes to Transit – 86th St Brooklyn The project will also include reconstruction of new bus pads, high-visibility crosswalks, relocation of existing manholes and utilities, ADA-compliant designs, and installation of City Benches and pedestrian wayfinding signs. The scope of the project will also include a trench restoration with full street reconstruction on 20th Ave from 86th Street to Bath Ave. | Safe Routes to Transit – Safety improvements along 86th Street and on 20th Ave from 86th Street to Bath Ave, Brooklyn. | Brooklyn |  | Transportation | Pre-Preliminary Design | Street Reconstruction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2019 | 2021 |  | DDC
HWTRK1 | HWTRK1 | Y | Infrastructure | BROOKLYN | TRENCH RESTORATION BROOKLYN | Trench Restoration in The Borough Of Brooklyn including Full Street Reconstruction. Locations: 1. Division Avenue from Berry Street to Bedford Avenue 2. Juliana Place from Clymer Street to Morton Street 3. Maujer Street from Union Avenue to Lorimer Street 4. Warren Street from Bond Street to Nevins Street 5. Hancock Street from Marcy Avenue to Tompkins Avenue 6. Bushwick Avenue from Woodbine Street to Madison Street 7. Hill Street from Crescent Street to Autumn Avenue 8. 7th Avenue from 14th Street to 15th Street 9. Bergen Street from Troy Avenue to Schenectady Avenue 10. Union Street from Troy Avenue to Schenectady Avenue 11. 9th Avenue from 63rd Street to 64th Street 12. 20th Avenue from 86th Street to Benson Avenue 13. Bay Parkway from Cropsey Avenue to Bath Avenue 14. 16th Avenue from 46th Street to 47th Street 15. New York Avenue from Glenwood Road to Avenue 16. East 80th Street from Foster Avenue to Glenwood Road | Trench Restoration in The Borough Of Brooklyn including Full Street Reconstruction | Brooklyn |  | Transportation | Pre-Preliminary Design | Street Reconstruction | Critical | Requirements TO | Requirements TO | PIMS | FALSE |  | 2018 | 2021 |  | DDC
HWTRQX1 | HWTRQX1 | Y | Infrastructure | BRONX & N. QUEENS | TRENCH RESTORATION QUEENS & THE BRONX | TRENCH RESTORATION, QUEENS & THE BRONX. INCLUDES RESTORATION OF TRENCHES, ROADWAY RECONSTRUCTION, REPLACE CURBS AND ADJACENT SIDEWALK FLAGS WHERE CONDITION IS POOR, INSTALL ACCESSIBLE PEDESTRIAN SYSTEMS AT SIGNALIZED INTERSECTIONS, ETC. | TRENCH RESTORATION, QUEENS & THE BRONX. INCLUDES RESTORATION OF TRENCHES, ROADWAY RECONSTRUCTION, REPLACE CURBS AND ADJACENT SIDEWALK FLAGS WHERE CONDITION IS POOR, INSTALL ACCESSIBLE PEDESTRIAN SYSTEMS AT SIGNALIZED INTERSECTIONS, ETC. | Bronx |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2018 | 2021 |  | DDC
HWTRR1 | HWTRR1 | Y | Infrastructure | STATEN ISLAND | Trench Restoration - Staten Island | This project has been initiated to bring three identified utility trenches in SI to a state of good repair. These sites, pulled from a master list, were prioritized with attention to ratings data, field observations, and community needs. The sites are split into scoping categories; full street reconstruction, and trench restoration with resurfacing. Projects will upgrade pedestrian facilities to ADA compliancy, and address adjacent capital assets in poor condition (curbs, sidewalks, and others as needed). |  | Staten Is. |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Standard | In-House/Consultant |  | PIMS | FALSE |  | 2018 | 2021 |  | DDC
HWX100SBS | HWX100SBS | Y | Infrastructure | BRONX & N. QUEENS | WEBSTER AVE SELECT BUS SERVICE, BRONX | WEBSTER AVE SELECT BUS SERVICE, BRONX | WEBSTER AVE SELECT BUS SERVICE, BRONX | Bronx |  | Transportation | Construction 25-50% | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2014 | 2015 |  | DDC
HWX1048 | HWX1048 | Y | Infrastructure | BRONX & N. QUEENS | SOUTH BRONX GREENWAY | CONSTRUCTION OF PROTECTED BIKE PATH ALONG BRUCKNER BLVD BETWEEN HUNTS POINT AVE & TIFFANY ST, TO ENHANCE SAFETY & CREATE NEW RECREATION AND NON-MOTORIZED TRANSPORTATION FACILITES IN THE SOUTH BRONX. | CONSTRUCTION OF PROTECTED BIKE PATH ALONG BRUCKNER BLVD BETWEEN HUNTS POINT AVE & TIFFANY ST, TO ENHANCE SAFETY & CREATE NEW RECREATION AND NON-MOTORIZED TRANSPORTATION FACILITES IN THE SOUTH BRONX. | Bronx |  | Transportation |  | Street Reconstruction | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
HWXFPLZA | HWXFPLZA | Y | Infrastructure | BRONX & N. QUEENS | FORDHAM PLAZA PHASE A | Fordham Plaza Phase A Between Park Ave to the West 3rd Ave to the East East Fordham Road to the North East 189th Street to the South | Fordham Plaza Phase A | Bronx |  | Transportation | Substantial Completion | Other | Standard | Requirements TO | Standard Consultant | PIMS | FALSE |  | 2011 | 2014 |  | DDC
HWXP093B | HWXP093B | Y | Infrastructure | BRONX & N. QUEENS | RECON OF BOLLER AVE | Boller Avenue from approximately 50 feet south of Crawford Avenue/Marolla Place to approximately 100 feet south of Needham Avenue. Needham Avenue from approximately east building line of Palmer Avenue to approximately 100 feet east of Boller Avenue. | Reconstruction of Boller Avenue. | Bronx |  | Transportation | Substantial Completion | Street Reconstruction | Standard | In-House/Consultant | Requirements TO | PIMS | FALSE |  | 2011 | 2014 |  | DDC
HWXP2007 | HWXP2007 | Y | Infrastructure | BRONX & N. QUEENS | RECONSTRUCTION OF E 177 STREET/DEVOE AVENUE | Road Reconstruction, Water Main and Combined Sewer Work E 177th Street from Devoe Ave to Bronx Park Ave East Tremont Ave from Bronx Park Ave to Boston Rd Devoe Ave from E 177th Street to East Tremont Ave | Road Reconstruction, Water Main and Combined Sewer Work E 177th Street from Devoe Ave to Bronx Park Ave East Tremont Ave from Bronx Park Ave to Boston Rd Devoe Ave from E 177th Street to East Tremont Ave | Bronx |  | Transportation | Final Design | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2008 | 2015 |  | DDC
HWX421AW | HWX421AW | Y | Infrastructure | BRONX & N. QUEENS | RECONSTRUCTION 0F THROGS NECK PENNYFIELD AREA | Full reconstruction of the Throgs Neck Pennyfield Area streets which are located south of the Throgs Neck Expressway, southeast of Hammond Cove Bay and west of the East Tremont Ave. Project Limits: -Prentiss from Harding Ave to Mullen Pl -Pennyfield Ave from East 177 St to Maritime College -Meagher Ave from East 177 St to Schurz Ave -Kearney Ave from Lawton Ave to Schurz Ave -Throgs Neck Blvd from East 177 St to Schurz Ave -Hollywood Ave from East 177 St to Dead End -Logan Ave from East 177 St to Lawton Ave -Sampson Ave from East Tremont Aveto Logan Ave -Gerber Pl from East Tremont Ave to Logan Ave -Miles Ave from East Tremont Ave to East 177 St -Lawton Ave from East Tremont Ave to Throgs Neck Blvd -Lawton Ave Meagher Ave to Pennyfield/E177 St -Milton Pl from East Tremont Ave to Throgs Neck Blvd -Harding Ave from East Tremont Ave to East 177 St -Silver Beach Pl/ Monsignor Halpin from East Tremont Ave to Throgs Neck Blvd -Schurz Ave from East Tremont Ave to Pennyfield Ave -Mullen Pl from Pennyfield Ave to Dead End -Chaffee Ave from Pennyfield Ave to Dead End -Hatting Pl from Pennyfield Ave to Dead End -Glennon Pl from Pennyfield Ave to Dead End -Geigerich Pl from Pennyfield Ave to Dead End -Mitchell Pl from Pennyfield Ave to Dead End -Fearn Pl from Pennyfield Ave to Dead End -Dare Pl from Pennyfield Ave to Dead End -Casler Pl from Pennyfield Ave to Dead End -Bevy Pl from Pennyfield Ave to Dead End | Full reconstruction of the Throgs Neck Pennyfield Area streets which are located south of the Throgs Neck Expressway, southeast of Hammond Cove Bay and west of the East Tremont Ave. | Bronx |  | Transportation | On-Hold | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | FALSE |  |  | 2024 |  | DDC
HWX710A | HWX710A | Y | Infrastructure | BRONX & N. QUEENS | PELHAM PKWY - Phase 2 | Pelham Pkwy main road W/B from Bronx River Pkwy to Hutchinson River Pkwy Pelham Pkwy North Service Rd. (S/R) from Bronx Park East to Eastchester Rd. Stillwell Ave from westbound mainline to north service road | Pelham Pkwy main road W/B from Bronx River Pkwy to Hutchinson River Pkwy Pelham Pkwy North Service Rd. (S/R) from Bronx Park East to Eastchester Rd. Stillwell Ave from westbound mainline to north service road | Bronx |  | Transportation | Construction 0-25% | Street Reconstruction | Standard | Standard Consultant | Standard Consultant | PIMS | FALSE |  |  |  |  | DDC
HWXF2000A | HWXF2000 | Y | Public Buildings | Transportation | Williamsbridge Rd., Bronx | Roof replacement. Repointing of entire brick façade and limestone bands. Reseal all coping stones at parapet walls and fill in basement windows with glass blocks. | Complete facade restoration and window replacement. |  |  | Transportation | Acceptance/Final Completion | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
HWXF2000B | HWXF2000B | Y | Public Buildings | TRANSPORTATION | 1400 Williamsbridge Rd, BX.HVAC Replacement | Replace existing mechanical systems with new systems and a BMS, replacement of the windows (1st & 2nd fl) and upgrade the existing fire alarm system. | Replace existing mechanical systems with new systems and a BMS, replacement of the windows (1st & 2nd fl) ad upgrade the existing fire alarm system. | Bronx |  |  | Design Development | Upgrade | Standard | Requirement Contract | Standard Consultant | PIMS | FALSE |  |  |  |  | DDC
HWXF2144W | HWXF2144W | Y | Public Buildings | TRANSPORTATION | 4409 Park Ave, BX.HVAC Replacement | To remove and replace the two RoofTop Units and re-connect to existing ductwork and restore the system management capabilities. Also add the ability to remotely access the system and program schedules. | To remove and replace the two RoofTop Units and re-connect to existing ductwork and restore the system management capabilities. Also add the ability to remotely access the system and program schedules. | Unknown |  | Transportation | Construction Procurement | Renovation | Standard | In-House | JOCS | PIMS | TRUE |  |  |  |  | DDC
HWXP136A | HWXP136A | Y | Infrastructure | BRONX & N. QUEENS | GRAND CONCOURSE SERVICE ROADS X770.18 | Reconstruction of Grand Concourse service roads between East 166 Street and East 171 Street including widening of median/malls, installation of bicycle lanes and landscaping and sewer work. Also, combined sewer work included in the following locations. - Grand Concourse Blvd. from E.166 Street to E.165 Street - Grand Concourse Blvd. from E.171 Street to E.172 Street - E.168 Street from Grand Concourse Blvd. to Grandview Pl. - Clarke Pl. bet. Grand Concourse Blvd. and Walton Ave. - Marcy Pl. bet. Grand Concourse Blvd. and Walton Ave. - Elliot Pl. bet. Grand Concourse Blvd. and Walton Ave. - E.170 Street from Wythe Pl. to Grand Concourse. | Reconstruction of Grand Concourse service roads between East 166 Street and East 171 Street including widening of median/malls, installation of bicycle lanes and landscaping and sewer work. Also, combined sewer work included in the following locations. - Grand Concourse Blvd. from E.166 Street to E.165 Street - Grand Concourse Blvd. from E.171 Street to E.172 Street - E.168 Street from Grand Concourse Blvd. to Grandview Pl. - Clarke Pl. bet. Grand Concourse Blvd. and Walton Ave. - Marcy Pl. bet. Grand Concourse Blvd. and Walton Ave. - Elliot Pl. bet. Grand Concourse Blvd. and Walton Ave. - E.170 Street from Wythe Pl. to Grand Concourse. | Bronx |  | Transportation | Substantial Completion | Street Reconstruction | Standard | Requirement Contract | DDC Managed/Consultant | PIMS | FALSE |  | 2009 | 2014 |  | DDC
HWXP136B | HWXP136B | Y | Infrastructure | BRONX & N. QUEENS | RECONSTRUCTION OF GRAND CONCOURSE, PHASE 3 | RECONSTRUCTION OF THE GRAND CONCOURSE - PHASE 3, BRONX | RECONSTRUCTION OF THE GRAND CONCOURSE - PHASE 3, BRONX | Bronx |  | Transportation | Construction 0-25% | Street Reconstruction | Critical | In-House/Consultant | DDC Managed/Consultant | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWXP136C | HWXP136C | Y | Infrastructure | BRONX & N. QUEENS | RECONSTRUCTION OF GRAND CONCOURSE - PHASE 4 | RECONSTRUCTION OF GRAND CONCOURSE FROM E 175 ST TO EAST FORDHAM RD- PHASE 4, BX | RECONSTRUCTION OF GRAND CONCOURSE FROM E 175 ST TO EAST FORDHAM RD- PHASE 4, BX | Bronx |  | Transportation | Final Design | Street Reconstruction | Critical | Requirement Contract | Standard Consultant | PIMS | FALSE |  | 2016 | 2018 |  | DDC
HWXP138 | HWXP138 | Y | Infrastructure | Bronx & N. Queens | Reconstruction of Hollers Ave | Reconstruction of the Hollers Ave Area, Including, improved, proper drainage, extensive regrading, curbs, sidewalks, and roadway construction. Project Limits: Hollers Ave from Conner Street to Steenwick Ave De Laval Ave from New England Thruway to Boston Rd Rombouts Ave from New England Thruway to Boston Rd Steenwick Ave from New England Thruway to Boston Rd and Sewer only on Merritt Ave from Hollers Ave to New England Thruway Limits: Hollers Ave, De Laval Ave, Rombouts Ave, Steenwick Ave, and City Line. | Street reconstruction including improved drainage, new curbs and sidewalks. | Bronx |  | Trans. & Env. Protection | On-Hold | Street Reconstruction | Standard | Standard Consultant | Requirements TO | PIMS | TRUE |  |  |  |  | DDC
HWXP138 | SEX002237 | Y | Infrastructure | Bronx & N. Queens | Reconstruction of Hollers Ave | Reconstruction of the Hollers Ave Area, Including, improved, proper drainage, extensive regrading, curbs, sidewalks, and roadway construction. Project Limits: Hollers Ave from Conner Street to Steenwick Ave De Laval Ave from New England Thruway to Boston Rd Rombouts Ave from New England Thruway to Boston Rd Steenwick Ave from New England Thruway to Boston Rd and Sewer only on Merritt Ave from Hollers Ave to New England Thruway Limits: Hollers Ave, De Laval Ave, Rombouts Ave, Steenwick Ave, and City Line. | Street reconstruction including improved drainage, new curbs and sidewalks. | Bronx |  | Trans. & Env. Protection | On-Hold | Street Reconstruction | Standard | Standard Consultant | Requirements TO | PIMS | TRUE |  |  |  |  | DDC
HWXP2022 | HWXP2022 | Y | Infrastructure | Bronx & N. Queens | RECONSTRUCTION OF CONNER STREET BULKHEAD | Reconstruction of Bulkhead in the NYC DOT storage/facility yard at 3200 Conner Street. | Rebuild bulkhead at the DOT Connor Street storage facility. | Bronx |  | Transportation | Construction 75%-Subst. | Street Reconstruction | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
HWXPRATT | HWXPRATT | Y | Infrastructure | BRONX & N. QUEENS | Pratt Avenue Retaining Wall and Roadway Recon | The retaining wall along the segment of Pratt Avenue (Needham Ave to Dead End) shows multiple signs of damage. This includes cracking (long cracks run the entire height of the wall) and movement of the individual elements of the wall. The cracks and movement of the wall has allowed the backfill that supports the roadway to escape. The roadway within the project limits has experienced significant damage due to settlement of supporting materials. The proposed scope includes reconstruction of the roadway and retaining wall along this segment. | The retaining wall along the segment of Pratt Avenue (Needham Ave to Dead End) shows multiple signs of damage. This includes cracking (long cracks run the entire height of the wall) and movement of the individual elements of the wall. The cracks and movement of the wall has allowed the backfill that supports the roadway to escape. The roadway within the project limits has experienced significant damage due to settlement of supporting materials. The proposed scope includes reconstruction of the roadway and retaining wall along this segment. |  |  | Transportation | [5 empty] | PIMS | FALSE |  |  |  | 2017-09-18 07:00:25.7030000 +00:00
HWXRCPLZ | HWXRCPLZ | Y | Infrastructure | BRONX & N. QUEENS | RECONSTRUCTION OF ROBERTO CLEMENTE PLAZA X550.49 | Reconstruction of Roberto Clemente Plaza and other related roadway reconstruction work. | Reconstruction of Roberto Clemente Plaza and other related roadway reconstruction work. | Bronx |  | Transportation | Construction 75%-Subst. | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2009 | 2013 |  | DDC
HWXRCPLZA | HWXRCPLZA | Y | Infrastructure | BRONX & N. QUEENS | ROBERTO CLEMENTE PLAZA ARTWORK | This project will install permanent artwork for the recently designed Roberto Clements Plaza in the Bronx, NY. | This project will install permanent artwork for the recently designed Roberto Clements Plaza in the Bronx, NY. | Bronx |  | Transportation | Pre-Design/PrgDevelopment | Other | Standard |  |  | PIMS | FALSE |  |  |  |  | DDC
HWXS311V1 | HWXS311V1 | Y | Infrastructure | BRONX & N. QUEENS | CLIFFORD PLACE STEP STREET | Rehabilitation of Clifford Place Step Street Retaining Wall. | Rehabilitation of Clifford Place Step Street Retaining Wall. | Bronx |  | Transportation | Construction 50-75% | Other | Standard | Requirements TO | Requirements TO | PIMS | FALSE |  | 2011 | 2016 |  | DDC
HWXS411 | HWXS411 | Y | Infrastructure | BRONX & N. QUEENS | WEST 229TH ST STEP STREET, BRONX | WEST 229TH ST STEP STREET, BRONX Reconstruction of West 229th Street Step Street from Heath Avenue to Kingsbridge Terrace. | Reconstruction of W229th Street Step Street from Heath Avenue to Kingsbridge Terrace. | Bronx |  | Transportation | Construction 0-25% | Street Reconstruction | Critical |  |  | PIMS | FALSE |  | 2014 | 2017 |  | DDC
HWXS511 | HWXS511 | Y | Infrastructure | BRONX & N. QUEENS | RECONSTRUCTION OF WEST TREMONT AVE STEP ST, BRONX | RECONSTRUCTION OF WEST TREMONT AVE STEP STREET, BRONX Reconstruction of West Tremont Avenue Step Street from Sedgwick Avenue to Fordham Place | Reconstruction of West Tremont Avenue Step Street from Sedgwick Avenue to Fordham Place | Bronx |  | Transportation | Construction Procurement | Street Reconstruction | Critical | Requirement Contract | DDC Managed | PIMS | FALSE |  | 2015 | 2017 |  | DDC
HWXS611 | HWXS611 | Y | Infrastructure | BRONX & N. QUEENS | WEST 231ST STEP ST RECONSTRUCTION | RECONSTRCUTION OF WEST 231ST STEP STREET, BRONX. REPLACEMENT-IN-KIND OF THE CENTRAL STAIRWAY, DRAINAGE IMPROVEMENTS, ETC. | RECONSTRCUTION OF WEST 231ST STEP STREET, BRONX. REPLACEMENT-IN-KIND OF THE CENTRAL STAIRWAY, DRAINAGE IMPROVEMENTS, ETC. | Bronx |  | Transportation | Pre-Design/PrgDevelopment | Street Reconstruction | Critical |  |  | PIMS | FALSE |  |  | 2018 |  | DDC
HYDREST04 | HYDREST04 | Y | Infrastructure | BROOKLYN | S/W RESTORATION - FIRE HYDRANTS/CATCH BASINS, CW | SIDEWALK RESTORATION AROUNd FIRE HYDRANTS AND CATCH BASINS, CW | Sidewalk restoration around fire hydrants and catch basins, Citywide | Citywide |  | Environmental Protection | Construction 0-25% | Water | Critical | In-House | DDC Managed | PIMS | FALSE |  | 2014 | 2017 |  | DDC
HYDREST05 | HYDREST05 | Y | Infrastructure | MANHATTAN & CITYWIDE | SIDEWALK RESTORATION AROUND FIRE HYDRANTS | SIDEWALK RESTORATION AROUND FIRE HYDRANTS, CATCH BASINS AND MAN HOLES | SIDEWALK RESTORATION AROUND FIRE HYDRANTS, CATCH BASINS AND MANHOLES | Citywide |  | Environmental Protection | Compliance | Water | Standard | In-House | DDC Managed | PIMS | FALSE |  | 2017 | 2018 |  | DDC
HYDREST06 | HYDREST06 | Y | Infrastructure | MANHATTAN & CITYWIDE | ROADWAY SIDEWALK RESTORATION AROUND FIRE HYDRANTS | ROADWAY AND SIDEWALK RESTORATION OVER WATER MAIN AND SEWER REPAIRS AND AROUND HYDRANTS, CATCH BASINS, MANHOLES AND OTHER APPURTENANCES. | ROADWAY AND SIDEWALK RESTORATION OVER WATER MAIN AND SEWER REPAIRS AND AROUND HYDRANTS, CATCH BASINS, MANHOLES AND OTHER APPURTENANCES. |  |  | Environmental Protection | Pre-Design/PrgDevelopment | Water | Standard | In-House |  | PIMS | FALSE |  |  |  | 2017-09-09 15:33:16.8900000 +00:00
IFPM01CW | IFPM01CW | Y | Infrastructure | MANHATTAN & CITYWIDE | INSTALLATION OF INTERIM FLOOD PROTECTION MEASURES | INSTALLATION OF INTERIM FLOOD PROTECTION MEASURES AT VARIOUS LOCATIONS, INCLUDING REPAIR AND DEINSTALLATION, CITYWIDE | INSTALLATION OF INTERIM FLOOD PROTECTION MEASURES AT VARIOUS LOCATIONS, INCLUDING REPAIR AND DEINSTALLATION, CITYWIDE |  |  | Emergency Management | Construction Procurement | Other | Critical | None | Requirements TO | PIMS | FALSE |  |  |  | 2017-09-09 15:33:20.6300000 +00:00
JJ1FACREN | JJ1FACREN | Y | Public Buildings | Corrections | FACILITIES RENOVATIONS | The project includes but it is not limited to: bedrooms wall reinforcement; bathroom reconfiguration; functional changes of existing dorm space to Psychiatric Medical suite; upgrade of all systems: lighting, roofing, plumbing, mech., electrical, security, fire alarm and fire suppression systems; upgrade and update of : existing classrooms, commercial kitchen & kitchen equipment; renovation of entire exterior recreational area to reflect shade areas and upgrade of the landscaping. The building systems need urgent upgrade. They are subject to heavy use and they are not efficient nor adequate to accommodate current facility demands. The function of the some areas needs to be renovated /retrofitted to accommodate the Juvenile Program new needs such as the medical suite, including Psychiatric services, among others. The kitchen equipment and layout needs upgrade to follow the current food prep, storage and cooking process. |  | Bronx |  |  | Construction 50-75% | Renovation | Mayoral Initiative | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LBC05BVRF1 | LBC05BVRF | Y | Public Buildings | Libraries | Brownsville Parapet Rehabilitation | Parapet Reconstruction | Rehabilitate building parapet. |  |  | Libraries-BPL | Maintenance | Renovation | Standard | Requirements TO | Requirements TO | Project Info | FALSE |  |  |  |  | DDC
LBC10CDHC1 | LBC10CDHC | Y | Public Buildings | LIBRARIES | Clarendon HVAC & BMS Upgrade | HVAC and Boiler Replacement and BMS Installations | HVAC and Boiler Replacement and BMS Installations | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC10LDHC | LBC10LDHC | Y | Public Buildings | Libraries | Leonard Boiler Replacement | Boiler Replacement and BMS system upgrade | Replace boiler and upgrade Building Management System. |  |  | Libraries-BPL | Substantial Completion | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE
LBC10NUHC | LBC10NUHC | Y | Public Buildings | LIBRARIES | New Utrecht Fire Alarm, HVAC & BMS upgrade | Fire Alarm ,HVAC, BMS system upgrade, and Interior and Exterior betterment at the New Utrecht Branch Library New Ultrecht Branch Library 1743 86th Street Brooklyn, NY 11214 Block: 6343 Lot: 64 C of O in BIN: Yes | Fire Alarm ,HVAC, BMS system upgrade, and Interior and Exterior betterment at the New Utrecht Branch Library | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC11BBHC | LBC11BBHC | Y | Public Buildings | Libraries | Brighton Beach HVAC & BMS Upgrade | HVAC Replacement and new BMS system | Replace HVAC and building management systems. |  |  | Libraries-BPL | Maintenance | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LBC11BBRF | LBC11BBRF | Y | Public Buildings | Libraries | Brighton Beach Roof Replacement | Roof replacement & related work | Replace roof and perform related work. |  |  | Libraries-BPL | Maintenance | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC11UPRF | LBC11UPRF | Y | Public Buildings | Libraries | Ulmer Park Roof Replacement | Roof replacement and related repair work | Ulmer park Library Branch replacement of roof and related work |  |  | Libraries-BPL | Maintenance | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC12ARRF | LBC12ARRF | Y | Public Buildings | Libraries | Arlington Roof Replacement | Roof Replacement of Existing Carnegie asphalt shingles and 3 ply roof. 3 ply roof will be replaced by Kemper roof | Replace roof. |  |  | Libraries-BPL | Maintenance | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE
LBC12EPRF | LBC12EPRF | Y | Public Buildings | Libraries | Eastern Parkway Roof Replacement | Roof Replacement Work | Replace roof and perform related work. |  |  | Libraries-BPL | Acceptance/Final Completion | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC12P2FS | LBC12P2FS | Y | Public Buildings | Libraries | Eastern Parkway Fire Alarm Upgrade | Fire Safety for Eastern parkway Library. Eastern Parkway Branch Library (Carnegies) 1044 Eastern Parkway Brooklyn, NY 11213 Block: 1396 Lot: 6 C of O in BIN: Yes | Replace fire and safety systems. |  |  | Libraries-BPL | Construction 75%-Subst. | Renovation | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LBC12STHC | LBC12STHC | Y | Public Buildings | LIBRARIES | Saratoga HVAC Replacement | Boiler, HVAC, BMS replacement at the Saratoga Branch Library | Saratoga Library Boiler, HVAC, BMS replacement | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC12WIRF | LBC12WIRF | Y | Public Buildings | LIBRARIES | Washington Irving roof replacement | Upgrade the exterior roofing system, replacement of deteriorated roof shingles and all copper flashings, reconstruction of entire drainage system. | Upgrade the exterior roofing system, replacement of deteriorated roof shingles and all copper flashings, reconstruction of entire drainage system. | Brooklyn |  | Libraries-BPL | Schematic Design | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC13BPRF | LBC13BPRF | Y | Public Buildings | LIBRARIES | Borough Park Major Renovation | Interior and Exterior Rehabilitation HVAC Replacement New Boiler and BMS Life Safety Systems New Roof and façade New interior program layout | On hold by client at 100% SD phase. | Brooklyn |  | Libraries-BPL | Schematic Design | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC13NLBR | LBC13NLBR | Y | Public Buildings | Libraries | New Lots Roof & Facade Renovation | New Lots Branch Library Rehabilitation | Roof and facade renovation. |  |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE
LBC14ARHC | LBC14ARHC | Y | Public Buildings | LIBRARIES | Arlington Boiler & BMS Upgrade | Replace the boiler and associated mechanical equipment and install BMS. | Arlington Library Replacement of the boiler and associated mechanical equipment and install BMS. | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC14BVHC | LBC14BVHC | Y | Public Buildings | LIBRARIES | Brownsville HVAC & BMS Upgrade | HVAC Replacement and new BMS | HVAC Replacement and new BMS | Brooklyn |  | Libraries-BPL | Final Design | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC14CNHC | LBC14CNHC | Y | Public Buildings | LIBRARIES | Brooklyn Central HVAC Replacement | Rooftop HVAC Equipment Replacement | CD Kick off meeting scheduled for 2/28/17. | Brooklyn |  | Libraries-BPL | Final Design | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC14CYHC | LBC14CYHC | Y | Public Buildings | LIBRARIES | Cypress Hills HVAC Upgrade | Replacement of HVAC system equipment and installation of new BMS | Replacement of HVAC system equipment and installation of new BMS | Brooklyn |  | Libraries-BPL | On-Hold | Other | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC14LDRF | LBC14LDRF | Y | Public Buildings | LIBRARIES | Leonard Roof Replacement | Roof Replacement | Leonard Library Roof Replacement | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC14MDBR | LBC14MDBR | Y | Public Buildings | Libraries | Midwood Plaza Renovation | Demo existing plaza and provide new paving, landscape, seating, lighting, and security camera. | Rehabilitate plaza with new paving, landscape, seating, lighting, and install security cameras. |  |  | Libraries-BPL | Acceptance/Final Completion | Renovation | Standard | In-House | JOCs | PIMS | FALSE |  |  |  |  | DDC
LBC14NLHC | LBC14NLHC | Y | Public Buildings | Libraries | New Lots HVAC & BMS Upgrade | HVAC Replacement & BMS System | Replace HVAC system and install a new BMS (building management system). |  |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | JOCs | PIMS | FALSE
LBC15BWHC | LBC15BWHC | Y | Public Buildings | Libraries | Bushwick HVAC Upgrade | HVAC Replacement and new BMS | Replace HVAC and install new Building Management System (BMS). |  |  | Libraries-BPL | On-Hold | Other | Standard | Requirements TO | DDC Managed | PIMS | FALSE
LBC15CHHC | LBC15CHHC | Y | Public Buildings | LIBRARIES | Clinton Hill HVAC Controls | Installation of HVAC, additional temperature controls | Installation of HVAC, additional temperature controls | Brooklyn |  | Libraries-BPL | Cancelled Project | Upgrade | Standard | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LBC15FBHC | LBC15FBHC | Y | Public Buildings | LIBRARIES | Flatbush Heating & Cooling Replacement | Heating and cooling replacement work | Heating and cooling replacement work | Brooklyn |  | Libraries-BPL | On-Hold | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC15FLRF | LBC15FLRF | Y | Public Buildings | LIBRARIES | Flatlands Roof Replacement | Building Envelope Rehabilitation | Building Envelope Rehabilitation | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC15GSRF | LBC15GSRF | Y | Public Buildings | LIBRARIES | Gravesend Roof Replacement | Rehabilitation of the building envelope | Gravesend Library Rehabilitation of the building envelope | Brooklyn |  | Libraries-BPL | Substantial Completion | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC15MPHC | LBC15MPHC | Y | Public Buildings | LIBRARIES | Mapleton Boiler/BMS System Replacement | Replacement of boiler and new BMS system. | Defunded Boiler scope. Project includes new BMS only. | Brooklyn |  | Libraries-BPL | Design Development | Upgrade | Standard | Requirements TO | Standard Consultant | PIMS | FALSE |  |  |  |  | DDC
LBC16MBHC | LBC16MBHC | Y | Public Buildings | Libraries | Mill Basin HVAC Upgrade | Replace heating and cooling equipment. Installation of new BMS | Mill Basin Library Branch replacement of HVAC equipment and installation of new BMS |  |  | Libraries-BPL | Substantial Completion | Upgrade | Critical | In-House | JOCs | PIMS | FALSE |  |  |  |  | DDC
LBC16MD2F | LBC16MD2F | Y | Public Buildings | LIBRARIES | Midwood 2nd Floor Renovation | 2nd Floor Interior Renovation to the Branch's Childrens Library. | 75% SD revised schemes for BPL review and approval. | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC16MPHC | LBC16MPHC | Y | Public Buildings | LIBRARIES | Mapleton HVAC Upgrade | Replacement of the existing cooling equipment | CD kick off meeting pending approved DDC A+E drawings revisions. | Brooklyn |  | Libraries-BPL | Design Development | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBC16PSGD | LBC16PSGD | Y | Public Buildings | Libraries | Park Slope Garden | New Reading Circle and Garden | Park Slope Library Branch - new reading circle and garden |  |  | Libraries-BPL | Maintenance | Renovation | Standard | In-House | JOCs | Project Info | FALSE |  |  |  |  | DDC
LBC17MPGD | LBC17MPGD | Y | Public Buildings | LIBRARIES | Mapleton Library Landscape & Exterior Improvements | MAPLETON GARDEN RENOVATION | Create an accessible connection between the library and garden. New lighting, new landscape, new site drainage, new hardscape and children's area. | Brooklyn |  | Libraries-BPL | Design Development | Renovation | Critical | In-House | Requirement Contract | PIMS | FALSE |  |  |  |  | DDC
LBC17MRAD | LBC17MRAD | Y | Public Buildings | LIBRARIES | Marcy Renovation of Meeting Room | Renovation of meeting room, providing ADA accessibility to meeting room. | Marcy Library meeting room renovation. | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | In-House | Requirement Contract | PIMS | FALSE |  | 2017 | 2019 |  | DDC
LBC17PCFS | LBC17PCFS | Y | Public Buildings | LIBRARIES | Pacific Fire Safety Upgrades | Pacific Fire Safety | New fire alarm system for Pacific Library. | Brooklyn |  | Libraries-BPL | Pre-Preliminary Design | Upgrade | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
LBCA07FBH3 | LBCA07FBH | Y | Public Buildings | Libraries | Flatbush Parapet & Masonry Reconstruction | Parapet and masonry Reeconstruction | Flatbush Library Branch restoration of building parapet and exterior masonry |  |  | Libraries-BPL | Substantial Completion | Renovation | Standard | Requirements TO | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
LBK13EFBR | LBK13EFBR | Y | Public Buildings | LIBRARIES | East Flatbush Major Rehabilitation | New Roof New HVAC and BMS New Boiler New interior Program layout. | 12/5/16: Design revision presentation scheduled for 12/7. PDC to be submitted January for February hearing. Mechanical system revision in progress. | Brooklyn |  | Libraries-BPL | Final Design | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBK14DRRF | LBK14DRRF | Y | Public Buildings | LIBRARIES | Dyker Roof Replacement | Roof Replacement | Dyker Library Roof Replacement | Brooklyn |  | Libraries-BPL | Maintenance | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBK15BDHC | LBK15BDHC | Y | Public Buildings | LIBRARIES | Bedford HVAC Upgrade | HVAC Upgrade at Bedford Library | HVAC Upgrade at Bedford Branch Library. | Brooklyn |  | Libraries-BPL | Design Development | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBK15BRRF | LBK15BRRF | Y | Public Buildings | LIBRARIES | Bay Ridge Building Envelope Upgrade | Rehabilitation of the Building Envelope | Bay Ridge Library Rehabilitation of building exterior. | Brooklyn |  | Libraries-BPL | Construction 0-25% | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBK15WTHC | LBK15WTHC | Y | Public Buildings | LIBRARIES | Windsor Terrace HVAC Upgrade | HVAC Replacement and Installation of BMS (Building Management System) | Windsor Terrace New HVAC installation and Building Management systems. | Brooklyn |  | Libraries-BPL | Design Development | Upgrade | Standard | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LBK16CIBR | LBK16CIBR | Y | Public Buildings | Libraries | Brooklyn Public Library0-Design Services | Upgrade and Comprehensive rehabilitation to accommodate the current programming need for the Coney Island Branch Library. This project is intended to rehabilitate the current library space on the second floor community room located on the north east end of the library. | Upgrade and Comprehensive rehabilitation to accommodate the current programming need for the Coney Island Branch Library. This project is intended to rehabilitate the current library space on the second floor community room located on the north east end of the library. | Brooklyn |  | Libraries-BPL | Final Design | Renovation | Standard | Requirement Contract | Individual Contract(s) | PIMS | FALSE |  |  |  |  | DDC
LBKA05RUG | LBKA05RUG | Y | Public Buildings | Libraries | Rugby Interior Renovation | Interior Renovation for the Rugby Branch Library. New HVAC upgrade, New Roof, New Temp Space for Library | Rugby Library Branch renovation of interior and replacement of HVAC equipment |  |  | Libraries-BPL | Construction 0-25% | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM08DKRF | LBM08DKRF | Y | Public Buildings | Libraries | DeKalb Roof Replacement | Roof Replacement & Related Repair Work | Replace roof and perform related repair work. |  |  | Libraries-BPL | Maintenance | Renovation | Standard | In-House | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
LBM08WBRF | LBM08WBRF | Y | Public Buildings | Libraries | Williamsburg Roof Replacement | Roof Replacement & related repair works | Replace roof and perform related repair work. |  |  | Libraries-BPL | Maintenance | Renovation | Standard | Standard Consultant | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
LBM13ARFS | LBM13ARFS | Y | Public Buildings | LIBRARIES | Arlington Fire Safety Upgrade | Replacement of Fire Safety and Fire detection systems @Arlington Branch Library, BPL | Arlington Library Replacement of Fire Safety and Fire detection systems | Brooklyn |  | Libraries-BPL | On-Hold | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM13ARHC | LBM13ARHC | Y | Public Buildings | LIBRARIES | Arlington HVAC & BMS System | Replace HVAC system. Install BMS system. | Arlington Library HVAC system Replacement and Install BMS system. | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM13CGHC | LBM13CGHC | Y | Public Buildings | LIBRARIES | Carroll Gardens HVAC Replacement | HVAC Replacement at Carroll Gardens Library | HVAC Replacement at Carroll Gardens Branch Library | Brooklyn |  | Libraries-BPL | On-Hold | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM13CHFS | LBM13CHFS | Y | Public Buildings | Libraries | Clinton Hill Fire Safety Upgrades | Replacement of Fire Safety and Fire detection systems @ CLINTON HILL Branch Library, BPL BLOCK:1945 LOT:36 | Replace fire safety and detection systems. |  |  | Libraries-BPL | Maintenance | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LBM13CYFS | LBM13CYFS | Y | Public Buildings | LIBRARIES | Cypress Hill Fire Safety Upgrades | Replacement of fire safety and fire detection system and equipment. | Replacement of fire safety and fire detection system and equipment for Cypress Hill Branch Library | Brooklyn |  | Libraries-BPL | Design Development | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM13DKBR | LBM13DKBR | Y | Public Buildings | LIBRARIES | Dekalb Major Renovation | Renovation of lower level, MEP infrastructure upgrade, window replacmeent, Façade rehabilitation, landscaping and fencing. | 100% DD delivery mid August | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM13DRFS | LBM13DRFS | Y | Public Buildings | LIBRARIES | Dyker Fire Safety Upgrades | Replacement of Fire Safety and Fire detection systems @DYKER Branch Library, BPL | Dyker Library fire safety and fire detection systems Replacement. | Brooklyn |  | Libraries-BPL | Maintenance | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LBM13FLHC | LBM13FLHC | Y | Public Buildings | LIBRARIES | Flatlands HVAC, BMS & Fire Safety Upgrades | Flatlands HVAC Boiler Replacement and BMS and Fire Alarm System | Flatlands HVAC Boiler Replacement and BMS and Fire Alarm System | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM13LDHC | LBM13LDHC | Y | Public Buildings | LIBRARIES | Leonard Library HVAC Replacement | HVAC replacement and new BMS | HVAC replacement and new BMS | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM13RDFS | LBM13RDFS | Y | Public Buildings | LIBRARIES | Ryder Fire Safety Upgrades | Replacement of Fire Safety and Fire detection systems @Arlington Branch Library, BPL BLOCK:6548 LOT:37 | Ryder Library Replacement of Fire Safety Detection System | Brooklyn |  | Libraries-BPL | Construction 0-25% | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LBM13SAFS | LBM13SAFS | Y | Public Buildings | LIBRARIES | Stone Avenue Fire Safety Upgrades | Replacement of Fire Safety and Fire detection systems @ STONE AVENUE Branch Library, BPL BLOCK:3794LOT:18 | Stone Avenue Library Fire Alarm safety system upgrade | Brooklyn |  | Libraries-BPL | Construction 75%-Subst. | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LBM13UPFS | LBM13UPFS | Y | Public Buildings | Libraries | Ulmer Park Fire Safety Upgrades | Fire Alarm Upgrade at the Ulmer Park Branch Library, BPL BLOCK:6897 LOT:34 | Fire Alarm upgrade at the Ulmer Park Branch Library. |  |  | Libraries-BPL | Maintenance | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LBM14BWRF | LBM14BWRF | Y | Public Buildings | LIBRARIES | Bushwick Roof Replacement | Roof Replacement at Bushwick Branch Library | Bushwick Library Roof Replacement at Bushwick Branch Library | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM14CDRF | LBM14CDRF | Y | Public Buildings | LIBRARIES | Clarendon Roof Replacement | Roof and Skylight replacement for the Clarendon Library. | Roof and Skylight replacement for the Clarendon Library. | Brooklyn |  | Libraries-BPL | Substantial Completion | Upgrade | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM14MRHC | LBM14MRHC | Y | Public Buildings | Libraries | Marcy HVAC & BMS Upgrade | Replacement of the HVAC equipment and installation of a BMS | Replace existing HVAC equipment and install a new Building Management System. |  |  | Libraries-BPL | Substantial Completion | Renovation | Critical | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LBM14WTRF | LBM14WTRF | Y | Public Buildings | LIBRARIES | Windsor Terrace Roof Replacement | Roof replacement and associated work. Minimal façade. | Windsor Terrace Roof Replacement and perform facade restoration work. | Brooklyn |  | Libraries-BPL | Acceptance/Final Completion | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM14WWRF | LBM14WWRF | Y | Public Buildings | LIBRARIES | Walt Whitman Roof Replacement | Roof replacement and associated masonry. | Walt Whitman Library Roof replacement and associated masonry. | Brooklyn |  | Libraries-BPL | Construction Procurement | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM15GBRF | LBM15GBRF | Y | Public Buildings | LIBRARIES | Gerritsen Beach Building Envelope Rehabilitation | Design and construction of roof and necessary enclosure work. | Design and construction of roof and necessary enclosure work. | Brooklyn |  | Libraries-BPL | On-Hold | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM15MPRF | LBM15MPRF | Y | Public Buildings | LIBRARIES | Mapleton Building Envelope Rehabilitation | Design and construction for the rehabilitation of the building envelope. | Awaiting amended design CP by OMB to proceed with design of 100% DD documents. | Brooklyn |  | Libraries-BPL | Design Development | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM15RDHC | LBM15RDHC | Y | Public Buildings | Libraries | Ryder HVAC Upgrade | HEATING AND COLLING REPLACEMENT AT RYDER BRANCH LIBRARY- BROOKLYN PUBLIC LIBRARY | Replace HVAC systems. |  |  | Libraries-BPL | On-Hold | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE
LBM15RDRF | LBM15RDRF | Y | Public Buildings | LIBRARIES | Ryder Building Envelope Rehabilitation | BUILDING ENVELOPE REHABILITATION AT RYDER BRANCH LIBRARY, BROOKLYN PUBLIC LIBRARY Block#;6548 Lot#;37 BIN# 3172049 | Ryder Library Building Envelope Rehabilitation | Brooklyn |  | Libraries-BPL | Design Development | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LBM15WTFS | LBM15WTFS | Y | Public Buildings | LIBRARIES | Windsor Terrace Fire Alarm Upgrade | Provision of a New Code-compliant Fire Alarm System | Windsor Terrace Library Provision of a New Code-compliant Fire Alarm System | Brooklyn |  | Libraries-BPL | Construction 0-25% | Upgrade | Standard | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LBM16GEEC | LBM16GEEC | Y | Public Buildings | PASS THROUGH | Greenpoint Public Library | This project is an effort to provide Greenpoint with a library that is sized appropriately for the growing community, fosters environmental learning, and supports the ways in which patrons are increasingly looking to engage with their library and each other. |  |  |  | Libraries-BPL | Construction Procurement | New Construction | Standard | Pass Through | Pass Through | Project Info | FALSE |  |  |  | 2017-09-15 11:07:53.7600000 +00:00
LBM16GSFC | LBM16GSFC | Y | Public Buildings | LIBRARIES | Gravesend Façade & Foundation Upgrade | Replace and Upgrade Building Envelope as well as building drainage | Gravesend Library Branch replacement and upgrade to building exterior as well as building drainage | Brooklyn |  | Libraries-BPL | On-Hold | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNBXA08LS4 | LNBXA08LS | Y | Public Buildings | Libraries | Mott Haven Fire Alarm Upgrade | Fire Alarm Mott Haven Branch Library 321 E. 140th street Bronx, NY 10454 Bronx Block 2315 Lot 18 | Install new fire alarm life safety system. |  |  | Libraries-NYPL | Construction 75%-Subst. | Upgrade | Standard | Requirements TO | JOCs | Project Info | FALSE |  |  |  |  | DDC
LNBXA08LS8 | LNBXA08LS | Y | Public Buildings | Libraries | City Island Fire Alarm Upgrade | Fire and life safety system installation. | Install new fire and life safety systems. |  |  | Libraries-NYPL | Maintenance | Upgrade | Standard | JOCS | JOCs | Project Info | FALSE |  |  |  |  | DDC
LNC002ROS | LNC002ROS | Y | Public Buildings | LIBRARIES | Charleston New Library | New Branch Library will be part of Charleston Mixed Use Development Site in Staten Island. | New Branch Library will be part of Charleston Mixed Use Development Site in Staten Island | Staten Is. |  | Libraries-NYPL | Cancelled Project | New Construction | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNC005CC3 | LNC005CC2 | Y | Public Buildings | Libraries | Countee Cullen HVAC Upgrade | PROJECT CONSISTS OF HVAC REPLACEMENT ONLY Installation of new energy-efficient windows and replacement of HVAC system. | Install new energy efficient HVAC system. |  |  | Libraries-NYPL | Acceptance/Final Completion | Renovation |  | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCA09TRE | LNCA09TRE | Y | Public Buildings | Libraries | Tremont Fire Alarm Upgrade | Upgrade Fire Alarm System, New Emergency Lighting, New Sprinkler Installation | Upgrade fire alarm system; install new sprinkler system; install new emergency lighting. |  |  | Libraries-NYPL | Maintenance | Upgrade | Critical | Requirements TO | JOCs | PIMS | FALSE
LNCA10115A | LNCA10115 | Y | Public Buildings | LIBRARIES | 115th Street Basement Slab and Boiler Replacement | RECONSTRUCTION OF BASEMENT SLAB | 115th Street Library Rehabilitation of deteriorated basement slab. | Manhattan |  | Libraries-NYPL | Final Design | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNC115REN2 | LNC115REN | Y | Public Buildings | Pass Through | 115 ST. ADOPT A BRANCH RENOVATION | General renovation of the exterior and interior of the branch library, to provide access for the disabled, and to improve public and staff spaces. Exterior: ADA Compliant Entry ( Doors, Steps, Foyer ) Window Restoration / Replacement ( to include insect and security screens, solar shades) -Façade : Repair / Re-point as necessary, Clean and apply anti-Graffiti coating. -Sidewalk Repair / Replacement -Repair of Upper Roof, Drains and Leaders -Banner Pole – restore / replace -Exterior lighting – evaluate and upgrade if necessary, current lighting for patrons, façade, banner and security. Interior -ADA access to all floors ( lower level – 3rd Floor)- install elevator -New Central Circulation Desk with contiguous staff workroom. ADA compliant radio frequency book theft detection system. -New layouts for the Adult, Young Adult, Staff Work Room, Staff Lounge and Children’s sections. These shall include rearranging furniture, shelving, computer stations, office space, story hour room, reference areas to meet today’s needs. -Community Room and Staff Lounge to be moved from basement to 3rd floor. -Lower Level to be used for Staff / Community activities ( review current CLASP, CRW, ESOL etc. programs for requirements at this location). -Shelving - reconfigure layout, refinish and rework to accommodate 12” books. -Layout and Install all stations and wiring for Tel. / Data systems ( see special requirements of NYPL). -Installation of new lighting, upgrade electric panels, new intrusion alarm, expand and install new fire alarm. -Installation of new finishes for ceilings, walls, floors. | Provide for the full renovation of the Library as required to improve circulation and operations |  |  | Libraries-NYPL | Substantial Completion | Renovation | Standard | Pass Through | Pass Through | PIMS | FALSE |  |  |  |  | DDC
LNC2STAPL2 | LNC2STAPL | Y | Public Buildings | Libraries | Stapleton Branch Library - ROOF | Roof Reconstruction of the Carnegie building | Reconstruction of the roof on this historic Carnegie building. |  |  | Libraries-NYPL | Acceptance/Final Completion | Renovation | Standard | Requirements TO | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
LNC4WLEX | LNC4WLEX | Y | Public Buildings | LIBRARIES | Woodlawn Heights Expansion & Interior Renovation | Through a 1,500 square foot addition and renovation of the existing building, this project is intended to enlarge, reorganize and modernize the existing branch library so it can meet current program needs. | Design Development documents due for submission on 9/22/2017. | Bronx |  | Libraries-NYPL | Design Development | New Construction | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA08BEL | LNCA08BEL | Y | Public Buildings | Libraries | Bloomingdale Elevator Upgrade | Replace and/or install ADA Elevator systems | Replace elevator in compliance with ADA regulations. |  |  | Libraries-NYPL | Maintenance | Other | Standard | Requirements TO | JOCs | PIMS | FALSE
LNCA08BEL1 | LNCA08BEL | Y | Public Buildings | Libraries | Belmont Elevator Upgrade | Elevator replacement | Replace elevator. |  |  | Libraries-NYPL | Maintenance | Upgrade | Standard | Requirements TO | JOCs | Project Info | FALSE
LNCA0996S | LNCA0996S | Y | Public Buildings | LIBRARIES | 96th Street Exterior Renovation | Exterior Renovation of the library, including masonry repointing, cleaning, new areaway railing and steps, new entrance stoop granite steps and cheek-walls. | 96th Street Library Exterior Rehabilitation work including: cleaning and repointing; new entrance stoop, stairway and railings. | Manhattan |  | Libraries-NYPL | Construction 0-25% | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA09BEL | LNCA09BEL | Y | Public Buildings | Libraries | Belmont Boiler Upgrade | Replacement of Existing Gas-Fired Boiler, Hydronic Specialties and Controls | Install a replacement gas fired boiler along with new hydronic devices and controls. |  |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCA10AGL | LNCA10AGL | Y | Public Buildings | LIBRARIES | Aguilar Facade Restoration | Restoration of Landmarked Façade. The consultant is to investigate the existing conditions of the (3-story high) building façade, and propose the means for the remediation of deterioration. | Aguilar Library Restoration of landmark building Façade. | Manhattan |  | Libraries-NYPL | Compliance | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA10EPH | LNCA10EPH | Y | Public Buildings | Libraries | Epiphany Elevator Upgrade | Elevator Replacement | Elevator replacement. |  |  | Libraries-NYPL | Maintenance | Upgrade | Standard | Standard Consultant | JOCs | PIMS | FALSE
LNCA10GRC | LNCA10GRC | Y | Public Buildings | Libraries | Grand Concourse Branch Library - ADA Accessibility | To determine ADA compliance issues and provide for improved accessibility at the entrance and other parts of the interior space. | Provide ADA compliant access at the main entrance and locations throughout the building. |  |  | Libraries-NYPL | Maintenance | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE
LNCA10JMB | LNCA10JMB | Y | Public Buildings | LIBRARIES | Jefferson Market Library Lobby Renovation | This interior renovation project provides for ADA work, including but not limited to the reconfiguration of 10th Street entrance, lift and staircase - work which inlcudes the design of new vertical transportation, and other general construction (drywalls, glazing, finishes, etc); reconfiguration of existing rest rooms per ADA, and creation of a new rest room on the 1st floor and/or lower level. | Jefferson Market Library Renovation work for ADA compliance including reconfiguration of the 10th Street entrance, reconfiguration of existing rest rooms and the addition of a new one. | Manhattan |  | Libraries-NYPL | Construction Procurement | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA10RIS | LNCA10RIS | Y | Public Buildings | LIBRARIES | Roosevelt Island Branch - New Branch Library | Interior build-out of ground floor of privately-owned commercial space, including complete new mechanical systems. | Roosevelt Island Branch - New Branch Library Interior build-out of ground floor privately-owned commercial space, including complete new mechanical systems. | Manhattan |  | Libraries-NYPL | Construction Procurement | New Construction | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA10TH1 | LNCA10TH1 | Y | Public Buildings | Libraries | Todt Hill Air Conditioning Upgrade | REPLACEMENT OF 5 ROOF TOP A/C UNITS | Replace five rooftop A/C units. |  |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade | Standard | Standard Consultant | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCA10YRK | LNCA10YRK | Y | Public Buildings | Libraries | Yorkville Boiler and HVAC Replacement | Boiler and HVAC Replacement | Replace boiler and HVAC equipment. |  |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCA1167S | LNCA1167S | Y | Public Buildings | LIBRARIES | 67th Street HVAC and Roof Upgrade | HVAC AND ROOF REPLACEMENT | 67th Street Library roof and HVAC systems replacement. | Manhattan |  | Libraries-NYPL | Construction Procurement | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA11BEL | LNCA11BEL | Y | Public Buildings | Libraries | Belmont Roof Replacement | Roof replacement & related work | Belmont Library Branch replacement of roof and restoration of existing parapets |  |  | Libraries-NYPL | Construction 0-25% | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA11BLD | LNCA11BLD | Y | Public Buildings | LIBRARIES | Bloomingdale Interior Renovation | To provide design and construction of a Teen Room on the first floor; renovate bathrooms on the 2nd floor (budget permitting); and to provide a drinking fountain within the public space of the branch. | Bloomingdale Branch Library Interior Renovation, new teen space, renovation of 2nd floor bathrooms and new drinking fountain | Manhattan |  | Libraries-NYPL | Construction Procurement | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA11CCL | LNCA11CCL | Y | Public Buildings | LIBRARIES | Countee Cullen Elevator Upgrade | Complete Elevator Replacement to serve all five floors. | Countee Cullen Library to Install new elevator to serve all five floors of the facility. | Manhattan |  | Libraries-NYPL | Construction 0-25% | Upgrade | Standard | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNCA11SNV | LNCA11SNV | Y | Public Buildings | Libraries | Soundview Branch Library Exterior / Interior Reno | Interior and Exterior renovation, including renovation of the community room, new electrical and data wiring, improved security at entrance area (with new book drop, fencing, gate, etc). | The scope includes renovation of the community room, new electrical and data wiring, improved entrance security, new book drop and new fencing. |  |  | Libraries-NYPL | Maintenance | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE
LNCA12EPH | LNCA12EPH | Y | Public Buildings | LIBRARIES | Epiphany Exterior Renovation | Entrance vestibule reconstruction and façade restoration | Epiphany Library Facade restoration and reconstruction of entrance vestibule. | Manhattan |  | Libraries-NYPL | Design Development | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA12RSD | LNCA12RSD | Y | Public Buildings | Libraries | Riverside Branch Library - ADA Upgrade | Renovation of the main entrance to the library, a leased facility, to conform to ADA accessibility requirements. The existing entrance has two sets of double door and a revolving door (not ADA compliant). | Upgrade main entrance to conform to ADA accessibility requirements. |  |  | Libraries-NYPL | Maintenance | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE
LNCA12SWP | LNCA12SWP | Y | Public Buildings | Libraries | Seward Park Branch - Sidewalk & Vault replacement | EXISTING Vault & Concrete sidewalk Slab Replacement | Replace sidewalk and concrete sidewalk vault. |  |  | Libraries-NYPL | Compliance | Sidewalks | Standard | Standard Consultant | JOCs | PIMS | FALSE
LNCA13CCL | LNCA13CCL | Y | Public Buildings | LIBRARIES | Countee Cullen Boiler Upgrade | Boilers Replacement and related work as necessary. | Countee Cullen Library Branch installation of new boiler and associated plumbing and wiring. | Manhattan |  | Libraries-NYPL | Construction 75%-Subst. | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNCA13ECH | LNCA13ECH | Y | Public Buildings | LIBRARIES | Eastchester HVAC Upgrade | HVAC EQUIPMENT REPLACEMENT | Eastchester Library HVAC equipment replacement. | Bronx |  | Libraries-NYPL | Compliance | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA13GBR | LNCA13GBR | Y | Public Buildings | LIBRARIES | George Bruce Interior, Pr Roof and Boiler upgrade | Partial Interior/Exterior Rehabilitation, Façade - 18000 SF Floor - 10000SF | George Bruce branch Library - EXTERIOR & INTERIOR RENOVATION | Manhattan |  | Libraries-NYPL | Design Development | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  | 2018 | 2019 |  | DDC
LNCA13HAM | LNCA13HAM | Y | Public Buildings | LIBRARIES | Hamilton Fish Park Branch Renovation | Exterior and interior renovations, new HVAC, Fire Alarm.and new boiler | NYPL - Hamilton Fish Branch Library - Interior & Exterior Renovation, New Fire Alarm, HVAC, and Boiler | Manhattan |  | Libraries-NYPL | Design Development | Renovation | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA13HUD | LNCA13HUD | Y | Public Buildings | LIBRARIES | Hudson Park Interior & Exterior Renovation | Partial Interior Rehabilitation of the Hudson Park Branch Library, including new lighting, finishes, circulation desk, in the mean reading room on the 2nd floor, and improvements in the lower level Community Room. The design phase is to include a Pre-Preliminary report to determine an improve library layout in public areas, including better spatial layout for patron strollers. The Consultant is to coordinate the scope of work and proposed design in connection with several other current design/construction exterior restoration (#LNCA12HUD), an ADA interior renovation project at this branch (#LNCEM09HP), a library HVAC & FAS upgrade (#LNEM08HUD). | Hudson Park Library Branch partial rehabilitation of main reading room and community room with new lighting, finishes and circulation desk, New ADA Entrance renovation including new elevator and accessible bathrooms. | Manhattan |  | Libraries-NYPL | On-Hold | Renovation | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA13MLB | LNCA13MLB | Y | Public Buildings | LIBRARIES | Muhlenberg Elevator Upgrade | Replace existing deteriorated elevator with higher capacity and improved ventilation, and clear existing multiple violations . | Replace existing deteriorated elevator with higher capacity and improved ventilation, and clear existing multiple violations . |  |  | Libraries-NYPL | Final Design | Other | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA13MOR | LNCA13MOR | Y | Public Buildings | LIBRARIES | Morrisania Roof & HVAC Upgrade | HVAC replacement | Morrisania Library roof and HVAC systems replacement. | Bronx |  | Libraries-NYPL | Compliance | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA13MOT | LNCA13MOT | Y | Public Buildings | LIBRARIES | Mott Haven HVAC Upgrade | The replacement/rehabilitation of the existing HVAC system | Mott Haven Library HVAC system replacement. | Bronx |  | Libraries-NYPL | Compliance | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA13NAM | LNCA13NAM | Y | Public Buildings | LIBRARIES | New Amsterdam HVAC and Interior Upgrade | HVAC, Cooling Tower, partial interior renovation | New Amsterdam Library Branch installation of new HVAC system, cooling tower and a partial interior renovation. | Manhattan |  | Libraries-NYPL | Compliance | Renovation | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA13THL | LNCA13THL | Y | Public Buildings | Libraries | Todt Hill Westerleigh ADA/Restroom Upgrade | Installation of ADA Restrooms | Installation of ADA compliant restrooms. |  |  | Libraries-NYPL | Acceptance/Final Completion | Renovation | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCA13TRE | LNCA13TRE | Y | Public Buildings | Libraries | Tremont Boiler Upgrade | BOILER REPLACEMENT 1866 WASHINGTON AVE BX NY 10457 | Tremont Library Branch replacement of boiler, including associated plumbing and associated wiring |  |  | Libraries-NYPL | Substantial Completion | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCA1458S | LNCA1458S | Y | Public Buildings | Libraries | 58th Street - Electric & Fire Alarm Upgrade | Replace aging feeders and circuit wires and electrical panels. Additional electrical outlets and emergency lighting were requested. A fire alarm system was also requested. | New York Public Library at 58th St. upgrades with new electrical system and installation of new emergency lighting and fire alarm upgrades. |  |  | Libraries-NYPL | Substantial Completion | Renovation |  | In-House | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCA14MBG | LNCA14MBG | Y | Public Buildings | LIBRARIES | Muhlenberg HVAC & Related Work | Replacement of current HVAC equipment. | Muhlenberg Library Replacement of HVAC systems. | Manhattan |  | Libraries-NYPL | Final Design | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA14SPD | LNCA14SPD | Y | Public Buildings | LIBRARIES | Spuyten Duyvil Roof Replacement | New roof and drains. | New roof and drains | Bronx |  | Libraries-NYPL | Construction Procurement | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA15BLD | LNCA15BLD | Y | Public Buildings | Libraries | Bloomingdale Electrical Upgrade | Replacement of existing deteriorated or non-code compliant Electrical System (equipment, panels & wirings), installation of new outlets for new equipment. No Pre-Preliminary phase was required by the Client Agency (CPI) | Bloomingdale Library Branch electrical upgrade to include replacement of deteriorated electrical panels, wiring and installation of outlets for new equipment |  |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade | Standard | In-House/Consultant | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCA15EDW | LNCA15EDW | Y | Public Buildings | LIBRARIES | Edenwald HVAC Upgrade | HVAC Replacement at Edenwald Branch Library | HVAC Replacement at Edenwald Branch Library | Bronx |  | Libraries-NYPL | Design Development | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA15MOT | LNCA15MOT | Y | Public Buildings | LIBRARIES | Mott Haven Window Replacement | Window Replacement at Mott Haven Branch | DD Submission by Designer | Bronx |  | Libraries-NYPL | Final Design | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  | 2016 | 2017 |  | DDC
LNCA15RSD | LNCA15RSD | Y | Public Buildings | LIBRARIES | Riverdale Retaining Wall Waterproofing | Reconstruction, stabilization, and waterproofing of rear retaining wall, selective restoration of brick and concrete block facades, and gutter and leader replacement. | 9/1/2017 SD / DD documents have been submitted for final DD review. A&E has approved the submission, and a Constructability 'kick-off' meeting is scheduled for 9/7/2017. | Bronx |  | Libraries-NYPL | Final Design | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCA15SPK | LNCA15SPK | Y | Public Buildings | Libraries | Seward Park Boiler Replacement | Boiler Replacement | Seward Park Library Branch boiler replacement, including associated wiring and plumbing |  |  | Libraries-NYPL | Substantial Completion | Upgrade | Standard | In-House | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCAL15CC | LNCAL15CC | Y | Public Buildings | LIBRARIES | Countee Cullen Exterior Rehabiliation | Countee Cullen Branch Exterior Rehabilitation | Countee Cullen Library Branch rehabilitation of exterior facade and parapets. | Manhattan |  | Libraries-NYPL | Schematic Design | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCAL15CP | LNCAL15CP | Y | Public Buildings | LIBRARIES | Clason's Point ADA Restrooms | Provide a completely operational, code compliant, and dependable ADA accessible restroom for library. | Clason's Point Branch Library ADA Bathroom Renovation | Bronx |  | Libraries-NYPL | Construction 75%-Subst. | Upgrade | Standard | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNCAL15TV | LNCAL15TV | Y | Public Buildings | LIBRARIES | Tottenville Roof Replacement | Roof Replacement | Tottenville Library Branch roof replacement. | Staten Is. |  | Libraries-NYPL | Compliance | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCEA08GC | LNCEA08GC | Y | Public Buildings | Libraries | Edenwald Landscaping and Exterior Lighting | Edenwald-Reconstruct existing exterior planters. New exterior lighting along the building side at planter. West New Brighton Branch Library- Repair and repoint the building's exterior to prevent water infiltration, including chimney. Replace main entrance with new door, frame and sidelights. Regarded site in rear of the building to re-direct site drainage away from building. Update exterior lighting | Exterior upgrades to Edenwald and West New Brighton branch libraries including masonry repairs, landscaping and new lighting. |  |  | Libraries-NYPL | Cancelled Project | Renovation | Standard | Requirements TO | JOCs | PIMS | FALSE
LNCEA08GC1 | LNCEA08GC | Y | Public Buildings | Libraries | West New Brighton Exterior Envelope and Entrance | West New Brighton Branch Library-Repair and repoint the building exterior to prevent water infilitration,including chimney. Replace main entrance with new door, frame and sidelights. Upgrade exterior lighting | Building exterior rehabilitation and waterproofing; new main entrance; upgraded exterior lighting. |  |  | Libraries-NYPL | Acceptance/Final Completion | Renovation | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNCL15CAS | LNCL15CAS | Y | Public Buildings | LIBRARIES | Castle Hill Renovation Projects | INTERIOR & EXTERIOR RENOVATION New Fire Alarm, EXTERIOR BUILDING ENVLOPE AND HVAC | INTERIOR & EXTERIOR RENOVATION | Bronx |  | Libraries-NYPL | Design Development | Renovation | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCM10DCH | LNCM10DCH | Y | Public Buildings | Pass Through | New Data Center / HEISKELL | Due to the pending sale of NYPL's Donnell Library building located at 20 West 53rd Street, NYPL has vacated the building and moved all functions from the building in accordance with the terms of the sale. The Donnell Library housed NYPL's Data Center that contained network, communications and server hardware that serves the entire NYPL system providing services for staff and patrons and infrastructure for the material reservation system and catalogue seaches. A new data center was created on the cellar level of the Stephen A. Schwrazman Building located at 5th Avenue and 42nd Street, New York, NY 10018 to house network, communications and server hardware for the entire NYPL system. Office space was created for ITG personnel on the 5th floor of the Andrew Heiskell Braille and Talking book Library located at 40 west 20th Street, New York, NY 10011 and will house NYPL's IT Helpdesk and Command Center. | Construct a new data center on the cellar level of the Stephen A. Schwartzman Building to house network, communications and server hardware for the entire NYPL system. Create office space for ITS personnel, including the Helpdesk and Command Center, on the 5th floor of the Andrew Heiskell Braille and Talking book Library located at 40 west 20th Street. |  |  | Libraries-NYPL | Substantial Completion | Renovation | Standard |  | Pass Through | PIMS | FALSE |  |  |  |  | DDC
LNCM10WCH | LNCM10WCH | Y | Public Buildings | LIBRARIES | New Westchester Square | New Branch Library building 12,000 sq,ft, and demolition of existing Storage building and bridge to Huntington Free Library | DDC Constructability comments anticipated by 5/31/17. Anticipated Construction Budget shortfall of $600k. Funding required to submit initial Construction CP. | Bronx |  | Libraries-NYPL | Compliance | New Construction | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCM10WCH1 | LNCM10WCH | Y | Public Buildings | Libraries | New Westchester Square (ULURP) | New Westchester Square ULURP process | NEW Westchester Square Library branch ULURP |  |  | Libraries-NYPL | Acceptance/Final Completion | Other | Standard | Requirements TO | None | Project Info | FALSE |  |  |  |  | DDC
LNCM12CPT | LNCM12CPT | Y | Public Buildings | LIBRARIES | Clason's Point Roof Replacement | Design, remove, and replace the existing roofing system for the entire facility. | Clason Point Library Branch roof replacement. | Bronx |  | Libraries-NYPL | Construction Procurement | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNCM12NDP | LNCM12NDP | Y | Public Buildings | LIBRARIES | New Dorp Fire Alarm Upgrade | Installation of new fire alarm system | Installation of new fire alarm system | Staten Is. |  | Libraries-NYPL | Substantial Completion | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNDSVRENO | LNDSVRENO | Y | Public Buildings | Libraries | Soundview HVAC and Fire Alarm Upgrade | HVAC replacement, fire alarm upgrade | HVAC replacement; fire alarm upgrade |  |  | Libraries-NYPL | Acceptance/Final Completion | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEA08MHV1 | LNEA08MHV | Y | Public Buildings | Libraries | 96th Street HVAC, BMS and Fire Alarm Upgrade | Replacement and or rehabilitation of HVAC, BMS and Fire Alarm Systems. | Replace/rehabilitate HVAC, BMS and fire alarm systems. |  |  | Libraries-NYPL | Maintenance | Renovation | Standard | In-House/Consultant | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
LNEA08MHV2 | LNEA08MHV | Y | Public Buildings | Libraries | 125th Street HVAC, BMS and Fire Alarm Upgrade | Replacement and or Rehabilitation of HVAC, BMS and Fire Alarm Systems. | Replacement/rehabilitation of HVAC, BMS and Fire Alarm systems. |  |  | Libraries-NYPL | Acceptance/Final Completion | Renovation | Standard | Standard Consultant | Requirements TO | Project Info | FALSE |  |  |  |  | DDC
LNEA08MHV3 | LNEA08MHV | Y | Public Buildings | LIBRARIES | George Bruce HVAC, Boiler,BMS & Fire Alarm Upgrade | Replacement and or Rehabilitation of HVAC, Boiler, BMS and Fire Alarm Systems | George Bruce Library to Replace/rehabilitate HVAC, BMS and fire alarm systems. | Manhattan |  | Libraries-NYPL | Final Design | Renovation | Standard | Requirement Contract | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
LNEA13HGR | LNEA13HGR | Y | Public Buildings | LIBRARIES | Hamilton Grange Exterior Renovation | Exterior Rehabilitation / Window Replacement and water filtration remedation. | Exterior Rehabilitation / Window Replacement and water filtration remediation. | Manhattan |  | Libraries-NYPL | Design Development | Renovation | Standard | Requirement Contract | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEA13MAC | LNEA13MAC | Y | Public Buildings | Libraries | Macomb's Bridge Fire Alarm Upgrade | Provision of a new code-compliant Fire Alarm System | Install new fire alarm system. |  |  | Libraries-NYPL | Cancelled Project | Upgrade |  | Requirements TO | JOCs | PIMS | FALSE
LNEA13MHU | LNEA13MHU | Y | Public Buildings | LIBRARIES | Mosholu Roof, Exterior & HVAC Upgrade | Mosholu Library roof replacement and perform exterior renovation work. | Mosholu Library roof replacement and perform exterior renovation work. | Bronx |  | Libraries-NYPL | Compliance | Upgrade | Standard | Requirement Contract | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEA13STG | LNEA13STG | Y | Public Buildings | LIBRARIES | St. George Exterior and Interior Renovation | Partial exterior and interior renovation. Work to include but not limited to façade rehabilitation, renovation of entry and circulation desk for ADA accessibility, electrical systems upgrade, and interior improvements ancilary to proposed work. Design procurement may include (t.b.d) Pre-Preliminary Design services. | Roof restoration. DD submission submitted on 4/17/2017, in review by DDC A&E team. | Staten Is. |  | Libraries-NYPL | Compliance | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEA13TNK | LNEA13TNK | Y | Public Buildings | LIBRARIES | Throgs Neck Roof & HVAC Upgrade | ROOF REPLACEMENT and HVAC UPGRADE | 9/1/2017 100% CD documents are in review by Constructability Unit. | Bronx |  | Libraries-NYPL | Compliance | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEA14ECH | LNEA14ECH | Y | Public Buildings | Libraries | Eastchester Roof and Facade upgrade | ROOF REPLACEMENT AND FAÇADE REPAIR | Eastchester Library Branch Replacement of roof and facade restoration |  |  | Libraries-NYPL | Acceptance/Final Completion | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEA14RTW | LNEA14RTW | Y | Public Buildings | Libraries | Richmond town Elevator Upgrade | Elevator Upgrade | Richmond Library Branch elevator upgrade |  |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade | Standard | In-House | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNEA14VNT | LNEA14VNT | Y | Public Buildings | LIBRARIES | Van Nest HVAC Upgrade | Replacement of HVAC system, including air condition, boiler, fans, pumps, piping, and automatic temperature controls. | Replacement of HVAC system, including air conditioning, boiler, fans, pumps, piping, and automatic temperature controls. | Bronx |  | Libraries-NYPL | Design Development | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEAL15RT | LNEAL15RT | Y | Public Buildings | LIBRARIES | Richmondtown Roof Replacement | Roof replacement | Roof replacement | Staten Is. |  | Libraries-NYPL | Compliance | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEM08AGL | LNEM08AGL | Y | Public Buildings | Libraries | Aguilar HVAC, BMS and Fire Alarm Upgrade | Replacement of HVAC, BMS and Fire Alarm system | Replace HVAC, fire alarm and building management systems. |  |  | Libraries-NYPL | Maintenance | Renovation |  | Requirements TO | DDC Managed | PIMS | FALSE
LNEM08CLB | LNEM08CLB | Y | Public Buildings | Libraries | Columbus Branch - HVAC | Boiler replacement. BMS and Fire Alarm installation | Replace boiler and install fire alarm system. |  |  | Libraries-NYPL | Maintenance | Renovation |  |  | Requirements TO | PIMS | FALSE
LNEM08EPH | LNEM08EPH | Y | Public Buildings | Libraries | Epiphany branch- HVAC | HVAC and Boiler replacement. BMSand Fire Alarm installation | HVAC and Boiler replacement. BMS and New Fire Alarm installation |  |  | Libraries-NYPL | Maintenance |  |  |  |  | PIMS | FALSE
LNEM08HUD | LNEM08HUD | Y | Public Buildings | Libraries | Hudson Park Branch - HVAC | Boiler and HVAC replacement and BMS and Fire Alarm installation. | Replace boiler and HVAC system, and install new fire alarm and building management systems. |  |  | Libraries-NYPL | Maintenance | Renovation |  |  | DDC Managed | PIMS | FALSE
LNEM12MLB | LNEM12MLB | Y | Public Buildings | LIBRARIES | Muhlenberg Branch Library - Vault & Sidewalk | Existing vault and deteriorating concrete sidewalk replacement | Existing vault and deteriorating concrete sidewalk replacement | Manhattan |  | Libraries-NYPL | Construction Procurement | Sidewalks | Critical | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNEM13ALL | LNEM13ALL | Y | Public Buildings | Libraries | Allerton Fire Alarm Upgrade | Provision of a new code-compliant Fire Alarm System. | Install new fire alarm system. |  |  | Libraries-NYPL | Construction 75%-Subst. | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNEM13EDW | LNEM13EDW | Y | Public Buildings | Libraries | Edenwald Fire Alarm Upgrade | Provision of a new code-compliant Fire Alarm System. | Edenwald Library Branch installation of new fire alarm system |  |  | Libraries-NYPL | Maintenance | Upgrade |  | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNEM13JMK | LNEM13JMK | Y | Public Buildings | LIBRARIES | Jefferson Market Fire Alarm Upgrade | Provision of a new code-compliant Fire Alarm System. | Jefferson Market Library new fire alarm system installation. | Manhattan |  | Libraries-NYPL | Construction 0-25% | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNEM13MSH | LNEM13MSH | Y | Public Buildings | Libraries | Mosholu Fire Alarm Upgrade | Provision of a new code-compliant Fire Alarm System. | Install new fire alarm system. |  |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNEM13SPV | LNEM13SPV | Y | Public Buildings | Libraries | Spuyten Duyvil Library Fire Alarm System | Provision of a new code-compliant Fire Alarm System. | Install new fire alarm system. |  |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNEM13VNE | LNEM13VNE | Y | Public Buildings | Libraries | Van Nest Library New Fire Alarm System | Provision of a new code-compliant Fire Alarm System. | Install new fire alarm system. |  |  | Libraries-NYPL | Maintenance | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNEM14HUG | LNEM14HUG | Y | Public Buildings | Libraries | Huguenot Park Fire Alarm Upgrade | Code compliant fire alarm system and smoke detector. | Install new code compliant fire alarm and smoke detection systems. |  |  | Libraries-NYPL | Maintenance | Renovation | Standard | In-House | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNEM14JPK | LNEM14JPK | Y | Public Buildings | Libraries | Jerome Park Roof Replacement | New roof and drains. | Install new roof and drains. |  |  | Libraries-NYPL | Maintenance | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEM14NDP | LNEM14NDP | Y | Public Buildings | LIBRARIES | New Dorp Roof Replacement | Flat roof replacement. | New Dorp Library Branch Roof replacement. | Staten Is. |  | Libraries-NYPL | Construction Procurement | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNEM14WKF | LNEM14WKF | Y | Public Buildings | Libraries | Wakefield Boiler & Flue Replacement | Replace existing boiler and flue at the building. | Wakefield Library Branch replacement of boiler and chimney flue structure |  |  | Libraries-NYPL | Construction 75%-Subst. | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNEM15PCH | LNEM15PCH | Y | Public Buildings | Libraries | Parkchester Fire Alarm | Code compliant fire alarm system and smoke detector. | Parkchester Library Branch installation of new fire alarm system |  |  | Libraries-NYPL | Maintenance | Upgrade | Standard | In-House | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNEM15RVD | LNEM15RVD | Y | Public Buildings | LIBRARIES | Riverdale Fire Alarm | Provide new fire alarm/scope detection system in existing facility. | Provide new fire alarm/scope detection system in existing facility. | Bronx |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade | Standard | Requirement Contract |  | PIMS | FALSE |  |  |  |  | DDC
LNEMA08WS | LNEMA08WS | Y | Public Buildings | Libraries | Woodstock Interior Renovation & ADA upgrade | ADA Compliance and Interior Renovation of 1st and 2nd Floors, MEP Building Systems Upgrade | Woodstock Library Branch renovation of Interior to including ADA compliance work, plus upgrades to mechanical, electrical and plumbing systems |  |  | Libraries-NYPL | Maintenance | Renovation | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNMA12TOT | LNMA12TOT | Y | Public Buildings | Libraries | Tottenville Branch Fire Alarms | Provision of a new code-compliant Fire Alarm System. | Install a new fire alarm system. |  |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade |  | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNMA12WAS | LNMA12WAS | Y | Public Buildings | Pass Through | Washington Heights Branch Library | LNMA12WAS 01/02/14 Contract registration #20141411271 Contract amount $6,042,507 PIN #8502013LN0001P Block 2109 / Lot 55 / BIN# 1062551 SC: Jan 15th, 2014 Beneficial Occupancy: Jan 15th, 2014 Opened to the public: Mar 3rd, 2014 Address: 1000 St. Nicholas Ave. (at West 160th St.) New York, NY 10032-5202 Building is 23,130 sq. ft. Project is 5,734 sq. ft. Design Start: 09/13/10 Design Finish: 11/18/11 Construction Start: 05/02/12 Construction Finish: Fall 2013 The Washington Heights Branch Library is an existing NYPL branch. The scope of work is for the rehabilitation of the 1st floor Adult & Young Adult Reading Rooms, the 2nd floor Children's Reading Room and the Basement level computer room. The project is providing much needed rehabilitation of spaces used by library Patrons. The rehabilitation will include building wide upgrades to electrical, telecommunications & security. ADA upgrades will include new four stop elevator and bathrooms for the first floor. The following list of the rehabilitation for Washington Heights Branch Library 1. Cellar Excavation of elevator pit and new incoming electrical service 2. Basement Elevator machine room, new electrical service room, IT closet and Computer Room, new lighting upgrades in hall and Corridor 3. 1st Floor Adult & Young Adult Reading Room Rehabilitation of space shall include walls & ceilings. New lighting upgrades, circulation & information desk, millwork, finishes, flooring, shelving, furniture and equipment. New ADA compliant bathrooms. Install sprinkler around Stair A per DOB’s determination. 4. 2nd Floor Children Reading Room Rehabilitation of space shall include walls & ceilings. New lighting upgrades, circulation desk, millwork, finishes, flooring, shelving, furniture and equipment. Rehabilitation of existing bathroom. New story hour area with millwork seating platform. Install sprinkler around Stair A per DOB’s determination. 5. 3rd Floor Install Gyp. Bd ceiling within Stair A, perform ceiling and shaft wall repair associated with new duct work, infill floor trenches associated with electrical roughing with lightweight concrete and flash patch existing floor. Install sprinkler around Stair A per DOB’s determination. 6. Roof New elevator smoke hatch and equipment placement including exhaust fans and compressors. 7. New ADA Compliant Elevator Install handicap accessible glass elevator form Basement to Third floor Construction Manager Hunter Roberts Construction Group 2 WFC, 6th Floor, NY, NY 10281 • David Campbell, Vice President, (917) 699-5385, dcampbell@hunterrobertscg.com • Montalee Hastanan, Project Manager (917) 574-6524 • Rocco Carlucci, Project Manager (646) 302-2027 • Dan Demonte, Superintendent (646) 210-7442 Architect Dattner Architects 1385 Broadway,15th Floor New York, NY 10018 • Joseph Coppola, Principal (212) 589-7057 • Joon Cho, Associate (212) 589-7051 • Eric Perez, Architect (917) 281-1685 Consultants Mechanical; Electrical; Plumbing/Fire Protection AG Consult. Engineers 260 West 35th Street, 13th Flr New York, NY 10001 T. 212-268-0958 Structural Engineer Robert Silman Assoc. 88 University Place New York, NY 10001 T. 212-620-7970 Architectural Lighting Consultant Tilitson Design 40 Worth Street, Ste 1680 New York, NY 10014 T. 212-675-7760 Telecommunications/Data/ Information Technology Consultant TM Tech. Partners, Inc. 250 West 39th Street New York, NY 10018 T. 212-398-2424 Security Consultant AG Consult. Engineers 260 West 35th Street, 13th Flr New York, NY 10001 T. 212-268-0958 Elevator/Escalator Consultant VDA LLC 5 Regent Street, Ste 524 Livingston, NJ 07039 T. 973-994-9220 $19,500 Architect (Children’s Room) Andre Berman Architect 77 Chambers Street, 4th Floor New York, NY 10007 • Andrew Berman, Principal (212) 226-5998 • Vinci So, Architect (212) 226-5998 Structural Engineer Robert Silman Assoc. 88 University Place New York, NY 10001 T. 212-620-7970 Mechanical; Electrical; Plumbing/Fire Protection L. Naoum Consulting Engineers 330 West 38th Street, Suite 602 New York, NY 10018 T. 212-714-0094 | Rehabilitation of the 1st floor adult and young adult reading rooms, the 2nd floor children's reading room, and the basement level computer room. The project includes building wide upgrades to electrical, telecommunications and security systems, ADA compliance, and a new elevator. |  |  | Libraries-NYPL | Substantial Completion | Renovation | Standard | Pass Through | Pass Through | PIMS | FALSE |  |  |  |  | DDC
LNMNA08LS | LNMNA08LS | Y | Public Buildings | Libraries | Hamilton Grange Fire Alarm Upgrade (8 of 10) | 10 Manhattan Branch Libraries Fire Alarm Project t - LIFE SAFETY PROGRAM OTTENDORFER BRANCH - SPRINKLER SYSTEM - SCOPE OF WORK REMOVED SEP -2010 JOCS REQUIREMENTS COTRACTFOR Kips Bay, Tompkins Square, Hamilton Fish and Bloomingdale Branch Libraries. | Install a fire suppression sprinkler system in the Ottendorfer Branch Library, as part of the Manhattan Branch Library life safety program. |  |  | Libraries-NYPL | Maintenance | Renovation | Standard | Requirements TO | JOCs | PIMS | FALSE
LNMNA08LS1 | LNMNA08LS | Y | Public Buildings | Libraries | Tompkins Square Fire Alarm Upgrade (1 of 10) | UPGRADING FIRE ALARM SYSTEM SPRINKLER SYSTEM | Install upgraded fire alarm and sprinkler systems. |  |  | Libraries-NYPL | Maintenance | Upgrade | Standard | In-House/Consultant | JOCs | Project Info | FALSE
LNMNA08LS5 | LNMNA08LS | Y | Public Buildings | LIBRARIES | Yorkville Fire Alarm Upgrade (5 of 10) | FIRE ALARM & EMERGENCY LIGHTING SYSTEMS | Yorkville Library Branch installation of new fire alarm and emergency lighting systems. | Manhattan |  | Libraries-NYPL | Construction 0-25% | Upgrade | Standard | Requirement Contract | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNMNA08LS6 | LNMNA08LS | Y | Public Buildings | Libraries | Webster Fire Alarm Upgrade | Fire Alarm & emergency Lighting Systems | Install new fire alarm and emergency lighting systems. |  |  | Libraries-NYPL | Maintenance | Upgrade | Standard | In-House/Consultant | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNMNA08LS7 | LNMNA08LS | Y | Public Buildings | LIBRARIES | Ottendorfer Fire Alarm Upgrade | Fire alarm,CCTV and sprinkler System. | Construction kick off meeting On June 07 2017 | Manhattan |  | Libraries-NYPL | Construction 0-25% | Upgrade | Standard | JOCS | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNMNA08LS8 | LNMNA08LS | Y | Public Buildings | LIBRARIES | Muhlenberg Fire Alarm Upgrade | FIRE ALARM SYSTEM | Pending Task order registration By comptroller office. | Manhattan |  | Libraries-NYPL | Construction Procurement | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNMNA08LS9 | LNMNA08LS | Y | Public Buildings | Libraries | Chatham Square Fire Alarm (10 of 10) | FIRE ALARM & SPRINKLER SYSTEM | Install new fire alarm and sprinkler systems. |  |  | Libraries-NYPL | Acceptance/Final Completion | Upgrade | Standard | In-House/Consultant | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNMWHTREA | LNMWHTREA | Y | Public Buildings | Libraries | Washington Heights Renovation | Renovation of the Washington Heights Branch Library | Renovate facility. |  |  | Libraries-NYPL | Maintenance | Renovation | Standard |  | DDC Managed | PIMS | FALSE
LNRA10STG | LNRA10STG | Y | Public Buildings | Libraries | St. Georges Boiler Replacement & Elevator Upgrade | BOILER REPLACEMENT AND ELEVATOR UPGRADE | Installation of a new boiler and elevator upgrade. |  |  | Libraries-NYPL | Acceptance/Final Completion | Renovation | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNSIM12LS | LNSIM12LS | Y | Public Buildings | Libraries | West New Brighton Fire Alarm Upgrade | Provision of a new code-compliant Fire Alarm System | Install new fire alarm system. |  |  | Libraries-NYPL | Maintenance | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LNXA11WFM | LNXA11WFM | Y | Public Buildings | LIBRARIES | West Farms Entrance & Interior Door ADA Upgrade | REPLACE ENTRANCE AND INTERIOR VESTIBLUE DOORS WITH POWER ASISTED ADA COMPLIANT HARDWARE RENOVATION /ADA COMPLIANCE | West Farms Library to Renovate main entry to meet ADA standards--includes power assisted exterior and interior vestibule doors. | Bronx |  | Libraries-NYPL | Final Design | Upgrade | Standard | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LNXA12GRC | LNXA12GRC | Y | Public Buildings | LIBRARIES | Grand Concourse ADA/Interior Upgrade | To provide ADA-compliant accessibility within the building, including ADA bathroom, elevator retrofit, and related changes to first floor staff areas. | Grand Concourse Library To provide ADA-compliant accessibility within the building, including ADA bathroom, elevator retrofit, and related changes to first floor staff areas. | Bronx |  | Libraries-NYPL | Construction Procurement | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNXA13SPV | LNXA13SPV | Y | Public Buildings | Libraries | Spuyten Duyvil Sidewalk Replacement | Sidewalk Replacement at front of building. | Replace sidewalk along the front of the building. |  |  | Libraries-NYPL | Maintenance | Renovation | Standard | In-House | JOCs | PIMS | FALSE
LNXA13WKF | LNXA13WKF | Y | Public Buildings | LIBRARIES | Wakefield ADA,Exterior/Interior Renovations | Renovation for the partial exterior and partial interior of the Wakefield Branch Library | Replace boiler and perform interior and exterior renovation work. | Bronx |  | Libraries-NYPL | Cancelled Project | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNXEA08BA | LNXEA08BA | Y | Public Buildings | LIBRARIES | Replacement of HVAC & BMS:Baychester Branch Librar | Replacement of HVAC & BMS:Baychester Branch . | Replacement of HVAC and BMS at the NYPL Baychester Branch Library | Bronx |  | Libraries-NYPL | Construction Procurement | Upgrade | Critical | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNXEA08BX | LNXEA08BX | Y | Public Buildings | Libraries | HVAC Upgrade Design - 3 Bronx Branches | This FMS # is for design only Replacement and/or rehabilitation of HVAC systems and BMS in Francis Martin and Clasons Pt. libraries. | Replace/rehabilitate HVAC and Building Management Systems. |  |  | Libraries-NYPL | Cancelled Project | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE
LNXEA08BX1 | LNXEA08BX | Y | Public Buildings | Libraries | Baychester HVAC Upgrade | HVAC replacement and BMS installation | Baychester Library HVAC and install Building Management Systems replacement. | Bronx |  | Libraries-NYPL | Cancelled Project | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNXEA08CP | LNXEA08CP | Y | Public Buildings | LIBRARIES | Clason's Point HVAC Upgrade | Replacement of Air Handler Units,pumps and work on metal ducts | Replacement of Air Handler Units,pumps and work on metal ducts | Bronx |  | Libraries-NYPL | Construction Procurement | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LNXEA08FN | LNXEA08FN | Y | Public Buildings | LIBRARIES | Francis Martin HVAC Upgrade | Upgrade the existing HVAC systems by replacing existing rooftop units, split type air conditioning units, fans, ductwork, and controls. | Francis Martin Library rooftop units replacement with a split type air conditioning system including new fans, ductwork, and controls. | Bronx |  | Libraries-NYPL | Construction Procurement | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQ122-BC2 | LQ122-BC2 | Y | Public Buildings | LIBRARIES | Broad Channel Roof Replacement | Roof Replacement at the Broad Channel library. Replacement of gutters/leaders. | Broad Channel Roof Replacement |  |  | Libraries-QBPL | Cancelled Project | Renovation | Standard | None | JOCs | PIMS | FALSE
LQ122-CEL | LQ122-CEL | Y | Public Buildings | Libraries | Central Generator Upgrade | A new Data Center with new A/C and UPS equipment in conjunction with major building renovation. | Major building renovation including a new data center with new HVAC and electrical supply systems. |  |  | Libraries-QBPL | Completed Project | Upgrade | Standard | None | JOCs | PIMS | FALSE |  |  |  |  | DDC
LQ122-FHR | LQ122-FHR | Y | Public Buildings | LIBRARIES | Forest Hills Roof Replacement | Roof replacement and Masonry restoration | Forest Hills Roof Replacement and Masonry restoration. | Queens |  | Libraries-QBPL | Maintenance | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQ122-LH | LQ122-LH | Y | Public Buildings | Libraries | Langston Hughes Masonry & Waterproofing | Complete selected masonry repairs for the north and part of the east building renovations where interior water-damage has occurred. Waterproofing system to be placed on interior surfaces. | Perform masonry repairs on renovated areas of the north and east buildings where water-damage has occurred. Install waterproofing system on interior surfaces. |  |  | Libraries-QBPL | Maintenance | Renovation | Standard | In-House/Consultant | JOCs | PIMS | FALSE
LQ122-W | LQ122-W | Y | Public Buildings | LIBRARIES | Whitestone Selected Masonry Upgrade | Selected building masonry repairs are required. Replace cracked precast spandrels on exterior façade and remove temporary shoring. | Masonry upgrade to exterior façade. | Queens |  | Libraries-QBPL | Construction 0-25% | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQARVEXPN | LQARVEXPN | Y | Public Buildings | LIBRARIES | Arverne Expansion | Addition to existing library building. | Expansion existing building. | Queens |  | Libraries-QBPL | Scope Development | Renovation | Standard | In-House/Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQASADA | LQASADA | Y | Public Buildings | LIBRARIES | Astoria Restrooms and Elevators Upgrade | Full upgrade to ADA accessibility, including bathrooms and new elevator. | Astoria Library Project - ADA Elevator and ADA restroom upgrades. | Queens |  | Libraries-QBPL | On-Hold | Upgrade | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQC122-GK | LQC122-GK | Y | Public Buildings | Libraries | Glen Oaks New Building | Replace existing 10, 000 sq. ft. library building with 18,000 sq.ft. new building. | Replace existing library building with a new 18,000 square foot facility. |  |  | Libraries-QBPL | Completed Project | New Construction | Critical | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQD122-AU | LQD122-AU | Y | Public Buildings | Libraries | Auburndale Roof Replacement | Auburndale Library roof replacement JOCS Contractor | Replace existing roof. |  |  | Libraries-QBPL | Completed Project | Other | Standard | In-House | DDC Managed | PIMS | FALSE
LQD122BCE | LQD122BCE | Y | Public Buildings | LIBRARIES | Broad Channel Gutter & Leader Upgrade | Replacement of gutters and leaders at the Broad Channel Library | Replacement of gutters and leaders at the Broad Channel Library | Queens |  | Libraries-QBPL | Cancelled Project | Upgrade | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
LQD122BR2 | LQD122BR2 | Y | Public Buildings | LIBRARIES | Broadway Interior Renovation | Library interior renovation/upgrade and all related work. | Broadway Library Interior Renovation and related work | Queens |  | Libraries-QBPL | Final Design | Upgrade |  | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQD122BT1 | LQD122BT1 | Y | Public Buildings | Libraries | Bay Terrace HVAC Controls and Roof Upgrade | HVAC System replacement and controls. | Bay Terrace Library Branch replacement of HVAC system and related controls |  |  | Libraries-QBPL | Schematic Design | Renovation |  | Requirements TO | DDC Managed | PIMS | FALSE
LQD122-BW | LQD122-BW | Y | Public Buildings | LIBRARIES | Briarwood Roof Replacement | Roof replacement and related work | Briarwood Library Roof replacement and related work. | Queens |  | Libraries-QBPL | Maintenance | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQD122-F2 | LQD122-F2 | Y | Public Buildings | LIBRARIES | Flushing Library hvac/window upgrades | Upgrade of selected HVAC controls and related components/equipment, as required and upgrade of electrically operated window treatment for increased energy efficiency. | HVAC Upgrade | Queens |  | Libraries-QBPL | Construction Procurement | Upgrade |  | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LQD122GL2 | LQD122GL2 | Y | Public Buildings | LIBRARIES | Glendale Library Renovations-Phase II | ADA Street Access, New ADA Elevator, Selective Interior Renovation, Fire Alarm, Security. | Renovation to accommodate patrons with disabilities, new fire alarm and interior improvements. | Queens |  | Libraries-QBPL | Construction Procurement | Renovation | Court Mandated | Design Excellence/24 | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQD122-HO | LQD122-HO | Y | Public Buildings | Libraries | Hollis Roof Replacement | Roof replacement | Replace roof. |  |  | Libraries-QBPL | Maintenance | Other | Standard | In-House | JOCs | PIMS | FALSE
LQD122HO1 | LQD122HO1 | Y | Public Buildings | LIBRARIES | Hollis Interior Renovation | Interior alteration with ADA upgrades and new HVAC system. | 7/14/16: DD comments from the Consultant anticipated back by 7/22. Awaiting approval from QBPL regarding bathroom layout revisions. Commissioning company engaged. Amended design CP required. | Queens |  | Libraries-QBPL | Design Development | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQD122HV3B | LQD122HV3 | Y | Public Buildings | Libraries | Baisley HVAC Replacement | HVAC system replacements/controls at Baisley Park Branch Library. | Replace HVAC system and related controls.. |  |  | Libraries-QBPL | Cancelled Project | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE
LQD122HV3O | LQD122HV3 | Y | Public Buildings | Libraries | Ozone Park HVAC Replacement | HVAC system replacements/controls at Ozone Park Branch Library. | Replace HVAC system and controls. |  |  | Libraries-QBPL | Maintenance | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE
LQD122HV3R | LQD122HV3 | Y | Public Buildings | Libraries | Rosedale HVAC Upgrade | HVAC system replacements/controls at Rosedale Branch Library. | Replace HVAC system and related controls. |  |  | Libraries-QBPL | Completed Project | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE |  |  |  |  | DDC
LQD122LIC | LQD122LIC | Y | Public Buildings | Libraries | Long Island City Security Cameras | EXTERIOR SECURITY LIGHTING_ LONG ISLAND CITY , QNS, QL Long Island City Community Branch Library 21-37 Avenue Long Island City, NY 11101 | Install exterior security lighting. |  |  | Libraries-QBPL | Construction 0-25% | Upgrade | Standard | Requirements TO | JOCs | PIMS | FALSE
LQD122-MG | LQD122-MG | Y | Public Buildings | LIBRARIES | McGoldrick HVAC & Controls | Replacement and upgrade of HVAC system, controls and related components. | Upgrade of HVAC system | Queens |  | Libraries-QBPL | Maintenance | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LQD122NF4 | LQD122NF4 | Y | Public Buildings | LIBRARIES | North Forest Park Renovation | Overall interior renovation of existing building and HVAC upgrade. | North Forest Park Library Interior renovation of existing building and HVAC upgrade. | Queens |  | Libraries-QBPL | Design Development | Renovation | Standard | In-House | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQD122QH1 | LQD122QH1 | Y | Public Buildings | LIBRARIES | Queensboro Hill Roof | ROOF REPLACEMENT AND RELATED WORK AS NECESSARY | Roof & parapet replacement & upgrade. | Queens |  | Libraries-QBPL | Maintenance | Renovation | Standard | In-House | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
LQD122-QW | LQD122-QW | Y | Public Buildings | Executive | QUEENS WEST LIBRARY HUNTERS POINT | New Branch Library and NY State Parks Office/Ranger Station | A new state of the art branch library with space provided for the New York State Parks Department. The Parks facility will house public restrooms, park ranger and police offices, reception and conference rooms, and storage areas. |  |  | Libraries-QBPL | Construction 50-75% | New Construction | Standard | Standard Consultant | DDC Managed | PIMS | FALSE
LQD122-QW-1 | LQD122-QW | Y | Public Buildings | Executive | Queens West New Branch Library | New Branch Library and NY State Parks Office/Ranger Station | Queens West Library Branch - A new state of the art branch library with space provided for the New York State Parks Department. The Parks facility will house public restrooms, park ranger and police offices, reception, conference rooms, and storage areas. |  |  | Libraries-QBPL | Construction 50-75% | New Construction | Standard | Standard Consultant | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
LQD122RF3A | LQD122RF3 | Y | Public Buildings | Libraries | Baisley Roof Replacement | Roof Replacement & related work | Replace roof and perform related rehabilitation work. |  |  | Libraries-QBPL | Completed Project | Renovation | Standard | Standard Consultant | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
LQD122RF3C | LQD122RF3 | Y | Public Buildings | LIBRARIES | South Jamaica Roof Replacement | Roof Replacement Work, Clerestory Windows, Skylights. | South Jamaica Library Roof Renovation | Queens |  | Libraries-QBPL | Construction 0-25% | Renovation | Standard | Standard Consultant | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
LQD122-RO | LQD122-RO | Y | Public Buildings | Libraries | Rochdale Villiage Adult Learning Center | Expansion and/or renovation to provide improved Adult Learning Center space., 1600 sq ft | Expansion/renovation to Adult Learning Center space. |  |  | Libraries-QBPL | Completed Project | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQD122RO2 | LQD122RO2 | Y | Public Buildings | LIBRARIES | Rochdale Village HVAC & Controls Upgrade | HVAC System Replacement/Controls at the Rochdale Village Community Library | HVAC System Replacement / Controls Upgrade | Queens |  | Libraries-QBPL | Final Design | Upgrade | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LQD122-RO3 | LQQ122-DL | Y | Public Buildings | Libraries | Rochdale Village Roof Replacement | Roof Replacement | Replace existing roof. |  |  | Libraries-QBPL | Completed Project | Upgrade |  | In-House | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
LQD122-S2 | LQD122-S2 | Y | Public Buildings | LIBRARIES | Steinway-Phase II Renovation | Proposed Scope of work includes upgrades/replacement to the exterior envelope. Scope also includes the installation of new ADA compliant elevator, new entrace and ramp and renovations to the children room. | Major interior renovation and improvement. | Queens |  | Libraries-QBPL | Construction Procurement | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQD122SA1 | LQD122SA1 | Y | Public Buildings | Libraries | St. Albans Supplemental heating & insulation | Suplemental heating and insulation of external walls. | Saint Albans Library Branch supplemental heating system and insulation of exterior walls |  |  | Libraries-QBPL | Cancelled Project | Renovation | Standard | Requirements TO | JOCs | PIMS | FALSE
LQD122-WN | LQD122-WN | Y | Public Buildings | LIBRARIES | Woodhaven ADA, Elevator & Exterior Rehabilitation | Exterior rehab including window replacement and roof replacement; interior alterations including new HVAC system; ADA upgrades with new elevator | Major renovation including ADA upgrades | Queens |  | Libraries-QBPL | Design Development | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQD122WS3 | LQD122WS3 | Y | Public Buildings | Libraries | Woodside Interior Lighting Upgrade | Provide new electrical panel and circuit breakers to replace the existing panel at the first floor. Provide lighting contactor to control lighting from remote switch at Costumer Service Desk. Provide new power and data floor boxes, replace existing lighting at mezzanine, manager’s office and teen reading area. Remove exterior conduit for light fixtures at building entrance and at the side of the building | Replace electrical panel and lighting controls; provide new lighting for the mezzanine, office space and teen reading area. |  |  | Libraries-QBPL | Completed Project | Renovation | Standard | In-House | JOCs | PIMS | FALSE |  |  |  |  | DDC
LQDLHVAC | LQDLHVAC | Y | Public Buildings | LIBRARIES | Douglaston HVAC Replacement | Installation of new HVAC system. | Douglaston Library Installation of new HVAC system. | Queens |  | Libraries-QBPL | Scope Development | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQDOUGMTG | LQDOUGMTG | Y | Public Buildings | LIBRARIES | Douglaston Meeting Room | Renovation of existing storage room into expanded meeting room space. | Douglaston Library Construction of new expanded meeting room | Queens |  | Libraries-QBPL | Schematic Design | Renovation | Standard | Requirements TO | DDC Managed/Consultant | PIMS | FALSE |  |  |  |  | DDC
LQFLELV | LQFLELV | Y | Public Buildings | LIBRARIES | Flushing New Elevator & Upgrades | Additional elevator to the building and upgrades to existing elevator. | Flushing Library project to add a new elevator to the building and upgrades to the existing elevator. | Queens |  | Libraries-QBPL | Design Development | Upgrade | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQHIHVAC | LQHIHVAC | Y | Public Buildings | LIBRARIES | Hillcrest HVAC Upgrade | Replacement of existing HVAC system . | Hillcrest Library Replacement of existing HVAC system. | Queens |  | Libraries-QBPL | Schematic Design | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQHIROOF | LQHIROOF | Y | Public Buildings | LIBRARIES | Hillcrest Roof Replacement | Roof Replacement | Hillcrest Library Roof Replacement | Queens |  | Libraries-QBPL | Schematic Design | Other | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQJHHVAC | LQJHHVAC | Y | Public Buildings | LIBRARIES | Jackson Heights HVAC Upgrade | HVAC and boiler replacement | Jackson Heights Library HVAC and boiler upgrade. | Queens |  | Libraries-QBPL | On-Hold | Upgrade | Standard | Requirements TO | DDC Managed/Consultant | PIMS | FALSE |  |  |  |  | DDC
LQLAROOF | LQLAROOF | Y | Public Buildings | LIBRARIES | Laurelton Roof Replacement | Exterior/Roof Restoration | Schematic Design | Queens |  | Libraries-QBPL | Schematic Design | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQMA-BLR | LQMA-BLR | Y | Public Buildings | LIBRARIES | MASPETH: New Boiler | This Project consists of the following scope items: • Remove & dispose Existing Boiler • Provide a new 400,000 btu/hr gas-fired, hot water boiler. • Install new circulating pumps (approximately 45 gpm capacity), expansion tank (approximately 30 gallon tank size), air separator and all other heating system accessory equipment required to be connected to the existing supply and return piping and terminal equipment distribution systems for proper system operation and control. • Provide boiler outdoor air reset, interfaced with the boiler control panel to control the minimum and maximum hot water supply temperatures enabling the circulating pumps upon receiving a signal from the space temperature zone sensors. • Provide heating system make-up water connections. • Install boiler low water safety limit controls, supply hot water temperature high limit controls, burner flame safeguard controls and a pressure relief valve. • Provide new gas and electrical power and control connections to the new boiler. • Provide new automatic combustion air louver damper. • Provide new gas and carbon monoxide leak detectors at the boiler. • Per the NYC Fuel Gas Code (Chap. 5, Sec. 504.3.19). Size the new chimney liner in accordance with the appropriate Venting Tables (Table 504.3). • Provide Emergency Break Glass Station just outside the boiler room. |  | Queens |  | Libraries-QBPL | Substantial Completion | Renovation | Critical |  |  | PIMS | FALSE |  |  |  |  | DDC
LQMVHVAC | LQMVHVAC | Y | Public Buildings | LIBRARIES | Middle Village HVAC Upgrade | HVAC and boiler replacement | Middle Village Library HVAC and boiler replacement. | Queens |  | Libraries-QBPL | Design Development | Upgrade | Standard | Requirements TO | DDC Managed/Consultant | PIMS | FALSE |  |  |  |  | DDC
LQOZROOF | LQOZROOF | Y | Public Buildings | LIBRARIES | Ozone Park Roof Upgrade | LQOZROOF Roof Replacement | Roof Replacement at Ozone Park Library | Queens |  | Libraries-QBPL | Design Development | Renovation |  |  |  | PIMS | FALSE |  | 2017 | 2018 |  | DDC
LQQ122-1E2 | LQQ122-1E | Y | Public Buildings | Libraries | New Elmhurst Branch Library | New Branch Library, to replace the 18,000 sf Carnegie Library with a new 30,000 sf modern building comprising 3 floors and basement, and featuring a façade of terra-cotta and metal panels and two oversized glass "cube" intrusions on the 1st floor and 2nd floor. The project include extensive landscape design on the existing open space and a percent-for-art component. | Construction of new branch library facility to replace the Carnegie Library |  |  | Libraries-QBPL | Completed Project | Renovation | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQQ122-BL | LQQ122-BL | Y | Public Buildings | LIBRARIES | Bellerose Masonry Repairs | Masonry restoration | Masonry restoration | Queens |  | Libraries-QBPL | Construction 0-25% | Renovation | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LQQ122CLD1 | LQQ122CLD | Y | Public Buildings | Libraries | Central - Children's Discovery Center | Children's Library Discovery Center (CLDC): Renovation & outfitting of the Central Library & the Central Library Annex to establish a Children's Library Discovery Center. | Renovate Central Library; Create new Children's Discovery Center. |  |  | Libraries-QBPL | Completed Project | Renovation | Standard | Requirements TO | CM-Build | PIMS | FALSE |  |  |  |  | DDC
LQQ122CLD4 | LQQ122CLD | Y | Public Buildings | Libraries | queens central library - electrical room replacem | Electrical Room Replacement | Rehabilitation of existing electrical room |  |  | Libraries-QBPL | Completed Project | Upgrade |  | Standard Consultant |  | Project Info | FALSE |  |  |  |  | DDC
LQQ122-DL1 | LQQ122-DL | Y | Public Buildings | Libraries | Douglaston Roof Replacement | Roof replacement Requirements Contractor | Replace existing roof. |  |  | Libraries-QBPL | Completed Project | Renovation | Standard | In-House | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
LQQ122-DL2 | LQQ122-DL | Y | Public Buildings | Libraries | North Hills Roof Replacement | Roof Replacement Requirements Contractor | Replace existing roof. |  |  | Libraries-QBPL | Completed Project | Renovation | Standard | In-House | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
LQQ122-DL3 | LQQ122-DL | Y | Public Buildings | LIBRARIES | South Ozone Park Roof Replacement | Roof Replacement - Façade Restoration. | Roof Replacement & Façade Restoration. | Queens |  | Libraries-QBPL | Construction 0-25% | Renovation | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LQQ122EE2 | LQQ122EE2 | Y | Public Buildings | LIBRARIES | East Elmhurst Expansion | Expansion of existing Community Library facility. | East Elmhurst library Expansion at Facility. | Queens |  | Libraries-QBPL | Construction 25-50% | New Construction | Standard | Standard Consultant | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQQ122-FA1 | LQQ122-FA | Y | Public Buildings | LIBRARIES | Far Rockaway New Facility | Construction of a new 18,000 sq.ft. Branch Library employing the latest technology and sustainable design. | Construction of a new 18,000 sq.ft. Branch employing the latest technology and sustainable design. | Queens |  | Libraries-QBPL | Construction Procurement | New Construction | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQQ122-FA2 | LQQ122-FA | Y | Public Buildings | LIBRARIES | Far Rockaway Facility Swing Space | Far Rockaway Teen Annex also known as Facility Swing Space is approx.7,200 sq.ft. Temporary space for Far Rockaway library until completion of new facility. | Far Rockaway Swing Space to serve the community during main branch construction. | Queens |  | Libraries-QBPL | Construction Procurement | Renovation |  | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LQQ122-KE | LQQ122-KE | Y | Public Buildings | Libraries | Kew Gardens Hills | 3,000 SF addition and major interior renovation of existing 8,500 SF space. New and upgraded Structural, Mechanical, Plumbing, Electrical, Data and Security systems. | 3,000 SF addition and major interior renovation of existing 8,500 SF space. New and upgraded Structural, Mechanical, Plumbing, Electrical, Data and Security systems. |  |  | Libraries-QBPL | Maintenance | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQQ122-KE1 | LQQ122-KE | Y | Public Buildings | Libraries | Kew Gardens Hills Swing Space | renovation of existing commercial space for the creation of temporary library for Kew Gardens hills communitty Contractor - S&N | Renovation of existing commercial space to accommodate the temporary library. |  |  | Libraries-QBPL | Maintenance | Renovation | Standard | Standard Consultant | DDC Managed | Project Info | FALSE |  |  |  |  | DDC
LQQ122LRC | LQQ122LRC | Y | Public Buildings | Libraries | Roof Replacement at Lefferts Library | Roof Replacement and related work | Replace roof and perform related work. |  |  | Libraries-QBPL | Completed Project | Renovation | Standard | In-House | Requirements TO | PIMS | FALSE |  |  |  |  | DDC
LQQBHHVAC | LQQBHHVAC | Y | Public Buildings | LIBRARIES | Queensboro Hill HVAC Upgrade | HVAC system upgrade and related work. | Queensboro Hill Library HVAC system upgrade and related work. | Queens |  | Libraries-QBPL | Design Development | Upgrade | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQQVHVAC | LQQVHVAC | Y | Public Buildings | LIBRARIES | Queens Village HVAC Upgrade | HVAC replacement | Queens Village Library HVAC Upgrade. | Queens |  | Libraries-QBPL | Design Development | Renovation |  | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQQVROOF | LQQVROOF | Y | Public Buildings | LIBRARIES | Queens Village Roof Replacement | Roof replacement | Queens Village Library Roof Replacement | Queens |  | Libraries-QBPL | Design Development | Renovation | Standard | Requirements TO | DDC Managed/Consultant | PIMS | FALSE |  |  |  |  | DDC
LQRAVUPK | LQRAVUPK | Y | Public Buildings | Libraries | Ravenswood Universal Pre-K | Construct two Universal Pre-K classrooms, pantry, etc. in Ravenswood library | Construct two Universal Pre-K classrooms, a pantry and related facilities in the Ravenswood library. |  |  | Libraries-QBPL | Completed Project | Renovation | Critical | In-House | JOCs | PIMS | FALSE |  |  |  |  | DDC
LQRDMASON | LQRDMASON | Y | Public Buildings | LIBRARIES | Ridgewood Roof & Masonry Repair | Roof & Façade Restoration | Roof & Façade Restoration | Queens |  | Libraries-QBPL | Design Development | Renovation | Standard | Standard Consultant | DDC Managed/Consultant | PIMS | FALSE |  |  |  |  | DDC
LQSARENOV | LQSARENOV | Y | Public Buildings | LIBRARIES | St. Albans Renovation | Exterior / Interior Renovation and Related Work. | Exterior / Interior Renovation and Related Work. | Queens |  | Libraries-QBPL | Scope Development | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQSAROOF | LQSAROOF | Y | Public Buildings | LIBRARIES | St Albans Roof Replacement | Roof and associated elements replacement | Roof replacement. | Queens |  | Libraries-QBPL | Construction Procurement | Renovation | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LQSEHVAC | LQSEHVAC | Y | Public Buildings | LIBRARIES | Seaside HVAC Upgrade | HVAC Upgrade | Facility HVAC Upgrade | Queens |  | Libraries-QBPL | Design Development | Renovation | Standard | Requirements TO | DDC Managed | PIMS | FALSE |  |  |  |  | DDC
LQSUADA | LQSUADA | Y | Public Buildings | LIBRARIES | Sunnyside ADA Entry Upgrade | ADA upgrade of entrance and vestibule doors. | Upgrade of entrance for ADA compliance. | Queens |  | Libraries-QBPL | Compliance | Upgrade | Standard | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LQWSADA | LQWSADA | Y | Public Buildings | LIBRARIES | Woodside ADA Entry Upgrade | ADA upgrade of entrance and vestibule doors. | Entrance upgrade for ADA compliance. | Queens |  | Libraries-QBPL | Cancelled Project | Upgrade | Standard | In-House | JOCS | PIMS | FALSE |  |  |  |  | DDC
LRCA08SCH | LRCA08SCH | Y | Public Buildings | Libraries | Schomburg Center-McKim Building Upgrades | Upgrade of Essential Building Systems. Roof replacement, sidewalk repalcement, Fire Alarm upgrade and new technology upgrade including computers. Interior renovation to major divisions of the facility Site address: 515 Malcolm X Boulevard, New York, NY 10037 | Rehabilitation work including: roof and sidewalk replacement, fire Alarm system upgrades and major interior renovations with technology upgrades for new computers. |  |  | Libraries-NYPL | Other | Renovation | Standard | Design Excellence/24 | DDC Managed | PIMS | FALSE
LRCA11LPA | LRCA11LPA | Y | Public Buildings | Pass Through | Library for the Performing Arts | The objective of this construction contract is to fully restore the building exterior in order to prolong the life of the original travertine panel façade, soffits and balustrades. The restoration will eliminate dangerous conditions on both the façade and soffits where aged and damaged stone has come loose. The work will also correct problems due to water penetration at the façade and around windows. As a result of this project the entire façade will be rehabilitated as needed. •100% resealing of all vertical and horizontal Travertine joints and metal joints with sealant. •Selective water mist and pressure rinse of travertine panels. •Selective cleaning and pressure rinse of biological growth at travertine panels. •Selective removal and replacement of exterior travertine panels and soffits. •Selective dutchman, pin anchor, mortar patch, and crack repairs at exterior travertine panels. •100% resealing of all metal coping joints. •Installation of a permanent tieback (fall arrest) system. •Selective Balustrade work. •Mock-ups for each restoration detail. •All protection implied/required at adjacent surfaces. •All sidewalk sheds and scaffolding. Block:1134 Lot:25 BIN:1028832 | Restore the building exterior to prolong the life of the original travertine panel façade, soffits and balustrades and to correct problems due to water penetration. |  |  | Libraries-NYPL | Substantial Completion | Renovation | Standard | Pass Through | Pass Through | PIMS | FALSE |  |  |  |  | DDC
LRCA13LPA | LRCA13LPA | Y | Public Buildings | LIBRARIES | Performing Arts Lighting Upgrade | Interior and Exterior Lighting Upgrade at NYPL Library for the Performing Arts | Library for the Performing Arts Interior and exterior lighting upgrades. | Manhattan |  | Libraries-NYPL | Substantial Completion | Renovation | Standard | Requirements TO | JOCS | PIMS | FALSE |  |  |  |  | DDC
LRCA17SCH | LRCA17SCH | Y | Public Buildings | PASS THROUGH | SCHOMBURG - Renovation Phase II Passthrough | The project is providing additional program space and overall upgrades to the facility including rehabilitation of major research support and building infrastructure. |  |  |  | Libraries-NYPL | [5 empty] | PIMS | FALSE |  |  |  | 2017-09-09 15:33:19.3900000 +00:00
MED594 | MED-594 | Y | Infrastructure | MANHATTAN & CITYWIDE | REPLACEMENT OF WATER MAIN IN E 46TH & E 47TH STREE | Distribution watermain replacement in E. 46th Street and E. 47th Street between Madison Ave. and Lexington Ave., Borough of Manhattan | Distribution watermain replacement in E. 46th Street and E. 47th Street between Madison Ave. and Lexington Ave., Borough of Manhattan | Manhattan |  | Environmental Protection | Final Design | Water | Standard | In-House | Requirements TO | PIMS | FALSE |  | 2014 | 2018 |  | DDC
MED597 | MED-597 | Y | Infrastructure | Manhattan & Citywide | TRUNK WATER MAINS IN EAST 31ST STREET Shaft #3 | Trunk water main in East 31st Street from 5th Ave to 2nd Ave., Borough of Manhattan | Install trunk water main in East 31st Street, between 2nd and 5th Avenues. | Manhattan |  | Environmental Protection | On-Hold | Water | Standard | In-House | Standard Consultant | PIMS | FALSE |  |  |  |  | DDC
MED598 | MED-598 | Y | Infrastructure | Manhattan & Citywide | TRUNK WATER MAINS IN WEST 30TH STREET (SHAFT 26B) | Installation of trunk water mains in 10th Ave. from West 30th St. to West 31st St.,etc., to connect Shaft 26B of City Tunnel #3 to the distribution system, Borough of Manhattan. 10th Avenue between West 30th Street and West 31st Street West 30th Street between 10th Avenue and 12th Avenue (Discharge main, combined sewer extension & distribution water main work) | Install trunk water main, connecting City Tunnel #3 to the distribution system: 10th Ave from 30th to 31st St & 30th St from 10th to 12th Ave, Manhattan | Manhattan |  | Environmental Protection | Construction 50-75% | Water | Standard | In-House | Standard Consultant | PIMS | FALSE |  |  |  |  | DDC
MED598B | MED-598B | Y | Infrastructure | MANHATTAN & CITYWIDE | TRUNK WATER MAINS IN WEST 30TH STREET, PHASE II | Installation of trunk water mains in West 30th Street from 9th Avenue to 10th Avenue, etc., to connect Shaft 26B of City Tunnel #3 to the distribution system, and Combine Sewer extensions & replacement, Borough of Manhattan. West 31st Street between 10th Avenue and 9th Avenue West 30th Street between 10th Avenue and 9th Avenue West 29th Street between 10th Avenue and 9th Avenue 9th Avenue between West 31st Street and West 29th Street 10th Avenue between West 30th Street and West 29th Street 10th Avenue between West 29th St. and West 28th St. (Combined sewer replacement work only) | Install trunk water main in W. 29th, 30th and 31st Streets | Manhattan |  | Environmental Protection | Construction 50-75% | Water | Standard | In-House | Standard Consultant | PIMS | FALSE |  | 2012 | 2016 |  | DDC
MED600B | MED-600B | Y | Infrastructure | Manhattan & Citywide | TRUNK WATER MAINS 58th St. (SHAFT 33B) | Installation of trunk water mains in 58th St., to connect Shaft 33B to the distribution system, PHASE 2, Borough of Manhattan. | Installation of trunk water main at various locations along 58th Street, connecting third water tunnel shaft 33B to the distribution system. |  |  | Environmental Protection | Substantial Completion | Water | Standard | In-House | Standard Consultant | PIMS | FALSE
MED607 | MED-607 | Y | Infrastructure | MANHATTAN & CITYWIDE | TRUNK WATER MAIN in 2nd Ave. ( SHAFT 32B) | Trunk and Distribution Main Connection to shaft 32B in 2nd Ave., etc., together with all work incidental thereto, Borough of Manhattan. 2nd Avenue from East 33rd Street to East 37th Street 3rd Avenue from East 33rd Street to East 35th Street East 35th Street from 1st Avenue to 3rd Avenue East 33rd Street from 2nd Avenue to 3rd Avenue East 34th Street from 1st Avenue to 3rd Avenue (Revised CPI 8/11 - Delete from MED607 and include under HWMBRT5A) | Trunk and Distribution Main Connection to shaft 32B in 2nd Ave., etc., together with all work incidental thereto, Borough of Manhattan. 2nd Avenue from East 33rd Street to East 37th Street | Manhattan |  | Environmental Protection | Construction 0-25% | Water | Standard | In-House | Standard Consultant | PIMS | FALSE |  | 2014 | 2017 |  | DDC
MED608 | MED-608 | Y | Infrastructure | MANHATTAN & CITYWIDE | WATER MAIN CONNECTION AT WASHINGTON SQUARE PARK | Replace old unlined cast iron pipe water main and improve water main distribution in the following areas: 1) Washington Square North between 5th Ave. & Washington Square East 2) Washington Square East between Washington Square North & Washington Square South 3) Washington Square South between Washington Square East & Thompson ST. 4) West 4 Street between Washington Square East & Broadway. 5)The intersection of 5th Ave. & Washington Square North. Notes: - The project is located in a historic district and will need to be coordinated with LPC, - The project is in the vicinity of NYCT subway line on Broadway and as such will need a Force Account and NYCT approved plans. | Replace old unlined cast iron pipe water main and improve water main distribution in the following areas: 1) Washington Square North between 5th Ave. & Washington Square East 2) Washington Square East between Washington Square North & Washington Square South 3) Washington Square South between Washington Square East & Thompson St. 4) West 4 Street between Washington Square East & Broadway 5)The intersection of 5th Ave. & Washington Square North Notes: - The project is located in a historic district and will need to be coordinated with LPC, - The project is in the vicinity of NYCT subway line on Broadway and as such will need a Force Account and NYCT approved plans. | Manhattan |  | Environmental Protection | Construction 25-50% | Water | Standard | In-House | DDC Managed/Consultant | PIMS | FALSE |  | 2013 | 2015 |  | DDC
MED609 | MED-609 | Y | Infrastructure | MANHATTAN & CITYWIDE | CONNECT SHAFTS 24B, 25B, 27B, 30B TO SYSTEM. | Sewer and Trunk Water Main in W.60th Street from West End Avenue to Columbus Avenue, Etc., to connect Shaft 24B to the distribution system, Together with all work Incidental Thereto, Borough of Manhattan. | Installation of 48", 36", 20", and 12" water mains to connect Shafts 24B, 25B, 27B, and 30B to the Distribution System; together with all work incidental thereto, Borough of Manhattan. | Manhattan |  | Environmental Protection | Construction 75%-Subst. | Water | Standard | In-House | Standard Consultant | PIMS | FALSE |  | 2010 | 2012 |  | DDC
MED611 | MED-611 | Y | Infrastructure | MANHATTAN & CITYWIDE | TRUNK WATER MAIN REPLACEMENT IN TRANSVERSE RD3, MN | Trunk Water Main Replacement in: Transverse Rd 3 between E86 Street and E85 Street and at Intersection of 5th Avenue and E85 Street. Distribution Water Main in Transverse Rd between E86 Street and E85 Street and at Intersection of 5th Avenue and E85 Street. | Trunk Water Main Replacement in: Transverse Rd 3 between E86 Street and E85 Street and at Intersection of 5th Avenue and E85 Street. Distribution Water Main in Transverse Rd between E86 Street and E85 Street and at Intersection of 5th Avenue and E85 Street. | Manhattan |  | Environmental Protection | On-Hold | Water | Critical | In-House |  | PIMS | FALSE |  | 2022 | 2023 |  | DDC
MED616 | MED-616 | Y | Infrastructure | MANHATTAN & CITYWIDE | TRUNK & DIST WM IN W 124TH STREET, MNS | CONSTRUCTION OF TRUNK & DIST WM IN W 124TH STREET, MNS | CONSTRUCTION OF TRUNK & DIST WM IN W 124TH STREET, MN | Manhattan |  | Environmental Protection | On-Hold | Water | Critical | In-House |  | PIMS | FALSE |  | 2016 | 2018 |  | DDC
MED617 | MED-617 | Y | Infrastructure | Manhattan & Citywide | DIST WM EXTEN & REPLACMTS, NEW BLGS | Distribution Water Main Extension and/or Replacement (New Buildings) at the following locations: 1. West 26th St. from 11th Ave. to 12th Ave. (Survey transmitted to Design on 01/20/2011) - No NYCT facility 2. 49th St. from 5th Ave. to 6th Ave. (Survey transmitted to Design on 5/12/11) - Interference with NYCT facility 3. West 10th St. West St. to 5th Ave. (Survey transmitted to Design on 6/02/11) - Interference with NYCT facility 4. Asser Levy Place, E. 23rd St. to E. 25th St. Following locations (4, 6, and 7) are transferred to MED625: 4. West 14th St.(N&S) from 9th Ave. to 10th Ave.; West 13th St. 9th Ave. to 10th Ave.; Little West 12th St. from 9th Ave. to West St.; from Greenwich St. to Washington St.; Washington St. from Bethune St. to W.14th St. (Survey ordered on 06/11/2010 expecting delivery on 07/22/11) - No NYCT facility 5. South Street from Promenade to Gouverneur Lane (Survey received and returned to ESSU, location is CANCELLED) 6. West 13th Street b/t 7th & 8th Ave. (Survey ordered on 12/02/10, expecting delivery on 07/29/11) - Interference with NYCT facility 7. Bowery (East & West side) b/t East 4th Street & Canal Street (Survey ordered 12/02/10, expecting delivery on 07/29/11) - Interference with NYCT facility | Provide distribution water main extensions (and replacements) for new buildings. |  |  | Environmental Protection | Substantial Completion | Water | Standard | In-House | DDC Managed | PIMS | FALSE

## Schedule
ProjectId | Benchmark (Y/N) | ProjectedProjectStart | ProjectedDesignStart | ProjectedDesignCompletion | ProjectedConstructionStart | ProjectedConstructionCompletion | OrgProjectStart | OrgDesignStart | OrgDesignCompletion | OrgConstructionStart | OrgConstructionCompletion | ClientExtProjectStart | ClientExtOrgDesignStart | ClientExtOrgDesignCompletion | ClientExtOrgConstructionStart | ClientExtOrgConstructionCompletion | ActProjectStart | ActDesignStart | ActDesignCompletion | ActConstructionStart | ActConstructionCompletion | ClientExtBaseDesignCompletion | ClientExtBaseConstructionCompletion | DesignBaselineProjectStart | ConstructionBaselineProjectStart | DesignBaselineDesignStart | ConstructionBaselineDesignStart | OrgSchematicDesignCompletion | ProjectedSchematicDesignCompletion | ActSchematicDesignCompletion | DesignBaselineSchematicDesignCompletion | ConstructionBaselineSchematicDesignCompletion | OrgDesignDevelopmentCompletion | ProjectedDesignDevelopmentCompletion | ActDesignDevelopmentCompletion | DesignBaselineDesignDevelopmentCompletion | ConstructionBaselineDesignDevelopmentCompletion | DesignBaselineDesignCompletion | ConstructionBaselineDesignCompletion | DesignBaselineConstructionStart | ConstructionBaselineConstructionStart | DesignBaselineConstructionCompletion | ConstructionBaselineConstructionCompletion | OrgProjectCloseout | ProjectedProjectCloseout | ActProjectCloseout | DesignBaselineProjectCloseout | ConstructionBaselineProjectCloseout | CreatedDate | ModifiedDate
ACEDOS501 | Y | 2014-07-11 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2014-12-23 00:00:00.0000000 +00:00 | 2016-11-10 00:00:00.0000000 +00:00 | 2017-11-11 00:00:00.0000000 +00:00 | 2014-07-11 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2014-12-29 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2014-07-11 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2014-12-29 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2014-07-11 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2014-12-23 00:00:00.0000000 +00:00 | 2015-08-11 00:00:00.0000000 +00:00 | 2016-04-08 18:00:00.0000000 +00:00 | 2014-12-23 00:00:00.0000000 +00:00 | 2017-11-11 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-01 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 |  |  |  | 2014-10-01 00:00:00.0000000 +00:00 | 2014-10-01 00:00:00.0000000 +00:00 | [8 empty] | 2018-06-29 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2017-02-07 00:00:00.0000000 +00:00 |  |  |  | 2017-09-12 10:25:44.1113172 -04:00
ACEDOS503 | Y | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2017-05-30 00:00:00.0000000 +00:00 | 2017-07-03 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2017-05-30 00:00:00.0000000 +00:00 | 2017-07-03 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | [5 empty] | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-14 17:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | 2017-07-03 17:00:00.0000000 +00:00 |  | 2017-05-30 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2017-03-14 00:00:00.0000000 +00:00 | 2017-03-14 00:00:00.0000000 +00:00 | 2017-03-14 00:00:00.0000000 +00:00 | 2017-03-14 00:00:00.0000000 +00:00 | 2017-03-14 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | 2017-05-30 00:00:00.0000000 +00:00 | 2017-05-30 00:00:00.0000000 +00:00 | 2017-07-03 00:00:00.0000000 +00:00 | 2017-07-03 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2019-03-01 00:00:00.0000000 +00:00 | 2019-03-01 00:00:00.0000000 +00:00 |  | 2019-03-01 00:00:00.0000000 +00:00 | 2019-03-01 00:00:00.0000000 +00:00 |  | 2017-09-06 10:32:10.3580276 -04:00
ACEDOT601 | Y
ACEDOT602 | Y
ACSLSPCAR | Y | 2015-08-20 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2016-03-14 00:00:00.0000000 +00:00 | 2017-08-29 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2016-02-05 00:00:00.0000000 +00:00 | 2016-06-03 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2016-02-05 00:00:00.0000000 +00:00 | 2016-06-03 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 |  | 2016-02-17 00:00:00.0000000 +00:00 | 2017-03-23 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | [20 empty] | 2018-06-03 00:00:00.0000000 +00:00 | 2019-10-29 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-25 17:37:35.4669730 -04:00
ADULTCARE | Y
AGCOVELLO | Y | 2008-12-23 00:00:00.0000000 +00:00 | 2011-06-23 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2015-06-23 00:00:00.0000000 +00:00 | 2008-12-23 00:00:00.0000000 +00:00 | 2009-05-27 00:00:00.0000000 +00:00 | 2010-03-04 00:00:00.0000000 +00:00 | 2010-09-06 00:00:00.0000000 +00:00 | 2011-03-27 00:00:00.0000000 +00:00 | 2008-12-23 00:00:00.0000000 +00:00 | 2011-06-23 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-12-18 00:00:00.0000000 +00:00 | 2016-03-28 00:00:00.0000000 +00:00 | 2008-12-23 00:00:00.0000000 +00:00 | 2011-06-23 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2015-06-23 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2008-12-23 00:00:00.0000000 +00:00 | 2008-12-23 00:00:00.0000000 +00:00 | 2011-06-23 00:00:00.0000000 +00:00 | 2011-06-23 00:00:00.0000000 +00:00 | 2009-09-07 00:00:00.0000000 +00:00 | 2012-01-03 00:00:00.0000000 +00:00 | 2012-01-03 00:00:00.0000000 +00:00 | 2012-01-03 00:00:00.0000000 +00:00 | 2012-01-03 00:00:00.0000000 +00:00 | 2010-01-11 00:00:00.0000000 +00:00 | 2012-08-06 00:00:00.0000000 +00:00 | 2012-08-06 00:00:00.0000000 +00:00 | 2012-08-06 00:00:00.0000000 +00:00 | 2012-08-06 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2015-06-23 00:00:00.0000000 +00:00 | 2015-06-23 00:00:00.0000000 +00:00 | 2011-09-27 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00
BED776 | Y | 2007-02-15 00:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 | 2018-12-29 00:00:00.0000000 +00:00 | 2019-07-06 00:00:00.0000000 +00:00 | 2021-09-09 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2009-07-15 00:00:00.0000000 +00:00 | 2012-01-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2014-07-13 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2020-04-11 00:00:00.0000000 +00:00 | 2020-10-10 00:00:00.0000000 +00:00 | 2022-10-08 00:00:00.0000000 +00:00 | 2007-02-15 12:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 |  |  |  | 2018-12-29 00:00:00.0000000 +00:00 | 2021-09-09 00:00:00.0000000 +00:00 | 2007-02-15 12:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 | 2010-07-12 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 |  | 2018-01-30 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 | [5 empty] | 2018-12-29 00:00:00.0000000 +00:00 | 2018-12-29 00:00:00.0000000 +00:00 | 2019-07-06 00:00:00.0000000 +00:00 | 2019-07-06 00:00:00.0000000 +00:00 | 2021-09-09 00:00:00.0000000 +00:00 | 2021-09-09 00:00:00.0000000 +00:00 | 2024-09-08 00:00:00.0000000 +00:00 | 2024-09-08 00:00:00.0000000 +00:00 |  | 2024-09-08 00:00:00.0000000 +00:00 | 2024-09-08 00:00:00.0000000 +00:00
BED777 | Y | 2007-02-15 00:00:00.0000000 +00:00 | 2012-07-30 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2016-11-28 00:00:00.0000000 +00:00 | 2019-11-27 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2008-07-15 00:00:00.0000000 +00:00 | 2011-01-15 00:00:00.0000000 +00:00 | 2011-07-15 00:00:00.0000000 +00:00 | 2013-07-13 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2017-07-13 00:00:00.0000000 +00:00 | 2007-02-15 12:00:00.0000000 +00:00 | 2008-07-15 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2016-11-28 17:00:00.0000000 +00:00 |  | 2015-06-25 00:00:00.0000000 +00:00 | 2019-11-27 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2007-02-15 12:00:00.0000000 +00:00 | 2008-07-15 00:00:00.0000000 +00:00 | 2008-07-15 00:00:00.0000000 +00:00 | 2010-09-15 00:00:00.0000000 +00:00 | 2014-09-26 00:00:00.0000000 +00:00 | 2014-09-26 00:00:00.0000000 +00:00 | 2014-09-26 00:00:00.0000000 +00:00 | 2014-09-26 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-25 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2016-11-28 00:00:00.0000000 +00:00 | 2016-11-28 17:00:00.0000000 +00:00 | 2019-11-27 00:00:00.0000000 +00:00 | 2019-11-27 00:00:00.0000000 +00:00 | 2022-11-26 00:00:00.0000000 +00:00 | 2022-11-26 00:00:00.0000000 +00:00 |  | 2022-11-26 00:00:00.0000000 +00:00 | 2022-11-26 00:00:00.0000000 +00:00 |  | 2017-08-30 14:23:51.4870776 -04:00
BED778A | Y | 2011-06-08 00:00:00.0000000 +00:00 | 2013-02-19 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2019-06-16 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2011-06-08 00:00:00.0000000 +00:00 | 2011-12-06 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-11 00:00:00.0000000 +00:00 | 2011-06-08 00:00:00.0000000 +00:00 | 2012-12-15 00:00:00.0000000 +00:00 | 2014-07-04 00:00:00.0000000 +00:00 | 2015-01-02 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2011-06-08 12:00:00.0000000 +00:00 | 2013-02-19 00:00:00.0000000 +00:00 |  |  |  | 2019-02-15 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2011-06-08 00:00:00.0000000 +00:00 | 2011-06-08 00:00:00.0000000 +00:00 | 2013-02-19 00:00:00.0000000 +00:00 | 2013-02-19 00:00:00.0000000 +00:00 | 2012-08-13 00:00:00.0000000 +00:00 | 2018-08-06 00:00:00.0000000 +00:00 |  | 2018-08-06 00:00:00.0000000 +00:00 | 2018-08-06 00:00:00.0000000 +00:00 | [5 empty] | 2019-02-15 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2019-06-16 00:00:00.0000000 +00:00 | 2019-06-16 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2023-06-14 00:00:00.0000000 +00:00 | 2023-06-14 00:00:00.0000000 +00:00 |  | 2023-06-14 00:00:00.0000000 +00:00 | 2023-06-14 00:00:00.0000000 +00:00
BED798 | Y | 2013-03-15 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2016-12-29 00:00:00.0000000 +00:00 | 2017-11-06 00:00:00.0000000 +00:00 | 2021-07-12 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2013-12-01 00:00:00.0000000 +00:00 | 2015-10-08 00:00:00.0000000 +00:00 | 2016-04-06 00:00:00.0000000 +00:00 | 2018-04-08 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2015-04-28 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2017-10-27 00:00:00.0000000 +00:00 | 2013-03-15 12:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2016-12-29 00:00:00.0000000 +00:00 |  |  | 2016-12-29 00:00:00.0000000 +00:00 | 2021-07-12 00:00:00.0000000 +00:00 | 2013-03-15 12:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2016-07-21 00:00:00.0000000 +00:00 | 2016-07-21 00:00:00.0000000 +00:00 | 2016-07-21 00:00:00.0000000 +00:00 | 2016-07-21 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-29 00:00:00.0000000 +00:00 | 2016-12-29 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2021-07-12 00:00:00.0000000 +00:00 | 2021-07-12 00:00:00.0000000 +00:00 | 2024-04-09 00:00:00.0000000 +00:00 | 2024-07-11 00:00:00.0000000 +00:00 |  | 2024-07-11 00:00:00.0000000 +00:00 | 2024-07-11 00:00:00.0000000 +00:00 |  | 2017-09-01 10:56:48.3830923 -04:00
BED809 | Y | 2014-05-16 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2020-09-25 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2020-07-20 00:00:00.0000000 +00:00 | [5 empty] | 2014-05-16 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2017-11-29 00:00:00.0000000 +00:00 |  |  | 2018-03-28 00:00:00.0000000 +00:00 | 2020-09-25 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2017-02-08 00:00:00.0000000 +00:00 | 2017-02-08 00:00:00.0000000 +00:00 | 2017-02-08 00:00:00.0000000 +00:00 | 2017-02-08 00:00:00.0000000 +00:00 | 2017-02-08 00:00:00.0000000 +00:00 | [5 empty] | 2017-11-30 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2020-09-25 00:00:00.0000000 +00:00 | 2020-09-25 00:00:00.0000000 +00:00 | 2023-09-15 00:00:00.0000000 +00:00 | 2023-09-24 00:00:00.0000000 +00:00 |  | 2023-09-24 00:00:00.0000000 +00:00 | 2023-09-24 00:00:00.0000000 +00:00 |  | 2017-11-29 14:21:26.5465906 -05:00
BED819 | Y | 2015-01-13 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2018-11-25 00:00:00.0000000 +00:00 | 2019-07-29 00:00:00.0000000 +00:00 | 2021-07-28 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2019-07-29 00:00:00.0000000 +00:00 | 2021-07-28 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-13 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 |  |  |  | 2018-11-25 00:00:00.0000000 +00:00 | 2021-07-28 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 |  | 2018-01-30 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 | [5 empty] | 2018-11-25 00:00:00.0000000 +00:00 | 2018-11-25 00:00:00.0000000 +00:00 | 2019-07-29 00:00:00.0000000 +00:00 | 2019-07-29 00:00:00.0000000 +00:00 | 2021-07-28 00:00:00.0000000 +00:00 | 2021-07-28 00:00:00.0000000 +00:00 | 2024-07-27 00:00:00.0000000 +00:00 | 2024-07-27 00:00:00.0000000 +00:00 |  | 2024-07-27 00:00:00.0000000 +00:00 | 2024-07-27 00:00:00.0000000 +00:00 |  | 2017-09-01 11:03:40.4389332 -04:00
BEDA001 | Y | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2015-01-10 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | [5 empty] | 2014-07-17 17:00:00.0000000 +00:00 | 2014-07-18 17:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2015-10-19 17:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-09 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2020-10-15 00:00:00.0000000 +00:00 | 2020-10-15 00:00:00.0000000 +00:00 |  | 2020-10-15 00:00:00.0000000 +00:00 | 2020-10-15 00:00:00.0000000 +00:00 |  | 2017-10-16 08:15:25.8292261 -04:00
BEDA002 | Y | 2015-02-13 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2015-11-27 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2018-10-02 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2015-12-28 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | 2017-07-06 00:00:00.0000000 +00:00 | [5 empty] | 2015-02-13 17:00:00.0000000 +00:00 | 2015-05-15 17:00:00.0000000 +00:00 | 2015-11-27 00:00:00.0000000 +00:00 | 2016-10-03 17:00:00.0000000 +00:00 |  | 2015-11-27 00:00:00.0000000 +00:00 | 2018-10-02 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-27 00:00:00.0000000 +00:00 | 2015-11-27 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2018-10-02 00:00:00.0000000 +00:00 | 2018-10-02 00:00:00.0000000 +00:00 | 2020-10-01 00:00:00.0000000 +00:00 | 2021-10-01 00:00:00.0000000 +00:00 |  | 2021-10-01 00:00:00.0000000 +00:00 | 2021-10-01 00:00:00.0000000 +00:00 |  | 2017-08-30 14:28:02.3448548 -04:00
BEDA003 | Y | 2015-02-13 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-12-14 00:00:00.0000000 +00:00 | 2018-03-12 00:00:00.0000000 +00:00 | 2019-09-07 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2017-07-16 00:00:00.0000000 +00:00 | 2018-07-17 00:00:00.0000000 +00:00 | [5 empty] | 2015-02-13 00:00:00.0000000 +00:00 | 2016-07-05 18:00:00.0000000 +00:00 | 2016-12-14 00:00:00.0000000 +00:00 |  |  | 2016-12-14 00:00:00.0000000 +00:00 | 2019-09-07 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2016-07-05 18:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 |  | 2016-09-30 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-14 00:00:00.0000000 +00:00 | 2016-12-14 00:00:00.0000000 +00:00 | 2018-03-12 00:00:00.0000000 +00:00 | 2018-03-12 00:00:00.0000000 +00:00 | 2019-09-07 00:00:00.0000000 +00:00 | 2019-09-07 00:00:00.0000000 +00:00 | 2022-09-06 00:00:00.0000000 +00:00 | 2022-09-06 00:00:00.0000000 +00:00 |  | 2022-09-06 00:00:00.0000000 +00:00 | 2022-09-06 00:00:00.0000000 +00:00 |  | 2017-11-21 10:36:57.6321343 -05:00
C114NEWRI | Y | 2010-10-25 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2021-04-11 00:00:00.0000000 +00:00 | 2010-10-25 00:00:00.0000000 +00:00 | 2011-09-16 00:00:00.0000000 +00:00 | 2013-12-14 00:00:00.0000000 +00:00 | 2014-05-14 00:00:00.0000000 +00:00 | 2017-10-24 00:00:00.0000000 +00:00 | 2010-10-25 00:00:00.0000000 +00:00 | 2011-12-15 00:00:00.0000000 +00:00 | 2016-09-10 00:00:00.0000000 +00:00 | 2017-02-08 00:00:00.0000000 +00:00 | 2020-07-21 00:00:00.0000000 +00:00 | 2010-10-25 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 |  |  |  | 2020-05-20 00:00:00.0000000 +00:00 | 2021-04-11 00:00:00.0000000 +00:00 | [20 empty] | 2019-10-24 00:00:00.0000000 +00:00 | [5 empty] | 2017-09-15 11:44:07.7724220 -04:00
C114NEWRIP1 | Y | 2013-04-29 00:00:00.0000000 +00:00 | 2013-04-30 00:00:00.0000000 +00:00 | 2013-09-18 00:00:00.0000000 +00:00 | 2014-07-29 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2013-04-30 00:00:00.0000000 +00:00 | 2013-09-18 00:00:00.0000000 +00:00 | 2014-07-29 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2013-04-30 00:00:00.0000000 +00:00 | 2013-09-18 00:00:00.0000000 +00:00 | 2014-07-29 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2013-04-30 00:00:00.0000000 +00:00 |  | 2014-07-29 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 |  | 2015-02-23 00:00:00.0000000 +00:00
C114NEWRIP2 | Y | 2014-07-02 00:00:00.0000000 +00:00 | 2014-07-03 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2015-08-12 00:00:00.0000000 +00:00 | 2017-06-30 17:00:00.0000000 +00:00 | 2014-07-02 00:00:00.0000000 +00:00 | 2014-07-03 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2015-07-24 00:00:00.0000000 +00:00 | 2016-08-14 00:00:00.0000000 +00:00 | 2014-07-02 00:00:00.0000000 +00:00 | 2014-07-03 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2015-08-12 00:00:00.0000000 +00:00 | 2016-09-02 00:00:00.0000000 +00:00 | 2014-07-02 00:00:00.0000000 +00:00 | 2014-07-03 00:00:00.0000000 +00:00 |  | 2015-08-12 00:00:00.0000000 +00:00 |  | 2015-03-06 00:00:00.0000000 +00:00 | 2017-08-12 00:00:00.0000000 +00:00 | [20 empty] | 2018-08-14 00:00:00.0000000 +00:00
C75FCADEMDC | Y | 2014-11-25 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 | 2017-07-03 00:00:00.0000000 +00:00 | 2018-06-13 00:00:00.0000000 +00:00 | 2014-11-25 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2016-06-21 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2018-01-19 00:00:00.0000000 +00:00 | 2014-11-25 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2016-06-21 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2018-01-19 00:00:00.0000000 +00:00 | 2014-11-25 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 |  |  |  | 2016-10-21 00:00:00.0000000 +00:00 | 2018-06-13 00:00:00.0000000 +00:00 | [20 empty] | 2018-11-16 00:00:00.0000000 +00:00 | 2018-09-22 00:00:00.0000000 +00:00
C75-FCADEMT | Y | 2007-11-12 00:00:00.0000000 +00:00 | 2007-11-12 00:00:00.0000000 +00:00 | 2009-02-26 00:00:00.0000000 +00:00 | 2009-07-09 00:00:00.0000000 +00:00 | 2016-12-31 00:00:00.0000000 +00:00 | 2007-11-12 00:00:00.0000000 +00:00 | 2007-11-12 00:00:00.0000000 +00:00 | 2008-12-06 00:00:00.0000000 +00:00 | 2009-06-15 00:00:00.0000000 +00:00 | 2011-04-28 00:00:00.0000000 +00:00 | 2007-11-12 00:00:00.0000000 +00:00 | 2007-11-12 00:00:00.0000000 +00:00 | 2009-02-27 00:00:00.0000000 +00:00 | 2009-09-06 00:00:00.0000000 +00:00 | 2016-08-14 00:00:00.0000000 +00:00 | 2007-11-12 00:00:00.0000000 +00:00 | 2007-11-12 00:00:00.0000000 +00:00 |  | 2009-07-09 00:00:00.0000000 +00:00 |  | 2009-02-27 00:00:00.0000000 +00:00 | 2016-06-16 00:00:00.0000000 +00:00
C75FCADGRVC | Y | 2010-06-07 00:00:00.0000000 +00:00 | 2011-04-12 00:00:00.0000000 +00:00 | 2012-07-20 00:00:00.0000000 +00:00 | 2013-08-12 00:00:00.0000000 +00:00 | 2015-11-28 00:00:00.0000000 +00:00 | 2010-06-07 00:00:00.0000000 +00:00 | 2010-11-23 00:00:00.0000000 +00:00 | 2012-05-29 00:00:00.0000000 +00:00 | 2012-09-26 00:00:00.0000000 +00:00 | 2013-11-26 00:00:00.0000000 +00:00 | 2010-06-07 00:00:00.0000000 +00:00 | 2011-04-12 00:00:00.0000000 +00:00 | 2012-07-20 00:00:00.0000000 +00:00 | 2013-08-21 00:00:00.0000000 +00:00 | 2015-08-10 00:00:00.0000000 +00:00 | 2010-06-07 00:00:00.0000000 +00:00 | 2011-04-12 00:00:00.0000000 +00:00 |  | 2013-08-12 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2012-07-20 00:00:00.0000000 +00:00 | 2015-02-08 00:00:00.0000000 +00:00
C75-FCADNIC | Y | 2006-08-07 00:00:00.0000000 +00:00 | 2006-08-08 00:00:00.0000000 +00:00 | 2008-04-02 00:00:00.0000000 +00:00 | 2008-10-15 00:00:00.0000000 +00:00 | 2011-08-01 00:00:00.0000000 +00:00 | 2006-08-07 00:00:00.0000000 +00:00 | 2006-08-08 00:00:00.0000000 +00:00 | 2008-04-11 00:00:00.0000000 +00:00 | 2008-09-23 00:00:00.0000000 +00:00 | 2010-04-10 00:00:00.0000000 +00:00 | 2006-08-07 00:00:00.0000000 +00:00 | 2006-08-08 00:00:00.0000000 +00:00 | 2008-04-02 00:00:00.0000000 +00:00 | 2008-10-14 00:00:00.0000000 +00:00 | 2011-07-30 00:00:00.0000000 +00:00 | 2006-08-07 00:00:00.0000000 +00:00 | 2006-08-08 00:00:00.0000000 +00:00 |  | 2008-10-15 00:00:00.0000000 +00:00 | 2011-08-01 00:00:00.0000000 +00:00 | 2008-04-02 00:00:00.0000000 +00:00 | 2011-07-31 00:00:00.0000000 +00:00
CC1C3 | Y | 2012-07-13 00:00:00.0000000 +00:00 | 2012-12-14 00:00:00.0000000 +00:00 | 2013-11-04 00:00:00.0000000 +00:00 | 2014-05-09 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2012-07-13 00:00:00.0000000 +00:00 | 2012-10-12 00:00:00.0000000 +00:00 | 2013-08-07 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2014-12-05 00:00:00.0000000 +00:00 | 2012-07-13 00:00:00.0000000 +00:00 | 2012-11-26 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2015-09-16 00:00:00.0000000 +00:00 | 2012-07-13 00:00:00.0000000 +00:00 | 2012-12-14 00:00:00.0000000 +00:00 | 2013-11-04 00:00:00.0000000 +00:00 | 2014-05-09 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2013-11-04 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 |  | 2012-07-13 00:00:00.0000000 +00:00 |  | 2012-12-14 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 |  | 2013-01-15 00:00:00.0000000 +00:00 | 2013-05-10 00:00:00.0000000 +00:00 | 2013-05-10 00:00:00.0000000 +00:00 | 2013-05-10 00:00:00.0000000 +00:00 |  | 2013-05-10 00:00:00.0000000 +00:00 |  | 2013-11-04 00:00:00.0000000 +00:00 |  | 2014-05-09 00:00:00.0000000 +00:00 |  | 2015-07-27 00:00:00.0000000 +00:00 | 2017-01-10 00:00:00.0000000 +00:00 | 2017-01-10 00:00:00.0000000 +00:00 |  |  | 2017-01-10 00:00:00.0000000 +00:00
CC253B-1 | Y | 2014-04-07 00:00:00.0000000 +00:00 |  |  | 2014-07-28 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2014-04-07 00:00:00.0000000 +00:00 |  |  | 2014-07-28 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2014-04-07 00:00:00.0000000 +00:00 |  |  | 2014-07-28 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2014-04-07 00:00:00.0000000 +00:00 |  |  | 2014-07-28 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 |  | 2015-06-30 00:00:00.0000000 +00:00 | [20 empty] | 2018-04-30 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00
CITYHALLR | Y | 2013-11-01 00:00:00.0000000 +00:00 |  |  | 2014-08-06 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2013-11-01 00:00:00.0000000 +00:00 | 2013-12-01 00:00:00.0000000 +00:00 | 2014-02-01 00:00:00.0000000 +00:00 | 2014-07-08 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2013-11-01 00:00:00.0000000 +00:00 | 2013-12-01 00:00:00.0000000 +00:00 | 2014-02-01 00:00:00.0000000 +00:00 | 2014-07-08 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2013-11-01 00:00:00.0000000 +00:00 |  |  | 2014-08-06 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | [28 empty] | 2017-10-04 15:25:48.8401909 -04:00
CJCREN | Y
CMEHVAC | Y | 2016-02-29 00:00:00.0000000 +00:00 | 2017-05-26 00:00:00.0000000 +00:00 | 2018-04-16 00:00:00.0000000 +00:00 | 2018-11-15 00:00:00.0000000 +00:00 | 2019-05-15 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2018-01-09 00:00:00.0000000 +00:00 | 2018-05-08 00:00:00.0000000 +00:00 | 2018-11-05 00:00:00.0000000 +00:00 | [5 empty] | 2016-02-29 17:00:00.0000000 +00:00 | 2017-05-26 00:00:00.0000000 +00:00 |  |  |  | 2018-01-09 00:00:00.0000000 +00:00 | [6 empty] | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-20 00:00:00.0000000 +00:00 |  |  |  | 2017-12-15 00:00:00.0000000 +00:00 | [9 empty] | 2019-11-05 00:00:00.0000000 +00:00 | 2020-05-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-13 09:35:46.2664826 -04:00
CO272ELC2 | Y | 2014-11-14 17:00:00.0000000 +00:00 | 2015-01-15 17:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-12-24 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-12-24 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2017-03-18 00:00:00.0000000 +00:00 | 2019-05-03 00:00:00.0000000 +00:00 | 2014-11-14 17:00:00.0000000 +00:00 | 2015-01-15 17:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 |  |  | 2017-05-31 00:00:00.0000000 +00:00 |  | 2014-11-14 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 | 2015-11-16 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-12-24 00:00:00.0000000 +00:00 | 2019-12-24 00:00:00.0000000 +00:00 | 2020-02-18 00:00:00.0000000 +00:00 | 2020-02-18 00:00:00.0000000 +00:00 |  | 2020-02-18 00:00:00.0000000 +00:00 | 2020-02-18 00:00:00.0000000 +00:00 |  | 2017-10-11 13:57:05.6610526 -04:00
CO272ELV2 | Y | 2012-07-08 18:00:00.0000000 +00:00 | 2012-07-26 18:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2017-04-18 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2012-07-08 00:00:00.0000000 +00:00 | 2012-07-26 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2017-04-18 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | 2015-09-26 00:00:00.0000000 +00:00 | 2016-03-13 00:00:00.0000000 +00:00 | 2017-03-14 00:00:00.0000000 +00:00 | 2012-07-08 18:00:00.0000000 +00:00 | 2012-07-26 18:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2017-04-18 00:00:00.0000000 +00:00 |  | 2016-01-07 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2012-07-08 00:00:00.0000000 +00:00 | 2012-07-08 00:00:00.0000000 +00:00 | 2012-07-26 00:00:00.0000000 +00:00 | 2012-07-26 00:00:00.0000000 +00:00 | 2012-08-26 00:00:00.0000000 +00:00 | 2012-08-26 00:00:00.0000000 +00:00 | 2012-08-26 00:00:00.0000000 +00:00 | 2012-08-26 00:00:00.0000000 +00:00 | 2012-08-26 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2017-04-18 00:00:00.0000000 +00:00 | 2017-04-18 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2020-04-01 00:00:00.0000000 +00:00 | 2020-04-01 00:00:00.0000000 +00:00 |  | 2020-04-01 00:00:00.0000000 +00:00 | 2020-04-01 00:00:00.0000000 +00:00 |  | 2017-09-26 14:03:51.4376621 -04:00
CO277ELV2 | Y | 2008-06-20 00:00:00.0000000 +00:00 | 2012-07-26 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2018-12-31 00:00:00.0000000 +00:00 | 2008-06-20 00:00:00.0000000 +00:00 | 2012-07-26 00:00:00.0000000 +00:00 | 2014-11-15 00:00:00.0000000 +00:00 | 2015-08-13 00:00:00.0000000 +00:00 | 2016-08-13 00:00:00.0000000 +00:00 | 2008-06-20 00:00:00.0000000 +00:00 | 2012-07-26 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2008-06-20 00:00:00.0000000 +00:00 | 2012-07-26 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 |  | 2017-07-04 00:00:00.0000000 +00:00 | 2019-01-31 00:00:00.0000000 +00:00 | [20 empty] | 2018-08-13 00:00:00.0000000 +00:00 | 2019-01-31 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-13 10:35:02.1650192 -04:00
CO277FA | Y | [48 empty] | 2017-10-12 16:26:07.9652749 -04:00
CO278EXT2 | Y | 2015-05-15 00:00:00.0000000 +00:00 | 2017-05-23 00:00:00.0000000 +00:00 | 2019-01-07 00:00:00.0000000 +00:00 | 2019-07-10 00:00:00.0000000 +00:00 | 2021-12-15 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2017-05-23 00:00:00.0000000 +00:00 | 2019-01-07 00:00:00.0000000 +00:00 | 2019-07-10 00:00:00.0000000 +00:00 | 2021-12-15 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-15 00:00:00.0000000 +00:00 | 2017-05-23 00:00:00.0000000 +00:00 |  |  |  | 2019-01-07 00:00:00.0000000 +00:00 |  | 2015-05-15 00:00:00.0000000 +00:00 |  | 2017-05-23 00:00:00.0000000 +00:00 |  | 2018-03-20 00:00:00.0000000 +00:00 | 2018-03-20 00:00:00.0000000 +00:00 |  |  |  | 2018-05-25 00:00:00.0000000 +00:00 | 2018-05-25 00:00:00.0000000 +00:00 | [9 empty] | 2022-10-24 00:00:00.0000000 +00:00 | 2022-10-24 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-12 10:46:33.2650638 -04:00
CO278FA3 | Y | 2015-07-07 00:00:00.0000000 +00:00 | 2017-03-31 00:00:00.0000000 +00:00 | 2018-05-12 00:00:00.0000000 +00:00 | 2019-01-19 00:00:00.0000000 +00:00 | 2022-02-22 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2017-03-31 00:00:00.0000000 +00:00 | 2018-05-12 00:00:00.0000000 +00:00 | 2019-01-19 00:00:00.0000000 +00:00 | 2022-02-22 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-07 00:00:00.0000000 +00:00 | 2017-03-31 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-07 00:00:00.0000000 +00:00 |  | 2017-03-31 00:00:00.0000000 +00:00 |  | 2017-07-17 00:00:00.0000000 +00:00 | 2017-07-17 00:00:00.0000000 +00:00 | 2017-07-17 00:00:00.0000000 +00:00 | 2017-07-17 00:00:00.0000000 +00:00 |  | 2017-10-16 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | [7 empty] | 2023-02-17 00:00:00.0000000 +00:00 | 2023-02-17 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-12 10:48:22.5245370 -04:00
CO281BOIL | Y | 2011-07-01 00:00:00.0000000 +00:00 |  |  | 2011-08-23 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2011-07-01 00:00:00.0000000 +00:00 |  |  | 2011-08-23 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2011-07-01 00:00:00.0000000 +00:00 |  |  | 2011-08-23 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2011-07-01 00:00:00.0000000 +00:00 |  |  | 2011-08-23 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 |  | 2013-12-03 00:00:00.0000000 +00:00
CO281ELEC | Y | 2010-10-12 00:00:00.0000000 +00:00 | 2011-06-09 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2013-10-29 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2010-10-12 00:00:00.0000000 +00:00 | 2011-06-09 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2013-10-29 00:00:00.0000000 +00:00 | 2016-02-27 00:00:00.0000000 +00:00 | 2010-10-12 00:00:00.0000000 +00:00 | 2011-06-09 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2013-10-29 00:00:00.0000000 +00:00 | 2016-02-27 00:00:00.0000000 +00:00 | 2010-10-12 00:00:00.0000000 +00:00 | 2011-06-09 00:00:00.0000000 +00:00 |  | 2013-10-29 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2016-02-27 00:00:00.0000000 +00:00
CO281FA | Y | 2012-10-11 00:00:00.0000000 +00:00 | 2012-10-23 00:00:00.0000000 +00:00 | 2014-06-05 00:00:00.0000000 +00:00 | 2013-12-19 00:00:00.0000000 +00:00 | 2015-12-17 00:00:00.0000000 +00:00 | 2012-10-11 00:00:00.0000000 +00:00 | 2012-10-23 00:00:00.0000000 +00:00 | 2013-03-25 00:00:00.0000000 +00:00 | 2013-03-26 00:00:00.0000000 +00:00 | 2014-01-26 00:00:00.0000000 +00:00 | 2012-10-11 00:00:00.0000000 +00:00 | 2012-10-23 00:00:00.0000000 +00:00 | 2013-08-12 00:00:00.0000000 +00:00 | 2013-10-19 00:00:00.0000000 +00:00 | 2015-02-18 00:00:00.0000000 +00:00 | 2012-10-11 00:00:00.0000000 +00:00 | 2012-10-23 00:00:00.0000000 +00:00 |  | 2013-12-19 00:00:00.0000000 +00:00 | 2015-12-17 00:00:00.0000000 +00:00 | 2013-08-12 00:00:00.0000000 +00:00 | 2014-07-26 00:00:00.0000000 +00:00
CO281TOIL | Y | 2015-12-04 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2018-03-02 00:00:00.0000000 +00:00 | 2018-07-25 00:00:00.0000000 +00:00 | 2020-10-20 00:00:00.0000000 +00:00 | 2015-12-04 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2018-03-02 00:00:00.0000000 +00:00 | 2018-07-25 00:00:00.0000000 +00:00 | 2020-10-20 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-04 00:00:00.0000000 +00:00 | 2016-10-18 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-04 00:00:00.0000000 +00:00 |  | 2016-10-18 00:00:00.0000000 +00:00 |  | 2017-04-12 00:00:00.0000000 +00:00 | 2017-04-12 00:00:00.0000000 +00:00 | 2017-05-11 00:00:00.0000000 +00:00 | 2017-05-11 00:00:00.0000000 +00:00 |  | 2017-07-20 00:00:00.0000000 +00:00 | 2017-07-20 00:00:00.0000000 +00:00 | 2017-07-20 00:00:00.0000000 +00:00 | 2017-07-20 00:00:00.0000000 +00:00 | [7 empty] | 2021-05-25 00:00:00.0000000 +00:00 | 2021-05-25 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-18 14:54:50.8319366 -04:00
CO283CTSP | Y | 2013-05-22 00:00:00.0000000 +00:00 |  |  | 2013-10-29 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2013-05-22 00:00:00.0000000 +00:00 |  |  | 2013-10-29 00:00:00.0000000 +00:00 | 2015-11-08 00:00:00.0000000 +00:00 | 2013-05-22 00:00:00.0000000 +00:00 |  |  | 2013-10-29 00:00:00.0000000 +00:00 | 2015-11-08 00:00:00.0000000 +00:00 | 2013-05-22 00:00:00.0000000 +00:00 |  |  | 2013-10-29 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 |  | 2015-11-08 00:00:00.0000000 +00:00
CO283ELEV | Y | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-02-15 00:00:00.0000000 +00:00 | 2015-03-05 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-02-15 00:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-02-15 00:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-02-15 00:00:00.0000000 +00:00 | 2015-03-05 00:00:00.0000000 +00:00 |  | 2015-02-15 00:00:00.0000000 +00:00 | [20 empty] | 2015-09-07 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00
CO283FIRE | Y | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-02-15 00:00:00.0000000 +00:00 | 2016-01-29 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-02-15 00:00:00.0000000 +00:00 | 2014-03-16 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-02-15 00:00:00.0000000 +00:00 | 2014-07-02 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-02-15 00:00:00.0000000 +00:00 | 2016-01-29 00:00:00.0000000 +00:00 |  | 2014-07-02 00:00:00.0000000 +00:00 | [20 empty] | 2016-07-29 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00
CO283SID2 | Y | 2013-01-27 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-12-08 00:00:00.0000000 +00:00 | 2019-03-03 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-12-08 00:00:00.0000000 +00:00 | 2019-03-03 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2014-10-10 00:00:00.0000000 +00:00 | 2015-10-10 00:00:00.0000000 +00:00 | 2018-06-09 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-12-08 17:00:00.0000000 +00:00 |  | 2015-10-15 00:00:00.0000000 +00:00 | 2019-03-03 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2014-12-17 00:00:00.0000000 +00:00 | 2014-12-17 00:00:00.0000000 +00:00 | 2014-12-17 00:00:00.0000000 +00:00 | 2014-12-17 00:00:00.0000000 +00:00 | 2014-12-17 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-12-08 17:00:00.0000000 +00:00 | 2016-12-08 00:00:00.0000000 +00:00 | 2019-03-03 00:00:00.0000000 +00:00 | 2019-03-03 00:00:00.0000000 +00:00 | 2020-03-03 00:00:00.0000000 +00:00 | 2020-03-03 00:00:00.0000000 +00:00 |  | 2020-03-03 00:00:00.0000000 +00:00 | 2020-03-03 00:00:00.0000000 +00:00
CO283TOIL | Y | 2015-12-04 00:00:00.0000000 +00:00 | 2017-10-06 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2020-04-01 00:00:00.0000000 +00:00 | 2022-06-30 00:00:00.0000000 +00:00 | 2015-12-04 00:00:00.0000000 +00:00 | 2017-10-06 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2020-04-01 00:00:00.0000000 +00:00 | 2022-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-04 00:00:00.0000000 +00:00 | 2017-09-27 00:00:00.0000000 +00:00 |  |  |  | 2019-06-18 00:00:00.0000000 +00:00 |  | 2015-12-04 00:00:00.0000000 +00:00 |  | 2017-09-27 00:00:00.0000000 +00:00 |  | 2018-05-22 00:00:00.0000000 +00:00 | 2018-05-22 00:00:00.0000000 +00:00 |  |  |  | 2018-09-21 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | [9 empty] | 2023-01-09 00:00:00.0000000 +00:00 | 2023-01-09 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-13 09:49:22.8726441 -04:00
CO284EXT2 | Y | 2014-11-01 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2016-09-08 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2019-02-20 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2018-05-30 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2018-05-30 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2016-09-08 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 |  | 2016-09-08 00:00:00.0000000 +00:00 | 2019-02-20 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2014-10-01 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2014-10-01 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2016-09-08 00:00:00.0000000 +00:00 | 2016-09-08 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2019-02-20 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 | 2021-06-14 00:00:00.0000000 +00:00 | 2019-05-30 00:00:00.0000000 +00:00 |  | 2019-05-30 00:00:00.0000000 +00:00 | 2020-08-20 00:00:00.0000000 +00:00 |  | 2017-09-13 10:05:06.5602628 -04:00
CO285FIRE | Y | [48 empty] | 2017-10-11 13:49:21.0484145 -04:00
CO290BCHJ | Y | 2014-02-06 00:00:00.0000000 +00:00 | 2014-03-06 00:00:00.0000000 +00:00 | 2015-01-31 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2019-10-04 00:00:00.0000000 +00:00 | 2014-02-06 00:00:00.0000000 +00:00 | 2014-03-06 00:00:00.0000000 +00:00 | 2015-01-31 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2017-10-14 00:00:00.0000000 +00:00 | 2014-02-06 00:00:00.0000000 +00:00 | 2014-03-06 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-06-11 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2014-02-06 00:00:00.0000000 +00:00 | 2014-03-06 00:00:00.0000000 +00:00 | 2015-01-31 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 |  | 2015-01-31 00:00:00.0000000 +00:00 | 2019-10-04 00:00:00.0000000 +00:00 | 2014-02-06 00:00:00.0000000 +00:00 | 2014-02-06 00:00:00.0000000 +00:00 | 2014-03-06 00:00:00.0000000 +00:00 | 2014-03-06 00:00:00.0000000 +00:00 | 2014-06-01 00:00:00.0000000 +00:00 | 2014-06-01 00:00:00.0000000 +00:00 | 2014-06-01 00:00:00.0000000 +00:00 |  |  | 2014-09-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 |  |  | 2015-01-31 00:00:00.0000000 +00:00 | 2015-01-31 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2019-10-04 00:00:00.0000000 +00:00 | 2019-10-04 00:00:00.0000000 +00:00 | 2020-12-31 00:00:00.0000000 +00:00 | 2020-12-31 00:00:00.0000000 +00:00 |  | 2020-12-31 00:00:00.0000000 +00:00 | 2020-12-31 00:00:00.0000000 +00:00 |  | 2017-12-11 09:08:30.6149936 -05:00
CO290BCHJ-2 | Y |  |  |  | 2017-01-12 00:00:00.0000000 +00:00 | 2020-01-11 00:00:00.0000000 +00:00 |  |  |  | 2017-01-12 00:00:00.0000000 +00:00 | 2019-01-11 00:00:00.0000000 +00:00 | [8 empty] | 2017-01-12 00:00:00.0000000 +00:00 |  |  | 2020-01-11 00:00:00.0000000 +00:00 | [17 empty] | 2017-01-12 00:00:00.0000000 +00:00 |  | 2020-01-11 00:00:00.0000000 +00:00 | 2021-01-11 00:00:00.0000000 +00:00 | 2021-01-11 00:00:00.0000000 +00:00 |  |  | 2021-01-11 00:00:00.0000000 +00:00 |  | 2017-09-18 11:11:36.7815001 -04:00
CO293BOIL | Y | [48 empty] | 2017-10-12 16:28:09.5310558 -04:00
CO293ELEC | Y | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-01-27 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-01-27 00:00:00.0000000 +00:00 | 2014-05-26 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-01-27 00:00:00.0000000 +00:00 | 2015-03-02 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-01-27 00:00:00.0000000 +00:00 | 2015-03-02 00:00:00.0000000 +00:00 |  | 2015-03-02 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | [14 empty] | 2013-01-27 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2015-05-27 00:00:00.0000000 +00:00 | 2015-05-27 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-15 09:12:40.9283273 -04:00
CO293SP | Y | 2017-03-21 00:00:00.0000000 +00:00 | 2018-02-22 00:00:00.0000000 +00:00 | 2019-03-25 00:00:00.0000000 +00:00 | 2019-11-22 00:00:00.0000000 +00:00 | 2023-01-13 00:00:00.0000000 +00:00 | 2017-03-21 00:00:00.0000000 +00:00 | 2018-02-22 00:00:00.0000000 +00:00 | 2019-03-25 00:00:00.0000000 +00:00 | 2019-11-22 00:00:00.0000000 +00:00 | 2023-01-13 00:00:00.0000000 +00:00 | [5 empty] | 2017-03-21 00:00:00.0000000 +00:00 | [6 empty] | 2017-03-21 00:00:00.0000000 +00:00 |  |  |  | 2018-05-31 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 |  |  |  | 2018-08-07 00:00:00.0000000 +00:00 | 2018-08-07 00:00:00.0000000 +00:00 | [9 empty] | 2024-01-08 00:00:00.0000000 +00:00 | 2024-01-08 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-04 15:47:37.8561121 -04:00
CO294BOIL | Y | [48 empty] | 2017-10-12 16:28:33.6552353 -04:00
CO294ELEC | Y | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-01-27 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-01-27 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-01-27 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 |  |  | 2013-01-27 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 |  | 2015-06-05 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | [14 empty] | 2013-01-27 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-15 13:04:35.8365329 -04:00
CO294LL | Y | 2015-09-17 00:00:00.0000000 +00:00 |  |  |  |  | 2015-09-17 00:00:00.0000000 +00:00 | [9 empty] | 2015-09-17 00:00:00.0000000 +00:00 | [32 empty] | 2017-10-12 16:29:01.4555604 -04:00
CO296ELEC | Y | 2016-09-26 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 |  |  |  | 2016-09-26 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | [8 empty] | 2016-09-26 00:00:00.0000000 +00:00 | [32 empty] | 2017-10-12 16:59:57.2351890 -04:00
CO296EX7B | Y
CO296EXT7 | Y | 2016-04-28 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 |  |  |  | 2016-04-28 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 | [8 empty] | 2016-04-28 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 | [31 empty] | 2017-10-17 15:12:52.8497121 -04:00
CO299EXTR | Y | [48 empty] | 2017-10-11 13:50:48.7817565 -04:00
CO299FIRE | Y | [48 empty] | 2017-10-11 13:47:32.9750224 -04:00
CO300ELV2 | Y | 2013-04-24 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | 2014-11-05 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2006-03-21 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | 2014-01-10 00:00:00.0000000 +00:00 | 2014-10-29 00:00:00.0000000 +00:00 | 2016-12-07 00:00:00.0000000 +00:00 | 2006-03-21 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-11-03 00:00:00.0000000 +00:00 | 2017-12-12 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | 2014-11-05 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2018-02-08 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | 2013-09-13 00:00:00.0000000 +00:00 | 2013-09-13 00:00:00.0000000 +00:00 | 2013-09-13 00:00:00.0000000 +00:00 | 2013-09-13 00:00:00.0000000 +00:00 | 2013-09-13 00:00:00.0000000 +00:00 | 2013-09-14 00:00:00.0000000 +00:00 | 2013-09-14 00:00:00.0000000 +00:00 | 2013-09-14 00:00:00.0000000 +00:00 | 2013-09-14 00:00:00.0000000 +00:00 | 2013-09-14 00:00:00.0000000 +00:00 | 2014-11-05 00:00:00.0000000 +00:00 | 2014-11-05 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2018-12-07 00:00:00.0000000 +00:00 | 2018-09-30 00:00:00.0000000 +00:00 |  |  | 2018-09-30 00:00:00.0000000 +00:00 |  | 2017-08-29 08:17:09.5854027 -04:00
CO300EXT2 | Y | 2016-03-03 00:00:00.0000000 +00:00 |  |  |  |  | 2016-03-03 00:00:00.0000000 +00:00 | [9 empty] | 2016-03-03 00:00:00.0000000 +00:00 | [32 empty] | 2017-10-11 15:08:06.2322567 -04:00
CO301LL | Y | 2015-10-21 00:00:00.0000000 +00:00 |  |  |  |  | 2015-10-21 00:00:00.0000000 +00:00 | [9 empty] | 2015-10-21 00:00:00.0000000 +00:00 | [6 empty] | 2015-10-21 00:00:00.0000000 +00:00 | [25 empty] | 2017-10-16 14:02:00.6748139 -04:00
CO301PD | Y | 2014-07-14 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2021-05-03 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2021-05-03 00:00:00.0000000 +00:00 | [5 empty] | 2014-07-14 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | [5 empty] | 2014-07-14 00:00:00.0000000 +00:00 |  |  |  | 2018-02-15 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 |  |  |  | 2018-04-06 00:00:00.0000000 +00:00 | 2018-04-06 00:00:00.0000000 +00:00 | [9 empty] | 2022-02-25 00:00:00.0000000 +00:00 | 2022-02-25 00:00:00.0000000 +00:00
CO304LL11 | Y
CO305REHB | Y | 2010-01-13 00:00:00.0000000 +00:00 |  |  | 2010-01-13 00:00:00.0000000 +00:00 | 2016-12-07 00:00:00.0000000 +00:00 | 2010-01-13 00:00:00.0000000 +00:00 |  |  | 2010-01-13 00:00:00.0000000 +00:00 | 2019-01-17 00:00:00.0000000 +00:00 | 2010-01-13 00:00:00.0000000 +00:00 |  |  | 2010-01-13 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2010-01-13 00:00:00.0000000 +00:00 |  |  | 2010-01-13 00:00:00.0000000 +00:00 | 2016-12-07 00:00:00.0000000 +00:00 |  | 2018-11-14 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-20 11:29:15.0009562 -04:00
CO306REHB | Y | [48 empty] | 2017-10-12 16:56:03.4605779 -04:00
CO80ROOF2 | Y | 2013-01-27 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2018-02-05 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2015-09-08 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-05-05 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-08-15 17:00:00.0000000 +00:00 |  | 2015-05-04 00:00:00.0000000 +00:00 | 2018-02-05 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2015-05-02 00:00:00.0000000 +00:00 | 2015-05-02 00:00:00.0000000 +00:00 | 2015-05-02 00:00:00.0000000 +00:00 | 2015-05-02 00:00:00.0000000 +00:00 |  | 2015-06-01 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 |  | 2018-02-05 00:00:00.0000000 +00:00 | 2018-10-26 00:00:00.0000000 +00:00 | 2018-10-26 00:00:00.0000000 +00:00 |  |  | 2018-10-26 00:00:00.0000000 +00:00 |  | 2017-11-14 15:25:57.6315202 -05:00
CO81ELEC | Y | 2016-06-13 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2019-07-02 00:00:00.0000000 +00:00 | 2020-04-06 00:00:00.0000000 +00:00 | 2022-04-08 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2019-07-02 00:00:00.0000000 +00:00 | 2020-04-06 00:00:00.0000000 +00:00 | 2022-04-08 00:00:00.0000000 +00:00 | [5 empty] | 2016-06-13 00:00:00.0000000 +00:00 | [6 empty] | 2016-06-13 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2018-12-03 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 |  | 2019-01-02 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2019-06-03 00:00:00.0000000 +00:00 | 2019-06-03 00:00:00.0000000 +00:00 |  | 2019-06-03 00:00:00.0000000 +00:00 | 2019-06-03 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2019-07-02 00:00:00.0000000 +00:00 | 2020-04-06 00:00:00.0000000 +00:00 | 2020-04-06 00:00:00.0000000 +00:00 | 2022-04-22 00:00:00.0000000 +00:00 | 2022-04-22 00:00:00.0000000 +00:00 | 2022-10-07 00:00:00.0000000 +00:00 | 2022-10-07 00:00:00.0000000 +00:00 |  | 2022-10-07 00:00:00.0000000 +00:00 | 2022-10-07 00:00:00.0000000 +00:00 |  | 2017-09-13 09:59:54.8525767 -04:00
CO81SKY2 | Y | 2013-05-03 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2014-06-27 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2018-10-29 00:00:00.0000000 +00:00 | 2013-05-03 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2014-06-24 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2013-07-01 00:00:00.0000000 +00:00 |  |  | 2014-07-03 00:00:00.0000000 +00:00 | 2015-07-03 00:00:00.0000000 +00:00 | 2013-05-06 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2014-06-27 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 |  | 2014-06-27 00:00:00.0000000 +00:00 | 2018-10-29 00:00:00.0000000 +00:00 | 2013-05-06 00:00:00.0000000 +00:00 | 2013-05-06 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2014-06-24 00:00:00.0000000 +00:00 | 2014-06-24 00:00:00.0000000 +00:00 | 2014-06-27 00:00:00.0000000 +00:00 | 2014-06-27 00:00:00.0000000 +00:00 | 2014-06-27 00:00:00.0000000 +00:00 | 2014-06-27 00:00:00.0000000 +00:00 | 2014-06-27 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 | 2018-10-29 00:00:00.0000000 +00:00 | 2018-10-29 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2019-05-03 00:00:00.0000000 +00:00 |  | 2019-05-03 00:00:00.0000000 +00:00 | 2019-05-03 00:00:00.0000000 +00:00
CONISPH01 | Y | 2010-07-23 00:00:00.0000000 +00:00 | 2011-06-14 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2017-08-31 00:00:00.0000000 +00:00 | 2010-07-23 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2016-01-13 00:00:00.0000000 +00:00 | 2010-07-23 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2013-08-13 00:00:00.0000000 +00:00 | 2014-07-03 00:00:00.0000000 +00:00 | 2019-12-01 00:00:00.0000000 +00:00 | 2010-07-23 00:00:00.0000000 +00:00 | 2011-06-14 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2017-08-31 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2017-08-31 00:00:00.0000000 +00:00 | 2010-07-23 00:00:00.0000000 +00:00 | 2010-07-23 00:00:00.0000000 +00:00 | 2011-06-14 00:00:00.0000000 +00:00 | 2011-06-14 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | [5 empty] | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2017-08-31 00:00:00.0000000 +00:00 | 2017-08-31 00:00:00.0000000 +00:00 | 2020-08-30 00:00:00.0000000 +00:00 | 2020-08-30 00:00:00.0000000 +00:00 |  | 2020-08-30 00:00:00.0000000 +00:00 | 2020-08-30 00:00:00.0000000 +00:00 |  | 2017-09-05 11:16:48.0148462 -04:00
CONISPH2A | Y | 2011-06-24 00:00:00.0000000 +00:00 | 2012-03-16 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2017-07-17 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2012-03-16 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2014-06-05 00:00:00.0000000 +00:00 | 2016-09-21 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2012-07-16 00:00:00.0000000 +00:00 | 2014-09-04 00:00:00.0000000 +00:00 | 2015-03-29 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2011-06-24 12:00:00.0000000 +00:00 | 2012-03-16 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2017-07-17 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2017-07-17 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2012-03-16 00:00:00.0000000 +00:00 | 2012-03-16 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | [5 empty] | 2013-11-11 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2017-07-17 00:00:00.0000000 +00:00 | 2017-07-17 00:00:00.0000000 +00:00 | 2020-07-16 00:00:00.0000000 +00:00 | 2020-07-16 00:00:00.0000000 +00:00 |  | 2020-07-16 00:00:00.0000000 +00:00 | 2020-07-16 00:00:00.0000000 +00:00 |  | 2017-08-30 14:28:39.7992417 -04:00
CONISPH2B | Y | 2011-06-24 00:00:00.0000000 +00:00 | 2012-03-30 00:00:00.0000000 +00:00 | 2015-04-17 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2019-04-23 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2012-03-30 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2014-10-10 00:00:00.0000000 +00:00 | 2017-03-09 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2012-07-27 00:00:00.0000000 +00:00 | 2014-11-08 00:00:00.0000000 +00:00 | 2015-06-06 00:00:00.0000000 +00:00 | 2017-11-03 00:00:00.0000000 +00:00 | 2011-06-24 12:00:00.0000000 +00:00 | 2012-03-30 00:00:00.0000000 +00:00 | 2015-04-17 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 |  | 2016-06-06 00:00:00.0000000 +00:00 | 2019-04-23 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2012-03-30 00:00:00.0000000 +00:00 | 2012-03-30 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-17 00:00:00.0000000 +00:00 | 2015-04-17 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2019-04-23 00:00:00.0000000 +00:00 | 2019-04-23 00:00:00.0000000 +00:00 | 2022-04-22 00:00:00.0000000 +00:00 | 2022-04-22 00:00:00.0000000 +00:00 |  | 2022-04-22 00:00:00.0000000 +00:00 | 2022-04-22 00:00:00.0000000 +00:00 |  | 2017-08-30 14:29:02.7216419 -04:00
CONISPH3A | Y | 2013-03-07 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2013-03-07 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2013-03-07 00:00:00.0000000 +00:00 | 2016-08-14 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2019-08-14 00:00:00.0000000 +00:00 | 2013-03-07 12:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2017-11-29 00:00:00.0000000 +00:00 |  |  | 2017-11-30 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2013-03-07 12:00:00.0000000 +00:00 | 2013-03-07 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2016-12-01 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | [5 empty] | 2017-11-30 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2024-07-14 00:00:00.0000000 +00:00 | 2025-07-14 00:00:00.0000000 +00:00 |  | 2025-07-14 00:00:00.0000000 +00:00 | 2025-07-14 00:00:00.0000000 +00:00 |  | 2017-11-29 14:27:30.8041314 -05:00
CONISPH3B | Y | 2013-03-07 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2017-08-22 00:00:00.0000000 +00:00 | 2020-11-09 00:00:00.0000000 +00:00 | 2013-03-07 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2013-03-07 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2017-10-13 00:00:00.0000000 +00:00 | 2019-10-13 00:00:00.0000000 +00:00 | 2013-03-07 12:00:00.0000000 +00:00 | 2014-09-16 17:00:00.0000000 +00:00 |  |  |  | 2017-12-05 00:00:00.0000000 +00:00 | 2020-11-09 00:00:00.0000000 +00:00 | [20 empty] | 2021-07-16 00:00:00.0000000 +00:00 | 2022-11-11 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-29 10:27:00.7295933 -04:00
CRO-AGS | Y | 2011-03-25 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2020-12-05 00:00:00.0000000 +00:00 | 2011-03-25 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 | 2017-08-17 00:00:00.0000000 +00:00 | [5 empty] | 2011-03-25 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2017-10-26 00:00:00.0000000 +00:00 |  |  | 2017-11-15 00:00:00.0000000 +00:00 |  | 2011-03-25 00:00:00.0000000 +00:00 |  | 2012-05-23 00:00:00.0000000 +00:00 |  | 2012-11-01 00:00:00.0000000 +00:00 | 2012-11-01 00:00:00.0000000 +00:00 | 2012-11-01 00:00:00.0000000 +00:00 | 2012-11-01 00:00:00.0000000 +00:00 |  | 2013-04-01 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 |  | 2017-11-15 00:00:00.0000000 +00:00 |  | 2018-06-19 00:00:00.0000000 +00:00 |  | 2020-12-05 00:00:00.0000000 +00:00 |  | 2018-08-17 00:00:00.0000000 +00:00 | 2021-12-05 00:00:00.0000000 +00:00 |  | 2021-12-05 00:00:00.0000000 +00:00 |  | 2017-10-17 07:00:23.0770000 +00:00
CS-ER-WCP | Y | 2012-06-26 00:00:00.0000000 +00:00 | 2013-08-16 00:00:00.0000000 +00:00 | 2015-12-22 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2021-10-23 00:00:00.0000000 +00:00 | 2012-06-26 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2012-06-26 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-09-16 00:00:00.0000000 +00:00 | 2017-09-14 00:00:00.0000000 +00:00 | 2012-06-26 12:00:00.0000000 +00:00 | 2013-08-16 00:00:00.0000000 +00:00 | 2015-12-22 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 |  | 2015-12-22 00:00:00.0000000 +00:00 | 2021-10-23 00:00:00.0000000 +00:00 | 2012-06-26 12:00:00.0000000 +00:00 | 2012-06-26 12:00:00.0000000 +00:00 | 2013-08-16 00:00:00.0000000 +00:00 | 2013-08-16 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-22 00:00:00.0000000 +00:00 | 2015-12-22 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2021-10-23 00:00:00.0000000 +00:00 | 2021-10-23 00:00:00.0000000 +00:00 | 2021-09-12 00:00:00.0000000 +00:00 | 2024-10-22 00:00:00.0000000 +00:00 |  | 2024-10-22 00:00:00.0000000 +00:00 | 2024-10-22 00:00:00.0000000 +00:00 |  | 2017-08-18 15:52:32.0663954 +00:00
CS-FB-LLD | Y | 2013-02-26 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-05-28 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2015-07-02 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2013-10-02 00:00:00.0000000 +00:00 | 2014-06-04 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | [5 empty] | 2013-11-13 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2018-07-01 00:00:00.0000000 +00:00 | 2020-09-14 00:00:00.0000000 +00:00 |  | 2020-09-14 00:00:00.0000000 +00:00 | 2020-09-14 00:00:00.0000000 +00:00 |  | 2017-10-25 11:40:57.8415041 -04:00
CT2-INTER | Y | 2014-07-24 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2020-10-01 00:00:00.0000000 +00:00 | 2014-07-24 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2016-01-30 00:00:00.0000000 +00:00 | 2016-07-30 00:00:00.0000000 +00:00 | 2017-07-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-07-24 17:00:00.0000000 +00:00 | 2014-12-16 17:00:00.0000000 +00:00 |  |  |  | 2018-06-30 00:00:00.0000000 +00:00 | 2020-10-01 00:00:00.0000000 +00:00 | 2014-07-24 17:00:00.0000000 +00:00 | 2014-07-24 00:00:00.0000000 +00:00 | 2014-12-16 17:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-30 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2020-10-01 00:00:00.0000000 +00:00 | 2020-10-01 00:00:00.0000000 +00:00 | 2022-07-31 00:00:00.0000000 +00:00 | 2023-09-30 00:00:00.0000000 +00:00 |  | 2023-09-30 00:00:00.0000000 +00:00 | 2023-09-30 00:00:00.0000000 +00:00 |  | 2017-08-30 14:29:42.3636672 -04:00
DDC7PSAC2 | Y | 2007-03-08 00:00:00.0000000 +00:00 | 2008-01-10 00:00:00.0000000 +00:00 | 2010-10-18 00:00:00.0000000 +00:00 | 2010-01-29 00:00:00.0000000 +00:00 | 2016-01-20 00:00:00.0000000 +00:00 | 2007-03-08 00:00:00.0000000 +00:00 | 2008-01-10 00:00:00.0000000 +00:00 | 2009-10-14 00:00:00.0000000 +00:00 | 2009-10-15 00:00:00.0000000 +00:00 | 2012-10-16 00:00:00.0000000 +00:00 | 2007-03-08 00:00:00.0000000 +00:00 | 2008-01-10 00:00:00.0000000 +00:00 | 2010-10-18 00:00:00.0000000 +00:00 | 2010-10-19 00:00:00.0000000 +00:00 | 2016-10-20 00:00:00.0000000 +00:00 | 2007-03-08 00:00:00.0000000 +00:00 | 2008-01-10 00:00:00.0000000 +00:00 |  | 2010-01-29 00:00:00.0000000 +00:00 | 2016-01-20 00:00:00.0000000 +00:00 | 2010-10-18 00:00:00.0000000 +00:00 | 2016-01-31 00:00:00.0000000 +00:00 | [6 empty] | 2008-05-22 00:00:00.0000000 +00:00 |  |  |  | 2008-12-18 00:00:00.0000000 +00:00 | [10 empty] | 2017-10-02 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-14 14:49:51.9264979 -04:00
DOIT1CNET | Y | [48 empty] | 2017-09-05 09:20:48.9835392 -04:00
DOIT1CQN | Y | 2013-01-27 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2016-11-02 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2015-08-12 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2015-01-02 00:00:00.0000000 +00:00 | 2013-01-27 12:00:00.0000000 +00:00 | 2013-09-17 12:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2015-06-01 17:00:00.0000000 +00:00 | 2016-11-02 17:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 |  | 2013-01-27 00:00:00.0000000 +00:00 |  | 2013-09-17 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 |  | 2013-10-31 00:00:00.0000000 +00:00 | 2014-01-08 00:00:00.0000000 +00:00 | 2014-01-08 00:00:00.0000000 +00:00 | 2014-01-08 00:00:00.0000000 +00:00 |  | 2014-01-08 00:00:00.0000000 +00:00 |  | 2014-04-09 00:00:00.0000000 +00:00 |  | 2015-06-01 00:00:00.0000000 +00:00 |  | 2016-11-02 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2017-12-20 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-05 09:21:23.2720776 -04:00
DOTSEQ01 | Y | [47 empty] | 2017-11-27 13:00:24.5500000 +00:00 | 2017-11-27 15:35:25.0687702 -05:00
DOTSEQ02 | Y | 2017-11-08 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2021-11-15 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2025-07-15 00:00:00.0000000 +00:00 | 2017-11-08 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2021-11-15 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2025-07-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-11-08 00:00:00.0000000 +00:00 | [10 empty] | 2021-01-15 00:00:00.0000000 +00:00 | 2021-01-15 00:00:00.0000000 +00:00 | [14 empty] | 2028-07-14 00:00:00.0000000 +00:00 | 2028-07-14 00:00:00.0000000 +00:00 |  |  |  | 2017-11-27 13:00:25.7500000 +00:00 | 2017-11-27 15:59:20.6072542 -05:00
E12-0023 | Y | 2012-10-15 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 | 2015-04-05 00:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-14 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-14 00:00:00.0000000 +00:00 | 2015-04-12 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2017-05-21 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 | 2015-08-12 00:00:00.0000000 +00:00 |  | 2015-09-08 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 |  | 2013-10-25 00:00:00.0000000 +00:00 | 2013-10-25 00:00:00.0000000 +00:00 | 2013-10-25 00:00:00.0000000 +00:00 | 2013-10-25 00:00:00.0000000 +00:00 |  | 2014-03-07 00:00:00.0000000 +00:00 | 2014-03-07 00:00:00.0000000 +00:00 | 2014-03-07 00:00:00.0000000 +00:00 | 2014-03-07 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 | 2015-08-12 00:00:00.0000000 +00:00 | 2015-08-12 00:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2017-05-14 00:00:00.0000000 +00:00 | 2018-12-30 00:00:00.0000000 +00:00 |  | 2018-12-30 00:00:00.0000000 +00:00 | 2018-12-30 00:00:00.0000000 +00:00 |  | 2017-09-14 08:57:27.6915605 -04:00
E12-0024 | Y | 2012-10-15 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 | 2014-10-27 00:00:00.0000000 +00:00 | 2016-03-18 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2014-05-30 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2015-11-28 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2015-05-08 00:00:00.0000000 +00:00 | 2016-07-07 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-09-10 00:00:00.0000000 +00:00 | 2014-10-27 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2016-12-22 17:00:00.0000000 +00:00 | 2014-10-25 00:00:00.0000000 +00:00 | 2017-05-18 00:00:00.0000000 +00:00 | [5 empty] | 2014-02-03 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 |  |  |  | 2014-06-02 00:00:00.0000000 +00:00 | 2014-06-02 00:00:00.0000000 +00:00 | [8 empty] | 2017-11-27 00:00:00.0000000 +00:00 | 2017-12-21 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-12 08:07:34.0647615 -04:00
E12-0031 | Y | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-21 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2017-02-17 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2014-02-14 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-21 00:00:00.0000000 +00:00 | 2014-07-12 00:00:00.0000000 +00:00 | 2015-05-09 00:00:00.0000000 +00:00 | 2016-11-05 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-21 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2015-10-27 00:00:00.0000000 +00:00 | 2017-02-10 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2018-05-27 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-21 00:00:00.0000000 +00:00 | 2013-06-21 00:00:00.0000000 +00:00 |  | 2013-09-15 00:00:00.0000000 +00:00 | 2013-09-15 00:00:00.0000000 +00:00 | 2013-09-15 00:00:00.0000000 +00:00 | 2013-09-15 00:00:00.0000000 +00:00 |  | 2013-12-12 00:00:00.0000000 +00:00 | 2013-12-12 00:00:00.0000000 +00:00 | 2013-12-12 00:00:00.0000000 +00:00 | 2013-12-12 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2015-10-27 00:00:00.0000000 +00:00 | 2015-10-27 00:00:00.0000000 +00:00 |  |  | 2017-08-14 00:00:00.0000000 +00:00 | 2018-02-09 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-12 10:19:09.2241798 -04:00
E12-0035 | Y | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-09 00:00:00.0000000 +00:00 | 2014-11-06 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2018-02-17 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-01-31 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2017-06-23 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-09 00:00:00.0000000 +00:00 | 2014-11-06 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 |  | 2015-03-06 00:00:00.0000000 +00:00 | 2018-02-17 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-09 00:00:00.0000000 +00:00 | 2013-05-09 00:00:00.0000000 +00:00 |  | 2013-07-09 00:00:00.0000000 +00:00 | 2013-07-09 00:00:00.0000000 +00:00 | 2013-07-09 00:00:00.0000000 +00:00 | 2013-07-09 00:00:00.0000000 +00:00 |  | 2013-10-01 00:00:00.0000000 +00:00 | 2013-10-01 00:00:00.0000000 +00:00 | 2013-10-01 00:00:00.0000000 +00:00 | 2013-10-01 00:00:00.0000000 +00:00 | 2014-11-06 00:00:00.0000000 +00:00 | 2014-11-06 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2018-02-17 00:00:00.0000000 +00:00 | 2018-02-17 00:00:00.0000000 +00:00 |  | 2019-02-18 00:00:00.0000000 +00:00 |  | 2019-02-18 00:00:00.0000000 +00:00 | 2019-02-18 00:00:00.0000000 +00:00
E12-0037 | Y | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-05 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2018-08-31 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2014-04-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-01 00:00:00.0000000 +00:00 | 2015-02-04 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2018-07-29 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-05 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2016-12-12 17:00:00.0000000 +00:00 |  | 2014-11-04 00:00:00.0000000 +00:00 | 2018-10-05 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-05 00:00:00.0000000 +00:00 | 2013-06-05 00:00:00.0000000 +00:00 |  | 2013-11-04 00:00:00.0000000 +00:00 | 2013-11-04 00:00:00.0000000 +00:00 | 2013-11-04 00:00:00.0000000 +00:00 | 2013-11-04 00:00:00.0000000 +00:00 |  | 2014-04-04 00:00:00.0000000 +00:00 | 2014-04-04 00:00:00.0000000 +00:00 | 2014-04-04 00:00:00.0000000 +00:00 | 2014-04-04 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2016-12-12 00:00:00.0000000 +00:00 | 2016-12-12 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2017-10-29 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 |  | 2019-04-30 00:00:00.0000000 +00:00 | 2019-04-30 00:00:00.0000000 +00:00 |  | 2017-11-03 11:28:46.9638317 -04:00
E12-0043 | Y | 2012-10-15 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-07-16 00:00:00.0000000 +00:00 | 2018-08-26 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2014-01-31 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2015-08-08 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-10-18 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 |  | 2017-03-11 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-05-30 00:00:00.0000000 +00:00 | 2014-05-30 00:00:00.0000000 +00:00 |  |  |  | 2015-03-02 00:00:00.0000000 +00:00 | 2015-03-02 00:00:00.0000000 +00:00 | [8 empty] | 2017-04-29 00:00:00.0000000 +00:00 | 2019-08-26 00:00:00.0000000 +00:00
E12-0043A | Y | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2018-08-26 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2014-01-31 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2016-08-14 00:00:00.0000000 +00:00 | 2017-05-14 00:00:00.0000000 +00:00 | 2012-10-15 17:00:00.0000000 +00:00 | 2013-10-18 17:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 |  | 2016-05-02 00:00:00.0000000 +00:00 | 2018-10-26 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-10-18 00:00:00.0000000 +00:00 | 2013-10-18 00:00:00.0000000 +00:00 |  | 2014-05-30 00:00:00.0000000 +00:00 | 2014-05-30 00:00:00.0000000 +00:00 | 2014-05-30 00:00:00.0000000 +00:00 | 2014-05-30 00:00:00.0000000 +00:00 |  | 2015-03-02 00:00:00.0000000 +00:00 | 2015-03-02 00:00:00.0000000 +00:00 | 2015-03-02 00:00:00.0000000 +00:00 | 2015-03-02 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2017-04-29 00:00:00.0000000 +00:00 | 2019-08-26 00:00:00.0000000 +00:00 |  | 2019-10-31 00:00:00.0000000 +00:00 | 2019-10-31 00:00:00.0000000 +00:00
E12-0043B | Y | 2017-02-16 00:00:00.0000000 +00:00 | 2017-02-17 00:00:00.0000000 +00:00 | 2017-06-06 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | [10 empty] | 2017-02-16 00:00:00.0000000 +00:00 | 2017-02-17 00:00:00.0000000 +00:00 | 2017-06-06 00:00:00.0000000 +00:00 |  |  | 2017-06-06 00:00:00.0000000 +00:00 |  | 2017-02-16 00:00:00.0000000 +00:00 | 2017-02-16 00:00:00.0000000 +00:00 | 2017-02-17 00:00:00.0000000 +00:00 | 2017-02-17 00:00:00.0000000 +00:00 |  | 2017-03-10 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 |  | 2017-03-13 00:00:00.0000000 +00:00 | 2017-03-13 00:00:00.0000000 +00:00 | 2017-03-13 00:00:00.0000000 +00:00 | 2017-03-13 00:00:00.0000000 +00:00 | 2017-06-06 00:00:00.0000000 +00:00 | 2017-06-06 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 |  | 2019-09-17 00:00:00.0000000 +00:00 |  | 2019-09-17 00:00:00.0000000 +00:00 | 2019-09-17 00:00:00.0000000 +00:00 |  | 2017-10-24 12:17:34.3753250 -04:00
E14-0001 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2017-06-18 00:00:00.0000000 +00:00 | 2018-07-21 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2016-06-18 00:00:00.0000000 +00:00 | 2017-06-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2017-03-29 17:00:00.0000000 +00:00 |  | 2015-12-03 00:00:00.0000000 +00:00 | 2018-07-21 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 |  | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 |  | 2015-03-03 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2018-07-21 00:00:00.0000000 +00:00 | 2018-07-21 00:00:00.0000000 +00:00 | 2019-11-04 00:00:00.0000000 +00:00 | 2019-07-20 00:00:00.0000000 +00:00 |  | 2019-07-20 00:00:00.0000000 +00:00 | 2019-07-20 00:00:00.0000000 +00:00
E14-0003 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-10-03 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-09-01 00:00:00.0000000 +00:00 | 2018-08-08 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-10-03 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 |  | 2015-10-03 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 |  | 2014-08-15 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 |  | 2014-09-01 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2015-10-03 00:00:00.0000000 +00:00 | 2015-10-03 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2020-01-24 00:00:00.0000000 +00:00 |  | 2020-01-24 00:00:00.0000000 +00:00 | 2020-01-24 00:00:00.0000000 +00:00
E14-0006 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2016-11-02 00:00:00.0000000 +00:00 | 2018-04-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2017-01-26 17:00:00.0000000 +00:00 |  | 2015-12-03 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 |  | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 |  | 2014-11-03 00:00:00.0000000 +00:00 | 2014-11-03 00:00:00.0000000 +00:00 | 2014-11-03 00:00:00.0000000 +00:00 | 2014-11-03 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2019-02-01 00:00:00.0000000 +00:00 | 2020-01-24 00:00:00.0000000 +00:00 |  | 2020-01-24 00:00:00.0000000 +00:00 | 2020-01-24 00:00:00.0000000 +00:00
E14-0007 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2018-11-15 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-11-29 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 |  |  |  | 2016-04-14 00:00:00.0000000 +00:00 | 2019-03-17 00:00:00.0000000 +00:00 | [20 empty] | 2019-02-01 00:00:00.0000000 +00:00 | 2019-02-01 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-24 12:15:46.1608441 -04:00
E14-0008 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2017-05-10 00:00:00.0000000 +00:00 | 2019-04-29 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-12-02 00:00:00.0000000 +00:00 | 2018-11-02 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2017-05-10 17:00:00.0000000 +00:00 |  | 2016-07-30 00:00:00.0000000 +00:00 | 2019-05-15 00:00:00.0000000 +00:00 |  | 2014-01-06 00:00:00.0000000 +00:00 |  | 2014-07-17 00:00:00.0000000 +00:00 |  | 2014-10-23 00:00:00.0000000 +00:00 | 2014-10-23 00:00:00.0000000 +00:00 |  | 2014-10-23 00:00:00.0000000 +00:00 |  | 2015-03-09 00:00:00.0000000 +00:00 | 2015-03-09 00:00:00.0000000 +00:00 |  | 2015-03-09 00:00:00.0000000 +00:00 |  | 2016-07-16 00:00:00.0000000 +00:00 |  | 2017-05-10 00:00:00.0000000 +00:00 |  | 2019-04-29 00:00:00.0000000 +00:00 | 2021-04-18 00:00:00.0000000 +00:00 | 2020-04-28 00:00:00.0000000 +00:00 |  |  | 2020-04-28 00:00:00.0000000 +00:00 |  | 2017-09-11 14:47:15.5471298 -04:00
E14-0010 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2017-03-15 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2018-01-16 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 |  |  |  | 2017-06-16 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 | [20 empty] | 2019-01-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00
E14-0011 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2017-06-07 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2018-01-16 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2017-06-07 00:00:00.0000000 +00:00 |  |  | 2017-07-16 00:00:00.0000000 +00:00 |  | 2014-01-06 00:00:00.0000000 +00:00 |  | 2014-07-18 00:00:00.0000000 +00:00 |  |  | 2015-02-18 00:00:00.0000000 +00:00 | 2015-02-18 00:00:00.0000000 +00:00 | 2015-02-18 00:00:00.0000000 +00:00 |  |  | 2015-06-09 00:00:00.0000000 +00:00 | 2015-06-09 00:00:00.0000000 +00:00 | 2015-06-09 00:00:00.0000000 +00:00 |  | 2017-06-07 00:00:00.0000000 +00:00 |  | 2018-02-15 00:00:00.0000000 +00:00 |  | 2019-06-15 00:00:00.0000000 +00:00 |  | 2019-01-15 00:00:00.0000000 +00:00 | 2019-11-30 00:00:00.0000000 +00:00 |  | 2019-06-15 00:00:00.0000000 +00:00 |  |  | 2017-09-14 12:26:32.2713005 -04:00
E14-0012 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2017-10-15 00:00:00.0000000 +00:00 | 2019-01-18 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2017-03-04 00:00:00.0000000 +00:00 | 2018-03-05 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 |  | 2016-07-15 00:00:00.0000000 +00:00 | 2019-01-18 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-07 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 |  | 2014-12-01 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 |  | 2015-04-24 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2019-01-18 00:00:00.0000000 +00:00 | 2019-01-18 00:00:00.0000000 +00:00 | 2019-02-01 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 |  | 2020-01-17 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 |  | 2017-09-29 08:21:35.1474937 -04:00
E14-0016 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2018-07-21 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2016-11-18 00:00:00.0000000 +00:00 | 2017-11-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2017-03-29 17:00:00.0000000 +00:00 |  | 2015-12-03 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 |  | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 |  | 2015-03-03 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2018-07-21 00:00:00.0000000 +00:00 | 2018-07-21 00:00:00.0000000 +00:00 | 2019-11-04 00:00:00.0000000 +00:00 | 2019-07-20 00:00:00.0000000 +00:00 |  | 2019-07-20 00:00:00.0000000 +00:00 | 2019-07-20 00:00:00.0000000 +00:00
E14-0017 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2016-01-01 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-07-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2016-01-01 00:00:00.0000000 +00:00 | 2017-03-29 17:00:00.0000000 +00:00 |  | 2016-06-04 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 |  | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 |  | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2016-01-01 00:00:00.0000000 +00:00 | 2016-01-01 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2020-01-03 00:00:00.0000000 +00:00 | 2019-09-18 00:00:00.0000000 +00:00 |  | 2019-09-18 00:00:00.0000000 +00:00 | 2019-09-18 00:00:00.0000000 +00:00
E14-0018 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-07-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2017-03-29 17:00:00.0000000 +00:00 |  | 2016-01-02 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 |  | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 |  | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2020-01-03 00:00:00.0000000 +00:00 | 2019-09-18 00:00:00.0000000 +00:00 |  | 2019-09-18 00:00:00.0000000 +00:00 | 2019-09-18 00:00:00.0000000 +00:00 |  | 2017-09-12 09:34:20.5043143 -04:00
E14-0019 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2017-01-17 00:00:00.0000000 +00:00 | 2018-01-18 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2017-03-29 17:00:00.0000000 +00:00 |  | 2016-01-02 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 |  | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 |  | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2020-01-03 00:00:00.0000000 +00:00 | 2019-09-18 00:00:00.0000000 +00:00 |  | 2019-09-18 00:00:00.0000000 +00:00 | 2019-09-18 00:00:00.0000000 +00:00 |  | 2017-09-12 09:34:49.8035222 -04:00
E14-0020 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-07-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2017-03-29 17:00:00.0000000 +00:00 |  | 2016-01-02 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 |  | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 |  | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2020-01-03 00:00:00.0000000 +00:00 | 2019-09-18 00:00:00.0000000 +00:00 |  | 2019-09-18 00:00:00.0000000 +00:00 | 2019-09-18 00:00:00.0000000 +00:00
E14-0060 | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2017-10-15 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-01 00:00:00.0000000 +00:00 | 2014-01-01 00:00:00.0000000 +00:00 | 2016-02-01 00:00:00.0000000 +00:00 | 2014-01-01 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2016-01-29 00:00:00.0000000 +00:00 | 2016-08-01 00:00:00.0000000 +00:00 | 2017-06-04 00:00:00.0000000 +00:00 | 2014-01-06 12:00:00.0000000 +00:00 | 2014-07-17 12:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 |  | 2014-12-17 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 |  | 2014-12-01 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 |  | 2015-04-24 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2019-01-18 00:00:00.0000000 +00:00 | 2019-01-18 00:00:00.0000000 +00:00 | 2016-01-01 00:00:00.0000000 +00:00 | 2024-12-29 00:00:00.0000000 +00:00 |  | 2020-01-17 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 |  | 2017-09-29 08:23:51.8609892 -04:00
E16-0002 | Y | 2015-09-22 00:00:00.0000000 +00:00 | 2017-03-15 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2020-08-07 00:00:00.0000000 +00:00 | 2015-09-09 00:00:00.0000000 +00:00 | 2015-09-09 00:00:00.0000000 +00:00 | 2015-09-09 00:00:00.0000000 +00:00 | 2015-09-09 00:00:00.0000000 +00:00 | 2015-09-09 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-14 18:00:00.0000000 +00:00 | 2017-02-15 17:00:00.0000000 +00:00 |  |  |  | 2018-05-15 00:00:00.0000000 +00:00 | 2020-08-07 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  |  | 2018-03-01 00:00:00.0000000 +00:00 | [9 empty] | 2017-09-08 00:00:00.9370000 +00:00 | 2021-08-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-13 15:41:51.9086464 -05:00
E16-0003 | Y | 2015-09-22 00:00:00.0000000 +00:00 | 2017-03-15 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2020-08-07 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-09-22 00:00:00.0000000 +00:00 | 2018-06-22 00:00:00.0000000 +00:00 | 2019-10-22 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-14 18:00:00.0000000 +00:00 | 2017-02-15 17:00:00.0000000 +00:00 |  |  |  | 2018-05-15 00:00:00.0000000 +00:00 | 2020-08-07 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  |  | 2018-03-01 00:00:00.0000000 +00:00 | [9 empty] | 2021-10-21 00:00:00.0000000 +00:00 | 2021-08-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-13 15:42:06.9486691 -05:00
E16-0004 | Y | 2015-09-22 00:00:00.0000000 +00:00 | 2017-03-15 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-02-12 00:00:00.0000000 +00:00 | 2020-06-13 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-09-22 00:00:00.0000000 +00:00 | 2018-06-22 00:00:00.0000000 +00:00 | 2019-10-22 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-14 18:00:00.0000000 +00:00 | 2017-03-07 17:00:00.0000000 +00:00 | [5 empty] | 2015-10-14 00:00:00.0000000 +00:00 |  | 2017-03-07 00:00:00.0000000 +00:00 |  |  | 2017-07-11 00:00:00.0000000 +00:00 | 2017-07-11 00:00:00.0000000 +00:00 | 2017-07-11 00:00:00.0000000 +00:00 |  |  | 2017-11-30 00:00:00.0000000 +00:00 |  | 2017-11-30 00:00:00.0000000 +00:00 |  | 2018-06-15 00:00:00.0000000 +00:00 |  | 2019-02-12 00:00:00.0000000 +00:00 |  | 2020-06-13 00:00:00.0000000 +00:00 |  | 2021-10-21 00:00:00.0000000 +00:00 | 2021-06-15 00:00:00.0000000 +00:00 |  | 2021-06-15 00:00:00.0000000 +00:00 |  |  | 2017-11-08 11:15:11.3199129 -05:00
E16-0005 | Y | 2015-09-22 00:00:00.0000000 +00:00 | 2017-03-15 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-02-12 00:00:00.0000000 +00:00 | 2020-06-13 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-09-22 00:00:00.0000000 +00:00 | 2018-06-22 00:00:00.0000000 +00:00 | 2019-10-22 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-14 18:00:00.0000000 +00:00 | 2017-03-07 17:00:00.0000000 +00:00 |  |  |  | 2018-05-15 00:00:00.0000000 +00:00 | 2020-06-13 00:00:00.0000000 +00:00 | 2015-10-14 00:00:00.0000000 +00:00 |  | 2017-03-07 00:00:00.0000000 +00:00 |  |  | 2017-07-11 00:00:00.0000000 +00:00 | 2017-07-11 00:00:00.0000000 +00:00 | 2017-07-11 00:00:00.0000000 +00:00 |  |  | 2017-11-30 00:00:00.0000000 +00:00 |  | 2017-11-30 00:00:00.0000000 +00:00 |  | 2018-06-15 00:00:00.0000000 +00:00 |  | 2019-02-12 00:00:00.0000000 +00:00 |  | 2020-06-13 00:00:00.0000000 +00:00 |  | 2021-10-21 00:00:00.0000000 +00:00 | 2021-06-15 00:00:00.0000000 +00:00 |  | 2021-06-15 00:00:00.0000000 +00:00 |  |  | 2017-11-08 11:14:52.5287334 -05:00
E16-0012 | Y
E17-0001 | Y | [48 empty] | 2017-11-27 14:14:05.7372790 -05:00
E17-0002 | Y | [48 empty] | 2017-11-17 10:47:39.6075803 -05:00
E17-0005 | Y | [48 empty] | 2017-11-17 10:50:39.3949637 -05:00
E17-0006 | Y | 2017-07-27 00:00:00.0000000 +00:00 | 2018-05-15 00:00:00.0000000 +00:00 | 2019-06-21 00:00:00.0000000 +00:00 | 2020-03-21 00:00:00.0000000 +00:00 | 2022-03-21 00:00:00.0000000 +00:00 | [10 empty] | 2017-07-27 00:00:00.0000000 +00:00 | [11 empty] | 2018-10-05 00:00:00.0000000 +00:00 |  |  |  |  | 2018-12-21 00:00:00.0000000 +00:00 | [10 empty] | 2023-03-21 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-08 11:16:58.7463575 -05:00
EP06-REM | Y | 2002-08-19 00:00:00.0000000 +00:00 | 2005-05-09 00:00:00.0000000 +00:00 | 2007-05-04 00:00:00.0000000 +00:00 | 2008-04-14 00:00:00.0000000 +00:00 | 2012-06-30 00:00:00.0000000 +00:00 | 2002-08-19 00:00:00.0000000 +00:00 | 2002-10-07 00:00:00.0000000 +00:00 | 2004-10-06 00:00:00.0000000 +00:00 | 2006-07-01 00:00:00.0000000 +00:00 | 2008-09-30 00:00:00.0000000 +00:00 | 2002-08-19 00:00:00.0000000 +00:00 | 2002-11-19 00:00:00.0000000 +00:00 | 2004-11-18 00:00:00.0000000 +00:00 | 2006-08-13 00:00:00.0000000 +00:00 | 2008-11-12 00:00:00.0000000 +00:00 | 2002-08-19 00:00:00.0000000 +00:00 | 2005-05-09 00:00:00.0000000 +00:00 |  | 2008-04-14 00:00:00.0000000 +00:00 | 2012-06-29 00:00:00.0000000 +00:00 | 2006-06-13 00:00:00.0000000 +00:00 | 2010-04-13 00:00:00.0000000 +00:00
EP16-CLOVE | Y | [5 empty] | 2016-03-04 00:00:00.0000000 +00:00 | [9 empty] | 2016-03-04 00:00:00.0000000 +00:00 | [32 empty] | 2017-10-06 16:01:44.7733494 -04:00
EP6-KENTD | Y | 2008-01-10 00:00:00.0000000 +00:00 | 2008-05-05 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-10-27 00:00:00.0000000 +00:00 | 2018-01-26 00:00:00.0000000 +00:00 | 2007-01-10 00:00:00.0000000 +00:00 | 2008-05-05 00:00:00.0000000 +00:00 | 2009-08-03 00:00:00.0000000 +00:00 | 2009-12-08 00:00:00.0000000 +00:00 | 2011-06-05 00:00:00.0000000 +00:00 | 2007-01-10 00:00:00.0000000 +00:00 | 2008-05-05 00:00:00.0000000 +00:00 | 2011-06-29 00:00:00.0000000 +00:00 | 2012-03-19 00:00:00.0000000 +00:00 | 2013-09-14 00:00:00.0000000 +00:00 | 2008-01-10 00:00:00.0000000 +00:00 | 2008-05-05 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-08-21 00:00:00.0000000 +00:00 |  | 2017-01-27 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 |  | 2008-01-10 00:00:00.0000000 +00:00 |  | 2008-05-05 00:00:00.0000000 +00:00 | 2008-11-05 00:00:00.0000000 +00:00 | 2009-09-18 00:00:00.0000000 +00:00 | 2009-09-18 00:00:00.0000000 +00:00 |  | 2009-09-18 00:00:00.0000000 +00:00 | 2009-03-06 00:00:00.0000000 +00:00 | 2012-02-02 00:00:00.0000000 +00:00 | 2012-02-02 00:00:00.0000000 +00:00 |  | 2012-02-02 00:00:00.0000000 +00:00 |  | 2013-12-15 00:00:00.0000000 +00:00 |  | 2014-08-21 00:00:00.0000000 +00:00 |  | 2018-01-26 00:00:00.0000000 +00:00 | 2011-06-05 00:00:00.0000000 +00:00 | 2019-01-26 00:00:00.0000000 +00:00 |  |  | 2019-01-26 00:00:00.0000000 +00:00 |  | 2017-11-14 12:05:51.3206933 -05:00
F1755C099 | Y | 1999-04-15 00:00:00.0000000 +00:00 | 1999-05-17 00:00:00.0000000 +00:00 | 2002-06-28 00:00:00.0000000 +00:00 | 2002-11-15 00:00:00.0000000 +00:00 | 2014-12-17 00:00:00.0000000 +00:00 | 1999-04-15 00:00:00.0000000 +00:00 | 1999-05-17 00:00:00.0000000 +00:00 | 1999-08-30 00:00:00.0000000 +00:00 | 2000-05-20 00:00:00.0000000 +00:00 | 2005-07-12 00:00:00.0000000 +00:00 | 1999-04-15 00:00:00.0000000 +00:00 | 1999-05-17 00:00:00.0000000 +00:00 | 2002-06-28 00:00:00.0000000 +00:00 | 2002-11-15 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 1999-04-15 00:00:00.0000000 +00:00 | 1999-05-17 00:00:00.0000000 +00:00 |  | 2002-11-15 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2002-06-28 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | [21 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-14 14:50:57.1022261 -04:00
F175COMP6-1 | Y | 2010-07-26 00:00:00.0000000 +00:00 | 2011-01-28 00:00:00.0000000 +00:00 | 2011-08-25 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2015-06-12 00:00:00.0000000 +00:00 | 2010-07-26 00:00:00.0000000 +00:00 | 2011-02-27 00:00:00.0000000 +00:00 | 2011-09-26 00:00:00.0000000 +00:00 | 2012-09-05 00:00:00.0000000 +00:00 | 2013-08-01 00:00:00.0000000 +00:00 | 2010-07-26 00:00:00.0000000 +00:00 | 2011-01-28 00:00:00.0000000 +00:00 | 2011-08-27 00:00:00.0000000 +00:00 | 2013-03-12 00:00:00.0000000 +00:00 | 2014-05-10 00:00:00.0000000 +00:00 | 2010-07-26 00:00:00.0000000 +00:00 | 2011-01-28 00:00:00.0000000 +00:00 |  | 2013-02-27 00:00:00.0000000 +00:00 | 2015-06-12 00:00:00.0000000 +00:00 | 2011-08-26 00:00:00.0000000 +00:00 | 2014-04-08 00:00:00.0000000 +00:00 | [21 empty] | 2017-12-29 00:00:00.0000000 +00:00
F175EC293A | Y | 2008-02-15 00:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2016-12-07 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2008-02-15 00:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2016-12-07 00:00:00.0000000 +00:00 | 2018-03-31 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 |  |  | 2016-04-06 00:00:00.0000000 +00:00 | 2017-07-21 00:00:00.0000000 +00:00 | 2008-02-15 00:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2016-12-07 17:00:00.0000000 +00:00 |  | 2015-09-15 00:00:00.0000000 +00:00 | 2018-07-01 00:00:00.0000000 +00:00 | 2008-02-15 00:00:00.0000000 +00:00 | 2008-02-15 00:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 |  | 2008-06-16 00:00:00.0000000 +00:00 | 2008-06-16 00:00:00.0000000 +00:00 | 2008-06-16 00:00:00.0000000 +00:00 | 2008-06-16 00:00:00.0000000 +00:00 |  | 2008-10-15 00:00:00.0000000 +00:00 | 2008-10-15 00:00:00.0000000 +00:00 | 2008-10-15 00:00:00.0000000 +00:00 | 2008-10-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2016-12-07 17:00:00.0000000 +00:00 | 2016-12-07 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2019-05-24 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 |  | 2019-10-30 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 |  | 2017-11-14 11:07:13.1061635 -05:00
F175EC63 | Y | 2007-04-30 00:00:00.0000000 +00:00 | 2007-09-06 00:00:00.0000000 +00:00 | 2009-12-04 00:00:00.0000000 +00:00 | 2011-05-27 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2007-04-30 00:00:00.0000000 +00:00 | 2007-08-01 00:00:00.0000000 +00:00 | 2008-10-03 00:00:00.0000000 +00:00 | 2009-05-17 00:00:00.0000000 +00:00 | 2010-06-30 00:00:00.0000000 +00:00 | 2007-04-30 00:00:00.0000000 +00:00 | 2007-09-06 00:00:00.0000000 +00:00 | 2010-02-04 00:00:00.0000000 +00:00 | 2011-08-28 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2007-04-30 00:00:00.0000000 +00:00 | 2007-09-06 00:00:00.0000000 +00:00 | 2009-12-04 00:00:00.0000000 +00:00 | 2011-05-27 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2010-02-14 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | [20 empty] | 2011-06-30 00:00:00.0000000 +00:00 | 2015-12-05 00:00:00.0000000 +00:00 | 2015-12-05 00:00:00.0000000 +00:00 |  |  |  | 2017-09-14 15:03:12.7329684 -04:00
F175GREEN | Y | 2006-08-17 00:00:00.0000000 +00:00 | 2007-04-11 00:00:00.0000000 +00:00 | 2009-05-13 00:00:00.0000000 +00:00 | 2010-09-20 00:00:00.0000000 +00:00 | 2013-08-12 00:00:00.0000000 +00:00 | 2006-08-17 00:00:00.0000000 +00:00 | 2007-01-03 00:00:00.0000000 +00:00 | 2008-03-02 00:00:00.0000000 +00:00 | 2008-07-26 00:00:00.0000000 +00:00 | 2010-03-02 00:00:00.0000000 +00:00 | 2006-08-17 00:00:00.0000000 +00:00 | 2007-02-19 00:00:00.0000000 +00:00 | 2009-04-18 00:00:00.0000000 +00:00 | 2010-09-10 00:00:00.0000000 +00:00 | 2013-12-02 00:00:00.0000000 +00:00 | 2006-08-17 00:00:00.0000000 +00:00 | 2007-04-11 00:00:00.0000000 +00:00 | 2009-05-13 00:00:00.0000000 +00:00 | 2010-09-20 00:00:00.0000000 +00:00 | 2013-08-12 00:00:00.0000000 +00:00 | 2009-06-08 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-14 15:12:58.8301842 -04:00
F175LC8 | Y | 2005-06-27 00:00:00.0000000 +00:00 | 2005-11-24 00:00:00.0000000 +00:00 | 2008-02-04 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2018-01-12 00:00:00.0000000 +00:00 | 2005-06-27 00:00:00.0000000 +00:00 | 2005-11-24 00:00:00.0000000 +00:00 | 2007-01-23 00:00:00.0000000 +00:00 | 2007-06-03 00:00:00.0000000 +00:00 | 2008-10-04 00:00:00.0000000 +00:00 | 2005-06-27 00:00:00.0000000 +00:00 | 2005-11-24 00:00:00.0000000 +00:00 | 2008-04-22 00:00:00.0000000 +00:00 | 2016-05-24 00:00:00.0000000 +00:00 | 2018-12-04 00:00:00.0000000 +00:00 | 2005-06-27 00:00:00.0000000 +00:00 | 2005-11-24 00:00:00.0000000 +00:00 | 2008-02-04 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 |  | 2008-04-22 00:00:00.0000000 +00:00 | 2017-12-25 00:00:00.0000000 +00:00 | 2005-06-27 00:00:00.0000000 +00:00 | 2005-06-27 00:00:00.0000000 +00:00 | 2005-11-24 00:00:00.0000000 +00:00 | 2005-11-24 00:00:00.0000000 +00:00 |  | 2006-02-15 00:00:00.0000000 +00:00 | 2006-02-15 00:00:00.0000000 +00:00 | 2006-02-15 00:00:00.0000000 +00:00 | 2006-02-15 00:00:00.0000000 +00:00 |  | 2006-06-15 00:00:00.0000000 +00:00 | 2006-06-15 00:00:00.0000000 +00:00 | 2006-06-15 00:00:00.0000000 +00:00 | 2006-06-15 00:00:00.0000000 +00:00 | 2008-02-04 00:00:00.0000000 +00:00 | 2008-02-04 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2018-01-12 00:00:00.0000000 +00:00 | 2018-01-12 00:00:00.0000000 +00:00 | 2010-06-04 00:00:00.0000000 +00:00 | 2019-06-28 00:00:00.0000000 +00:00 |  | 2019-06-28 00:00:00.0000000 +00:00 | 2019-06-28 00:00:00.0000000 +00:00 |  | 2017-12-07 10:52:36.2540394 -05:00
F175MCE23 | Y | 2013-10-24 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2018-10-06 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2013-12-12 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2015-06-22 00:00:00.0000000 +00:00 | 2016-05-25 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2015-08-18 00:00:00.0000000 +00:00 | 2017-04-07 00:00:00.0000000 +00:00 | 2018-09-16 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 |  | 2015-08-07 00:00:00.0000000 +00:00 |  | 2013-10-24 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 |  | 2014-08-25 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 |  | 2014-12-19 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2018-10-06 00:00:00.0000000 +00:00 | 2018-10-06 00:00:00.0000000 +00:00 | 2018-05-25 00:00:00.0000000 +00:00 | 2019-10-06 00:00:00.0000000 +00:00 |  | 2019-10-06 00:00:00.0000000 +00:00 | 2019-10-06 00:00:00.0000000 +00:00 |  | 2017-09-12 17:43:54.4829646 -04:00
F175QUEEN1B | Y | 2012-05-18 00:00:00.0000000 +00:00 |  |  | 2013-12-02 00:00:00.0000000 +00:00 | 2016-03-15 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 |  |  | 2013-08-17 00:00:00.0000000 +00:00 | 2015-03-14 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 |  |  | 2013-12-02 00:00:00.0000000 +00:00 | 2016-07-10 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 |  |  | 2013-12-02 00:00:00.0000000 +00:00 | 2016-03-25 00:00:00.0000000 +00:00 |  | 2016-03-25 00:00:00.0000000 +00:00 | [21 empty] | 2017-05-25 00:00:00.0000000 +00:00 | 2017-05-25 00:00:00.0000000 +00:00 |  |  |  | 2017-09-14 15:21:24.8051636 -04:00
F175RES2 | Y | 2013-12-16 00:00:00.0000000 +00:00 | 2014-04-10 00:00:00.0000000 +00:00 | 2015-09-18 00:00:00.0000000 +00:00 | 2016-07-20 00:00:00.0000000 +00:00 | 2018-12-10 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-03-21 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2015-08-12 00:00:00.0000000 +00:00 | 2017-08-10 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-04-17 00:00:00.0000000 +00:00 | 2015-10-31 00:00:00.0000000 +00:00 | 2016-06-11 00:00:00.0000000 +00:00 | 2018-09-08 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-04-10 00:00:00.0000000 +00:00 | 2015-09-18 00:00:00.0000000 +00:00 | 2016-07-20 00:00:00.0000000 +00:00 |  | 2016-06-06 00:00:00.0000000 +00:00 | 2018-09-25 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-04-10 00:00:00.0000000 +00:00 | 2014-04-10 00:00:00.0000000 +00:00 |  | 2014-09-11 00:00:00.0000000 +00:00 | 2014-09-11 00:00:00.0000000 +00:00 | 2014-09-11 00:00:00.0000000 +00:00 | 2014-09-11 00:00:00.0000000 +00:00 |  | 2015-02-02 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | 2015-09-18 00:00:00.0000000 +00:00 | 2015-09-18 00:00:00.0000000 +00:00 | 2016-07-20 00:00:00.0000000 +00:00 | 2016-07-20 00:00:00.0000000 +00:00 | 2018-12-10 00:00:00.0000000 +00:00 | 2018-12-10 00:00:00.0000000 +00:00 | 2019-08-10 00:00:00.0000000 +00:00 | 2019-12-10 00:00:00.0000000 +00:00 |  | 2019-12-10 00:00:00.0000000 +00:00 | 2019-12-10 00:00:00.0000000 +00:00 |  | 2017-09-12 17:59:35.5017554 -04:00
F175SOUND | Y | 2007-10-22 00:00:00.0000000 +00:00 | 2008-02-12 00:00:00.0000000 +00:00 | 2010-05-19 00:00:00.0000000 +00:00 | 2012-04-25 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2007-10-22 00:00:00.0000000 +00:00 | 2008-03-22 00:00:00.0000000 +00:00 | 2009-10-22 00:00:00.0000000 +00:00 | 2010-03-22 00:00:00.0000000 +00:00 | 2011-12-21 00:00:00.0000000 +00:00 | 2007-10-22 00:00:00.0000000 +00:00 | 2008-03-22 00:00:00.0000000 +00:00 | 2010-11-04 00:00:00.0000000 +00:00 | 2013-02-22 00:00:00.0000000 +00:00 | 2014-10-09 00:00:00.0000000 +00:00 | 2007-10-22 00:00:00.0000000 +00:00 | 2008-02-12 00:00:00.0000000 +00:00 | 2010-05-19 00:00:00.0000000 +00:00 | 2012-04-25 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2010-09-16 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | [21 empty] | 2015-07-24 00:00:00.0000000 +00:00 | 2015-07-24 00:00:00.0000000 +00:00 |  |  |  | 2017-09-14 15:33:55.0600162 -04:00
FD175273H | Y | 2012-10-24 00:00:00.0000000 +00:00 | 2013-05-23 00:00:00.0000000 +00:00 | 2013-11-08 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2015-07-22 00:00:00.0000000 +00:00 | 2012-10-24 00:00:00.0000000 +00:00 | 2013-06-07 00:00:00.0000000 +00:00 | 2013-10-23 00:00:00.0000000 +00:00 | 2014-06-01 00:00:00.0000000 +00:00 | 2015-03-01 00:00:00.0000000 +00:00 | 2012-10-24 00:00:00.0000000 +00:00 | 2013-06-07 00:00:00.0000000 +00:00 | 2013-11-25 00:00:00.0000000 +00:00 | 2014-09-14 00:00:00.0000000 +00:00 | 2015-07-12 00:00:00.0000000 +00:00 | 2012-10-24 00:00:00.0000000 +00:00 | 2013-05-23 00:00:00.0000000 +00:00 | 2013-11-08 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2015-07-22 00:00:00.0000000 +00:00 | 2013-11-10 00:00:00.0000000 +00:00 | 2015-07-24 00:00:00.0000000 +00:00 | [21 empty] | 2016-07-25 00:00:00.0000000 +00:00 | 2016-07-25 00:00:00.0000000 +00:00 |  |  |  | 2017-09-14 15:32:21.9769734 -04:00
FORTWSH2 | Y | 2004-05-05 00:00:00.0000000 +00:00 | 2004-12-01 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 | 2005-08-05 00:00:00.0000000 +00:00 | 2007-02-06 00:00:00.0000000 +00:00 | 2004-05-05 00:00:00.0000000 +00:00 | 2004-12-01 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 | 2005-08-05 00:00:00.0000000 +00:00 | 2007-02-06 00:00:00.0000000 +00:00 | 2004-05-05 00:00:00.0000000 +00:00 | 2004-12-01 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 | 2005-08-05 00:00:00.0000000 +00:00 | 2007-02-06 00:00:00.0000000 +00:00 | 2004-05-05 00:00:00.0000000 +00:00 | 2004-12-01 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 | 2005-08-05 00:00:00.0000000 +00:00 | 2007-02-06 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 | 2007-02-06 00:00:00.0000000 +00:00 |  |  |  |  | 2005-02-15 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 |  |  | 2005-02-15 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00
FRTWASH2 | Y | 2002-11-10 00:00:00.0000000 +00:00 | 2002-12-10 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00 | 2003-10-30 00:00:00.0000000 +00:00 | 2004-01-01 00:00:00.0000000 +00:00 | 2002-11-10 00:00:00.0000000 +00:00 | 2002-12-10 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00 | 2003-10-30 00:00:00.0000000 +00:00 | 2004-10-30 00:00:00.0000000 +00:00 | 2002-11-10 00:00:00.0000000 +00:00 | 2002-12-10 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00 | 2003-10-30 00:00:00.0000000 +00:00 | 2004-10-30 00:00:00.0000000 +00:00 | 2002-11-10 00:00:00.0000000 +00:00 | 2002-12-10 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00 | 2003-11-03 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00 | 2004-10-30 00:00:00.0000000 +00:00 |  |  |  |  | 2003-01-28 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00 |  |  | 2003-01-28 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00
GCHP24-01 | Y | 2012-05-11 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2012-05-11 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2015-03-13 00:00:00.0000000 +00:00 | 2012-05-11 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2015-03-13 00:00:00.0000000 +00:00 | 2012-05-11 12:00:00.0000000 +00:00 | 2013-06-12 17:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2012-05-11 12:00:00.0000000 +00:00 | 2012-05-11 12:00:00.0000000 +00:00 | 2013-06-12 17:00:00.0000000 +00:00 | 2013-06-12 17:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | [5 empty] | 2013-08-14 00:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2014-10-04 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2018-03-11 00:00:00.0000000 +00:00 | 2019-05-15 00:00:00.0000000 +00:00 |  | 2019-05-15 00:00:00.0000000 +00:00 | 2019-05-15 00:00:00.0000000 +00:00
GCHP24-02 | Y | 2012-11-03 00:00:00.0000000 +00:00 | 2013-12-05 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2018-03-27 00:00:00.0000000 +00:00 | 2019-09-21 00:00:00.0000000 +00:00 | 2012-05-11 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 | 2013-10-30 00:00:00.0000000 +00:00 | 2014-05-15 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2012-05-11 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 | 2014-08-30 00:00:00.0000000 +00:00 | 2015-03-15 00:00:00.0000000 +00:00 | 2016-03-13 00:00:00.0000000 +00:00 | 2012-05-11 12:00:00.0000000 +00:00 | 2013-06-12 12:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 |  |  | 2017-03-27 00:00:00.0000000 +00:00 |  | 2012-05-11 12:00:00.0000000 +00:00 |  | 2013-06-12 12:00:00.0000000 +00:00 |  | 2013-08-15 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | [6 empty] | 2017-03-27 00:00:00.0000000 +00:00 |  | 2018-03-27 00:00:00.0000000 +00:00 |  | 2019-09-21 00:00:00.0000000 +00:00 |  | 2018-05-12 00:00:00.0000000 +00:00 | 2022-09-19 00:00:00.0000000 +00:00 |  | 2022-09-19 00:00:00.0000000 +00:00 |  |  | 2017-09-05 14:15:07.9201800 -04:00
GCJA03-3A | Y | 2015-09-29 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2018-01-18 00:00:00.0000000 +00:00 | 2018-10-15 00:00:00.0000000 +00:00 | 2019-10-14 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2018-01-18 00:00:00.0000000 +00:00 | 2018-10-15 00:00:00.0000000 +00:00 | 2019-10-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-29 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-29 00:00:00.0000000 +00:00 |  | 2015-09-29 00:00:00.0000000 +00:00 |  | 2017-11-15 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | [6 empty] | 2018-01-18 00:00:00.0000000 +00:00 |  | 2018-10-15 00:00:00.0000000 +00:00 |  | 2019-10-14 00:00:00.0000000 +00:00 |  | 2022-10-12 00:00:00.0000000 +00:00 | 2022-10-12 00:00:00.0000000 +00:00 |  | 2022-10-12 00:00:00.0000000 +00:00 |  | 2017-12-14 07:00:20.8300000 +00:00 | 2017-12-14 10:43:10.7681296 -05:00
GCJAM-01 | Y | 2015-09-26 00:00:00.0000000 +00:00 | 2015-09-26 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2015-09-26 00:00:00.0000000 +00:00 | 2015-09-26 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-28 17:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 |  | 2015-12-31 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2015-09-28 17:00:00.0000000 +00:00 | 2015-09-28 17:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-31 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2021-09-24 00:00:00.0000000 +00:00 | 2021-05-01 00:00:00.0000000 +00:00 |  | 2021-05-01 00:00:00.0000000 +00:00 | 2021-05-01 00:00:00.0000000 +00:00 |  | 2017-11-03 10:44:44.7952276 -04:00
GCNC77-01 | Y | 2012-03-07 00:00:00.0000000 +00:00 | 2013-06-11 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2013-06-11 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2015-03-13 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2013-06-11 00:00:00.0000000 +00:00 | 2013-11-07 00:00:00.0000000 +00:00 | 2014-04-21 00:00:00.0000000 +00:00 | 2015-04-20 00:00:00.0000000 +00:00 | 2012-03-07 12:00:00.0000000 +00:00 | 2013-06-11 12:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2017-06-30 17:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2012-03-07 12:00:00.0000000 +00:00 | 2013-06-11 00:00:00.0000000 +00:00 | 2013-06-11 12:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | [5 empty] | 2013-09-30 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2017-06-30 17:00:00.0000000 +00:00 | 2018-03-13 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 |  | 2020-06-30 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00
GCNC77-02 | Y | 2012-03-07 00:00:00.0000000 +00:00 | 2013-06-11 00:00:00.0000000 +00:00 | 2013-10-30 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2016-12-23 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2013-06-11 00:00:00.0000000 +00:00 | 2013-10-30 00:00:00.0000000 +00:00 | 2014-05-15 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2013-06-11 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-03-31 00:00:00.0000000 +00:00 | 2016-03-29 00:00:00.0000000 +00:00 | 2012-03-07 12:00:00.0000000 +00:00 | 2013-06-11 12:00:00.0000000 +00:00 | 2013-10-30 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2016-12-23 17:00:00.0000000 +00:00 | 2013-10-30 00:00:00.0000000 +00:00 | 2016-12-23 00:00:00.0000000 +00:00 |  | 2012-03-07 12:00:00.0000000 +00:00 |  | 2013-06-11 12:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 |  | 2013-08-15 00:00:00.0000000 +00:00 | [6 empty] | 2013-10-30 00:00:00.0000000 +00:00 |  | 2015-07-13 00:00:00.0000000 +00:00 |  | 2016-12-23 17:00:00.0000000 +00:00 | 2018-05-14 00:00:00.0000000 +00:00 | 2019-12-23 00:00:00.0000000 +00:00 |  |  | 2019-12-23 00:00:00.0000000 +00:00 |  | 2017-12-15 09:53:28.0709232 -05:00
GCTI11-01 | Y | 2014-09-17 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2014-09-17 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2017-08-10 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-17 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2014-09-17 00:00:00.0000000 +00:00 | 2014-09-17 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | [5 empty] | 2015-08-03 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2020-08-09 00:00:00.0000000 +00:00 | 2020-06-04 00:00:00.0000000 +00:00 |  | 2020-06-04 00:00:00.0000000 +00:00 | 2020-06-04 00:00:00.0000000 +00:00
GCTI11-02 | Y | 2014-04-24 00:00:00.0000000 +00:00 | 2015-11-17 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2020-01-12 00:00:00.0000000 +00:00 | 2014-04-24 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2016-02-28 00:00:00.0000000 +00:00 | 2017-02-28 00:00:00.0000000 +00:00 | [5 empty] | 2014-04-24 00:00:00.0000000 +00:00 | 2015-11-17 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 |  |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2014-04-24 00:00:00.0000000 +00:00 |  | 2015-11-17 00:00:00.0000000 +00:00 |  | 2015-03-30 00:00:00.0000000 +00:00 | 2016-04-13 00:00:00.0000000 +00:00 | 2016-04-13 00:00:00.0000000 +00:00 | 2016-04-13 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-15 00:00:00.0000000 +00:00 |  | 2018-07-16 00:00:00.0000000 +00:00 |  | 2020-01-12 00:00:00.0000000 +00:00 |  | 2020-02-28 00:00:00.0000000 +00:00 | 2023-01-01 00:00:00.0000000 +00:00 |  | 2023-01-01 00:00:00.0000000 +00:00 |  | 2017-09-27 13:00:19.8370000 +00:00 | 2017-10-24 14:20:16.1678864 -04:00
GE353 | Y | 2013-01-09 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2014-10-22 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2016-04-01 00:00:00.0000000 +00:00 | 2013-01-09 00:00:00.0000000 +00:00 | 2013-08-16 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-08-16 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2013-01-09 00:00:00.0000000 +00:00 | 2013-08-16 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-08-16 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2013-01-09 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2014-10-22 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2016-04-01 00:00:00.0000000 +00:00 | 2014-12-29 00:00:00.0000000 +00:00 | 2016-04-01 00:00:00.0000000 +00:00 | 2013-01-09 00:00:00.0000000 +00:00 |  | 2013-09-16 00:00:00.0000000 +00:00 |  |  | 2014-06-16 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | [6 empty] | 2014-10-22 00:00:00.0000000 +00:00 |  | 2015-08-03 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2016-04-01 00:00:00.0000000 +00:00 | 2016-04-01 00:00:00.0000000 +00:00 | 2018-08-16 00:00:00.0000000 +00:00 | 2018-04-02 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-29 12:33:03.8523373 -04:00
GE354 | Y | 2013-03-26 00:00:00.0000000 +00:00 | 2013-05-08 00:00:00.0000000 +00:00 | 2013-07-26 00:00:00.0000000 +00:00 | 2014-09-26 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2013-03-26 00:00:00.0000000 +00:00 | 2013-05-26 00:00:00.0000000 +00:00 | 2013-09-04 00:00:00.0000000 +00:00 | 2014-11-04 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2013-03-26 00:00:00.0000000 +00:00 | 2013-05-26 00:00:00.0000000 +00:00 | 2013-08-13 00:00:00.0000000 +00:00 |  |  | 2013-03-26 00:00:00.0000000 +00:00 | 2013-05-08 00:00:00.0000000 +00:00 | 2013-07-26 00:00:00.0000000 +00:00 | 2014-09-26 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2013-07-04 00:00:00.0000000 +00:00 |  | 2013-03-26 00:00:00.0000000 +00:00 |  | 2013-05-08 00:00:00.0000000 +00:00 | [11 empty] | 2013-07-26 00:00:00.0000000 +00:00 |  | 2014-09-26 00:00:00.0000000 +00:00 | 2014-09-26 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2015-12-02 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00
GE-355 | Y | 2014-03-27 00:00:00.0000000 +00:00 | 2014-04-16 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2014-04-16 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2016-05-19 00:00:00.0000000 +00:00 | [5 empty] | 2014-03-27 17:00:00.0000000 +00:00 | 2014-04-16 17:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2015-08-13 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2014-03-27 17:00:00.0000000 +00:00 | 2014-03-27 17:00:00.0000000 +00:00 | 2014-04-16 17:00:00.0000000 +00:00 | 2014-04-16 17:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-19 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2017-05-19 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 |  | 2019-05-01 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 |  | 2017-09-01 15:56:19.7718595 -04:00
GE-356 | Y | 2014-03-27 00:00:00.0000000 +00:00 | 2014-04-16 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2014-04-16 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | [5 empty] | 2014-03-27 08:00:00.0000000 +00:00 | 2014-04-16 08:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2014-11-15 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2014-03-27 08:00:00.0000000 +00:00 | 2014-03-27 08:00:00.0000000 +00:00 | 2014-04-16 08:00:00.0000000 +00:00 | 2014-04-16 08:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2019-04-03 00:00:00.0000000 +00:00 | 2019-04-03 00:00:00.0000000 +00:00 |  | 2019-04-03 00:00:00.0000000 +00:00 | 2019-04-03 00:00:00.0000000 +00:00 |  | 2017-09-01 15:57:08.2482869 -04:00
GE357 | Y | 2015-01-07 00:00:00.0000000 +00:00 | 2015-11-01 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2017-05-08 00:00:00.0000000 +00:00 | 2018-05-07 00:00:00.0000000 +00:00 | 2015-01-07 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-07 17:00:00.0000000 +00:00 | 2015-11-01 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2017-05-08 00:00:00.0000000 +00:00 |  | 2016-10-14 00:00:00.0000000 +00:00 |  | 2015-01-07 17:00:00.0000000 +00:00 | 2015-01-07 17:00:00.0000000 +00:00 | 2015-11-01 00:00:00.0000000 +00:00 | 2015-11-01 00:00:00.0000000 +00:00 | 2015-11-15 00:00:00.0000000 +00:00 | 2016-05-15 00:00:00.0000000 +00:00 | 2016-05-15 00:00:00.0000000 +00:00 | 2016-05-15 00:00:00.0000000 +00:00 | 2016-05-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-08-30 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2017-05-08 00:00:00.0000000 +00:00 | 2017-05-08 00:00:00.0000000 +00:00 | 2018-05-07 00:00:00.0000000 +00:00 | 2018-05-07 00:00:00.0000000 +00:00 | 2018-06-20 00:00:00.0000000 +00:00 | 2020-05-06 00:00:00.0000000 +00:00 |  | 2020-05-06 00:00:00.0000000 +00:00 | 2020-05-06 00:00:00.0000000 +00:00
GE358 | Y | 2015-01-07 00:00:00.0000000 +00:00 | 2015-11-01 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2018-04-02 00:00:00.0000000 +00:00 | 2015-01-07 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-07 17:00:00.0000000 +00:00 | 2015-11-01 17:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 |  | 2016-02-16 00:00:00.0000000 +00:00 | 2018-04-02 00:00:00.0000000 +00:00 | 2015-01-07 17:00:00.0000000 +00:00 | 2015-01-07 17:00:00.0000000 +00:00 | 2015-11-01 17:00:00.0000000 +00:00 | 2015-11-01 17:00:00.0000000 +00:00 | 2015-11-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-21 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2018-04-02 00:00:00.0000000 +00:00 | 2018-04-02 00:00:00.0000000 +00:00 | 2019-06-20 00:00:00.0000000 +00:00 | 2020-03-22 00:00:00.0000000 +00:00 |  | 2020-03-22 00:00:00.0000000 +00:00 | 2020-03-22 00:00:00.0000000 +00:00 |  | 2017-09-01 15:58:03.9131258 -04:00
GE-359 | Y | 2017-02-10 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-06-14 00:00:00.0000000 +00:00 | 2017-02-10 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-06-14 00:00:00.0000000 +00:00 | [5 empty] | 2017-02-10 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 |  |  |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2017-02-10 00:00:00.0000000 +00:00 |  | 2017-06-05 00:00:00.0000000 +00:00 |  | 2017-09-08 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-15 00:00:00.0000000 +00:00 |  | 2018-06-15 00:00:00.0000000 +00:00 |  | 2019-06-14 00:00:00.0000000 +00:00 |  | 2021-06-14 00:00:00.0000000 +00:00 | 2021-06-14 00:00:00.0000000 +00:00 |  | 2021-06-14 00:00:00.0000000 +00:00 |  |  | 2017-10-24 12:57:03.9430823 -04:00
GE-360-KR | Y | 2017-03-06 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2019-08-26 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2018-05-19 00:00:00.0000000 +00:00 | 2019-05-20 00:00:00.0000000 +00:00 | [5 empty] | 2017-03-06 00:00:00.0000000 +00:00 | 2017-04-17 17:00:00.0000000 +00:00 |  |  |  | 2017-12-30 00:00:00.0000000 +00:00 | 2019-08-26 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2017-04-17 17:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2017-07-20 00:00:00.0000000 +00:00 | 2017-07-20 00:00:00.0000000 +00:00 | 2017-07-20 00:00:00.0000000 +00:00 | 2017-07-20 00:00:00.0000000 +00:00 | 2017-07-20 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-30 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2019-08-26 00:00:00.0000000 +00:00 | 2019-08-26 00:00:00.0000000 +00:00 | 2022-08-25 00:00:00.0000000 +00:00 | 2022-08-25 00:00:00.0000000 +00:00 |  | 2022-08-25 00:00:00.0000000 +00:00 | 2022-08-25 00:00:00.0000000 +00:00 |  | 2017-08-30 14:29:59.8908738 -04:00
GE-360-MX | Y | 2017-06-21 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | 2017-12-14 00:00:00.0000000 +00:00 | 2018-08-26 00:00:00.0000000 +00:00 | 2019-08-26 00:00:00.0000000 +00:00 | 2017-06-21 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2018-08-26 00:00:00.0000000 +00:00 | 2019-08-26 00:00:00.0000000 +00:00 | [5 empty] | 2017-06-21 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | 2017-12-13 00:00:00.0000000 +00:00 |  |  | 2017-12-01 00:00:00.0000000 +00:00 |  | 2017-06-21 00:00:00.0000000 +00:00 |  | 2017-09-01 00:00:00.0000000 +00:00 |  | 2017-09-30 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-14 00:00:00.0000000 +00:00 |  | 2018-08-26 00:00:00.0000000 +00:00 |  | 2019-08-26 00:00:00.0000000 +00:00 |  | 2019-10-26 00:00:00.0000000 +00:00 | 2019-10-26 00:00:00.0000000 +00:00 |  | 2019-10-26 00:00:00.0000000 +00:00 |  |  | 2017-11-16 16:19:26.8585430 -05:00
GE-360-Q | Y | 2017-06-20 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | 2019-08-13 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 | [5 empty] | 2017-06-20 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2017-12-13 00:00:00.0000000 +00:00 |  |  | 2017-12-29 00:00:00.0000000 +00:00 |  | 2017-06-21 17:00:00.0000000 +00:00 |  | 2017-06-28 00:00:00.0000000 +00:00 |  | 2017-09-01 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-08-14 00:00:00.0000000 +00:00 |  | 2019-08-13 00:00:00.0000000 +00:00 |  | 2022-06-27 00:00:00.0000000 +00:00 | 2022-08-12 00:00:00.0000000 +00:00 |  | 2022-08-12 00:00:00.0000000 +00:00 |  |  | 2017-12-14 10:15:08.6686223 -05:00
GI-NTWN-A | Y | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2019-01-29 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2019-01-29 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 |  | 2017-01-13 00:00:00.0000000 +00:00 | 2019-01-29 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2019-01-29 00:00:00.0000000 +00:00 | 2019-01-29 00:00:00.0000000 +00:00 | 2022-01-28 00:00:00.0000000 +00:00 | 2022-01-28 00:00:00.0000000 +00:00 |  | 2022-01-28 00:00:00.0000000 +00:00 | 2022-01-28 00:00:00.0000000 +00:00
GI-UTOP-1 | Y
GK-CM-01 | Y | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2016-08-19 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2016-04-21 00:00:00.0000000 +00:00 | [5 empty] | 2014-10-30 18:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2016-08-19 17:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2016-08-19 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2016-08-19 00:00:00.0000000 +00:00 | 2016-08-19 00:00:00.0000000 +00:00 | 2019-08-18 00:00:00.0000000 +00:00 | 2019-08-18 00:00:00.0000000 +00:00 |  | 2019-08-18 00:00:00.0000000 +00:00 | 2019-08-18 00:00:00.0000000 +00:00
GKNC14-05 | Y | 2012-03-07 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2018-09-08 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | [5 empty] | 2012-03-07 17:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 |  |  |  | 2018-09-08 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2012-03-07 17:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | [5 empty] | 2018-09-08 00:00:00.0000000 +00:00 | 2018-09-08 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2017-11-17 12:34:16.0528955 -05:00
GKNC14-06 | Y | 2012-03-07 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 | 2021-09-29 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | [5 empty] | 2012-03-07 17:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 |  |  |  | 2019-02-14 00:00:00.0000000 +00:00 | 2021-09-29 00:00:00.0000000 +00:00 | 2012-03-07 17:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | [5 empty] | 2019-02-14 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 | 2021-09-29 00:00:00.0000000 +00:00 | 2021-09-29 00:00:00.0000000 +00:00 | 2024-09-28 00:00:00.0000000 +00:00 | 2024-09-28 00:00:00.0000000 +00:00 |  | 2024-09-28 00:00:00.0000000 +00:00 | 2024-09-28 00:00:00.0000000 +00:00 |  | 2017-11-20 11:18:13.7457010 -05:00
GKNC14-07 | Y | 2012-03-07 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2018-04-10 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | [5 empty] | 2012-03-07 17:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 |  |  |  | 2018-04-10 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2012-03-07 17:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | [5 empty] | 2018-04-10 00:00:00.0000000 +00:00 | 2018-04-10 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2017-11-20 11:18:41.8337383 -05:00
GKOH15-01 | Y | 2016-07-29 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2020-08-15 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2020-08-15 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-29 00:00:00.0000000 +00:00 | 2017-08-01 17:00:00.0000000 +00:00 |  |  |  | 2019-11-29 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-08-01 17:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 |  | 2019-01-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2019-11-29 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2020-08-15 00:00:00.0000000 +00:00 | 2020-08-15 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | 2025-08-13 00:00:00.0000000 +00:00 | 2025-08-13 00:00:00.0000000 +00:00 |  | 2025-08-13 00:00:00.0000000 +00:00 | 2025-08-13 00:00:00.0000000 +00:00
GKOH15-02 | Y | 2016-07-29 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2020-02-27 00:00:00.0000000 +00:00 | 2020-11-12 00:00:00.0000000 +00:00 | 2022-11-11 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2020-02-27 00:00:00.0000000 +00:00 | 2020-11-12 00:00:00.0000000 +00:00 | 2022-11-11 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-29 17:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 |  |  |  | 2020-02-27 00:00:00.0000000 +00:00 | 2022-11-11 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 |  | 2019-01-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2020-02-27 00:00:00.0000000 +00:00 | 2020-02-27 00:00:00.0000000 +00:00 | 2020-11-12 00:00:00.0000000 +00:00 | 2020-11-12 00:00:00.0000000 +00:00 | 2022-11-11 00:00:00.0000000 +00:00 | 2022-11-11 00:00:00.0000000 +00:00 | 2025-11-10 00:00:00.0000000 +00:00 | 2025-11-10 00:00:00.0000000 +00:00 |  | 2025-11-10 00:00:00.0000000 +00:00 | 2025-11-10 00:00:00.0000000 +00:00
GKOH15-03 | Y | 2016-07-29 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2020-08-15 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2020-08-15 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-29 00:00:00.0000000 +00:00 | 2017-08-01 17:00:00.0000000 +00:00 |  |  |  | 2019-11-29 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-08-01 17:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2018-12-31 00:00:00.0000000 +00:00 | 2018-12-31 00:00:00.0000000 +00:00 |  | 2018-12-31 00:00:00.0000000 +00:00 | 2018-12-31 00:00:00.0000000 +00:00 | [5 empty] | 2019-11-29 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2020-08-15 00:00:00.0000000 +00:00 | 2020-08-15 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | 2022-08-14 00:00:00.0000000 +00:00 | 2025-08-13 00:00:00.0000000 +00:00 | 2025-08-13 00:00:00.0000000 +00:00 |  | 2025-08-13 00:00:00.0000000 +00:00 | 2025-08-13 00:00:00.0000000 +00:00
GKOH15-04 | Y | 2017-11-22 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2020-05-01 00:00:00.0000000 +00:00 | 2021-03-01 00:00:00.0000000 +00:00 | 2023-02-28 00:00:00.0000000 +00:00 | 2017-11-22 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2020-05-01 00:00:00.0000000 +00:00 | 2021-03-01 00:00:00.0000000 +00:00 | 2023-02-28 00:00:00.0000000 +00:00 | [5 empty] | 2017-11-22 00:00:00.0000000 +00:00 | [6 empty] | 2017-11-22 00:00:00.0000000 +00:00 | 2017-11-22 00:00:00.0000000 +00:00 |  |  | 2019-05-01 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | [14 empty] | 2026-02-27 00:00:00.0000000 +00:00 | 2026-02-27 00:00:00.0000000 +00:00 |  |  |  | 2017-12-01 07:00:23.0270000 +00:00
GNCB14-1A | Y | 2012-03-07 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2020-01-29 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2020-01-29 00:00:00.0000000 +00:00 | [5 empty] | 2012-03-07 00:00:00.0000000 +00:00 | 2014-08-27 18:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 |  |  | 2017-11-30 00:00:00.0000000 +00:00 | 2020-01-29 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-08-27 18:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | [5 empty] | 2017-11-30 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2020-01-29 00:00:00.0000000 +00:00 | 2020-01-29 00:00:00.0000000 +00:00 | 2023-01-28 00:00:00.0000000 +00:00 | 2023-01-28 00:00:00.0000000 +00:00 |  | 2023-01-28 00:00:00.0000000 +00:00 | 2023-01-28 00:00:00.0000000 +00:00 |  | 2017-10-30 13:48:27.7400270 -04:00
GNCB14-2A | Y | [48 empty] | 2017-09-01 13:08:10.2376899 -04:00
GNCB14-3A | Y | [48 empty] | 2017-09-01 13:08:30.0509132 -04:00
GQBB09-01 | Y | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2016-08-26 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2018-06-28 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2016-08-26 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2018-06-28 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2016-08-26 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 |  | 2016-02-02 00:00:00.0000000 +00:00 | 2018-06-28 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-08-26 00:00:00.0000000 +00:00 | 2016-08-26 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2018-06-28 00:00:00.0000000 +00:00 | 2018-06-28 00:00:00.0000000 +00:00 | 2021-06-26 00:00:00.0000000 +00:00 | 2021-06-27 00:00:00.0000000 +00:00 |  | 2021-06-27 00:00:00.0000000 +00:00 | 2021-06-27 00:00:00.0000000 +00:00 |  | 2017-10-18 14:32:56.2966001 -04:00
GQ-CM-01 | Y
GQJA03-01 | Y | 2015-08-16 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2017-01-18 00:00:00.0000000 +00:00 | 2019-08-15 00:00:00.0000000 +00:00 | 2020-08-14 00:00:00.0000000 +00:00 | 2015-08-16 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2016-12-29 00:00:00.0000000 +00:00 | 2019-08-15 00:00:00.0000000 +00:00 | 2020-08-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-08-17 18:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2017-01-18 00:00:00.0000000 +00:00 |  |  | 2017-01-18 00:00:00.0000000 +00:00 |  | 2015-08-17 18:00:00.0000000 +00:00 |  | 2015-09-25 00:00:00.0000000 +00:00 |  | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 | [6 empty] | 2017-01-18 00:00:00.0000000 +00:00 |  | 2019-08-15 00:00:00.0000000 +00:00 |  | 2020-08-14 00:00:00.0000000 +00:00 |  | 2023-08-14 00:00:00.0000000 +00:00 | 2023-08-14 00:00:00.0000000 +00:00 |  | 2023-08-14 00:00:00.0000000 +00:00
GQJA03-02 | Y | 2015-08-17 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2018-09-29 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2021-01-09 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-18 00:00:00.0000000 +00:00 | 2018-09-29 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2021-01-09 00:00:00.0000000 +00:00 | [5 empty] | 2015-08-17 18:00:00.0000000 +00:00 | 2015-09-29 17:00:00.0000000 +00:00 |  |  |  | 2018-09-29 00:00:00.0000000 +00:00 |  | 2015-08-17 18:00:00.0000000 +00:00 |  | 2015-09-29 17:00:00.0000000 +00:00 |  | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 | [6 empty] | 2018-09-29 00:00:00.0000000 +00:00 |  | 2019-07-15 00:00:00.0000000 +00:00 |  | 2021-01-09 00:00:00.0000000 +00:00 |  | 2024-01-08 00:00:00.0000000 +00:00 | 2024-01-08 00:00:00.0000000 +00:00 |  | 2024-01-08 00:00:00.0000000 +00:00 |  |  | 2017-09-14 16:37:05.4255677 -04:00
GQJA03-03 | Y | 2015-08-17 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2018-01-18 00:00:00.0000000 +00:00 | 2019-01-30 00:00:00.0000000 +00:00 | 2020-07-27 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2018-01-18 00:00:00.0000000 +00:00 | 2019-01-30 00:00:00.0000000 +00:00 | 2020-07-27 00:00:00.0000000 +00:00 | [5 empty] | 2015-08-17 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 |  |  |  | 2018-01-18 00:00:00.0000000 +00:00 |  | 2015-08-17 00:00:00.0000000 +00:00 |  | 2015-09-25 00:00:00.0000000 +00:00 |  | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 | [6 empty] | 2018-01-18 00:00:00.0000000 +00:00 |  | 2019-01-30 00:00:00.0000000 +00:00 |  | 2020-07-27 00:00:00.0000000 +00:00 |  | 2023-07-26 00:00:00.0000000 +00:00 | 2023-07-26 00:00:00.0000000 +00:00 |  | 2023-07-26 00:00:00.0000000 +00:00 |  |  | 2017-09-14 16:37:53.1215459 -04:00
GQTI03-23 | Y | 2017-05-18 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2018-07-31 00:00:00.0000000 +00:00 |  |  | 2017-05-18 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2018-07-31 00:00:00.0000000 +00:00 | [7 empty] | 2017-05-18 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 |  |  |  | 2018-07-31 00:00:00.0000000 +00:00 | [5 empty] | 2018-03-30 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | [19 empty] | 2017-11-06 13:00:21.6400000 +00:00
GQTI10-01 | Y | 2014-11-14 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2020-10-29 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2018-09-08 00:00:00.0000000 +00:00 | [5 empty] | 2014-11-14 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 |  |  |  | 2018-03-30 00:00:00.0000000 +00:00 |  | 2014-11-14 00:00:00.0000000 +00:00 |  | 2016-05-04 00:00:00.0000000 +00:00 |  | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | [6 empty] | 2018-03-30 00:00:00.0000000 +00:00 |  | 2018-10-30 00:00:00.0000000 +00:00 |  | 2020-10-29 00:00:00.0000000 +00:00 |  | 2021-09-07 00:00:00.0000000 +00:00 | 2023-10-29 00:00:00.0000000 +00:00 |  | 2023-10-29 00:00:00.0000000 +00:00 |  |  | 2017-11-03 14:51:27.4336229 -04:00
GQTI10-02 | Y | 2014-11-14 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 | 2018-10-17 00:00:00.0000000 +00:00 | 2019-05-31 00:00:00.0000000 +00:00 | 2021-05-30 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2018-09-08 00:00:00.0000000 +00:00 | [5 empty] | 2014-11-14 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 |  |  |  | 2018-10-17 00:00:00.0000000 +00:00 |  | 2014-11-14 00:00:00.0000000 +00:00 |  | 2016-05-04 00:00:00.0000000 +00:00 |  | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | [6 empty] | 2018-10-17 00:00:00.0000000 +00:00 |  | 2019-05-31 00:00:00.0000000 +00:00 |  | 2021-05-30 00:00:00.0000000 +00:00 |  | 2021-09-07 00:00:00.0000000 +00:00 | 2024-05-29 00:00:00.0000000 +00:00 |  | 2024-05-29 00:00:00.0000000 +00:00 |  |  | 2017-11-03 14:57:57.4372053 -04:00
GQTI10-03 | Y | 2014-11-14 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 | 2018-10-01 00:00:00.0000000 +00:00 | 2019-05-31 00:00:00.0000000 +00:00 | 2021-05-30 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2018-09-08 00:00:00.0000000 +00:00 | [5 empty] | 2014-11-14 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 |  |  |  | 2018-10-01 00:00:00.0000000 +00:00 |  | 2014-11-14 00:00:00.0000000 +00:00 |  | 2016-05-04 00:00:00.0000000 +00:00 |  | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | [6 empty] | 2018-10-01 00:00:00.0000000 +00:00 |  | 2019-05-31 00:00:00.0000000 +00:00 |  | 2021-05-30 00:00:00.0000000 +00:00 |  | 2021-09-07 00:00:00.0000000 +00:00 | 2024-05-29 00:00:00.0000000 +00:00 |  | 2024-05-29 00:00:00.0000000 +00:00
GQTI10-04 | Y | 2015-05-26 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 | 2020-02-28 00:00:00.0000000 +00:00 | 2020-08-24 00:00:00.0000000 +00:00 | 2022-08-24 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2016-05-20 00:00:00.0000000 +00:00 | 2017-05-19 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2018-12-11 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-26 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 |  |  |  | 2020-02-28 00:00:00.0000000 +00:00 |  | 2015-05-26 00:00:00.0000000 +00:00 |  | 2016-05-04 00:00:00.0000000 +00:00 |  | 2016-12-12 00:00:00.0000000 +00:00 | 2016-12-12 00:00:00.0000000 +00:00 | 2016-12-12 00:00:00.0000000 +00:00 | 2016-12-12 00:00:00.0000000 +00:00 | [6 empty] | 2020-02-28 00:00:00.0000000 +00:00 |  | 2020-08-24 00:00:00.0000000 +00:00 |  | 2022-08-24 00:00:00.0000000 +00:00 |  | 2021-12-10 00:00:00.0000000 +00:00 | 2025-08-23 00:00:00.0000000 +00:00 |  | 2025-08-23 00:00:00.0000000 +00:00
GQTI11-22 | Y | 2014-04-24 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2020-07-15 00:00:00.0000000 +00:00 | 2014-04-24 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2016-02-28 00:00:00.0000000 +00:00 | 2017-02-28 00:00:00.0000000 +00:00 | [5 empty] | 2014-04-24 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 |  |  |  | 2017-12-29 00:00:00.0000000 +00:00 |  | 2014-04-24 00:00:00.0000000 +00:00 |  | 2014-08-14 00:00:00.0000000 +00:00 |  | 2015-03-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-07-16 00:00:00.0000000 +00:00 |  | 2020-07-15 00:00:00.0000000 +00:00 |  | 2020-02-28 00:00:00.0000000 +00:00 | 2023-07-16 00:00:00.0000000 +00:00 |  | 2023-07-16 00:00:00.0000000 +00:00
GRANSTBID | Y | 2012-08-29 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2013-12-17 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2012-08-29 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-12 00:00:00.0000000 +00:00 | 2012-08-29 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2013-12-17 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2015-06-13 00:00:00.0000000 +00:00 | 2012-08-29 12:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2013-10-07 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2016-06-30 18:00:00.0000000 +00:00 | 2013-10-07 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | 2012-08-29 00:00:00.0000000 +00:00 | 2012-08-29 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | [5 empty] | 2013-10-07 00:00:00.0000000 +00:00 | 2013-10-07 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 |  | 2019-06-29 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 |  | 2017-08-30 14:30:46.6426938 -04:00
GRINFRA01 | Y | 2012-05-11 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2016-08-19 00:00:00.0000000 +00:00 | 2013-08-03 00:00:00.0000000 +00:00 | 2013-08-03 00:00:00.0000000 +00:00 | 2012-05-11 00:00:00.0000000 +00:00 | 2013-06-17 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2012-05-11 00:00:00.0000000 +00:00 | 2013-10-17 00:00:00.0000000 +00:00 | 2016-08-21 00:00:00.0000000 +00:00 |  |  | 2012-05-11 12:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 |  |  |  | 2016-06-12 00:00:00.0000000 +00:00 | [27 empty] | 2017-11-29 09:06:30.2402411 -05:00
GRINFRA02 | Y | 2012-03-07 00:00:00.0000000 +00:00 | 2014-10-03 00:00:00.0000000 +00:00 | 2014-05-13 00:00:00.0000000 +00:00 |  |  | 2012-03-07 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2014-04-12 00:00:00.0000000 +00:00 |  |  | 2012-03-07 00:00:00.0000000 +00:00 | 2014-11-06 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 |  |  | 2012-03-07 00:00:00.0000000 +00:00 | 2013-10-04 00:00:00.0000000 +00:00 |  |  |  | 2014-06-30 00:00:00.0000000 +00:00
GXHP24-01 | Y | 2012-03-07 00:00:00.0000000 +00:00 | 2013-06-10 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2017-11-01 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2012-07-16 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-01 00:00:00.0000000 +00:00 | 2014-07-02 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2013-04-16 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2012-03-07 12:00:00.0000000 +00:00 | 2013-06-10 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2017-11-01 00:00:00.0000000 +00:00 |  | 2017-03-29 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2012-03-07 12:00:00.0000000 +00:00 | 2012-03-07 12:00:00.0000000 +00:00 | 2013-06-10 00:00:00.0000000 +00:00 | 2013-06-10 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-03-29 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2017-11-01 00:00:00.0000000 +00:00 | 2017-11-01 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | 2022-04-30 00:00:00.0000000 +00:00 |  | 2022-04-30 00:00:00.0000000 +00:00 | 2022-04-30 00:00:00.0000000 +00:00 |  | 2017-09-01 08:31:52.7635875 -04:00
HAM16MRCC | Y | 2015-06-22 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-08-01 00:00:00.0000000 +00:00 | 2016-08-24 00:00:00.0000000 +00:00 | 2015-06-22 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-13 00:00:00.0000000 +00:00 | 2016-08-24 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-22 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-08-01 00:00:00.0000000 +00:00 | 2016-08-24 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-08-24 00:00:00.0000000 +00:00 | 2015-06-22 00:00:00.0000000 +00:00 | 2015-06-22 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-08-01 00:00:00.0000000 +00:00 | 2016-08-01 00:00:00.0000000 +00:00 | 2016-08-24 00:00:00.0000000 +00:00 | 2016-08-24 00:00:00.0000000 +00:00 | 2017-02-24 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 |  | 2017-11-03 09:20:34.8932430 -04:00
HBMA24529 | Y | [47 empty] | 2017-10-05 13:00:19.0670000 +00:00
HBMA24662 | Y | [47 empty] | 2017-12-01 07:00:24.2230000 +00:00
HBPED100M | Y | 2005-03-11 00:00:00.0000000 +00:00 | 2006-01-10 00:00:00.0000000 +00:00 | 2012-11-14 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2017-12-28 00:00:00.0000000 +00:00 | 2005-03-11 00:00:00.0000000 +00:00 | 2006-01-10 00:00:00.0000000 +00:00 | 2012-11-14 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2005-03-11 00:00:00.0000000 +00:00 | 2006-01-10 00:00:00.0000000 +00:00 | 2012-11-14 00:00:00.0000000 +00:00 | 2014-07-08 00:00:00.0000000 +00:00 | 2015-12-29 00:00:00.0000000 +00:00 | 2005-03-11 17:00:00.0000000 +00:00 | 2006-01-10 17:00:00.0000000 +00:00 | 2012-11-14 00:00:00.0000000 +00:00 | 2014-11-24 17:00:00.0000000 +00:00 |  | 2012-11-14 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2005-03-11 17:00:00.0000000 +00:00 | 2005-03-11 17:00:00.0000000 +00:00 | 2006-01-10 17:00:00.0000000 +00:00 | 2006-01-10 17:00:00.0000000 +00:00 | 2010-10-15 00:00:00.0000000 +00:00 | 2010-10-15 00:00:00.0000000 +00:00 | 2010-10-15 00:00:00.0000000 +00:00 | 2010-10-15 00:00:00.0000000 +00:00 | 2010-10-15 00:00:00.0000000 +00:00 | [5 empty] | 2012-11-14 00:00:00.0000000 +00:00 | 2012-11-14 00:00:00.0000000 +00:00 | 2014-11-24 17:00:00.0000000 +00:00 | 2014-11-24 17:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2020-09-29 00:00:00.0000000 +00:00 | 2019-12-29 00:00:00.0000000 +00:00 |  | 2019-09-30 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 |  | 2017-09-05 14:56:51.8256830 -04:00
HBPED100Q | Y | 2005-03-11 00:00:00.0000000 +00:00 | 2006-01-10 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2019-02-18 00:00:00.0000000 +00:00 | 2020-08-16 00:00:00.0000000 +00:00 | 2005-03-11 00:00:00.0000000 +00:00 | 2005-08-15 00:00:00.0000000 +00:00 | 2006-01-15 00:00:00.0000000 +00:00 | 2006-07-15 00:00:00.0000000 +00:00 | 2007-01-15 00:00:00.0000000 +00:00 | 2005-03-11 00:00:00.0000000 +00:00 | 2005-08-29 00:00:00.0000000 +00:00 | 2015-04-14 00:00:00.0000000 +00:00 | 2015-10-12 00:00:00.0000000 +00:00 | 2016-04-13 00:00:00.0000000 +00:00 | 2005-03-11 00:00:00.0000000 +00:00 | 2006-01-10 00:00:00.0000000 +00:00 |  |  |  | 2018-07-15 00:00:00.0000000 +00:00 |  | 2005-03-11 00:00:00.0000000 +00:00 |  | 2006-01-10 00:00:00.0000000 +00:00 |  | 2005-11-30 00:00:00.0000000 +00:00 | 2008-11-20 00:00:00.0000000 +00:00 | 2008-11-20 00:00:00.0000000 +00:00 | 2008-11-20 00:00:00.0000000 +00:00 | [6 empty] | 2018-07-15 00:00:00.0000000 +00:00 |  | 2019-02-18 00:00:00.0000000 +00:00 |  | 2020-08-16 00:00:00.0000000 +00:00 |  | 2010-01-14 00:00:00.0000000 +00:00 | 2023-08-14 00:00:00.0000000 +00:00 |  | 2023-08-14 00:00:00.0000000 +00:00
HBPED216S | Y | 2005-03-22 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2018-06-25 00:00:00.0000000 +00:00 | 2019-02-20 00:00:00.0000000 +00:00 | 2005-03-22 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2018-06-25 00:00:00.0000000 +00:00 | 2019-02-20 00:00:00.0000000 +00:00 | [5 empty] | 2005-03-22 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 |  |  | 2017-12-11 00:00:00.0000000 +00:00 | [5 empty] | 2017-08-02 00:00:00.0000000 +00:00 | 2017-08-02 00:00:00.0000000 +00:00 | 2017-08-02 00:00:00.0000000 +00:00 | [13 empty] | 2022-02-18 00:00:00.0000000 +00:00 | 2022-02-18 00:00:00.0000000 +00:00 |  |  |  | 2017-12-14 13:00:23.5200000 +00:00 | 2017-12-15 11:36:35.8189493 -05:00
HBPED700E | Y | 2013-12-05 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-01-17 00:00:00.0000000 +00:00 | 2014-02-10 00:00:00.0000000 +00:00 | 2014-08-08 00:00:00.0000000 +00:00 | 2013-12-05 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-01-17 00:00:00.0000000 +00:00 | 2014-02-10 00:00:00.0000000 +00:00 | 2014-08-08 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-05 17:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-01-17 00:00:00.0000000 +00:00 | 2014-02-10 00:00:00.0000000 +00:00 | 2014-08-08 00:00:00.0000000 +00:00 | 2014-01-17 00:00:00.0000000 +00:00 | 2014-08-08 00:00:00.0000000 +00:00 | 2013-12-05 17:00:00.0000000 +00:00 | 2013-12-05 17:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-01-17 00:00:00.0000000 +00:00 | 2014-01-17 00:00:00.0000000 +00:00 | 2014-02-10 00:00:00.0000000 +00:00 | 2014-02-10 00:00:00.0000000 +00:00 | 2014-08-08 00:00:00.0000000 +00:00 | 2014-08-08 00:00:00.0000000 +00:00 | 2017-08-07 00:00:00.0000000 +00:00 | 2017-08-07 00:00:00.0000000 +00:00 | 2017-08-07 00:00:00.0000000 +00:00 | 2017-08-07 00:00:00.0000000 +00:00 | 2017-08-07 00:00:00.0000000 +00:00
HBPED700Q | Y | 2011-12-20 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2014-10-28 00:00:00.0000000 +00:00 |  |  | 2011-12-20 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 |  |  | 2011-12-20 00:00:00.0000000 +00:00 | 2012-11-14 00:00:00.0000000 +00:00 | 2014-09-09 00:00:00.0000000 +00:00 |  |  | 2011-12-20 12:00:00.0000000 +00:00 | 2013-05-16 12:00:00.0000000 +00:00 | 2014-10-28 00:00:00.0000000 +00:00 |  |  | 2014-10-28 00:00:00.0000000 +00:00 | [5 empty] | 2012-09-28 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00
HBPED800Q | Y | 2012-11-19 00:00:00.0000000 +00:00 | 2017-09-18 00:00:00.0000000 +00:00 | 2019-09-17 00:00:00.0000000 +00:00 | 2020-07-29 00:00:00.0000000 +00:00 | 2023-07-29 00:00:00.0000000 +00:00 | 2012-11-19 00:00:00.0000000 +00:00 | 2013-03-05 00:00:00.0000000 +00:00 | 2014-01-20 00:00:00.0000000 +00:00 | 2020-09-25 00:00:00.0000000 +00:00 | 2022-09-24 00:00:00.0000000 +00:00 | 2012-11-19 00:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 |  |  | 2012-11-19 12:00:00.0000000 +00:00 | 2017-09-18 00:00:00.0000000 +00:00 |  |  |  | 2019-09-17 00:00:00.0000000 +00:00 |  | 2012-11-19 00:00:00.0000000 +00:00 | 2012-11-19 00:00:00.0000000 +00:00 | 2017-09-18 00:00:00.0000000 +00:00 | 2017-09-18 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 |  | 2018-09-17 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | [5 empty] | 2019-09-17 00:00:00.0000000 +00:00 | 2019-09-17 00:00:00.0000000 +00:00 |  |  |  |  | 2025-09-23 00:00:00.0000000 +00:00 | 2026-07-28 00:00:00.0000000 +00:00
HBPEDMRS | Y | 2005-11-16 00:00:00.0000000 +00:00 | 2006-10-05 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2021-02-10 00:00:00.0000000 +00:00 | 2022-02-10 00:00:00.0000000 +00:00 | 2005-11-16 00:00:00.0000000 +00:00 | 2006-10-05 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-06-15 00:00:00.0000000 +00:00 | 2015-06-16 00:00:00.0000000 +00:00 | 2005-11-16 00:00:00.0000000 +00:00 | 2006-10-05 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-04-20 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2005-11-16 12:00:00.0000000 +00:00 | 2006-10-05 12:00:00.0000000 +00:00 |  |  |  | 2016-07-15 00:00:00.0000000 +00:00 | 2018-01-29 00:00:00.0000000 +00:00 | [20 empty] | 2018-06-15 00:00:00.0000000 +00:00 | 2025-02-10 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 15:10:59.6041633 -04:00
HBQA70551 | Y | [47 empty] | 2017-10-05 13:00:20.3830000 +00:00
HD153C1 | Y | [10 empty] | 2000-03-01 00:00:00.0000000 +00:00 | 2006-01-11 00:00:00.0000000 +00:00 | 2007-12-28 00:00:00.0000000 +00:00 | 2009-04-27 00:00:00.0000000 +00:00 | 2014-11-30 00:00:00.0000000 +00:00 | [33 empty] | 2017-09-14 08:34:02.3382948 -04:00
HD153C2 | Y | 2000-03-01 00:00:00.0000000 +00:00 | 2007-04-09 00:00:00.0000000 +00:00 | 2010-02-11 00:00:00.0000000 +00:00 | 2011-09-06 00:00:00.0000000 +00:00 | 2015-09-27 00:00:00.0000000 +00:00 | 2000-03-01 00:00:00.0000000 +00:00 | 2007-04-16 00:00:00.0000000 +00:00 | 2009-02-20 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-01-20 00:00:00.0000000 +00:00 | 2000-03-01 00:00:00.0000000 +00:00 | 2007-04-09 00:00:00.0000000 +00:00 | 2010-02-04 00:00:00.0000000 +00:00 | 2012-01-22 00:00:00.0000000 +00:00 | 2015-08-18 00:00:00.0000000 +00:00 | 2000-03-01 00:00:00.0000000 +00:00 | 2007-04-09 00:00:00.0000000 +00:00 | 2010-02-11 00:00:00.0000000 +00:00 | 2011-09-06 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2010-02-11 00:00:00.0000000 +00:00 | 2016-07-27 00:00:00.0000000 +00:00 | 2000-03-01 00:00:00.0000000 +00:00 | 2000-03-01 00:00:00.0000000 +00:00 | 2007-04-09 00:00:00.0000000 +00:00 | 2007-04-09 00:00:00.0000000 +00:00 | 2007-11-15 00:00:00.0000000 +00:00 | 2007-11-15 00:00:00.0000000 +00:00 | 2007-11-15 00:00:00.0000000 +00:00 | 2007-11-15 00:00:00.0000000 +00:00 | 2007-11-15 00:00:00.0000000 +00:00 | [5 empty] | 2010-02-11 00:00:00.0000000 +00:00 | 2010-02-11 00:00:00.0000000 +00:00 | 2011-09-06 00:00:00.0000000 +00:00 | 2011-09-06 00:00:00.0000000 +00:00 | 2015-09-27 00:00:00.0000000 +00:00 | 2015-09-27 00:00:00.0000000 +00:00 | 2013-01-19 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 |  | 2018-09-26 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 |  | 2017-09-13 16:47:47.3780289 -04:00
HD161C | Y | 2005-04-15 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2012-01-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2014-01-07 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2013-01-12 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2011-08-30 00:00:00.0000000 +00:00 | 2011-08-30 00:00:00.0000000 +00:00 | 2011-08-30 00:00:00.0000000 +00:00 | 2011-08-30 00:00:00.0000000 +00:00 | 2011-08-30 00:00:00.0000000 +00:00 | [5 empty] | 2012-03-15 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2020-06-25 00:00:00.0000000 +00:00 | 2020-06-25 00:00:00.0000000 +00:00 |  | 2020-06-25 00:00:00.0000000 +00:00 | 2020-06-25 00:00:00.0000000 +00:00 |  | 2017-09-01 10:07:31.1401407 -04:00
HD-161C | Y | 2005-04-15 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2005-06-15 00:00:00.0000000 +00:00 | 2011-05-16 00:00:00.0000000 +00:00 | 2011-11-13 00:00:00.0000000 +00:00 | 2013-05-15 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2011-10-10 00:00:00.0000000 +00:00 | 2011-10-10 00:00:00.0000000 +00:00 | 2011-10-10 00:00:00.0000000 +00:00 | 2011-10-10 00:00:00.0000000 +00:00 | 2011-10-10 00:00:00.0000000 +00:00 | [5 empty] | 2012-03-15 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2020-06-25 00:00:00.0000000 +00:00 | 2020-06-25 00:00:00.0000000 +00:00 |  | 2020-06-25 00:00:00.0000000 +00:00 | 2020-06-25 00:00:00.0000000 +00:00 |  | 2017-08-30 14:31:04.9040240 -04:00
HD-161D | Y | 2005-04-15 00:00:00.0000000 +00:00 | 2006-06-15 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2016-01-06 00:00:00.0000000 +00:00 | 2018-04-12 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2006-06-15 00:00:00.0000000 +00:00 | 2008-03-15 00:00:00.0000000 +00:00 | 2008-08-15 00:00:00.0000000 +00:00 | 2010-02-15 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2011-10-16 00:00:00.0000000 +00:00 | 2016-06-16 00:00:00.0000000 +00:00 | 2017-02-04 00:00:00.0000000 +00:00 | 2018-08-07 00:00:00.0000000 +00:00 | 2005-04-15 12:00:00.0000000 +00:00 | 2006-06-15 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2016-01-06 00:00:00.0000000 +00:00 |  | 2009-12-26 00:00:00.0000000 +00:00 | 2018-04-12 00:00:00.0000000 +00:00 | 2005-04-15 00:00:00.0000000 +00:00 | 2005-04-15 12:00:00.0000000 +00:00 | 2006-06-15 00:00:00.0000000 +00:00 | 2006-06-15 00:00:00.0000000 +00:00 | 2007-06-15 00:00:00.0000000 +00:00 | 2012-11-16 00:00:00.0000000 +00:00 | 2012-11-16 00:00:00.0000000 +00:00 | 2012-11-16 00:00:00.0000000 +00:00 | 2012-11-16 00:00:00.0000000 +00:00 | [5 empty] | 2013-01-28 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2016-01-06 00:00:00.0000000 +00:00 | 2016-01-06 00:00:00.0000000 +00:00 | 2018-04-12 00:00:00.0000000 +00:00 | 2018-04-12 00:00:00.0000000 +00:00 | 2021-04-11 00:00:00.0000000 +00:00 | 2021-04-11 00:00:00.0000000 +00:00 |  | 2021-04-11 00:00:00.0000000 +00:00 | 2021-04-11 00:00:00.0000000 +00:00 |  | 2017-10-13 10:45:43.8800681 -04:00
HD161E | Y | 2013-09-17 00:00:00.0000000 +00:00 | 2013-11-17 00:00:00.0000000 +00:00 | 2015-02-11 00:00:00.0000000 +00:00 | 2016-09-22 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2013-11-17 00:00:00.0000000 +00:00 | 2015-01-10 00:00:00.0000000 +00:00 | 2015-07-11 00:00:00.0000000 +00:00 | 2016-07-10 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2013-11-17 00:00:00.0000000 +00:00 | 2015-01-10 00:00:00.0000000 +00:00 | 2015-07-11 00:00:00.0000000 +00:00 | 2016-07-10 00:00:00.0000000 +00:00 | 2013-09-17 12:00:00.0000000 +00:00 | 2013-11-17 17:00:00.0000000 +00:00 | 2015-02-11 00:00:00.0000000 +00:00 | 2016-09-22 18:00:00.0000000 +00:00 |  | 2015-02-11 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2013-11-17 00:00:00.0000000 +00:00 | 2013-11-17 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | [5 empty] | 2015-02-11 00:00:00.0000000 +00:00 | 2015-02-11 00:00:00.0000000 +00:00 | 2016-09-22 00:00:00.0000000 +00:00 | 2016-09-22 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2021-09-20 00:00:00.0000000 +00:00 | 2021-09-20 00:00:00.0000000 +00:00 |  | 2021-09-20 00:00:00.0000000 +00:00 | 2021-09-20 00:00:00.0000000 +00:00 |  | 2017-08-30 14:31:32.4190920 -04:00
HDWR17K | Y | 2016-01-19 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 | 2018-04-25 00:00:00.0000000 +00:00 | 2016-01-19 00:00:00.0000000 +00:00 | 2016-04-19 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-06-14 00:00:00.0000000 +00:00 | 2018-07-13 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-19 17:00:00.0000000 +00:00 | 2016-05-16 18:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 |  |  | 2017-01-11 00:00:00.0000000 +00:00 | 2018-04-25 00:00:00.0000000 +00:00 | 2016-01-19 17:00:00.0000000 +00:00 | 2016-01-19 00:00:00.0000000 +00:00 | 2016-05-16 18:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-27 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 | 2018-04-25 00:00:00.0000000 +00:00 | 2018-04-25 00:00:00.0000000 +00:00 | 2021-04-24 00:00:00.0000000 +00:00 | 2021-04-24 00:00:00.0000000 +00:00 |  | 2021-04-24 00:00:00.0000000 +00:00 | 2021-04-24 00:00:00.0000000 +00:00 |  | 2017-08-29 11:24:59.9695721 -04:00
HDWR17M | Y | 2016-02-16 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2018-04-28 00:00:00.0000000 +00:00 | 2019-10-24 00:00:00.0000000 +00:00 | 2016-02-16 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2017-03-15 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-02-16 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 |  |  | 2016-09-27 00:00:00.0000000 +00:00 |  | 2016-02-16 00:00:00.0000000 +00:00 |  | 2016-04-04 00:00:00.0000000 +00:00 |  | 2016-06-15 00:00:00.0000000 +00:00 | 2016-07-27 00:00:00.0000000 +00:00 | 2016-07-27 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | [6 empty] | 2016-07-15 00:00:00.0000000 +00:00 |  | 2017-03-15 00:00:00.0000000 +00:00 |  | 2018-03-15 00:00:00.0000000 +00:00 |  | 2020-03-15 00:00:00.0000000 +00:00 | 2022-10-24 00:00:00.0000000 +00:00 |  | 2020-03-15 00:00:00.0000000 +00:00
HDWR17Q | Y | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2019-05-28 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2017-08-28 00:00:00.0000000 +00:00 | 2019-02-22 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2017-10-20 00:00:00.0000000 +00:00 |  | 2016-09-27 00:00:00.0000000 +00:00 | 2019-05-28 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-27 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2017-10-20 00:00:00.0000000 +00:00 | 2019-05-28 00:00:00.0000000 +00:00 | 2019-04-17 00:00:00.0000000 +00:00 | 2022-02-20 00:00:00.0000000 +00:00 | 2022-05-27 00:00:00.0000000 +00:00 |  | 2022-05-27 00:00:00.0000000 +00:00 | 2022-04-16 00:00:00.0000000 +00:00 |  | 2017-11-03 08:50:36.0580528 -04:00
HDWR17R | Y | 2016-04-06 00:00:00.0000000 +00:00 | 2016-04-25 00:00:00.0000000 +00:00 | 2016-09-29 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2019-12-29 00:00:00.0000000 +00:00 | 2016-04-06 00:00:00.0000000 +00:00 | 2016-04-25 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2018-04-02 00:00:00.0000000 +00:00 | [5 empty] | 2016-04-06 00:00:00.0000000 +00:00 | 2016-04-25 00:00:00.0000000 +00:00 | 2016-09-29 00:00:00.0000000 +00:00 |  |  | 2016-09-29 00:00:00.0000000 +00:00 | 2019-12-29 00:00:00.0000000 +00:00 | 2016-04-06 00:00:00.0000000 +00:00 |  | 2016-04-25 00:00:00.0000000 +00:00 |  |  | 2016-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | [6 empty] | 2016-09-29 00:00:00.0000000 +00:00 |  | 2018-07-02 00:00:00.0000000 +00:00 |  | 2019-12-29 00:00:00.0000000 +00:00 |  | 2018-10-02 00:00:00.0000000 +00:00 | 2022-12-28 00:00:00.0000000 +00:00 |  | 2022-12-28 00:00:00.0000000 +00:00 |  |  | 2017-11-30 08:52:15.8491928 -05:00
HDWR17X | Y | 2016-01-05 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2018-03-09 00:00:00.0000000 +00:00 | 2019-09-05 00:00:00.0000000 +00:00 | 2016-01-05 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2016-12-05 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2019-09-03 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-05 00:00:00.0000000 +00:00 | 2016-06-13 18:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 |  |  | 2016-09-27 00:00:00.0000000 +00:00 |  | 2016-01-05 00:00:00.0000000 +00:00 |  | 2016-06-13 18:00:00.0000000 +00:00 |  | 2016-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | [6 empty] | 2016-09-27 00:00:00.0000000 +00:00 |  | 2018-03-09 00:00:00.0000000 +00:00 |  | 2019-09-05 00:00:00.0000000 +00:00 |  | 2022-09-04 00:00:00.0000000 +00:00 | 2022-09-04 00:00:00.0000000 +00:00 |  | 2022-09-04 00:00:00.0000000 +00:00 |  |  | 2017-11-03 10:08:30.8379988 -04:00
HED553 | Y | 1999-05-14 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 | 2019-02-01 00:00:00.0000000 +00:00 | 1999-05-14 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2011-02-13 00:00:00.0000000 +00:00 | 2011-09-13 00:00:00.0000000 +00:00 | 2012-09-13 00:00:00.0000000 +00:00 | 1999-05-14 00:00:00.0000000 +00:00 | 2013-04-08 00:00:00.0000000 +00:00 | 2016-03-21 00:00:00.0000000 +00:00 | 2017-04-02 00:00:00.0000000 +00:00 | 2018-04-03 00:00:00.0000000 +00:00 | 1999-05-14 12:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2015-09-21 17:00:00.0000000 +00:00 |  | 2014-10-02 00:00:00.0000000 +00:00 | 2019-02-01 00:00:00.0000000 +00:00 |  | 1999-05-14 12:00:00.0000000 +00:00 |  | 2009-09-14 00:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 |  | 2013-12-20 00:00:00.0000000 +00:00 | [6 empty] | 2014-10-02 00:00:00.0000000 +00:00 |  | 2015-09-21 17:00:00.0000000 +00:00 |  | 2019-02-01 00:00:00.0000000 +00:00 | 2015-09-13 00:00:00.0000000 +00:00 | 2022-01-31 00:00:00.0000000 +00:00 |  |  | 2022-01-31 00:00:00.0000000 +00:00
HED-556A | Y | 2004-07-23 00:00:00.0000000 +00:00 | 2022-06-15 00:00:00.0000000 +00:00 | 2025-12-15 00:00:00.0000000 +00:00 | 2026-09-13 00:00:00.0000000 +00:00 | 2027-09-12 00:00:00.0000000 +00:00 | 2004-06-25 00:00:00.0000000 +00:00 | 2005-03-15 00:00:00.0000000 +00:00 | 2006-02-15 00:00:00.0000000 +00:00 | 2006-07-15 00:00:00.0000000 +00:00 | 2007-07-14 00:00:00.0000000 +00:00 | 2004-06-25 00:00:00.0000000 +00:00 | 2008-09-01 00:00:00.0000000 +00:00 | 2016-02-02 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2004-06-25 00:00:00.0000000 +00:00 | [10 empty] | 2005-08-15 00:00:00.0000000 +00:00 | 2023-06-15 00:00:00.0000000 +00:00 | [14 empty] | 2010-07-12 00:00:00.0000000 +00:00 | 2030-09-10 00:00:00.0000000 +00:00
HED562 | Y | 2012-07-11 00:00:00.0000000 +00:00 | 2015-10-01 00:00:00.0000000 +00:00 | 2018-12-14 00:00:00.0000000 +00:00 | 2019-08-14 00:00:00.0000000 +00:00 | 2020-08-13 00:00:00.0000000 +00:00 | 2012-07-11 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2017-01-16 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2012-07-11 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2017-01-16 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2012-07-11 12:00:00.0000000 +00:00 | 2015-10-01 17:00:00.0000000 +00:00 |  |  |  | 2018-12-14 00:00:00.0000000 +00:00 |  | 2012-07-11 12:00:00.0000000 +00:00 |  | 2015-10-01 17:00:00.0000000 +00:00 |  | 2016-02-15 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | [6 empty] | 2018-12-14 00:00:00.0000000 +00:00 |  | 2019-08-14 00:00:00.0000000 +00:00 |  | 2020-08-13 00:00:00.0000000 +00:00 |  | 2022-09-12 00:00:00.0000000 +00:00 | 2023-08-10 00:00:00.0000000 +00:00 |  | 2023-08-10 00:00:00.0000000 +00:00 |  |  | 2017-08-30 13:32:35.9694156 -04:00
HED563 | Y | 2013-10-24 00:00:00.0000000 +00:00 | 2014-01-29 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2017-08-11 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2013-11-24 00:00:00.0000000 +00:00 | 2014-10-21 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2016-02-07 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2013-12-28 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2015-03-12 00:00:00.0000000 +00:00 | 2016-03-12 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2014-01-29 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2017-08-11 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2017-08-11 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2014-01-29 00:00:00.0000000 +00:00 | 2014-01-29 00:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | [5 empty] | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2017-08-11 00:00:00.0000000 +00:00 | 2017-08-11 00:00:00.0000000 +00:00 | 2019-02-06 00:00:00.0000000 +00:00 | 2020-08-10 00:00:00.0000000 +00:00 |  | 2020-08-10 00:00:00.0000000 +00:00 | 2020-08-10 00:00:00.0000000 +00:00 |  | 2017-10-18 12:32:48.0522822 -04:00
HED564 | Y | 2010-10-25 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2016-12-27 00:00:00.0000000 +00:00 | 2018-05-28 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2010-10-25 00:00:00.0000000 +00:00 | 2011-03-25 00:00:00.0000000 +00:00 | 2012-01-10 00:00:00.0000000 +00:00 | 2012-10-08 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2010-10-25 00:00:00.0000000 +00:00 | 2011-03-25 00:00:00.0000000 +00:00 | 2014-01-08 00:00:00.0000000 +00:00 | 2014-10-07 00:00:00.0000000 +00:00 | 2015-10-08 00:00:00.0000000 +00:00 | 2010-10-25 12:00:00.0000000 +00:00 | 2011-12-28 12:00:00.0000000 +00:00 | 2016-12-27 00:00:00.0000000 +00:00 |  |  | 2016-12-27 00:00:00.0000000 +00:00 |  | 2010-10-25 12:00:00.0000000 +00:00 |  | 2011-12-28 12:00:00.0000000 +00:00 |  | 2011-09-15 00:00:00.0000000 +00:00 | 2013-07-25 00:00:00.0000000 +00:00 | 2013-07-25 00:00:00.0000000 +00:00 | 2013-07-25 00:00:00.0000000 +00:00 | [6 empty] | 2016-12-27 00:00:00.0000000 +00:00 |  | 2018-05-28 00:00:00.0000000 +00:00 |  | 2019-06-02 00:00:00.0000000 +00:00 |  | 2016-10-08 00:00:00.0000000 +00:00 | 2022-11-28 00:00:00.0000000 +00:00 |  | 2022-11-28 00:00:00.0000000 +00:00 |  |  | 2017-10-05 08:56:40.2576289 -04:00
HED568 | Y | 2011-11-07 00:00:00.0000000 +00:00 | 2012-04-19 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2015-10-01 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2011-11-07 00:00:00.0000000 +00:00 | 2012-05-06 00:00:00.0000000 +00:00 | 2013-02-01 00:00:00.0000000 +00:00 | 2013-08-17 00:00:00.0000000 +00:00 | 2014-05-13 00:00:00.0000000 +00:00 | 2011-11-07 00:00:00.0000000 +00:00 | 2012-05-06 00:00:00.0000000 +00:00 | 2014-08-01 00:00:00.0000000 +00:00 | 2015-02-14 00:00:00.0000000 +00:00 | 2015-11-10 00:00:00.0000000 +00:00 | 2011-11-07 00:00:00.0000000 +00:00 | 2012-04-19 12:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2015-10-01 00:00:00.0000000 +00:00 |  | 2014-06-19 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2011-11-07 00:00:00.0000000 +00:00 | 2011-11-07 00:00:00.0000000 +00:00 | 2012-04-19 12:00:00.0000000 +00:00 | 2012-04-19 12:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | 2013-09-12 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-19 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2015-10-01 00:00:00.0000000 +00:00 | 2015-10-01 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2017-05-12 00:00:00.0000000 +00:00 | 2021-09-13 00:00:00.0000000 +00:00 |  | 2021-09-13 00:00:00.0000000 +00:00 | 2021-09-13 00:00:00.0000000 +00:00
HED569 | Y | 2012-09-14 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2012-09-14 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2012-09-14 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2012-09-14 12:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 |  | 2015-04-07 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2012-09-14 12:00:00.0000000 +00:00 | 2012-09-14 12:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-07 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2020-09-12 00:00:00.0000000 +00:00 | 2022-06-29 00:00:00.0000000 +00:00 |  | 2022-06-29 00:00:00.0000000 +00:00 | 2022-06-29 00:00:00.0000000 +00:00 |  | 2017-09-05 14:38:12.7940415 -04:00
HED570 | Y | 2015-01-05 00:00:00.0000000 +00:00 | 2018-12-03 00:00:00.0000000 +00:00 | 2020-12-30 00:00:00.0000000 +00:00 | 2021-08-30 00:00:00.0000000 +00:00 | 2023-02-21 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2020-01-11 00:00:00.0000000 +00:00 | 2020-07-10 00:00:00.0000000 +00:00 | 2022-01-01 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-05 00:00:00.0000000 +00:00 | [10 empty] | 2019-08-15 00:00:00.0000000 +00:00 | 2020-02-03 00:00:00.0000000 +00:00 | [14 empty] | 2025-12-31 00:00:00.0000000 +00:00 | 2026-02-20 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-18 14:27:15.9284981 -04:00
HED573 | Y | 2014-05-16 00:00:00.0000000 +00:00 | 2015-09-08 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 | 2018-03-26 00:00:00.0000000 +00:00 | 2019-09-22 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2018-01-03 00:00:00.0000000 +00:00 | 2018-04-06 00:00:00.0000000 +00:00 | 2019-08-07 00:00:00.0000000 +00:00 | [5 empty] | 2014-05-16 00:00:00.0000000 +00:00 | 2015-09-08 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 |  |  | 2017-03-22 00:00:00.0000000 +00:00 |  | 2014-05-16 00:00:00.0000000 +00:00 |  | 2015-09-08 00:00:00.0000000 +00:00 |  | 2016-07-12 00:00:00.0000000 +00:00 | 2016-07-12 00:00:00.0000000 +00:00 | 2016-07-12 00:00:00.0000000 +00:00 | 2016-07-12 00:00:00.0000000 +00:00 | [6 empty] | 2017-03-22 00:00:00.0000000 +00:00 |  | 2018-03-26 00:00:00.0000000 +00:00 |  | 2019-09-22 00:00:00.0000000 +00:00 |  | 2022-08-06 00:00:00.0000000 +00:00 | 2022-09-21 00:00:00.0000000 +00:00 |  | 2022-09-21 00:00:00.0000000 +00:00 |  |  | 2017-10-12 13:40:38.3904691 -04:00
HED574 | Y | 2014-11-07 00:00:00.0000000 +00:00 | 2016-02-08 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2018-04-12 00:00:00.0000000 +00:00 | 2014-11-07 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2018-04-12 00:00:00.0000000 +00:00 | [5 empty] | 2014-11-07 17:00:00.0000000 +00:00 | 2016-02-08 17:00:00.0000000 +00:00 |  |  |  | 2016-08-21 00:00:00.0000000 +00:00 | 2018-04-12 00:00:00.0000000 +00:00 | [20 empty] | 2018-10-09 00:00:00.0000000 +00:00 | 2018-10-09 00:00:00.0000000 +00:00
HEDA001 | Y | 2014-07-22 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | [5 empty] | 2014-07-22 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-15 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2019-09-12 00:00:00.0000000 +00:00 | 2020-01-12 00:00:00.0000000 +00:00 |  | 2019-09-12 00:00:00.0000000 +00:00 | 2019-09-12 00:00:00.0000000 +00:00 |  | 2017-09-13 14:49:47.4519624 -04:00
HEDA002 | Y | 2015-02-13 00:00:00.0000000 +00:00 | 2015-09-11 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2016-10-17 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | [5 empty] | 2015-02-13 00:00:00.0000000 +00:00 | 2015-09-11 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 |  | 2015-12-24 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-09-11 00:00:00.0000000 +00:00 | 2015-09-11 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-24 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2020-10-14 00:00:00.0000000 +00:00 | 2021-06-28 00:00:00.0000000 +00:00 |  | 2021-06-28 00:00:00.0000000 +00:00 | 2021-06-28 00:00:00.0000000 +00:00 |  | 2017-11-13 11:43:25.4625335 -05:00
HEDA003 | Y | 2016-02-16 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | 2020-03-14 00:00:00.0000000 +00:00 | 2016-02-16 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | [5 empty] | 2016-02-16 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 |  |  | 2016-10-21 00:00:00.0000000 +00:00 |  | 2016-02-16 00:00:00.0000000 +00:00 |  | 2016-05-02 00:00:00.0000000 +00:00 |  | 2016-08-21 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 | [6 empty] | 2016-10-21 00:00:00.0000000 +00:00 |  | 2018-09-17 00:00:00.0000000 +00:00 |  | 2020-03-14 00:00:00.0000000 +00:00 |  | 2021-09-12 00:00:00.0000000 +00:00 | 2023-03-13 00:00:00.0000000 +00:00 |  | 2023-03-13 00:00:00.0000000 +00:00 |  |  | 2017-09-13 12:44:58.2460725 -04:00
HED-CLUB | Y | 2011-03-25 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2020-12-05 00:00:00.0000000 +00:00 | 2011-03-25 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 | 2017-08-17 00:00:00.0000000 +00:00 | 2011-03-25 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2016-09-25 00:00:00.0000000 +00:00 | 2019-04-30 00:00:00.0000000 +00:00 | 2021-10-29 00:00:00.0000000 +00:00 | 2011-03-25 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2017-10-26 00:00:00.0000000 +00:00 |  |  | 2017-11-15 00:00:00.0000000 +00:00 |  | 2011-03-25 00:00:00.0000000 +00:00 |  | 2012-05-23 00:00:00.0000000 +00:00 |  | 2012-11-01 00:00:00.0000000 +00:00 | 2012-11-01 00:00:00.0000000 +00:00 | 2012-11-01 00:00:00.0000000 +00:00 | 2012-11-01 00:00:00.0000000 +00:00 |  | 2013-04-01 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 |  | 2017-11-15 00:00:00.0000000 +00:00 |  | 2018-06-19 00:00:00.0000000 +00:00 |  | 2020-12-05 00:00:00.0000000 +00:00 |  | 2018-08-17 00:00:00.0000000 +00:00 | 2021-12-05 00:00:00.0000000 +00:00 |  | 2021-12-05 00:00:00.0000000 +00:00
HH112AAFS | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2019-05-19 00:00:00.0000000 +00:00 | 2020-05-21 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2019-05-19 00:00:00.0000000 +00:00 | 2020-05-21 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 |  |  |  | 2018-09-19 00:00:00.0000000 +00:00 | 2020-05-21 00:00:00.0000000 +00:00 |  |  |  |  | 2017-12-29 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  | 2018-03-30 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | [9 empty] | 2020-11-13 00:00:00.0000000 +00:00 | 2020-11-13 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-25 17:36:34.5672084 -04:00
HH112BATV | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-08-26 00:00:00.0000000 +00:00 | 2018-10-26 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2019-12-13 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2017-01-25 00:00:00.0000000 +00:00 | 2017-05-22 00:00:00.0000000 +00:00 | 2017-11-16 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-08-16 18:00:00.0000000 +00:00 |  |  |  | 2018-02-15 00:00:00.0000000 +00:00 |  | 2015-10-23 18:00:00.0000000 +00:00 |  | 2016-08-16 18:00:00.0000000 +00:00 |  | 2016-09-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 |  | 2016-11-16 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 |  | 2018-07-20 00:00:00.0000000 +00:00 |  | 2018-10-26 00:00:00.0000000 +00:00 |  | 2019-07-19 00:00:00.0000000 +00:00 |  | 2019-12-13 00:00:00.0000000 +00:00 |  | 2018-05-11 00:00:00.0000000 +00:00 | 2020-02-21 00:00:00.0000000 +00:00 |  | 2020-02-21 00:00:00.0000000 +00:00
HH112BDFA | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2018-09-13 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2020-05-15 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-04-07 00:00:00.0000000 +00:00 | 2017-11-24 00:00:00.0000000 +00:00 | 2018-05-18 00:00:00.0000000 +00:00 | 2018-12-28 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 |  |  |  | 2018-09-13 00:00:00.0000000 +00:00 | [5 empty] | 2017-06-23 00:00:00.0000000 +00:00 | 2017-12-26 00:00:00.0000000 +00:00 |  |  |  | 2017-09-01 00:00:00.0000000 +00:00 | 2018-03-26 00:00:00.0000000 +00:00 | [9 empty] | 2019-06-28 00:00:00.0000000 +00:00 | 2020-11-13 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-19 12:07:29.0848962 -04:00
HH112BEES | Y | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-12-08 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-06-18 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-10-13 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-06-18 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-22 17:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 |  |  |  | 2018-07-05 00:00:00.0000000 +00:00 |  | 2016-01-22 17:00:00.0000000 +00:00 |  | 2016-07-22 00:00:00.0000000 +00:00 |  | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-11-08 00:00:00.0000000 +00:00 | 2016-11-08 00:00:00.0000000 +00:00 |  | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 |  | 2017-12-08 00:00:00.0000000 +00:00 |  | 2018-06-29 00:00:00.0000000 +00:00 |  | 2020-06-18 00:00:00.0000000 +00:00 |  | 2020-12-18 00:00:00.0000000 +00:00 | 2020-12-18 00:00:00.0000000 +00:00 |  | 2020-12-18 00:00:00.0000000 +00:00 |  |  | 2017-10-25 17:44:04.7287353 -04:00
HH112BEES-G | Y | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-06-18 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-10-13 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-06-18 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 |  |  |  | 2018-01-15 00:00:00.0000000 +00:00 |  | 2016-01-22 00:00:00.0000000 +00:00 |  | 2016-07-22 00:00:00.0000000 +00:00 |  | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-11-08 00:00:00.0000000 +00:00 | 2016-11-08 00:00:00.0000000 +00:00 |  | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 |  | 2017-12-08 00:00:00.0000000 +00:00 |  | 2018-06-29 00:00:00.0000000 +00:00 |  | 2020-06-18 00:00:00.0000000 +00:00 |  | 2020-12-18 00:00:00.0000000 +00:00 | 2020-12-18 00:00:00.0000000 +00:00 |  | 2021-06-18 00:00:00.0000000 +00:00 |  |  | 2017-10-25 17:44:27.1836546 -04:00
HH112BEGE | Y | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-12-08 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-06-18 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-10-13 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-06-18 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-22 17:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 |  |  |  | 2018-01-15 00:00:00.0000000 +00:00 |  | 2016-01-22 17:00:00.0000000 +00:00 |  | 2016-07-22 00:00:00.0000000 +00:00 |  | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-11-08 00:00:00.0000000 +00:00 | 2016-11-08 00:00:00.0000000 +00:00 |  | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 |  | 2017-12-08 00:00:00.0000000 +00:00 |  | 2018-06-29 00:00:00.0000000 +00:00 |  | 2020-06-18 00:00:00.0000000 +00:00 |  | 2020-12-18 00:00:00.0000000 +00:00 | 2020-12-18 00:00:00.0000000 +00:00 |  | 2020-12-18 00:00:00.0000000 +00:00 |  |  | 2017-09-07 11:28:40.4102372 -04:00
HH112BLBR | Y | 2016-09-23 00:00:00.0000000 +00:00 | 2018-01-03 00:00:00.0000000 +00:00 | 2019-01-04 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2023-07-28 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-11-09 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2023-07-28 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-23 17:00:00.0000000 +00:00 |  |  |  |  | 2018-11-10 00:00:00.0000000 +00:00 | [5 empty] | 2018-02-16 00:00:00.0000000 +00:00 | 2018-04-18 00:00:00.0000000 +00:00 |  |  |  | 2018-05-18 00:00:00.0000000 +00:00 | 2018-07-27 00:00:00.0000000 +00:00 | [9 empty] | 2024-01-26 00:00:00.0000000 +00:00 | 2024-01-26 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 08:27:27.8445833 -04:00
HH112BLCY | Y | 2016-09-23 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-03-15 00:00:00.0000000 +00:00 | 2019-12-13 00:00:00.0000000 +00:00 | 2021-12-20 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-06-26 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-23 17:00:00.0000000 +00:00 | [10 empty] | 2016-12-16 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 |  |  |  | 2017-03-17 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | [9 empty] | 2020-12-18 00:00:00.0000000 +00:00 | 2022-06-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 08:27:46.8139666 -04:00
HH112BLEL | Y | 2012-06-15 00:00:00.0000000 +00:00 | 2012-09-27 00:00:00.0000000 +00:00 | 2015-01-23 00:00:00.0000000 +00:00 | 2016-02-16 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2014-05-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2015-03-13 00:00:00.0000000 +00:00 | 2016-01-13 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2012-09-27 00:00:00.0000000 +00:00 | 2015-01-23 00:00:00.0000000 +00:00 | 2016-02-16 00:00:00.0000000 +00:00 |  | 2015-01-23 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2012-09-27 00:00:00.0000000 +00:00 | 2012-09-27 00:00:00.0000000 +00:00 | 2013-01-18 00:00:00.0000000 +00:00 | 2013-04-20 00:00:00.0000000 +00:00 | 2013-04-20 00:00:00.0000000 +00:00 | 2013-04-20 00:00:00.0000000 +00:00 | 2013-04-20 00:00:00.0000000 +00:00 | 2013-04-19 00:00:00.0000000 +00:00 | 2013-10-25 00:00:00.0000000 +00:00 | 2013-10-25 00:00:00.0000000 +00:00 | 2013-10-25 00:00:00.0000000 +00:00 | 2013-10-25 00:00:00.0000000 +00:00 | 2015-01-23 00:00:00.0000000 +00:00 | 2015-01-23 00:00:00.0000000 +00:00 | 2016-02-16 00:00:00.0000000 +00:00 | 2016-02-16 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2016-06-24 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 |  | 2018-09-21 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 |  | 2017-10-31 13:29:40.5102085 -04:00
HH112BLEN | Y | 2016-09-23 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-03-15 00:00:00.0000000 +00:00 | 2019-12-20 00:00:00.0000000 +00:00 | 2021-12-17 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-07-17 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-23 17:00:00.0000000 +00:00 | [10 empty] | 2016-12-16 00:00:00.0000000 +00:00 | 2018-06-21 00:00:00.0000000 +00:00 |  |  |  | 2017-03-17 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | [9 empty] | 2021-01-15 00:00:00.0000000 +00:00 | 2022-06-17 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 08:28:03.9211153 -04:00
HH112BLFS | Y | 2016-08-31 00:00:00.0000000 +00:00 | 2018-01-05 00:00:00.0000000 +00:00 | 2018-12-21 00:00:00.0000000 +00:00 | 2019-10-01 00:00:00.0000000 +00:00 | 2021-11-28 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2017-10-29 00:00:00.0000000 +00:00 | 2018-12-21 00:00:00.0000000 +00:00 | 2019-10-01 00:00:00.0000000 +00:00 | 2021-11-28 00:00:00.0000000 +00:00 | [5 empty] | 2016-08-31 17:00:00.0000000 +00:00 | [10 empty] | 2018-01-26 00:00:00.0000000 +00:00 | 2018-04-18 00:00:00.0000000 +00:00 |  |  |  | 2018-04-27 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | [9 empty] | 2022-05-27 00:00:00.0000000 +00:00 | 2022-05-27 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 08:28:29.2618060 -04:00
HH112BLRR | Y | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-04-21 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2020-12-18 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-11-24 00:00:00.0000000 +00:00 | 2018-09-05 00:00:00.0000000 +00:00 | 2021-08-31 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-22 17:00:00.0000000 +00:00 | 2016-07-05 18:00:00.0000000 +00:00 | 2017-04-21 00:00:00.0000000 +00:00 |  |  | 2017-12-14 00:00:00.0000000 +00:00 |  | 2016-01-22 00:00:00.0000000 +00:00 |  | 2016-07-05 00:00:00.0000000 +00:00 |  | 2017-01-27 00:00:00.0000000 +00:00 | 2016-11-25 00:00:00.0000000 +00:00 | 2016-11-25 00:00:00.0000000 +00:00 | 2016-11-25 00:00:00.0000000 +00:00 |  | 2017-04-28 00:00:00.0000000 +00:00 | 2017-02-24 00:00:00.0000000 +00:00 | 2017-02-24 00:00:00.0000000 +00:00 | 2017-02-24 00:00:00.0000000 +00:00 |  | 2017-04-21 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2020-12-18 00:00:00.0000000 +00:00 |  | 2022-02-25 00:00:00.0000000 +00:00 | 2021-06-18 00:00:00.0000000 +00:00 |  | 2021-12-18 00:00:00.0000000 +00:00
HH112BLRRFW | Y | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | 2023-08-25 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | 2023-08-25 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-22 17:00:00.0000000 +00:00 | 2016-07-05 17:00:00.0000000 +00:00 | 2017-10-19 00:00:00.0000000 +00:00 |  |  | 2017-10-19 00:00:00.0000000 +00:00 |  | 2016-01-02 00:00:00.0000000 +00:00 |  | 2016-07-05 00:00:00.0000000 +00:00 |  | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 |  | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 |  | 2017-10-31 00:00:00.0000000 +00:00 |  | 2018-08-17 00:00:00.0000000 +00:00 |  | 2023-08-25 00:00:00.0000000 +00:00 |  | 2024-02-23 00:00:00.0000000 +00:00 | 2024-02-23 00:00:00.0000000 +00:00 |  | 2024-02-23 00:00:00.0000000 +00:00 |  |  | 2017-10-26 08:31:42.0944698 -04:00
HH112BLRR-FW | Y | 2016-01-22 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2018-07-04 00:00:00.0000000 +00:00 | 2023-07-04 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-22 17:00:00.0000000 +00:00 | 2016-07-05 17:00:00.0000000 +00:00 |  |  |  | 2017-03-24 00:00:00.0000000 +00:00
HH112BLTV | Y | 2016-01-15 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2016-05-20 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2016-05-20 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-15 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2016-05-20 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-05-20 00:00:00.0000000 +00:00 |  | 2016-01-15 00:00:00.0000000 +00:00 |  | 2016-02-19 00:00:00.0000000 +00:00 |  | 2016-03-18 00:00:00.0000000 +00:00 | 2016-03-18 00:00:00.0000000 +00:00 | 2016-03-18 00:00:00.0000000 +00:00 | 2016-03-18 00:00:00.0000000 +00:00 |  | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 |  | 2016-05-20 00:00:00.0000000 +00:00 |  | 2016-06-17 00:00:00.0000000 +00:00 |  | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 | 2016-10-21 00:00:00.0000000 +00:00 |  | 2017-10-25 17:45:10.7365393 -04:00
HH112BLVT | Y | 2016-09-23 00:00:00.0000000 +00:00 | 2018-01-05 00:00:00.0000000 +00:00 | 2018-12-21 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2023-07-28 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-11-02 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2023-07-28 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-23 17:00:00.0000000 +00:00 |  |  |  |  | 2018-12-21 00:00:00.0000000 +00:00 | [5 empty] | 2018-02-16 00:00:00.0000000 +00:00 | 2018-04-18 00:00:00.0000000 +00:00 |  |  |  | 2018-05-18 00:00:00.0000000 +00:00 | 2018-07-25 00:00:00.0000000 +00:00 | [9 empty] | 2024-01-26 00:00:00.0000000 +00:00 | 2024-01-26 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 08:28:47.0565608 -04:00
HH112BVDV | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2018-04-24 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2018-04-24 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2017-05-01 17:00:00.0000000 +00:00 |  | 2016-10-25 00:00:00.0000000 +00:00 | 2018-04-24 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2018-04-24 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2018-08-24 00:00:00.0000000 +00:00 | 2018-08-24 00:00:00.0000000 +00:00 |  | 2018-08-24 00:00:00.0000000 +00:00 | 2018-12-31 00:00:00.0000000 +00:00 |  | 2017-10-25 17:43:25.1477829 -04:00
HH112BVFA | Y | 2016-07-01 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2019-03-22 00:00:00.0000000 +00:00 | 2020-03-20 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2019-03-22 00:00:00.0000000 +00:00 | 2020-03-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-01 17:00:00.0000000 +00:00 | 2017-11-09 00:00:00.0000000 +00:00 |  |  |  | 2018-08-15 00:00:00.0000000 +00:00 | [5 empty] | 2018-02-15 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 |  |  |  | 2018-05-15 00:00:00.0000000 +00:00 | 2018-05-15 00:00:00.0000000 +00:00 | [9 empty] | 2020-09-18 00:00:00.0000000 +00:00 | 2020-09-18 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-09 13:44:21.9825936 -05:00
HH112CGIU | Y | 2016-09-28 00:00:00.0000000 +00:00 | 2018-01-05 00:00:00.0000000 +00:00 | 2018-11-16 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2020-07-17 00:00:00.0000000 +00:00 | 2016-09-28 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-11-16 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2020-07-17 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-28 17:00:00.0000000 +00:00 | [10 empty] | 2018-02-16 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 |  |  |  | 2018-06-22 00:00:00.0000000 +00:00 | 2018-07-13 00:00:00.0000000 +00:00 | [9 empty] | 2021-01-22 00:00:00.0000000 +00:00 | 2021-01-22 00:00:00.0000000 +00:00
HH112CTFS | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2018-01-05 00:00:00.0000000 +00:00 | 2019-11-15 00:00:00.0000000 +00:00 | 2020-08-14 00:00:00.0000000 +00:00 | 2021-08-20 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2019-11-15 00:00:00.0000000 +00:00 | 2020-08-14 00:00:00.0000000 +00:00 | 2021-08-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | [10 empty] | 2018-02-23 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 |  |  |  | 2018-06-22 00:00:00.0000000 +00:00 | 2018-07-13 00:00:00.0000000 +00:00 | [9 empty] | 2022-02-18 00:00:00.0000000 +00:00 | 2022-02-18 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 08:29:10.1472913 -04:00
HH112CWFR | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2017-06-09 00:00:00.0000000 +00:00 | 2018-02-26 00:00:00.0000000 +00:00 | 2019-02-26 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2017-06-09 00:00:00.0000000 +00:00 | 2017-11-10 00:00:00.0000000 +00:00 | 2018-08-10 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2016-10-19 12:00:00.0000000 +00:00 | 2017-06-09 00:00:00.0000000 +00:00 |  |  | 2017-05-31 00:00:00.0000000 +00:00 |  | 2016-07-26 00:00:00.0000000 +00:00 |  | 2016-10-19 00:00:00.0000000 +00:00 |  | 2017-01-26 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 |  | 2017-05-05 00:00:00.0000000 +00:00 | 2017-05-05 00:00:00.0000000 +00:00 | 2017-05-05 00:00:00.0000000 +00:00 | 2017-05-05 00:00:00.0000000 +00:00 |  | 2017-06-09 00:00:00.0000000 +00:00 |  | 2018-02-26 00:00:00.0000000 +00:00 |  | 2019-02-26 00:00:00.0000000 +00:00 |  | 2019-02-27 00:00:00.0000000 +00:00 | 2019-05-26 00:00:00.0000000 +00:00 |  | 2019-05-26 00:00:00.0000000 +00:00 |  |  | 2017-09-11 16:50:01.4294226 -04:00
HH112FBFS | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2019-05-15 00:00:00.0000000 +00:00 | 2020-05-15 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2020-05-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-11-09 00:00:00.0000000 +00:00 | [9 empty] | 2018-02-15 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 |  |  |  | 2018-05-15 00:00:00.0000000 +00:00 | 2018-05-15 00:00:00.0000000 +00:00 | [9 empty] | 2020-11-26 00:00:00.0000000 +00:00 | 2020-11-26 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-09 13:44:00.9220349 -05:00
HH112FWFA | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2018-01-19 00:00:00.0000000 +00:00 | 2018-10-19 00:00:00.0000000 +00:00 | 2020-10-16 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-07-14 00:00:00.0000000 +00:00 | 2020-07-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-01-13 17:00:00.0000000 +00:00 |  |  |  | 2018-03-15 00:00:00.0000000 +00:00 |  | 2015-10-23 00:00:00.0000000 +00:00 |  | 2016-01-13 00:00:00.0000000 +00:00 |  | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 |  | 2017-08-10 00:00:00.0000000 +00:00 | 2017-08-10 00:00:00.0000000 +00:00 | 2017-08-10 00:00:00.0000000 +00:00 | 2017-08-10 00:00:00.0000000 +00:00 |  | 2018-01-19 00:00:00.0000000 +00:00 |  | 2018-10-19 00:00:00.0000000 +00:00 |  | 2020-10-16 00:00:00.0000000 +00:00 |  | 2020-10-30 00:00:00.0000000 +00:00 | 2021-04-16 00:00:00.0000000 +00:00 |  | 2021-04-16 00:00:00.0000000 +00:00
HH112GDFA | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | 2018-04-09 00:00:00.0000000 +00:00 | 2018-12-17 00:00:00.0000000 +00:00 | 2019-12-16 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | 2018-03-09 00:00:00.0000000 +00:00 | 2018-11-16 00:00:00.0000000 +00:00 | 2019-11-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-05-24 17:00:00.0000000 +00:00 |  |  |  | 2018-03-09 00:00:00.0000000 +00:00 |  | 2016-07-26 17:00:00.0000000 +00:00 |  | 2017-05-24 17:00:00.0000000 +00:00 |  | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 |  | 2017-11-17 00:00:00.0000000 +00:00 | 2017-12-18 00:00:00.0000000 +00:00 |  | 2017-12-18 00:00:00.0000000 +00:00 |  | 2018-04-09 00:00:00.0000000 +00:00 |  | 2018-12-17 00:00:00.0000000 +00:00 |  | 2019-12-16 00:00:00.0000000 +00:00 |  | 2020-05-15 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 |  | 2020-06-15 00:00:00.0000000 +00:00 |  |  | 2017-11-08 17:17:13.3081768 -05:00
HH112HMFA | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | 2018-04-09 00:00:00.0000000 +00:00 | 2018-12-17 00:00:00.0000000 +00:00 | 2019-12-16 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 | 2018-11-16 00:00:00.0000000 +00:00 | 2019-11-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-05-24 17:00:00.0000000 +00:00 |  |  |  | 2018-03-16 00:00:00.0000000 +00:00 |  | 2016-07-26 17:00:00.0000000 +00:00 |  | 2017-05-24 17:00:00.0000000 +00:00 |  | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 |  | 2017-11-17 00:00:00.0000000 +00:00 | 2017-12-18 00:00:00.0000000 +00:00 |  | 2017-12-18 00:00:00.0000000 +00:00 |  | 2018-04-09 00:00:00.0000000 +00:00 |  | 2018-12-17 00:00:00.0000000 +00:00 |  | 2019-12-16 00:00:00.0000000 +00:00 |  | 2020-05-15 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 |  | 2020-06-15 00:00:00.0000000 +00:00 |  |  | 2017-10-19 12:18:35.2644068 -04:00
HH112HSFA | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2018-02-12 00:00:00.0000000 +00:00 | 2018-11-09 00:00:00.0000000 +00:00 | 2019-08-09 00:00:00.0000000 +00:00 | 2020-08-28 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2018-02-12 00:00:00.0000000 +00:00 | 2018-11-09 00:00:00.0000000 +00:00 | 2019-08-09 00:00:00.0000000 +00:00 | 2020-08-28 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | [6 empty] | 2016-07-26 00:00:00.0000000 +00:00 |  | 2018-02-12 00:00:00.0000000 +00:00 |  | 2018-05-14 00:00:00.0000000 +00:00 | 2018-05-14 00:00:00.0000000 +00:00 |  |  |  | 2018-08-14 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | [9 empty] | 2020-11-30 00:00:00.0000000 +00:00 | 2020-11-30 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 08:29:34.6395379 -04:00
HH112HWFS | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2018-09-29 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2020-04-17 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2018-09-29 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2020-04-17 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 |  |  |  | 2018-09-29 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-29 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  | 2018-04-27 00:00:00.0000000 +00:00 | 2018-04-27 00:00:00.0000000 +00:00 | [9 empty] | 2020-10-16 00:00:00.0000000 +00:00 | 2020-10-16 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-19 12:19:31.7166320 -04:00
HH112KEFA | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-11-23 00:00:00.0000000 +00:00 | 2019-07-26 00:00:00.0000000 +00:00 | 2020-07-17 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | 2019-04-19 00:00:00.0000000 +00:00 | 2020-04-17 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | [10 empty] | 2017-12-31 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 |  |  |  | 2018-03-31 00:00:00.0000000 +00:00 | 2018-07-13 00:00:00.0000000 +00:00 | [9 empty] | 2020-10-16 00:00:00.0000000 +00:00 | 2021-01-22 00:00:00.0000000 +00:00
HH112LXFA | Y | 2016-08-02 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2018-08-18 00:00:00.0000000 +00:00 | 2019-02-02 00:00:00.0000000 +00:00 | 2019-09-17 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2018-08-18 00:00:00.0000000 +00:00 | 2019-02-20 00:00:00.0000000 +00:00 | 2019-09-17 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-01 17:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 |  |  |  | 2018-08-18 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-29 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  | 2018-04-27 00:00:00.0000000 +00:00 | 2018-04-27 00:00:00.0000000 +00:00 | [9 empty] | 2020-03-27 00:00:00.0000000 +00:00 | 2020-03-27 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-16 08:57:42.7759367 -04:00
HH112NPFS | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | 2018-04-09 00:00:00.0000000 +00:00 | 2018-12-17 00:00:00.0000000 +00:00 | 2019-12-16 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2019-09-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 |  |  |  | 2018-03-15 00:00:00.0000000 +00:00 |  | 2016-07-26 17:00:00.0000000 +00:00 |  | 2017-05-24 00:00:00.0000000 +00:00 |  | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 |  | 2017-11-17 00:00:00.0000000 +00:00 | 2017-12-18 00:00:00.0000000 +00:00 |  | 2017-12-18 00:00:00.0000000 +00:00 |  | 2018-04-09 00:00:00.0000000 +00:00 |  | 2018-12-17 00:00:00.0000000 +00:00 |  | 2019-12-16 00:00:00.0000000 +00:00 |  | 2020-03-20 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 |  | 2020-06-15 00:00:00.0000000 +00:00 |  |  | 2017-10-19 12:20:24.9743487 -04:00
HH112PJBO | Y | 2016-02-22 17:00:00.0000000 +00:00 | 2017-09-22 00:00:00.0000000 +00:00 | 2018-09-28 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2021-07-16 00:00:00.0000000 +00:00 | 2016-02-22 00:00:00.0000000 +00:00 | 2017-09-22 00:00:00.0000000 +00:00 | 2018-09-28 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2021-07-16 00:00:00.0000000 +00:00 | [5 empty] | 2016-02-22 17:00:00.0000000 +00:00 | 2017-09-21 00:00:00.0000000 +00:00 |  |  |  | 2018-09-28 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-15 00:00:00.0000000 +00:00 | 2018-01-17 00:00:00.0000000 +00:00 |  |  |  | 2018-04-13 00:00:00.0000000 +00:00 | 2018-04-13 00:00:00.0000000 +00:00 | [9 empty] | 2022-01-21 00:00:00.0000000 +00:00 | 2022-01-21 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-25 17:37:16.1331186 -04:00
HH112PJRC | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2019-05-15 00:00:00.0000000 +00:00 | 2020-05-15 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2019-05-15 00:00:00.0000000 +00:00 | 2020-05-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-11-09 00:00:00.0000000 +00:00 |  |  |  | 2018-08-15 00:00:00.0000000 +00:00 | [5 empty] | 2018-02-15 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 |  |  |  | 2018-05-15 00:00:00.0000000 +00:00 | 2018-05-15 00:00:00.0000000 +00:00 | [9 empty] | 2020-11-25 00:00:00.0000000 +00:00 | 2020-11-25 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-09 13:43:32.3994076 -05:00
HH112POTV | Y | 2016-01-22 17:00:00.0000000 +00:00 | 2018-04-26 00:00:00.0000000 +00:00 | 2019-03-22 00:00:00.0000000 +00:00 | 2019-09-20 00:00:00.0000000 +00:00 | 2020-09-18 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-04-26 00:00:00.0000000 +00:00 | 2018-10-26 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2019-12-13 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-22 17:00:00.0000000 +00:00 | [6 empty] | 2016-01-22 00:00:00.0000000 +00:00 |  |  |  | 2016-10-14 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 |  |  |  | 2018-07-20 00:00:00.0000000 +00:00 | 2018-11-23 00:00:00.0000000 +00:00 | [9 empty] | 2020-02-21 00:00:00.0000000 +00:00 | 2021-03-26 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-25 17:45:36.2467509 -04:00
HH112SKFA | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-07-06 00:00:00.0000000 +00:00 | 2018-07-11 00:00:00.0000000 +00:00 | 2019-04-10 00:00:00.0000000 +00:00 | 2020-04-09 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | [26 empty] | 2018-07-26 00:00:00.7670000 +00:00 | 2022-04-09 00:00:00.7670000 +00:00 |  |  |  |  | 2017-10-25 17:45:59.5539657 -04:00
HH112SKTV | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2018-01-26 00:00:00.0000000 +00:00 | 2018-08-02 00:00:00.0000000 +00:00 | 2019-01-27 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2017-01-25 00:00:00.0000000 +00:00 | 2017-05-22 00:00:00.0000000 +00:00 | 2017-11-16 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-08-16 18:00:00.0000000 +00:00 |  |  |  | 2018-01-26 00:00:00.0000000 +00:00 | [21 empty] | 2019-11-16 00:00:00.0000000 +00:00 | 2021-01-26 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-01 14:42:56.7474101 -04:00
HH112SWFA | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2018-01-05 00:00:00.0000000 +00:00 | 2018-11-16 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2020-07-24 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2020-07-24 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 |  |  |  |  | 2018-09-21 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-31 00:00:00.0000000 +00:00 | 2018-03-23 00:00:00.0000000 +00:00 |  |  |  | 2018-03-31 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | [9 empty] | 2021-01-22 00:00:00.0000000 +00:00 | 2021-01-22 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 08:30:13.9661669 -04:00
HH112THFA | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | 2018-04-09 00:00:00.0000000 +00:00 | 2018-12-17 00:00:00.0000000 +00:00 | 2019-12-16 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | 2018-03-07 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2019-09-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-05-24 17:00:00.0000000 +00:00 |  |  |  | 2018-04-09 00:00:00.0000000 +00:00 |  | 2016-07-26 00:00:00.0000000 +00:00 |  | 2017-05-24 00:00:00.0000000 +00:00 |  | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 |  | 2017-11-17 00:00:00.0000000 +00:00 | 2017-12-18 00:00:00.0000000 +00:00 |  | 2017-12-18 00:00:00.0000000 +00:00 |  | 2018-04-09 00:00:00.0000000 +00:00 |  | 2018-12-17 00:00:00.0000000 +00:00 |  | 2019-12-16 00:00:00.0000000 +00:00 |  | 2020-03-20 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 |  | 2020-06-15 00:00:00.0000000 +00:00 |  |  | 2017-10-19 12:20:46.6052072 -04:00
HH112VEFP | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-11-16 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2020-07-17 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2020-07-17 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | [10 empty] | 2017-12-31 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 |  |  |  | 2018-04-30 00:00:00.0000000 +00:00 | 2018-07-13 00:00:00.0000000 +00:00 | [9 empty] | 2021-01-15 00:00:00.0000000 +00:00 | 2021-01-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 08:30:40.0465053 -04:00
HH112WBLR | Y | 2012-03-15 00:00:00.0000000 +00:00 | 2012-06-18 00:00:00.0000000 +00:00 | 2013-02-21 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2015-12-16 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2013-05-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2015-11-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-06-18 00:00:00.0000000 +00:00 |  | 2013-10-24 00:00:00.0000000 +00:00 | 2015-12-16 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00
HH112WLFA | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2018-02-26 00:00:00.0000000 +00:00 | 2019-02-26 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2017-11-14 00:00:00.0000000 +00:00 | 2018-07-17 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2016-10-19 12:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 |  |  | 2017-05-31 00:00:00.0000000 +00:00 |  | 2016-07-26 00:00:00.0000000 +00:00 |  | 2016-10-19 00:00:00.0000000 +00:00 |  | 2017-02-03 00:00:00.0000000 +00:00 | 2017-02-03 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 |  | 2017-05-17 00:00:00.0000000 +00:00 | 2017-05-17 00:00:00.0000000 +00:00 | 2017-05-17 00:00:00.0000000 +00:00 | 2017-05-17 00:00:00.0000000 +00:00 |  | 2017-06-13 00:00:00.0000000 +00:00 |  | 2017-11-14 00:00:00.0000000 +00:00 |  | 2019-02-26 00:00:00.0000000 +00:00 |  | 2019-01-30 00:00:00.0000000 +00:00 | 2019-05-26 00:00:00.0000000 +00:00 |  | 2019-05-26 00:00:00.0000000 +00:00
HH115BWFA | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2019-05-24 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-03-02 17:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 17:00:00.0000000 +00:00 |  | 2016-09-07 00:00:00.0000000 +00:00 | 2019-05-24 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-03-02 00:00:00.0000000 +00:00 | 2016-03-02 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2018-11-15 00:00:00.0000000 +00:00 | 2018-09-28 00:00:00.0000000 +00:00 | 2019-05-30 00:00:00.0000000 +00:00 |  | 2018-09-28 00:00:00.0000000 +00:00 | 2019-05-30 00:00:00.0000000 +00:00
HH115BWKF | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2018-05-25 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2018-01-31 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-03-17 18:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 |  |  | 2016-09-07 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 |  | 2016-03-17 00:00:00.0000000 +00:00 |  | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 |  | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 |  | 2016-09-23 00:00:00.0000000 +00:00 |  | 2018-01-31 00:00:00.0000000 +00:00 |  | 2019-03-30 00:00:00.0000000 +00:00 |  | 2019-06-28 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 |  | 2019-09-30 00:00:00.0000000 +00:00
HH115CSBR-F | Y | 2010-11-15 00:00:00.0000000 +00:00 | 2010-12-15 00:00:00.0000000 +00:00 | 2011-02-11 00:00:00.0000000 +00:00 | 2011-06-17 00:00:00.0000000 +00:00 | 2012-06-21 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2010-12-15 00:00:00.0000000 +00:00 | 2011-02-15 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-12-15 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2010-12-15 00:00:00.0000000 +00:00 | 2011-02-15 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2010-12-15 00:00:00.0000000 +00:00 |  | 2011-06-17 00:00:00.0000000 +00:00 | 2012-06-21 00:00:00.0000000 +00:00 | 2011-02-15 00:00:00.0000000 +00:00 | 2012-06-17 00:00:00.0000000 +00:00
HH115CSRR | Y | 2007-09-05 00:00:00.0000000 +00:00 | 2008-02-26 00:00:00.0000000 +00:00 | 2008-12-08 00:00:00.0000000 +00:00 | 2009-10-29 00:00:00.0000000 +00:00 | 2011-02-20 00:00:00.0000000 +00:00 | 2007-09-05 00:00:00.0000000 +00:00 | 2008-03-05 00:00:00.0000000 +00:00 | 2009-01-03 00:00:00.0000000 +00:00 | 2009-06-05 00:00:00.0000000 +00:00 | 2010-06-12 00:00:00.0000000 +00:00 | 2007-09-05 00:00:00.0000000 +00:00 | 2008-02-26 00:00:00.0000000 +00:00 | 2008-12-26 00:00:00.0000000 +00:00 | 2009-11-23 00:00:00.0000000 +00:00 | 2011-03-23 00:00:00.0000000 +00:00 | 2007-09-05 00:00:00.0000000 +00:00 | 2008-02-26 00:00:00.0000000 +00:00 |  | 2009-10-29 00:00:00.0000000 +00:00 | 2010-12-23 00:00:00.0000000 +00:00 | 2008-12-26 00:00:00.0000000 +00:00 | 2011-02-20 00:00:00.0000000 +00:00
HH115DSFA | Y | 2016-07-12 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2019-04-19 00:00:00.0000000 +00:00 | 2020-04-17 00:00:00.0000000 +00:00 | 2016-07-12 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2019-04-19 00:00:00.0000000 +00:00 | 2020-04-17 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-12 17:00:00.0000000 +00:00 | 2017-11-09 00:00:00.0000000 +00:00 | [9 empty] | 2018-02-15 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 |  |  |  | 2018-05-18 00:00:00.0000000 +00:00 | 2018-05-15 00:00:00.0000000 +00:00 | [9 empty] | 2020-10-16 00:00:00.0000000 +00:00 | 2020-10-16 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-09 13:43:44.4582680 -05:00
HH115FFTV | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-08-26 00:00:00.0000000 +00:00 | 2018-04-20 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2019-09-20 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-08-26 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-06-22 00:00:00.0000000 +00:00 | 2019-03-22 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 17:00:00.0000000 +00:00 | 2016-08-26 17:00:00.0000000 +00:00 |  |  |  | 2018-02-05 00:00:00.0000000 +00:00 | 2019-03-27 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 |  | 2016-08-26 00:00:00.0000000 +00:00 |  | 2016-11-30 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 |  | 2017-10-19 00:00:00.0000000 +00:00 | 2018-01-19 00:00:00.0000000 +00:00 |  | 2017-11-23 00:00:00.0000000 +00:00 |  | 2018-01-31 00:00:00.0000000 +00:00 |  | 2018-06-22 00:00:00.0000000 +00:00 |  | 2019-03-22 00:00:00.0000000 +00:00 |  | 2020-03-23 00:00:00.0000000 +00:00 | 2020-03-23 00:00:00.0000000 +00:00 |  | 2020-03-23 00:00:00.0000000 +00:00 |  |  | 2017-09-13 13:36:25.9599438 -04:00
HH115FRFA | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2019-05-24 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2018-08-31 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-03-02 17:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2017-06-16 17:00:00.0000000 +00:00 |  | 2016-11-03 00:00:00.0000000 +00:00 | 2019-02-27 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-03-02 00:00:00.0000000 +00:00 | 2016-03-02 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2017-04-03 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2018-08-31 00:00:00.0000000 +00:00 | 2018-08-31 00:00:00.0000000 +00:00 | 2019-02-28 00:00:00.0000000 +00:00 | 2019-11-15 00:00:00.0000000 +00:00 |  | 2019-02-28 00:00:00.0000000 +00:00 | 2019-02-28 00:00:00.0000000 +00:00
HH115FTXUCW | Y | 2012-02-25 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2012-05-25 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2012-02-25 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2012-05-25 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2012-02-25 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2012-05-25 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2015-05-13 00:00:00.0000000 +00:00 | 2012-02-25 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 |  | 2013-06-03 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2012-05-25 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00
HH115HHFA | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2015-12-01 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2018-05-23 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2015-12-01 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2018-05-23 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2015-12-01 17:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2017-06-20 17:00:00.0000000 +00:00 |  | 2016-03-18 00:00:00.0000000 +00:00 | 2018-05-23 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-23 18:00:00.0000000 +00:00 | 2015-12-01 00:00:00.0000000 +00:00 | 2015-12-01 17:00:00.0000000 +00:00 | 2016-02-02 00:00:00.0000000 +00:00 | 2016-02-02 00:00:00.0000000 +00:00 | 2016-02-02 00:00:00.0000000 +00:00 | 2016-02-02 00:00:00.0000000 +00:00 | 2016-02-02 00:00:00.0000000 +00:00 | 2016-05-10 00:00:00.0000000 +00:00 | 2016-05-10 00:00:00.0000000 +00:00 | 2016-05-10 00:00:00.0000000 +00:00 | 2016-05-10 00:00:00.0000000 +00:00 | 2016-05-10 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2017-06-20 17:00:00.0000000 +00:00 | 2018-05-23 00:00:00.0000000 +00:00 | 2018-05-23 00:00:00.0000000 +00:00 | 2018-11-27 00:00:00.0000000 +00:00 | 2018-11-27 00:00:00.0000000 +00:00 |  | 2018-11-27 00:00:00.0000000 +00:00 | 2018-11-27 00:00:00.0000000 +00:00 |  | 2017-09-15 14:01:26.3385619 -04:00
HH115HLEK | Y
HH115HLFS | Y
HH115JCFB | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2018-05-25 00:00:00.0000000 +00:00 | 2019-11-22 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2018-02-09 00:00:00.0000000 +00:00 | 2019-11-22 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-02-23 17:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 |  |  | 2017-01-30 00:00:00.0000000 +00:00 |  | 2015-10-23 00:00:00.0000000 +00:00 |  | 2016-02-23 00:00:00.0000000 +00:00 |  | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 |  | 2016-09-30 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 |  | 2017-01-30 00:00:00.0000000 +00:00 |  | 2018-02-09 00:00:00.0000000 +00:00 |  | 2019-11-22 00:00:00.0000000 +00:00 |  | 2020-05-27 00:00:00.0000000 +00:00 | 2020-05-27 00:00:00.0000000 +00:00 |  | 2020-05-27 00:00:00.0000000 +00:00 |  |  | 2017-10-26 08:31:59.8970926 -04:00
HH115JCFS | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2017-06-14 00:00:00.0000000 +00:00 | 2018-05-25 00:00:00.0000000 +00:00 | 2019-02-26 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2017-06-14 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-07-18 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2016-10-19 12:00:00.0000000 +00:00 | 2017-06-14 00:00:00.0000000 +00:00 |  |  | 2017-01-30 00:00:00.0000000 +00:00 |  | 2016-07-26 00:00:00.0000000 +00:00 |  | 2016-10-19 00:00:00.0000000 +00:00 |  | 2017-01-27 00:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 |  | 2017-05-17 00:00:00.0000000 +00:00 | 2017-05-17 00:00:00.0000000 +00:00 | 2017-05-17 00:00:00.0000000 +00:00 | 2017-05-17 00:00:00.0000000 +00:00 |  | 2017-06-14 00:00:00.0000000 +00:00 |  | 2018-02-26 00:00:00.0000000 +00:00 |  | 2019-02-26 00:00:00.0000000 +00:00 |  | 2019-01-30 00:00:00.0000000 +00:00 | 2019-05-26 00:00:00.0000000 +00:00 |  | 2019-05-26 00:00:00.0000000 +00:00 |  |  | 2017-10-26 08:32:25.6614532 -04:00
HH115JCTV | Y | 2015-10-23 17:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2020-04-30 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2020-04-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 17:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 |  |  |  | 2018-10-31 00:00:00.0000000 +00:00 | 2020-04-30 00:00:00.0000000 +00:00 | 2015-10-23 17:00:00.0000000 +00:00 |  | 2016-10-14 00:00:00.0000000 +00:00 |  | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 |  | 2018-07-27 00:00:00.0000000 +00:00 | 2018-07-27 00:00:00.0000000 +00:00 |  | 2018-07-27 00:00:00.0000000 +00:00 |  | 2018-10-31 00:00:00.0000000 +00:00 |  | 2019-04-01 00:00:00.0000000 +00:00 |  | 2020-04-30 00:00:00.0000000 +00:00 |  | 2020-07-31 00:00:00.0000000 +00:00 | 2020-07-31 00:00:00.0000000 +00:00 |  | 2020-07-31 00:00:00.0000000 +00:00 |  |  | 2017-10-26 08:26:34.1595341 -04:00
HH115JWTV | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-08-16 00:00:00.0000000 +00:00 | 2018-07-27 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-08-16 00:00:00.0000000 +00:00 | 2018-07-27 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 17:00:00.0000000 +00:00 | 2016-08-16 17:00:00.0000000 +00:00 |  |  |  | 2018-01-26 00:00:00.0000000 +00:00 |  | 2015-10-23 17:00:00.0000000 +00:00 |  | 2016-08-16 17:00:00.0000000 +00:00 |  | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 |  | 2018-04-20 00:00:00.0000000 +00:00 | 2018-04-20 00:00:00.0000000 +00:00 |  | 2018-04-20 00:00:00.0000000 +00:00 |  | 2018-07-27 00:00:00.0000000 +00:00 |  | 2018-10-31 00:00:00.0000000 +00:00 |  | 2019-10-30 00:00:00.0000000 +00:00 |  | 2020-01-31 00:00:00.0000000 +00:00 | 2020-01-31 00:00:00.0000000 +00:00 |  | 2020-01-31 00:00:00.0000000 +00:00
HH115LFAU | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2020-05-15 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2020-05-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 17:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 |  |  |  | 2018-09-21 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-29 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  | 2018-04-27 00:00:00.0000000 +00:00 | 2018-04-27 00:00:00.0000000 +00:00 | [9 empty] | 2020-11-20 00:00:00.0000000 +00:00 | 2020-11-20 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-16 09:01:45.4305686 -04:00
HH115LFTV | Y | 2013-10-21 00:00:00.0000000 +00:00 | 2013-11-18 00:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2014-08-19 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2013-10-21 00:00:00.0000000 +00:00 | 2013-11-18 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-06-15 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2013-10-21 00:00:00.0000000 +00:00 | 2013-11-18 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-08-19 00:00:00.0000000 +00:00 | 2015-08-19 00:00:00.0000000 +00:00 | 2013-10-21 00:00:00.0000000 +00:00 | 2013-11-18 00:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2014-08-19 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2015-08-19 00:00:00.0000000 +00:00
HH115REGX-1 | Y | 2014-12-15 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2018-02-27 00:00:00.0000000 +00:00 | 2019-06-27 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2016-12-24 00:00:00.0000000 +00:00 | 2018-11-24 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-07-30 00:00:00.0000000 +00:00 | 2017-01-23 00:00:00.0000000 +00:00 | 2018-12-24 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 |  |  | 2017-05-31 00:00:00.0000000 +00:00 |  | 2014-12-15 00:00:00.0000000 +00:00 |  | 2015-06-25 00:00:00.0000000 +00:00 |  | 2015-09-18 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 |  | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 |  | 2017-06-16 00:00:00.0000000 +00:00 |  | 2018-02-27 00:00:00.0000000 +00:00 |  | 2019-08-27 00:00:00.0000000 +00:00 |  | 2019-05-10 00:00:00.0000000 +00:00 | 2019-12-31 00:00:00.0000000 +00:00 |  | 2020-02-27 00:00:00.0000000 +00:00 |  |  | 2017-10-26 08:32:43.5145202 -04:00
HH115RFEU | Y | 2016-01-22 17:00:00.0000000 +00:00 | 2017-10-25 00:00:00.0000000 +00:00 | 2018-10-26 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2021-01-15 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2017-10-13 00:00:00.0000000 +00:00 | 2018-10-26 00:00:00.0000000 +00:00 | 2019-07-19 00:00:00.0000000 +00:00 | 2021-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-22 17:00:00.0000000 +00:00 | 2017-10-25 00:00:00.0000000 +00:00 |  |  |  | 2018-10-26 00:00:00.0000000 +00:00 | [5 empty] | 2018-01-19 00:00:00.0000000 +00:00 | 2018-01-19 00:00:00.0000000 +00:00 |  |  |  | 2018-04-20 00:00:00.0000000 +00:00 | 2018-04-20 00:00:00.0000000 +00:00 | [9 empty] | 2021-07-30 00:00:00.0000000 +00:00 | 2021-07-30 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 10:10:37.3691550 -04:00
HH115RGEL | Y | 2016-09-15 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2018-11-04 00:00:00.0000000 +00:00 | 2019-08-16 00:00:00.0000000 +00:00 | 2021-02-19 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2018-11-04 00:00:00.0000000 +00:00 | 2019-08-16 00:00:00.0000000 +00:00 | 2021-02-19 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-15 17:00:00.0000000 +00:00 | 2017-10-25 00:00:00.0000000 +00:00 |  |  |  | 2018-11-04 00:00:00.0000000 +00:00 | [5 empty] | 2018-02-23 00:00:00.0000000 +00:00 | 2018-02-23 00:00:00.0000000 +00:00 |  |  |  | 2018-06-22 00:00:00.0000000 +00:00 | 2018-06-22 00:00:00.0000000 +00:00 | [9 empty] | 2021-08-20 00:00:00.0000000 +00:00 | 2021-08-20 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 10:11:02.0539411 -04:00
HH115SFFA | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2018-01-31 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2019-01-31 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-03-15 18:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 |  | 2016-09-07 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-23 18:00:00.0000000 +00:00 | 2016-03-15 00:00:00.0000000 +00:00 | 2016-03-15 18:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2018-01-31 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2019-01-31 00:00:00.0000000 +00:00 | 2019-01-31 00:00:00.0000000 +00:00 | 2019-04-30 00:00:00.0000000 +00:00 | 2019-07-31 00:00:00.0000000 +00:00 |  | 2019-07-31 00:00:00.0000000 +00:00 | 2019-07-31 00:00:00.0000000 +00:00
HH115SGFA | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-02-23 17:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 17:00:00.0000000 +00:00 |  | 2016-09-07 00:00:00.0000000 +00:00 | 2019-04-19 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | 2018-12-20 00:00:00.0000000 +00:00 | 2019-01-18 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 |  | 2019-01-18 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00
HH115SNFA | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2018-04-27 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2017-11-24 00:00:00.0000000 +00:00 | 2018-06-18 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-03-02 17:00:00.0000000 +00:00 |  |  |  | 2018-04-14 00:00:00.0000000 +00:00 |  | 2015-10-23 00:00:00.0000000 +00:00 |  | 2016-03-02 00:00:00.0000000 +00:00 |  | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 |  | 2016-11-18 00:00:00.0000000 +00:00 | 2016-11-18 00:00:00.0000000 +00:00 | 2016-11-18 00:00:00.0000000 +00:00 | 2016-11-18 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2018-09-14 00:00:00.0000000 +00:00 |  | 2019-06-18 00:00:00.0000000 +00:00 |  | 2019-09-30 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 |  | 2020-01-17 00:00:00.0000000 +00:00 |  |  | 2017-09-20 16:25:23.4810616 -04:00
HH115SRFA | Y | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2018-05-18 00:00:00.0000000 +00:00 | 2018-11-23 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2018-02-16 00:00:00.0000000 +00:00 | 2018-11-23 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 18:00:00.0000000 +00:00 | 2016-03-18 18:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 |  |  | 2016-09-07 00:00:00.0000000 +00:00 |  | 2015-10-23 00:00:00.0000000 +00:00 |  | 2016-03-18 00:00:00.0000000 +00:00 |  | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 |  | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 |  | 2016-09-23 00:00:00.0000000 +00:00 |  | 2018-02-16 00:00:00.0000000 +00:00 |  | 2018-11-23 00:00:00.0000000 +00:00 |  | 2019-02-28 00:00:00.0000000 +00:00 | 2019-02-28 00:00:00.0000000 +00:00 |  | 2019-02-28 00:00:00.0000000 +00:00
HH115UNFA | Y | 2015-10-30 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2018-04-27 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2019-09-20 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2018-06-02 00:00:00.0000000 +00:00 | 2019-06-20 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-25 18:00:00.0000000 +00:00 | 2016-03-21 18:00:00.0000000 +00:00 |  |  |  | 2018-04-14 00:00:00.0000000 +00:00 |  | 2015-10-23 00:00:00.0000000 +00:00 |  | 2016-03-21 00:00:00.0000000 +00:00 |  | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 |  | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2018-09-21 00:00:00.0000000 +00:00 |  | 2019-09-20 00:00:00.0000000 +00:00 |  | 2019-09-30 00:00:00.0000000 +00:00 | 2020-03-20 00:00:00.0000000 +00:00 |  | 2020-03-20 00:00:00.0000000 +00:00 |  |  | 2017-09-20 16:51:25.7411999 -04:00
HL82125VR | Y | 2013-04-04 00:00:00.0000000 +00:00 | 2013-08-30 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2016-12-08 00:00:00.0000000 +00:00 | 2013-04-04 00:00:00.0000000 +00:00 | 2013-08-30 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2013-04-04 00:00:00.0000000 +00:00 | 2013-08-30 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 | 2013-04-04 00:00:00.0000000 +00:00 | 2013-08-30 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2016-12-08 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2016-12-08 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 |  |  |  | 2014-03-31 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 | [9 empty] | 2018-01-31 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-11 16:07:42.0053353 -04:00
HL82BRKLN | Y | 2015-07-23 00:00:00.0000000 +00:00 | 2016-07-25 00:00:00.0000000 +00:00 | 2019-04-17 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 | 2022-01-17 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2016-07-25 00:00:00.0000000 +00:00 | 2018-08-28 00:00:00.0000000 +00:00 | 2019-03-27 00:00:00.0000000 +00:00 | 2021-03-29 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2016-01-23 00:00:00.0000000 +00:00 | 2017-07-23 00:00:00.0000000 +00:00 | 2018-01-23 00:00:00.0000000 +00:00 | 2020-01-23 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2016-07-20 00:00:00.0000000 +00:00 |  |  |  | 2019-04-17 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  |  | 2018-03-06 00:00:00.0000000 +00:00 | [9 empty] | 2022-03-29 00:00:00.0000000 +00:00 | 2023-01-17 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-18 11:09:20.1043787 -04:00
HL82BUSHX-1 | Y | 2015-05-01 00:00:00.0000000 +00:00 | 2016-01-12 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2018-12-12 00:00:00.0000000 +00:00 | 2020-12-12 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2015-11-01 00:00:00.0000000 +00:00 | 2016-11-01 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2019-06-01 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2016-01-25 00:00:00.0000000 +00:00 | 2017-01-25 00:00:00.0000000 +00:00 | 2017-07-25 00:00:00.0000000 +00:00 | 2019-08-25 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2016-01-12 00:00:00.0000000 +00:00 |  |  |  | 2018-03-15 00:00:00.0000000 +00:00 | [6 empty] | 2016-09-27 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 |  |  |  | 2017-10-16 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | [8 empty] | 2021-05-31 00:00:00.0000000 +00:00 | 2021-12-20 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-02 08:39:41.1994211 -04:00
HL82CHELI-R | Y | 2009-07-30 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2013-02-05 00:00:00.0000000 +00:00 | 2014-04-03 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2009-07-30 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2013-01-17 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2009-07-30 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2013-02-05 00:00:00.0000000 +00:00 | 2013-11-18 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2009-07-30 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2013-02-05 00:00:00.0000000 +00:00 | 2014-04-03 00:00:00.0000000 +00:00 |  | 2013-02-05 00:00:00.0000000 +00:00 | 2017-11-01 00:00:00.0000000 +00:00 | 2009-07-30 00:00:00.0000000 +00:00 | 2009-07-30 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 |  | 2009-12-31 00:00:00.0000000 +00:00 | 2009-12-31 00:00:00.0000000 +00:00 | 2009-12-31 00:00:00.0000000 +00:00 | 2009-12-31 00:00:00.0000000 +00:00 |  | 2010-06-30 00:00:00.0000000 +00:00 | 2010-06-30 00:00:00.0000000 +00:00 | 2010-06-30 00:00:00.0000000 +00:00 | 2010-06-30 00:00:00.0000000 +00:00 | 2013-02-05 00:00:00.0000000 +00:00 | 2013-02-05 00:00:00.0000000 +00:00 | 2014-04-03 00:00:00.0000000 +00:00 | 2014-04-03 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 |  | 2018-10-31 00:00:00.0000000 +00:00 |  | 2018-11-30 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 |  | 2017-09-18 11:10:04.9397890 -04:00
HL82CORHC | Y | 2017-07-24 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-06-27 00:00:00.0000000 +00:00 | 2020-03-26 00:00:00.0000000 +00:00 | 2022-03-24 00:00:00.0000000 +00:00 | [10 empty] | 2017-06-15 00:00:00.0000000 +00:00 | [11 empty] | 2018-08-27 00:00:00.0000000 +00:00 |  |  |  |  | 2018-12-20 00:00:00.0000000 +00:00 | [10 empty] | 2023-03-23 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-03 15:11:50.3477590 -04:00
HL82FGHVC-B | Y | 2009-02-05 00:00:00.0000000 +00:00 | 2009-03-24 00:00:00.0000000 +00:00 | 2011-02-17 00:00:00.0000000 +00:00 | 2011-08-24 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2009-02-05 00:00:00.0000000 +00:00 | 2009-03-24 00:00:00.0000000 +00:00 | 2010-04-30 00:00:00.0000000 +00:00 | 2011-01-15 00:00:00.0000000 +00:00 | 2012-06-25 00:00:00.0000000 +00:00 | 2009-02-05 00:00:00.0000000 +00:00 | 2009-03-24 00:00:00.0000000 +00:00 | 2011-03-01 00:00:00.0000000 +00:00 | 2011-11-16 00:00:00.0000000 +00:00 | 2013-11-26 00:00:00.0000000 +00:00 | 2009-02-05 00:00:00.0000000 +00:00 | 2009-03-24 00:00:00.0000000 +00:00 |  | 2011-08-24 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2011-03-01 00:00:00.0000000 +00:00 | 2013-09-15 00:00:00.0000000 +00:00
HL82GRPRSIT | Y | 2012-04-15 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2013-07-08 00:00:00.0000000 +00:00 | 2012-04-15 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2012-04-15 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2013-06-07 00:00:00.0000000 +00:00 | 2012-04-15 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2013-07-08 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2013-07-08 00:00:00.0000000 +00:00
HL82HCRST | Y | 2007-01-10 00:00:00.0000000 +00:00 | 2008-01-29 00:00:00.0000000 +00:00 | 2009-04-29 00:00:00.0000000 +00:00 | 2011-06-02 00:00:00.0000000 +00:00 | 2013-12-27 00:00:00.0000000 +00:00 | 2007-01-10 00:00:00.0000000 +00:00 | 2007-07-02 00:00:00.0000000 +00:00 | 2008-07-02 00:00:00.0000000 +00:00 | 2009-02-02 00:00:00.0000000 +00:00 | 2010-03-11 00:00:00.0000000 +00:00 | 2007-01-10 00:00:00.0000000 +00:00 | 2007-11-05 00:00:00.0000000 +00:00 | 2009-02-02 00:00:00.0000000 +00:00 | 2010-12-08 00:00:00.0000000 +00:00 | 2013-02-16 00:00:00.0000000 +00:00 | 2007-01-10 00:00:00.0000000 +00:00 | 2008-01-29 00:00:00.0000000 +00:00 | 2009-04-29 00:00:00.0000000 +00:00 | 2011-06-02 00:00:00.0000000 +00:00 | 2013-12-27 00:00:00.0000000 +00:00 | 2009-04-29 00:00:00.0000000 +00:00 | 2013-08-09 00:00:00.0000000 +00:00
HL82JAMCXF | Y | 2011-01-03 00:00:00.0000000 +00:00 | 2011-04-09 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2011-09-23 00:00:00.0000000 +00:00 | 2012-06-27 00:00:00.0000000 +00:00 | 2011-01-03 00:00:00.0000000 +00:00 | 2011-04-09 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2011-09-26 00:00:00.0000000 +00:00 | 2012-02-26 00:00:00.0000000 +00:00 | 2011-01-03 00:00:00.0000000 +00:00 | 2011-04-09 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2011-09-26 00:00:00.0000000 +00:00 | 2012-04-27 00:00:00.0000000 +00:00 | 2011-01-03 00:00:00.0000000 +00:00 | 2011-04-09 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2011-09-23 00:00:00.0000000 +00:00 | 2012-06-27 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2012-06-21 00:00:00.0000000 +00:00 | [5 empty] | 2011-05-09 00:00:00.0000000 +00:00 | 2011-05-09 00:00:00.0000000 +00:00 |  |  |  | 2011-06-09 00:00:00.0000000 +00:00 | 2011-06-09 00:00:00.0000000 +00:00
HL82MANAT | Y | 2015-10-21 00:00:00.0000000 +00:00 | 2016-10-27 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2020-11-17 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2018-11-21 00:00:00.0000000 +00:00 | 2019-06-21 00:00:00.0000000 +00:00 | 2021-06-21 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-21 18:00:00.0000000 +00:00 | 2016-10-27 00:00:00.0000000 +00:00 |  |  |  | 2018-11-29 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  |  | 2018-02-12 00:00:00.0000000 +00:00 | [9 empty] | 2022-06-21 00:00:00.0000000 +00:00 | 2021-11-17 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-06 09:24:55.6057412 -04:00
HL82RPZ2-1 | Y | 2012-12-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2013-06-17 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2014-05-25 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 |  | 2015-05-06 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2015-12-18 00:00:00.0000000 +00:00
HL82RPZ2-2 | Y | 2012-12-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2015-01-21 00:00:00.0000000 +00:00 | 2015-10-07 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2013-06-17 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2014-05-29 00:00:00.0000000 +00:00 | 2016-01-29 00:00:00.0000000 +00:00 | 2016-01-29 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 |  | 2015-01-21 00:00:00.0000000 +00:00 | 2015-10-07 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2016-02-20 00:00:00.0000000 +00:00
HL82RPZ2-3 | Y | 2012-12-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2015-01-21 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2013-06-17 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2014-05-29 00:00:00.0000000 +00:00 | 2016-01-29 00:00:00.0000000 +00:00 | 2016-01-29 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 |  | 2015-01-21 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2016-02-21 00:00:00.0000000 +00:00
HL82RVREX-E | Y | 2005-01-15 00:00:00.0000000 +00:00 | 2005-02-14 00:00:00.0000000 +00:00 | 2008-05-02 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2014-03-18 00:00:00.0000000 +00:00 | 2005-01-15 00:00:00.0000000 +00:00 | 2005-02-14 00:00:00.0000000 +00:00 | 2008-05-04 00:00:00.0000000 +00:00 | 2008-10-06 00:00:00.0000000 +00:00 | 2010-12-31 00:00:00.0000000 +00:00 | 2005-01-15 00:00:00.0000000 +00:00 | 2005-02-14 00:00:00.0000000 +00:00 | 2008-03-18 00:00:00.0000000 +00:00 | 2009-09-24 00:00:00.0000000 +00:00 | 2012-11-25 00:00:00.0000000 +00:00 | 2005-01-15 00:00:00.0000000 +00:00 | 2005-02-14 00:00:00.0000000 +00:00 | 2008-05-02 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2014-03-18 00:00:00.0000000 +00:00 | 2007-11-13 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | [5 empty] | 2006-02-28 00:00:00.0000000 +00:00 | 2006-02-28 00:00:00.0000000 +00:00 |  |  |  | 2007-04-05 00:00:00.0000000 +00:00 | 2007-04-05 00:00:00.0000000 +00:00 | [9 empty] | 2015-03-18 00:00:00.0000000 +00:00 | 2015-03-18 00:00:00.0000000 +00:00
HL82SIABEX | Y | 2011-05-02 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-04-23 00:00:00.0000000 +00:00 | 2013-11-20 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2011-05-02 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2011-12-15 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2014-06-15 00:00:00.0000000 +00:00 | 2011-05-02 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-05-06 00:00:00.0000000 +00:00 | 2013-12-07 00:00:00.0000000 +00:00 | 2018-01-06 00:00:00.0000000 +00:00 | 2011-05-02 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-04-23 00:00:00.0000000 +00:00 | 2013-11-20 00:00:00.0000000 +00:00 |  | 2012-05-06 00:00:00.0000000 +00:00 | 2018-02-22 00:00:00.0000000 +00:00 | 2011-05-02 00:00:00.0000000 +00:00 | 2011-05-02 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 |  | 2011-11-11 00:00:00.0000000 +00:00 | 2011-11-11 00:00:00.0000000 +00:00 | 2011-11-11 00:00:00.0000000 +00:00 | 2011-11-11 00:00:00.0000000 +00:00 |  | 2012-02-24 00:00:00.0000000 +00:00 | 2012-02-24 00:00:00.0000000 +00:00 | 2012-02-24 00:00:00.0000000 +00:00 | 2012-02-24 00:00:00.0000000 +00:00 | 2012-04-23 00:00:00.0000000 +00:00 | 2012-04-23 00:00:00.0000000 +00:00 | 2013-11-20 00:00:00.0000000 +00:00 | 2013-11-20 00:00:00.0000000 +00:00 | 2017-12-24 00:00:00.0000000 +00:00 | 2017-12-24 00:00:00.0000000 +00:00 |  | 2018-12-24 00:00:00.0000000 +00:00 |  | 2018-12-24 00:00:00.0000000 +00:00 | 2018-12-24 00:00:00.0000000 +00:00 |  | 2017-11-13 13:25:54.9022609 -05:00
HLEXP17BR | Y | 2016-03-25 00:00:00.0000000 +00:00 | 2016-03-25 00:00:00.0000000 +00:00 | 2016-09-13 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 | 2016-03-25 00:00:00.0000000 +00:00 | 2016-03-25 00:00:00.0000000 +00:00 | 2016-09-13 00:00:00.0000000 +00:00 | 2016-09-27 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 | [5 empty] | 2016-03-25 17:00:00.0000000 +00:00 | 2016-03-25 17:00:00.0000000 +00:00 | 2016-09-13 00:00:00.0000000 +00:00 | 2016-09-27 17:00:00.0000000 +00:00 | 2016-12-28 17:00:00.0000000 +00:00 | 2016-09-13 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 | [5 empty] | 2016-04-25 00:00:00.0000000 +00:00 | 2016-04-25 00:00:00.0000000 +00:00 |  |  |  | 2016-06-24 00:00:00.0000000 +00:00 | 2016-06-24 00:00:00.0000000 +00:00 | [8 empty] | 2017-06-30 00:00:00.0000000 +00:00 | 2017-12-28 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-11 16:42:10.1162605 -04:00
HR25FACA-1 | Y | 2010-09-24 00:00:00.0000000 +00:00 | 2011-10-15 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2016-05-06 00:00:00.0000000 +00:00 | 2010-09-24 00:00:00.0000000 +00:00 | 2011-10-15 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2013-09-19 00:00:00.0000000 +00:00 | 2015-03-13 00:00:00.0000000 +00:00 | 2010-09-24 00:00:00.0000000 +00:00 | 2011-10-15 00:00:00.0000000 +00:00 | 2013-05-03 00:00:00.0000000 +00:00 | 2014-11-08 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2010-09-24 00:00:00.0000000 +00:00 | 2011-10-15 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 |  | 2013-05-03 00:00:00.0000000 +00:00 | 2015-08-12 00:00:00.0000000 +00:00
HR25FACA-2 | Y | 2013-07-09 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2017-08-26 00:00:00.0000000 +00:00 | 2013-07-09 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2017-01-11 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2013-07-09 18:00:00.0000000 +00:00 | 2014-09-12 18:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2015-10-29 18:00:00.0000000 +00:00 | 2017-08-26 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2017-08-26 00:00:00.0000000 +00:00 | 2013-07-09 00:00:00.0000000 +00:00 | 2013-07-09 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2017-08-26 00:00:00.0000000 +00:00 | 2017-08-26 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2019-05-30 00:00:00.0000000 +00:00 |  | 2019-05-30 00:00:00.0000000 +00:00 | 2019-05-30 00:00:00.0000000 +00:00 |  | 2017-09-14 08:52:41.6684345 -04:00
HR25FACA-3 | Y | 2014-03-12 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2018-10-12 00:00:00.0000000 +00:00 | 2014-03-12 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2013-09-15 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2016-02-14 00:00:00.0000000 +00:00 | 2016-08-13 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | 2014-03-12 18:00:00.0000000 +00:00 | 2015-07-15 18:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2017-01-20 17:00:00.0000000 +00:00 |  | 2016-01-01 00:00:00.0000000 +00:00 | 2018-10-12 00:00:00.0000000 +00:00 | 2014-03-12 00:00:00.0000000 +00:00 | 2014-03-12 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-11-20 00:00:00.0000000 +00:00 | 2015-11-20 00:00:00.0000000 +00:00 | 2015-11-20 00:00:00.0000000 +00:00 | 2015-11-20 00:00:00.0000000 +00:00 | 2015-11-20 00:00:00.0000000 +00:00 | 2016-01-08 00:00:00.0000000 +00:00 | 2016-01-08 00:00:00.0000000 +00:00 | 2016-01-08 00:00:00.0000000 +00:00 | 2016-01-08 00:00:00.0000000 +00:00 | 2016-01-08 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2019-06-28 00:00:00.0000000 +00:00 | 2019-06-28 00:00:00.0000000 +00:00 | 2019-03-14 00:00:00.0000000 +00:00 | 2020-06-27 00:00:00.0000000 +00:00 |  | 2020-06-27 00:00:00.0000000 +00:00 | 2020-06-27 00:00:00.0000000 +00:00
HW2CR14B | Y | 2012-08-13 00:00:00.0000000 +00:00 | 2012-08-23 00:00:00.0000000 +00:00 | 2012-10-18 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-09-23 00:00:00.0000000 +00:00 | 2012-08-13 00:00:00.0000000 +00:00 | 2012-11-19 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2013-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2012-08-13 00:00:00.0000000 +00:00 | 2012-11-19 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2012-08-13 12:00:00.0000000 +00:00 | 2012-08-23 00:00:00.0000000 +00:00 | 2012-10-18 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-09-23 17:00:00.0000000 +00:00 | 2012-10-18 00:00:00.0000000 +00:00 | 2015-09-23 00:00:00.0000000 +00:00 | 2012-08-13 00:00:00.0000000 +00:00 | 2012-08-13 00:00:00.0000000 +00:00 | 2012-08-23 00:00:00.0000000 +00:00 | 2012-08-23 00:00:00.0000000 +00:00 |  | 2012-09-15 00:00:00.0000000 +00:00 | 2012-09-15 00:00:00.0000000 +00:00 | 2012-09-15 00:00:00.0000000 +00:00 | 2012-09-15 00:00:00.0000000 +00:00 | [5 empty] | 2012-10-18 00:00:00.0000000 +00:00 | 2012-10-18 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-09-23 00:00:00.0000000 +00:00 | 2015-09-23 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2018-09-23 00:00:00.0000000 +00:00 |  | 2018-09-23 00:00:00.0000000 +00:00 | 2018-09-23 00:00:00.0000000 +00:00
HW2CR14C | Y | 2012-08-30 00:00:00.0000000 +00:00 | 2012-09-03 00:00:00.0000000 +00:00 | 2012-12-20 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2012-08-30 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2012-08-30 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2015-02-09 00:00:00.0000000 +00:00 | 2017-01-08 00:00:00.0000000 +00:00 | 2012-08-30 12:00:00.0000000 +00:00 | 2012-09-03 17:00:00.0000000 +00:00 | 2012-12-20 00:00:00.0000000 +00:00 | 2014-03-17 17:00:00.0000000 +00:00 | 2015-06-30 17:00:00.0000000 +00:00 | 2012-12-20 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 |  | 2012-08-30 12:00:00.0000000 +00:00 |  | 2012-09-03 17:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 |  | 2012-11-30 00:00:00.0000000 +00:00 | [6 empty] | 2012-12-20 00:00:00.0000000 +00:00 |  | 2014-03-17 17:00:00.0000000 +00:00 |  | 2015-06-30 17:00:00.0000000 +00:00 | 2019-06-13 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 |  |  | 2018-06-30 00:00:00.0000000 +00:00
HW2CR15A | Y | 2013-10-21 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2013-10-21 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2013-10-21 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2013-10-21 12:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2016-11-16 00:00:00.0000000 +00:00 | 2013-10-21 00:00:00.0000000 +00:00 | 2013-10-21 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-01-24 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 |  | 2019-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00
HW2CR15CW | Y | 2013-10-24 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-10-27 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2013-10-24 12:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-10-27 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2013-10-24 12:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 |  | 2013-12-16 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | [5 empty] | 2014-01-24 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-10-27 00:00:00.0000000 +00:00 | 2014-10-27 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2019-10-15 00:00:00.0000000 +00:00 |  | 2016-10-25 00:00:00.0000000 +00:00 | 2019-10-15 00:00:00.0000000 +00:00
HW2CR16B | Y | 2014-09-10 00:00:00.0000000 +00:00 | 2014-09-23 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2016-03-14 00:00:00.0000000 +00:00 | 2018-03-13 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2014-09-23 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 |  | 2017-08-17 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-10 17:00:00.0000000 +00:00 | 2014-09-24 17:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2016-03-14 18:00:00.0000000 +00:00 |  | 2014-10-30 00:00:00.0000000 +00:00 | 2018-10-07 00:00:00.0000000 +00:00 | 2014-09-10 17:00:00.0000000 +00:00 | 2014-09-10 17:00:00.0000000 +00:00 | 2014-09-24 17:00:00.0000000 +00:00 | 2014-09-24 17:00:00.0000000 +00:00 |  | 2014-10-15 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2016-03-14 18:00:00.0000000 +00:00 | 2016-03-14 18:00:00.0000000 +00:00 | 2018-03-13 00:00:00.0000000 +00:00 | 2018-03-13 00:00:00.0000000 +00:00 |  | 2019-03-07 00:00:00.0000000 +00:00 |  | 2019-03-07 00:00:00.0000000 +00:00 | 2019-03-07 00:00:00.0000000 +00:00 |  | 2017-11-30 08:59:11.2190310 -05:00
HW2CR16C | Y | 2014-09-12 00:00:00.0000000 +00:00 | 2014-10-08 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2017-11-28 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2014-10-08 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-10-12 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-12 17:00:00.0000000 +00:00 | 2014-10-08 17:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-11-30 17:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2017-11-28 00:00:00.0000000 +00:00 |  | 2014-09-12 17:00:00.0000000 +00:00 |  | 2014-10-08 17:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 |  | 2014-10-30 00:00:00.0000000 +00:00 | [6 empty] | 2014-11-10 00:00:00.0000000 +00:00 |  | 2015-11-30 17:00:00.0000000 +00:00 |  | 2016-12-15 00:00:00.0000000 +00:00 | 2020-10-08 00:00:00.0000000 +00:00 | 2020-11-26 00:00:00.0000000 +00:00 |  |  | 2020-11-26 00:00:00.0000000 +00:00 |  | 2017-09-19 09:35:14.3801854 -04:00
HW2CR16D | Y | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2018-05-30 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-08-08 00:00:00.0000000 +00:00 | 2018-08-07 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 |  | 2015-10-15 00:00:00.0000000 +00:00 | 2018-05-30 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2018-05-30 00:00:00.0000000 +00:00 | 2018-05-30 00:00:00.0000000 +00:00 | 2021-08-06 00:00:00.0000000 +00:00 | 2021-05-29 00:00:00.0000000 +00:00 |  | 2021-05-29 00:00:00.0000000 +00:00 | 2021-05-29 00:00:00.0000000 +00:00
HW2CR16E | Y | 2015-07-07 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-06-20 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2018-06-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-07 17:00:00.0000000 +00:00 | 2015-08-17 17:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-06-20 17:00:00.0000000 +00:00 |  | 2015-10-15 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-06-20 00:00:00.0000000 +00:00 | 2016-06-20 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2021-06-18 00:00:00.0000000 +00:00 | 2021-06-18 00:00:00.0000000 +00:00 |  | 2021-06-18 00:00:00.0000000 +00:00 | 2021-06-18 00:00:00.0000000 +00:00 |  | 2017-08-29 11:27:58.7492976 -04:00
HW2CR17A | Y | 2015-10-16 00:00:00.0000000 +00:00 | 2016-01-05 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2016-01-05 00:00:00.0000000 +00:00 | 2016-04-05 00:00:00.0000000 +00:00 | 2016-11-18 00:00:00.0000000 +00:00 | 2018-11-19 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-16 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 |  | 2016-05-30 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | [5 empty] | 2016-05-30 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 | 2022-02-13 00:00:00.0000000 +00:00 | 2022-02-13 00:00:00.0000000 +00:00 |  | 2022-02-13 00:00:00.0000000 +00:00 | 2022-02-13 00:00:00.0000000 +00:00 |  | 2017-11-29 11:16:56.8526800 -05:00
HW2CR17CW | Y | 2015-10-18 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-03-30 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2019-01-31 00:00:00.0000000 +00:00 | 2015-10-18 00:00:00.0000000 +00:00 | 2016-03-06 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-03-14 00:00:00.0000000 +00:00 | 2018-03-17 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-18 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 |  |  |  | 2015-11-29 00:00:00.0000000 +00:00 | 2020-01-27 00:00:00.0000000 +00:00 | [20 empty] | 2019-03-13 00:00:00.0000000 +00:00 | 2020-01-27 00:00:00.0000000 +00:00
HW2CR18B | Y | [48 empty] | 2017-08-31 16:59:46.1625964 -04:00
HW2CR18C | Y | 2016-06-01 00:00:00.0000000 +00:00 | 2016-10-11 00:00:00.0000000 +00:00 | 2017-02-23 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2016-10-11 00:00:00.0000000 +00:00 | 2017-02-23 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 | [5 empty] | 2016-06-01 18:00:00.0000000 +00:00 | 2016-10-11 17:00:00.0000000 +00:00 |  |  |  | 2017-02-23 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 | [20 empty] | 2021-05-07 00:00:00.0000000 +00:00 | 2021-05-07 00:00:00.0000000 +00:00
HW2CR18D | Y | 2016-05-30 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | 2016-07-25 00:00:00.0000000 +00:00 | 2016-07-28 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2018-07-13 00:00:00.0000000 +00:00 | [5 empty] | 2016-05-30 18:00:00.0000000 +00:00 | 2016-07-15 17:00:00.0000000 +00:00 |  |  | 2016-07-28 17:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | [21 empty] | 2019-07-13 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 10:38:02.7528536 -04:00
HW2CR18E | Y | 2016-06-01 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2019-09-04 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2019-09-04 00:00:00.0000000 +00:00 | [5 empty] | 2016-06-01 18:00:00.0000000 +00:00 | [26 empty] | 2020-03-03 00:00:00.0000000 +00:00 | 2020-03-03 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-29 07:46:56.8882721 -04:00
HW349FED2 | Y | 2014-07-10 00:00:00.0000000 +00:00 | 2014-07-10 00:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2016-09-28 00:00:00.0000000 +00:00 | 2014-07-10 00:00:00.0000000 +00:00 | 2014-07-10 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2015-04-01 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-07-10 17:00:00.0000000 +00:00 | 2014-07-10 17:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2015-09-14 17:00:00.0000000 +00:00 | 2016-09-28 18:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2016-09-28 00:00:00.0000000 +00:00 | 2014-07-10 00:00:00.0000000 +00:00 | 2014-07-10 17:00:00.0000000 +00:00 | 2014-07-10 00:00:00.0000000 +00:00 | 2014-07-10 17:00:00.0000000 +00:00 |  | 2014-07-25 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | [5 empty] | 2014-08-11 00:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2015-09-14 17:00:00.0000000 +00:00 | 2016-09-28 00:00:00.0000000 +00:00 | 2016-09-28 18:00:00.0000000 +00:00 | 2016-04-07 00:00:00.0000000 +00:00 | 2019-09-27 00:00:00.0000000 +00:00 |  | 2019-09-27 00:00:00.0000000 +00:00 | 2019-09-27 00:00:00.0000000 +00:00 |  | 2017-08-25 12:28:36.5919816 -04:00
HW349FED3 | Y | 2015-07-01 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2017-03-13 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 | 2015-07-01 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2017-03-13 00:00:00.0000000 +00:00 | 2019-12-07 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-01 18:00:00.0000000 +00:00 | 2015-07-15 18:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2017-03-13 08:00:00.0000000 +00:00 | 2017-12-01 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 | 2015-07-01 00:00:00.0000000 +00:00 | 2015-07-01 18:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-07-15 18:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2017-03-13 00:00:00.0000000 +00:00 | 2017-03-13 08:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 | 2020-12-06 00:00:00.0000000 +00:00 | 2020-12-06 00:00:00.0000000 +00:00 |  | 2020-12-06 00:00:00.0000000 +00:00 | 2020-12-06 00:00:00.0000000 +00:00 |  | 2017-12-01 16:10:57.5344230 -05:00
HWBARUCH | Y | 2013-07-30 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2020-03-13 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2018-01-14 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2017-04-01 00:00:00.0000000 +00:00 | 2018-10-01 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 |  |  | 2016-09-16 00:00:00.0000000 +00:00 |  | 2013-07-30 00:00:00.0000000 +00:00 |  | 2014-03-10 00:00:00.0000000 +00:00 |  |  | 2015-11-17 00:00:00.0000000 +00:00 | 2015-11-17 00:00:00.0000000 +00:00 | 2015-11-17 00:00:00.0000000 +00:00 | [6 empty] | 2016-09-16 00:00:00.0000000 +00:00 |  | 2018-01-15 00:00:00.0000000 +00:00 |  | 2020-01-14 00:00:00.0000000 +00:00 |  | 2021-01-13 00:00:00.0000000 +00:00 | 2023-03-13 00:00:00.0000000 +00:00 |  | 2023-01-13 00:00:00.0000000 +00:00 |  |  | 2017-10-20 11:37:23.4811299 -04:00
HWBUSPAD6 | Y | 2014-11-07 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 | 2019-06-06 00:00:00.0000000 +00:00 | 2014-11-07 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2017-03-01 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | [5 empty] | 2014-11-07 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 |  | 2016-11-30 00:00:00.0000000 +00:00 | 2019-04-16 00:00:00.0000000 +00:00 | 2014-11-07 00:00:00.0000000 +00:00 | 2014-11-07 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | [5 empty] | 2016-11-30 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-10-19 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 | 2019-04-16 00:00:00.0000000 +00:00 | 2019-06-06 00:00:00.0000000 +00:00 | 2020-02-29 00:00:00.0000000 +00:00 | 2022-04-16 00:00:00.0000000 +00:00 |  | 2022-04-16 00:00:00.0000000 +00:00 | 2022-04-16 00:00:00.0000000 +00:00 |  | 2017-10-30 11:09:08.6405728 -04:00
HWCBLSTN1 | Y | 2006-12-05 00:00:00.0000000 +00:00 | 2007-03-06 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2019-01-16 00:00:00.0000000 +00:00 | 2006-12-05 00:00:00.0000000 +00:00 | 2007-03-06 00:00:00.0000000 +00:00 | 2008-01-09 00:00:00.0000000 +00:00 | 2008-03-25 00:00:00.0000000 +00:00 | 2009-03-25 00:00:00.0000000 +00:00 | 2006-12-05 00:00:00.0000000 +00:00 | 2007-09-25 00:00:00.0000000 +00:00 | 2014-09-27 00:00:00.0000000 +00:00 | 2015-03-28 00:00:00.0000000 +00:00 | 2017-03-28 00:00:00.0000000 +00:00 | 2006-12-05 12:00:00.0000000 +00:00 | 2007-12-03 12:00:00.0000000 +00:00 |  |  |  | 2024-12-20 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-27 15:44:06.0703937 -04:00
HWCPEDLOC | Y | [47 empty] | 2017-12-01 13:00:19.9570000 +00:00
HWCSCH3A | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2009-08-22 00:00:00.0000000 +00:00 | 2010-02-23 00:00:00.0000000 +00:00 | 2011-05-17 00:00:00.0000000 +00:00 | 2012-06-23 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2009-06-01 00:00:00.0000000 +00:00 | 2010-01-16 00:00:00.0000000 +00:00 | 2010-07-16 00:00:00.0000000 +00:00 | 2011-07-15 00:00:00.0000000 +00:00 | [5 empty] | 2008-08-20 17:00:00.0000000 +00:00 | 2009-08-22 17:00:00.0000000 +00:00 | 2010-02-23 00:00:00.0000000 +00:00 | 2011-05-02 00:00:00.0000000 +00:00 | 2012-06-08 18:00:00.0000000 +00:00 | 2010-01-10 00:00:00.0000000 +00:00 | 2012-08-01 00:00:00.0000000 +00:00 |  | 2008-08-20 17:00:00.0000000 +00:00 |  | 2009-08-22 17:00:00.0000000 +00:00 | 2009-11-10 00:00:00.0000000 +00:00 | 2009-11-10 00:00:00.0000000 +00:00 | 2009-11-10 00:00:00.0000000 +00:00 |  | 2009-11-10 00:00:00.0000000 +00:00 | [6 empty] | 2010-02-23 00:00:00.0000000 +00:00 |  | 2011-05-02 00:00:00.0000000 +00:00 |  | 2012-06-08 18:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 |  |  | 2018-07-15 00:00:00.0000000 +00:00 |  | 2017-09-29 07:54:03.5425770 -04:00
HWCSCH3B2 | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2013-08-08 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-12 00:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2013-12-27 00:00:00.0000000 +00:00 | 2014-12-27 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2013-10-27 00:00:00.0000000 +00:00 | 2014-05-26 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-12 12:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 |  | 2013-09-19 00:00:00.0000000 +00:00 | 2016-07-24 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-12 12:00:00.0000000 +00:00 | 2010-04-12 12:00:00.0000000 +00:00 |  | 2013-01-04 00:00:00.0000000 +00:00 | 2013-01-04 00:00:00.0000000 +00:00 | 2013-01-04 00:00:00.0000000 +00:00 | 2013-01-04 00:00:00.0000000 +00:00 | [5 empty] | 2013-08-08 00:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2016-07-24 00:00:00.0000000 +00:00 | 2016-07-24 00:00:00.0000000 +00:00 | 2017-12-26 00:00:00.0000000 +00:00 | 2020-11-30 00:00:00.0000000 +00:00 |  | 2019-07-24 00:00:00.0000000 +00:00 | 2019-07-24 00:00:00.0000000 +00:00 |  | 2017-09-11 15:14:50.6572684 -04:00
HWCSCH3B3 | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2012-12-28 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2015-06-14 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2014-05-11 00:00:00.0000000 +00:00 | 2015-05-11 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-05-12 12:00:00.0000000 +00:00 | 2012-12-28 00:00:00.0000000 +00:00 | 2013-07-15 12:00:00.0000000 +00:00 | 2015-06-12 17:00:00.0000000 +00:00 | 2013-05-28 00:00:00.0000000 +00:00 | 2015-06-14 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2010-05-12 12:00:00.0000000 +00:00 | 2012-01-18 00:00:00.0000000 +00:00 | 2012-01-18 00:00:00.0000000 +00:00 | 2012-01-18 00:00:00.0000000 +00:00 | 2012-01-18 00:00:00.0000000 +00:00 | 2012-01-18 00:00:00.0000000 +00:00 | [5 empty] | 2012-12-28 00:00:00.0000000 +00:00 | 2012-12-28 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 12:00:00.0000000 +00:00 | 2015-06-14 00:00:00.0000000 +00:00 | 2015-06-12 17:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2018-06-14 00:00:00.0000000 +00:00 |  | 2018-06-14 00:00:00.0000000 +00:00 | 2018-06-14 00:00:00.0000000 +00:00
HWCSCH3E1 | Y | 2004-04-08 00:00:00.0000000 +00:00 | 2010-08-10 00:00:00.0000000 +00:00 | 2014-02-25 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 | 2016-01-19 00:00:00.0000000 +00:00 | 2004-04-08 00:00:00.0000000 +00:00 | 2010-08-12 00:00:00.0000000 +00:00 | 2011-10-13 00:00:00.0000000 +00:00 | 2012-06-27 00:00:00.0000000 +00:00 | 2013-06-26 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2014-12-24 00:00:00.0000000 +00:00 | 2017-07-08 00:00:00.0000000 +00:00 | 2018-02-05 00:00:00.0000000 +00:00 | 2019-07-27 00:00:00.0000000 +00:00 | 2004-04-08 12:00:00.0000000 +00:00 | 2010-08-10 00:00:00.0000000 +00:00 | 2014-02-25 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 | 2016-01-19 00:00:00.0000000 +00:00 | 2014-02-25 00:00:00.0000000 +00:00 | 2016-01-19 00:00:00.0000000 +00:00 | 2004-04-08 00:00:00.0000000 +00:00 | 2004-04-08 00:00:00.0000000 +00:00 | 2010-08-10 00:00:00.0000000 +00:00 | 2010-08-10 00:00:00.0000000 +00:00 | 2011-02-28 00:00:00.0000000 +00:00 | 2011-02-28 00:00:00.0000000 +00:00 | 2011-02-28 00:00:00.0000000 +00:00 | 2011-02-28 00:00:00.0000000 +00:00 | 2011-02-28 00:00:00.0000000 +00:00 | [5 empty] | 2014-02-25 00:00:00.0000000 +00:00 | 2014-02-25 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 | 2016-01-19 00:00:00.0000000 +00:00 | 2016-01-19 00:00:00.0000000 +00:00 | 2019-01-17 00:00:00.0000000 +00:00 | 2019-01-17 00:00:00.0000000 +00:00 |  | 2019-01-17 00:00:00.0000000 +00:00 | 2019-01-17 00:00:00.0000000 +00:00 |  | 2017-11-20 12:09:05.6097669 -05:00
HWCSCH3E-R | Y | 2012-10-12 00:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2013-01-31 00:00:00.0000000 +00:00 | 2014-12-21 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2012-10-13 00:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2013-01-31 00:00:00.0000000 +00:00 | 2013-08-06 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2012-10-12 00:00:00.0000000 +00:00 | 2012-10-16 00:00:00.0000000 +00:00 | 2013-02-16 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2012-10-13 12:00:00.0000000 +00:00 | 2012-10-17 12:00:00.0000000 +00:00 | 2013-01-31 00:00:00.0000000 +00:00 | 2014-04-14 18:00:00.0000000 +00:00 | 2016-06-30 18:00:00.0000000 +00:00 |  | 2016-06-30 00:00:00.0000000 +00:00 |  | 2012-10-13 12:00:00.0000000 +00:00 |  | 2012-10-17 12:00:00.0000000 +00:00 | 2012-11-25 00:00:00.0000000 +00:00 | 2012-11-25 00:00:00.0000000 +00:00 | 2012-11-25 00:00:00.0000000 +00:00 |  | 2012-11-25 00:00:00.0000000 +00:00 | [6 empty] | 2013-01-31 00:00:00.0000000 +00:00 |  | 2014-04-14 18:00:00.0000000 +00:00 |  | 2016-06-30 18:00:00.0000000 +00:00 | 2018-01-29 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 |  |  | 2019-06-30 00:00:00.0000000 +00:00
HWCSCH3F | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2013-10-28 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2016-05-09 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-27 00:00:00.0000000 +00:00 | 2013-10-28 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2016-05-09 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-27 00:00:00.0000000 +00:00 | 2014-04-26 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2026-05-29 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-27 00:00:00.0000000 +00:00 | 2013-10-28 00:00:00.0000000 +00:00 | 2015-05-04 18:00:00.0000000 +00:00 | 2016-05-09 17:00:00.0000000 +00:00 |  | 2016-05-09 00:00:00.0000000 +00:00 |  |  |  |  | 2012-10-28 00:00:00.0000000 +00:00 | 2012-10-28 00:00:00.0000000 +00:00 | 2012-10-28 00:00:00.0000000 +00:00 | [7 empty] | 2013-10-28 00:00:00.0000000 +00:00 |  | 2015-05-04 00:00:00.0000000 +00:00 |  | 2016-05-09 00:00:00.0000000 +00:00 |  | 2019-05-09 00:00:00.0000000 +00:00 | 2019-05-09 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-13 15:14:29.8426179 -04:00
HWCSCH3F1 | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-27 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2014-06-04 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-27 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | 2015-03-14 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-27 00:00:00.0000000 +00:00 | 2013-05-17 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-27 12:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-27 12:00:00.0000000 +00:00 | 2010-04-27 12:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | [5 empty] | 2013-11-06 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2014-06-04 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2018-03-13 00:00:00.0000000 +00:00 | 2020-06-29 00:00:00.0000000 +00:00 |  | 2020-06-29 00:00:00.0000000 +00:00 | 2020-06-29 00:00:00.0000000 +00:00
HWCSCH3G1 | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-30 00:00:00.0000000 +00:00 | 2014-06-17 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | 2016-12-02 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-30 00:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2013-12-27 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-30 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2014-12-27 00:00:00.0000000 +00:00 | 2015-12-26 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-30 12:00:00.0000000 +00:00 | 2014-06-17 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | 2016-12-02 00:00:00.0000000 +00:00 | 2014-06-17 00:00:00.0000000 +00:00 | 2016-12-02 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-30 12:00:00.0000000 +00:00 | 2010-04-30 12:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-17 00:00:00.0000000 +00:00 | 2014-06-17 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | 2016-12-02 00:00:00.0000000 +00:00 | 2016-12-02 00:00:00.0000000 +00:00 | 2017-12-25 00:00:00.0000000 +00:00 | 2019-12-01 00:00:00.0000000 +00:00 |  | 2019-12-01 00:00:00.0000000 +00:00 | 2019-12-02 00:00:00.0000000 +00:00
HWCSCH3G2 | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2017-12-06 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2013-12-28 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-04-16 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-09 12:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2017-10-06 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2017-12-06 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-16 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2017-12-06 00:00:00.0000000 +00:00 | 2017-12-06 00:00:00.0000000 +00:00 | 2020-12-05 00:00:00.0000000 +00:00 | 2020-12-05 00:00:00.0000000 +00:00 |  | 2020-12-05 00:00:00.0000000 +00:00 | 2020-12-05 00:00:00.0000000 +00:00 |  | 2017-11-21 12:12:35.9086527 -05:00
HWCSCH3G3 | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-24 00:00:00.0000000 +00:00 | 2012-08-14 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-24 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-16 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-24 00:00:00.0000000 +00:00 | 2012-11-20 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-24 17:00:00.0000000 +00:00 | 2012-08-14 00:00:00.0000000 +00:00 | 2013-12-16 17:00:00.0000000 +00:00 | 2014-12-08 17:00:00.0000000 +00:00 | 2012-08-14 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 |  | 2008-08-20 12:00:00.0000000 +00:00 |  | 2010-04-24 17:00:00.0000000 +00:00 | 2011-05-15 00:00:00.0000000 +00:00 | 2011-05-15 00:00:00.0000000 +00:00 | 2011-05-15 00:00:00.0000000 +00:00 |  | 2011-05-15 00:00:00.0000000 +00:00 | [6 empty] | 2012-08-14 00:00:00.0000000 +00:00 |  | 2013-12-16 17:00:00.0000000 +00:00 |  | 2014-12-08 17:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2017-12-08 00:00:00.0000000 +00:00 |  |  | 2017-12-08 00:00:00.0000000 +00:00
HWCSCH3H1 | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-13 00:00:00.0000000 +00:00 | 2014-11-30 00:00:00.0000000 +00:00 | 2015-05-31 00:00:00.0000000 +00:00 | 2016-05-29 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-13 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2013-07-17 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-04-13 00:00:00.0000000 +00:00 | 2014-11-30 00:00:00.0000000 +00:00 | 2015-05-31 00:00:00.0000000 +00:00 | 2016-05-29 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-04-13 12:00:00.0000000 +00:00 |  |  |  | 2016-10-13 00:00:00.0000000 +00:00 | 2016-05-29 00:00:00.0000000 +00:00
HWCSCH3H2 | Y | 2008-08-20 00:00:00.0000000 +00:00 | 2010-05-06 00:00:00.0000000 +00:00 | 2013-04-22 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 | 2015-06-19 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-05-06 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2010-05-06 00:00:00.0000000 +00:00 | 2013-04-22 00:00:00.0000000 +00:00 | 2013-10-20 00:00:00.0000000 +00:00 | 2014-10-20 00:00:00.0000000 +00:00 | 2008-08-20 12:00:00.0000000 +00:00 | 2010-05-06 12:00:00.0000000 +00:00 |  | 2014-03-24 08:00:00.0000000 +00:00 | 2015-06-19 17:00:00.0000000 +00:00 | 2013-07-28 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | [20 empty] | 2018-06-21 00:00:00.0000000 +00:00 | 2025-07-10 00:00:00.0000000 +00:00
HWCSCH3MM | Y | 2012-07-30 00:00:00.0000000 +00:00 | 2012-09-28 00:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2018-02-06 00:00:00.0000000 +00:00 | 2012-07-30 00:00:00.0000000 +00:00 | 2012-09-28 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2014-06-29 00:00:00.0000000 +00:00 | 2012-07-30 00:00:00.0000000 +00:00 | 2012-09-28 00:00:00.0000000 +00:00 | 2014-01-23 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2012-07-30 12:00:00.0000000 +00:00 | 2012-09-28 12:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 |  | 2015-03-18 00:00:00.0000000 +00:00 | 2018-02-06 00:00:00.0000000 +00:00 | 2012-07-30 00:00:00.0000000 +00:00 | 2012-07-30 00:00:00.0000000 +00:00 | 2012-09-28 00:00:00.0000000 +00:00 | 2012-09-28 00:00:00.0000000 +00:00 | 2012-10-22 00:00:00.0000000 +00:00 | 2013-01-01 00:00:00.0000000 +00:00 | 2013-01-01 00:00:00.0000000 +00:00 | 2013-01-01 00:00:00.0000000 +00:00 | 2013-01-01 00:00:00.0000000 +00:00 | [5 empty] | 2014-02-21 00:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2018-02-06 00:00:00.0000000 +00:00 | 2018-02-06 00:00:00.0000000 +00:00 | 2020-10-23 00:00:00.0000000 +00:00 | 2021-02-05 00:00:00.0000000 +00:00 |  | 2021-02-05 00:00:00.0000000 +00:00 | 2021-02-05 00:00:00.0000000 +00:00
HWCSCH4A | Y | 2013-06-19 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2015-08-16 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2015-08-16 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 |  | 2015-01-03 00:00:00.0000000 +00:00 | 2017-05-09 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 |  | 2013-11-07 00:00:00.0000000 +00:00 | 2013-11-07 00:00:00.0000000 +00:00 | 2013-11-07 00:00:00.0000000 +00:00 | 2013-11-07 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-09 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2015-07-25 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2016-11-13 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2021-04-29 00:00:00.0000000 +00:00 |  | 2020-01-20 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 |  | 2017-10-31 14:39:44.9540593 -04:00
HWCSCH4B1 | Y | 2013-09-19 00:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 | 2015-10-08 00:00:00.0000000 +00:00 | 2016-10-17 00:00:00.0000000 +00:00 | 2018-02-05 00:00:00.0000000 +00:00 | 2013-09-19 00:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2013-09-19 00:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2013-09-19 12:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 | 2015-10-08 00:00:00.0000000 +00:00 | 2016-10-17 00:00:00.0000000 +00:00 |  | 2016-07-15 00:00:00.0000000 +00:00 | 2017-10-19 00:00:00.0000000 +00:00 | 2013-09-19 00:00:00.0000000 +00:00 | 2013-09-19 12:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-08 00:00:00.0000000 +00:00 | 2015-10-08 00:00:00.0000000 +00:00 | 2016-10-17 00:00:00.0000000 +00:00 | 2016-10-17 00:00:00.0000000 +00:00 | 2018-02-05 00:00:00.0000000 +00:00 | 2018-02-05 00:00:00.0000000 +00:00 | 2020-10-15 00:00:00.0000000 +00:00 | 2021-02-04 00:00:00.0000000 +00:00 |  | 2021-02-04 00:00:00.0000000 +00:00 | 2021-02-04 00:00:00.0000000 +00:00
HWCSCH4B3 | Y | 2016-06-09 00:00:00.0000000 +00:00 | 2016-07-19 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-07-28 00:00:00.0000000 +00:00 | 2019-07-27 00:00:00.0000000 +00:00 | 2016-06-09 00:00:00.0000000 +00:00 | 2016-07-19 00:00:00.0000000 +00:00 | 2017-11-01 00:00:00.0000000 +00:00 | 2018-05-30 00:00:00.0000000 +00:00 | 2019-05-16 00:00:00.0000000 +00:00 | [5 empty] | 2016-06-09 18:00:00.0000000 +00:00 | 2016-07-19 17:00:00.0000000 +00:00 |  |  |  | 2017-12-30 00:00:00.0000000 +00:00 | 2019-07-27 00:00:00.0000000 +00:00 | 2016-06-09 18:00:00.0000000 +00:00 | 2016-06-09 00:00:00.0000000 +00:00 | 2016-07-19 17:00:00.0000000 +00:00 | 2016-07-19 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | 2017-01-23 00:00:00.0000000 +00:00 | 2017-01-23 00:00:00.0000000 +00:00 | 2017-01-23 00:00:00.0000000 +00:00 | 2017-01-23 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-30 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-07-28 00:00:00.0000000 +00:00 | 2018-07-28 00:00:00.0000000 +00:00 | 2019-07-27 00:00:00.0000000 +00:00 | 2019-07-27 00:00:00.0000000 +00:00 | 2022-07-26 00:00:00.0000000 +00:00 | 2022-07-26 00:00:00.0000000 +00:00 |  | 2022-07-26 00:00:00.0000000 +00:00 | 2022-07-26 00:00:00.0000000 +00:00
HWCSCH4C1 | Y | 2015-03-31 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2018-05-15 00:00:00.0000000 +00:00 | 2019-11-11 00:00:00.0000000 +00:00 | 2015-03-31 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2019-02-08 00:00:00.0000000 +00:00 | [5 empty] | 2015-03-31 17:00:00.0000000 +00:00 | 2015-05-06 17:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 |  |  | 2016-11-30 00:00:00.0000000 +00:00 | 2019-11-11 00:00:00.0000000 +00:00 | 2015-03-31 17:00:00.0000000 +00:00 |  | 2015-05-06 17:00:00.0000000 +00:00 |  | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | [6 empty] | 2016-11-30 00:00:00.0000000 +00:00 |  | 2018-05-15 00:00:00.0000000 +00:00 |  | 2019-11-11 00:00:00.0000000 +00:00 |  | 2022-02-06 00:00:00.0000000 +00:00 | 2022-11-11 00:00:00.0000000 +00:00 |  | 2022-11-11 00:00:00.0000000 +00:00 |  |  | 2017-09-05 08:50:30.0968094 -04:00
HWCSCH4C2 | Y | 2015-05-26 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-10-27 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2019-09-04 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-11-10 00:00:00.0000000 +00:00 | 2017-05-10 00:00:00.0000000 +00:00 | 2018-05-09 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-26 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-10-27 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 |  | 2016-10-27 00:00:00.0000000 +00:00 | 2019-09-04 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 |  |  | 2015-09-18 00:00:00.0000000 +00:00 | 2015-09-18 00:00:00.0000000 +00:00 | 2015-09-18 00:00:00.0000000 +00:00 | [5 empty] | 2016-10-27 00:00:00.0000000 +00:00 | 2016-10-27 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2019-09-04 00:00:00.0000000 +00:00 | 2019-09-04 00:00:00.0000000 +00:00 | 2020-05-09 00:00:00.0000000 +00:00 | 2022-09-04 00:00:00.0000000 +00:00 |  | 2022-09-04 00:00:00.0000000 +00:00 | 2022-09-04 00:00:00.0000000 +00:00 |  | 2017-10-12 10:20:32.8564233 -04:00
HWCSCHPBX | Y | 2017-05-31 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2019-05-09 00:00:00.0000000 +00:00 | 2019-09-16 00:00:00.0000000 +00:00 | 2021-03-14 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2019-05-09 00:00:00.0000000 +00:00 | 2019-09-16 00:00:00.0000000 +00:00 | 2021-03-14 00:00:00.0000000 +00:00 | [5 empty] | 2017-05-31 00:00:00.0000000 +00:00 | [10 empty] | 2018-12-21 00:00:00.0000000 +00:00 | 2018-12-21 00:00:00.0000000 +00:00 | [14 empty] | 2024-03-13 00:00:00.0000000 +00:00 | 2024-03-13 00:00:00.0000000 +00:00
HWCSCHPKR | Y | [47 empty] | 2017-10-30 07:00:23.0370000 +00:00
HWCSCHPQN | Y | 2018-02-01 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2021-02-15 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 | 2023-09-14 00:00:00.0000000 +00:00 | 2018-02-01 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2021-02-15 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 | 2023-09-14 00:00:00.0000000 +00:00 | [16 empty] | 2020-02-17 00:00:00.0000000 +00:00 | 2019-02-17 00:00:00.0000000 +00:00 | [14 empty] | 2026-09-13 00:00:00.0000000 +00:00 | 2026-09-13 00:00:00.0000000 +00:00 |  |  |  | 2017-10-30 07:00:24.5200000 +00:00 | 2017-10-31 13:11:50.7338502 -04:00
HWCURB09 | Y | 2017-03-15 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2017-05-25 00:00:00.0000000 +00:00 | 2018-03-27 00:00:00.0000000 +00:00 | 2019-05-25 00:00:00.0000000 +00:00 | 2017-03-15 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2017-05-19 00:00:00.0000000 +00:00 | 2017-11-21 00:00:00.0000000 +00:00 | 2018-09-06 00:00:00.0000000 +00:00 | [5 empty] | 2017-03-15 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2017-05-25 00:00:00.0000000 +00:00 |  |  | 2017-05-25 00:00:00.0000000 +00:00 |  | 2017-03-15 00:00:00.0000000 +00:00 |  | 2017-03-27 00:00:00.0000000 +00:00 |  | 2017-04-19 00:00:00.0000000 +00:00 | 2017-04-25 00:00:00.0000000 +00:00 | 2017-04-25 00:00:00.0000000 +00:00 | 2017-04-19 00:00:00.0000000 +00:00 | [6 empty] | 2017-05-19 00:00:00.0000000 +00:00 |  | 2017-11-21 00:00:00.0000000 +00:00 |  | 2018-09-06 00:00:00.0000000 +00:00 |  | 2021-09-05 00:00:00.0000000 +00:00 | 2022-10-20 00:00:00.0000000 +00:00 |  | 2021-09-05 00:00:00.0000000 +00:00 |  |  | 2017-08-31 15:29:01.2627227 -04:00
HWD005K01 | Y | 2011-11-08 00:00:00.0000000 +00:00 | 2013-03-26 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2017-06-24 00:00:00.0000000 +00:00 | 2011-11-08 00:00:00.0000000 +00:00 | 2012-12-27 00:00:00.0000000 +00:00 | 2013-12-25 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2015-07-16 00:00:00.0000000 +00:00 | 2011-11-08 00:00:00.0000000 +00:00 | 2013-02-21 00:00:00.0000000 +00:00 | 2014-10-06 00:00:00.0000000 +00:00 | 2016-01-29 00:00:00.0000000 +00:00 | 2017-01-28 00:00:00.0000000 +00:00 | 2011-11-08 00:00:00.0000000 +00:00 | 2013-03-26 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2016-05-31 18:00:00.0000000 +00:00 | 2017-06-24 00:00:00.0000000 +00:00 | 2014-11-09 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2011-11-08 00:00:00.0000000 +00:00 | 2011-11-08 00:00:00.0000000 +00:00 | 2013-03-26 00:00:00.0000000 +00:00 | 2013-03-26 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-26 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2017-06-24 00:00:00.0000000 +00:00 | 2017-06-24 00:00:00.0000000 +00:00 | 2020-06-23 00:00:00.0000000 +00:00 | 2020-06-23 00:00:00.0000000 +00:00 |  | 2020-06-23 00:00:00.0000000 +00:00 | 2020-06-23 00:00:00.0000000 +00:00
HWD10105 | Y | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-19 00:00:00.0000000 +00:00 | 2016-12-23 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 | 2019-09-24 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-19 00:00:00.0000000 +00:00 | 2017-02-28 00:00:00.0000000 +00:00 | 2017-10-09 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-02-05 17:00:00.0000000 +00:00 | 2015-02-19 17:00:00.0000000 +00:00 | 2016-12-23 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 |  | 2017-06-20 00:00:00.0000000 +00:00 | 2019-09-24 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-05 17:00:00.0000000 +00:00 | 2015-02-19 00:00:00.0000000 +00:00 | 2015-02-19 17:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-23 00:00:00.0000000 +00:00 | 2016-12-23 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 | 2019-09-24 00:00:00.0000000 +00:00 | 2019-09-24 00:00:00.0000000 +00:00 | 2020-09-23 00:00:00.0000000 +00:00 | 2020-09-23 00:00:00.0000000 +00:00 |  | 2020-09-23 00:00:00.0000000 +00:00 | 2020-09-23 00:00:00.0000000 +00:00 |  | 2017-11-27 10:52:15.5672491 -05:00
HWD10105A | Y | 2015-07-06 00:00:00.0000000 +00:00 | 2016-08-04 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2020-01-11 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-06 17:00:00.0000000 +00:00 | 2016-08-04 18:00:00.0000000 +00:00 |  |  |  | 2018-11-24 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 | 2015-07-06 17:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2016-08-04 18:00:00.0000000 +00:00 | 2016-08-04 00:00:00.0000000 +00:00 | 2017-01-17 00:00:00.0000000 +00:00 | 2018-01-17 00:00:00.0000000 +00:00 |  | 2018-01-17 00:00:00.0000000 +00:00 | 2018-01-17 00:00:00.0000000 +00:00 | [5 empty] | 2018-10-30 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 | 2024-06-29 00:00:00.0000000 +00:00 | 2024-06-29 00:00:00.0000000 +00:00 |  | 2024-06-29 00:00:00.0000000 +00:00 | 2024-06-29 00:00:00.0000000 +00:00 |  | 2017-09-01 11:40:49.2684614 -04:00
HWD10211 | Y | 2011-10-14 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2017-12-18 00:00:00.0000000 +00:00 | 2011-10-14 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2013-04-17 00:00:00.0000000 +00:00 | 2013-12-13 00:00:00.0000000 +00:00 | 2014-12-13 00:00:00.0000000 +00:00 | 2011-10-14 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2016-02-22 00:00:00.0000000 +00:00 | 2016-08-26 00:00:00.0000000 +00:00 | 2011-10-14 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 |  | 2014-12-30 00:00:00.0000000 +00:00 | 2017-06-24 00:00:00.0000000 +00:00 | 2011-10-14 00:00:00.0000000 +00:00 | 2011-10-14 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 |  | 2014-01-07 00:00:00.0000000 +00:00 | 2014-01-07 00:00:00.0000000 +00:00 | 2014-01-07 00:00:00.0000000 +00:00 | 2014-01-07 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-30 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2015-07-11 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2017-06-24 00:00:00.0000000 +00:00 | 2017-12-13 00:00:00.0000000 +00:00 | 2020-12-18 00:00:00.0000000 +00:00 |  | 2019-03-07 00:00:00.0000000 +00:00 | 2020-06-24 00:00:00.0000000 +00:00 |  | 2017-10-19 16:08:43.5512204 -04:00
HWD104-05 | Y | 2009-11-16 00:00:00.0000000 +00:00 | 2012-08-13 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2009-11-16 00:00:00.0000000 +00:00 | 2010-01-04 00:00:00.0000000 +00:00 | 2011-12-24 00:00:00.0000000 +00:00 | 2012-08-06 00:00:00.0000000 +00:00 | 2013-07-01 00:00:00.0000000 +00:00 | 2009-11-16 00:00:00.0000000 +00:00 | 2011-04-15 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2014-10-10 00:00:00.0000000 +00:00 | 2009-11-16 12:00:00.0000000 +00:00 | 2012-08-13 18:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2016-11-14 17:00:00.0000000 +00:00 | 2017-06-30 17:00:00.0000000 +00:00 |  | 2017-06-30 00:00:00.0000000 +00:00 |  | 2009-11-16 12:00:00.0000000 +00:00 |  | 2012-08-13 18:00:00.0000000 +00:00 |  | 2014-12-12 00:00:00.0000000 +00:00 | 2014-12-12 00:00:00.0000000 +00:00 |  | 2014-12-12 00:00:00.0000000 +00:00 | [6 empty] | 2015-06-03 00:00:00.0000000 +00:00 |  | 2016-11-14 17:00:00.0000000 +00:00 |  | 2017-06-30 17:00:00.0000000 +00:00 | 2020-05-29 00:00:00.0000000 +00:00 | 2018-06-22 00:00:00.0000000 +00:00 |  |  | 2018-06-22 00:00:00.0000000 +00:00 |  | 2017-08-29 11:30:53.7700266 -04:00
HWD10501A-R | Y | 2007-07-12 00:00:00.0000000 +00:00 | 2009-06-09 00:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2013-09-03 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2007-07-12 00:00:00.0000000 +00:00 | 2009-06-09 00:00:00.0000000 +00:00 | 2012-06-26 00:00:00.0000000 +00:00 | 2012-11-11 00:00:00.0000000 +00:00 | 2013-08-07 00:00:00.0000000 +00:00 | 2007-07-12 00:00:00.0000000 +00:00 | 2009-06-09 00:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2013-06-18 00:00:00.0000000 +00:00 | 2014-03-30 00:00:00.0000000 +00:00 | 2007-07-12 12:00:00.0000000 +00:00 | 2009-06-09 12:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2013-09-03 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2013-02-28 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2007-07-12 12:00:00.0000000 +00:00 | 2007-07-12 12:00:00.0000000 +00:00 | 2009-06-09 12:00:00.0000000 +00:00 | 2009-06-09 12:00:00.0000000 +00:00 | 2010-08-13 00:00:00.0000000 +00:00 | 2010-12-17 00:00:00.0000000 +00:00 | 2010-12-17 00:00:00.0000000 +00:00 | 2010-12-17 00:00:00.0000000 +00:00 | 2010-12-17 00:00:00.0000000 +00:00 | [5 empty] | 2013-02-08 00:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2013-09-03 00:00:00.0000000 +00:00 | 2013-09-03 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-08-06 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 |  | 2018-06-29 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00
HWD105-03 | Y | 2010-10-26 00:00:00.0000000 +00:00 | 2011-11-15 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2018-10-18 00:00:00.0000000 +00:00 | 2020-10-17 00:00:00.0000000 +00:00 | 2010-10-26 00:00:00.0000000 +00:00 | 2011-02-24 00:00:00.0000000 +00:00 | 2012-01-16 00:00:00.0000000 +00:00 | 2012-07-31 00:00:00.0000000 +00:00 | 2013-08-01 00:00:00.0000000 +00:00 | 2010-10-26 00:00:00.0000000 +00:00 | 2011-05-23 00:00:00.0000000 +00:00 | 2016-03-25 00:00:00.0000000 +00:00 | 2016-10-08 00:00:00.0000000 +00:00 | 2017-10-09 00:00:00.0000000 +00:00 | 2010-10-26 00:00:00.0000000 +00:00 | 2011-11-15 00:00:00.0000000 +00:00 |  |  |  | 2018-03-30 00:00:00.0000000 +00:00 |  | 2010-10-26 00:00:00.0000000 +00:00 |  | 2011-11-15 00:00:00.0000000 +00:00 |  | 2011-11-18 00:00:00.0000000 +00:00 | 2014-04-01 00:00:00.0000000 +00:00 | 2014-04-01 00:00:00.0000000 +00:00 | 2014-04-01 00:00:00.0000000 +00:00 | [6 empty] | 2018-03-30 00:00:00.0000000 +00:00 |  | 2018-10-18 00:00:00.0000000 +00:00 |  | 2020-10-17 00:00:00.0000000 +00:00 |  | 2016-07-31 00:00:00.0000000 +00:00 | 2023-10-17 00:00:00.0000000 +00:00 |  | 2023-10-17 00:00:00.0000000 +00:00
HWHARPER | Y | 2015-07-17 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2019-04-30 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2021-05-03 00:00:00.0000000 +00:00 | 2015-07-17 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2018-07-31 00:00:00.0000000 +00:00 | 2020-07-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-17 18:00:00.0000000 +00:00 | [10 empty] | 2017-10-13 00:00:00.0000000 +00:00 | 2018-08-30 00:00:00.0000000 +00:00 |  |  |  | 2018-02-13 00:00:00.0000000 +00:00 | 2019-01-04 00:00:00.0000000 +00:00 | [9 empty] | 2021-08-02 00:00:00.0000000 +00:00 | 2022-05-03 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-13 09:59:13.0604601 -04:00
HWK100BUS | Y | 2014-04-08 00:00:00.0000000 +00:00 | 2014-10-21 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2019-12-02 00:00:00.0000000 +00:00 | 2014-04-08 00:00:00.0000000 +00:00 | 2014-10-21 00:00:00.0000000 +00:00 | 2016-03-15 00:00:00.0000000 +00:00 | 2016-09-12 00:00:00.0000000 +00:00 | 2018-09-13 00:00:00.0000000 +00:00 | [5 empty] | 2014-04-08 17:00:00.0000000 +00:00 | 2014-10-21 17:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-06-05 17:00:00.0000000 +00:00 |  | 2016-06-30 00:00:00.0000000 +00:00 | 2019-12-02 00:00:00.0000000 +00:00 | 2014-04-08 00:00:00.0000000 +00:00 | 2014-04-08 17:00:00.0000000 +00:00 | 2014-10-21 00:00:00.0000000 +00:00 | 2014-10-21 17:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-03-11 00:00:00.0000000 +00:00 | 2016-03-11 00:00:00.0000000 +00:00 | 2016-03-11 00:00:00.0000000 +00:00 | 2016-03-11 00:00:00.0000000 +00:00 | [5 empty] | 2016-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2017-06-05 17:00:00.0000000 +00:00 | 2019-12-02 00:00:00.0000000 +00:00 | 2019-12-02 00:00:00.0000000 +00:00 | 2022-12-01 00:00:00.0000000 +00:00 | 2022-12-01 00:00:00.0000000 +00:00 |  | 2022-12-01 00:00:00.0000000 +00:00 | 2022-12-01 00:00:00.0000000 +00:00
HWK1048A | Y | 2010-09-21 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2014-07-24 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2010-09-21 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2012-01-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2010-09-21 00:00:00.0000000 +00:00 | 2011-06-10 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-04-15 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2010-09-21 12:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2014-07-24 00:00:00.0000000 +00:00 | 2015-11-02 17:00:00.0000000 +00:00 |  | 2017-02-04 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2010-09-21 00:00:00.0000000 +00:00 | 2010-09-21 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-10-17 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | [5 empty] | 2014-07-24 00:00:00.0000000 +00:00 | 2014-07-24 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2021-08-26 00:00:00.0000000 +00:00 | 2021-08-26 00:00:00.0000000 +00:00 |  | 2021-08-26 00:00:00.0000000 +00:00 | 2021-08-26 00:00:00.0000000 +00:00
HWK1048B | Y | 2011-04-28 00:00:00.0000000 +00:00 | 2012-03-13 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2015-08-10 00:00:00.0000000 +00:00 | 2019-03-31 00:00:00.0000000 +00:00 | 2011-04-28 00:00:00.0000000 +00:00 | 2012-01-24 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-06-16 00:00:00.0000000 +00:00 | 2014-06-12 00:00:00.0000000 +00:00 | 2011-04-28 00:00:00.0000000 +00:00 | 2012-01-23 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-03-16 00:00:00.0000000 +00:00 | 2015-03-12 00:00:00.0000000 +00:00 | 2011-04-28 00:00:00.0000000 +00:00 | 2012-03-13 00:00:00.0000000 +00:00 | 2014-10-28 00:00:00.0000000 +00:00 | 2015-08-10 00:00:00.0000000 +00:00 |  | 2014-02-06 00:00:00.0000000 +00:00 | 2019-03-31 00:00:00.0000000 +00:00 | 2011-04-28 00:00:00.0000000 +00:00 | 2011-04-28 00:00:00.0000000 +00:00 | 2012-03-13 00:00:00.0000000 +00:00 | 2012-03-13 00:00:00.0000000 +00:00 | 2012-11-21 00:00:00.0000000 +00:00 | 2014-04-21 00:00:00.0000000 +00:00 | 2014-04-21 00:00:00.0000000 +00:00 | 2014-04-21 00:00:00.0000000 +00:00 | 2014-04-21 00:00:00.0000000 +00:00 | [5 empty] | 2014-10-28 00:00:00.0000000 +00:00 | 2014-10-28 00:00:00.0000000 +00:00 | 2015-08-10 00:00:00.0000000 +00:00 | 2015-08-10 00:00:00.0000000 +00:00 | 2019-03-31 00:00:00.0000000 +00:00 | 2019-03-31 00:00:00.0000000 +00:00 | 2022-03-30 00:00:00.0000000 +00:00 | 2022-03-30 00:00:00.0000000 +00:00 |  | 2022-03-30 00:00:00.0000000 +00:00 | 2022-03-30 00:00:00.0000000 +00:00
HWK1048C | Y | 2013-08-08 00:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2018-05-15 00:00:00.0000000 +00:00 | 2020-05-14 00:00:00.0000000 +00:00 | 2013-08-08 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2019-07-16 00:00:00.0000000 +00:00 | 2013-08-08 00:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2015-02-14 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2016-09-29 00:00:00.0000000 +00:00 | 2013-08-08 00:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 |  |  | 2017-06-13 00:00:00.0000000 +00:00 | 2020-05-14 00:00:00.0000000 +00:00 | 2013-08-08 00:00:00.0000000 +00:00 | 2013-08-08 00:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | 2016-06-06 00:00:00.0000000 +00:00 | [5 empty] | 2017-06-13 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2018-05-15 00:00:00.0000000 +00:00 | 2018-05-15 00:00:00.0000000 +00:00 | 2020-05-14 00:00:00.0000000 +00:00 | 2020-05-14 00:00:00.0000000 +00:00 | 2023-04-13 00:00:00.0000000 +00:00 | 2023-05-13 00:00:00.0000000 +00:00 |  | 2023-05-13 00:00:00.0000000 +00:00 | 2023-05-13 00:00:00.0000000 +00:00
HWK1048D | Y | 2014-02-12 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2014-02-12 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-03-17 00:00:00.0000000 +00:00 | 2019-01-18 00:00:00.0000000 +00:00 | [5 empty] | 2014-02-12 17:00:00.0000000 +00:00 | 2015-05-26 17:00:00.0000000 +00:00 |  |  |  | 2018-11-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2014-02-12 17:00:00.0000000 +00:00 | 2014-02-12 00:00:00.0000000 +00:00 | 2015-05-26 17:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2015-12-29 00:00:00.0000000 +00:00 | 2018-05-25 00:00:00.0000000 +00:00 |  | 2018-05-25 00:00:00.0000000 +00:00 | 2018-05-25 00:00:00.0000000 +00:00 | [5 empty] | 2018-11-30 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2017-09-18 10:39:49.2283046 -04:00
HWK1048G | Y | 2013-08-07 00:00:00.0000000 +00:00 | 2013-08-27 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 | 2019-09-24 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2012-05-31 00:00:00.0000000 +00:00 | 2014-05-31 00:00:00.0000000 +00:00 | 2015-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2013-08-07 00:00:00.0000000 +00:00 | 2013-08-27 00:00:00.0000000 +00:00 | 2017-01-28 00:00:00.0000000 +00:00 | 2017-10-13 00:00:00.0000000 +00:00 | 2019-10-12 00:00:00.0000000 +00:00 | 2013-08-07 00:00:00.0000000 +00:00 | 2013-08-27 18:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 |  | 2016-11-30 00:00:00.0000000 +00:00 | 2019-09-24 00:00:00.0000000 +00:00 | 2013-08-07 00:00:00.0000000 +00:00 | 2013-08-07 00:00:00.0000000 +00:00 | 2013-08-27 18:00:00.0000000 +00:00 | 2013-08-27 18:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | [5 empty] | 2016-11-30 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 | 2019-09-24 00:00:00.0000000 +00:00 | 2019-09-24 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2017-08-29 11:53:44.1143390 -04:00
HWK1130B | Y | 2012-02-27 00:00:00.0000000 +00:00 | 2013-04-17 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2016-03-18 00:00:00.0000000 +00:00 | 2012-02-27 00:00:00.0000000 +00:00 | 2012-10-24 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-16 00:00:00.0000000 +00:00 | 2012-02-27 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2014-12-23 00:00:00.0000000 +00:00 | 2015-12-22 00:00:00.0000000 +00:00 | 2012-02-27 12:00:00.0000000 +00:00 | 2013-04-17 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2016-03-18 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2012-02-27 00:00:00.0000000 +00:00 | 2012-02-27 00:00:00.0000000 +00:00 | 2013-04-17 00:00:00.0000000 +00:00 | 2013-04-17 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | [5 empty] | 2014-02-28 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2016-03-18 00:00:00.0000000 +00:00 | 2016-03-18 00:00:00.0000000 +00:00 | 2019-03-12 00:00:00.0000000 +00:00 | 2019-03-12 00:00:00.0000000 +00:00 |  | 2019-03-12 00:00:00.0000000 +00:00 | 2019-03-12 00:00:00.0000000 +00:00
HWK1173A | Y | 2006-01-03 00:00:00.0000000 +00:00 | 2021-01-01 00:00:00.0000000 +00:00 | 2023-11-15 00:00:00.0000000 +00:00 | 2024-07-15 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 | 2006-01-03 00:00:00.0000000 +00:00 | 2007-03-01 00:00:00.0000000 +00:00 | 2009-01-15 00:00:00.0000000 +00:00 | 2009-07-15 00:00:00.0000000 +00:00 | 2010-07-14 00:00:00.0000000 +00:00 | 2006-01-03 00:00:00.0000000 +00:00 | 2019-09-13 00:00:00.0000000 +00:00 | 2023-07-30 00:00:00.0000000 +00:00 | 2024-01-27 00:00:00.0000000 +00:00 | 2025-01-25 00:00:00.0000000 +00:00 | 2006-01-03 12:00:00.0000000 +00:00 |  |  |  |  | 2023-11-15 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 | 2006-01-03 00:00:00.0000000 +00:00 | 2006-01-03 00:00:00.0000000 +00:00 | 2021-01-01 00:00:00.0000000 +00:00 | 2021-01-01 00:00:00.0000000 +00:00 | 2008-03-03 00:00:00.0000000 +00:00 | 2022-12-15 00:00:00.0000000 +00:00 |  | 2022-12-15 00:00:00.0000000 +00:00 | 2022-12-15 00:00:00.0000000 +00:00 | [5 empty] | 2023-11-15 00:00:00.0000000 +00:00 | 2023-11-15 00:00:00.0000000 +00:00 | 2024-07-15 00:00:00.0000000 +00:00 | 2024-07-15 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 | 2030-07-13 00:00:00.0000000 +00:00 | 2030-07-13 00:00:00.0000000 +00:00 |  | 2030-07-13 00:00:00.0000000 +00:00 | 2030-07-13 00:00:00.0000000 +00:00
HWK1173B | Y | 2006-01-03 00:00:00.0000000 +00:00 | 2022-07-04 00:00:00.0000000 +00:00 | 2023-11-30 00:00:00.0000000 +00:00 | 2024-07-15 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 | 2006-01-03 00:00:00.0000000 +00:00 | 2008-01-15 00:00:00.0000000 +00:00 | 2010-01-15 00:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 | 2006-01-03 00:00:00.0000000 +00:00 | 2022-02-01 00:00:00.0000000 +00:00 | 2025-08-03 00:00:00.0000000 +00:00 | 2026-01-31 00:00:00.0000000 +00:00 | 2028-02-01 00:00:00.0000000 +00:00 | 2006-01-03 12:00:00.0000000 +00:00 |  |  |  |  | 2023-11-30 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 | 2006-01-03 00:00:00.0000000 +00:00 | 2006-01-03 00:00:00.0000000 +00:00 | 2022-07-04 00:00:00.0000000 +00:00 | 2022-07-04 00:00:00.0000000 +00:00 | 2009-01-12 00:00:00.0000000 +00:00 | 2022-12-15 00:00:00.0000000 +00:00 |  | 2022-12-15 00:00:00.0000000 +00:00 | 2022-12-15 00:00:00.0000000 +00:00 | [5 empty] | 2023-11-30 00:00:00.0000000 +00:00 | 2023-11-30 00:00:00.0000000 +00:00 | 2024-07-15 00:00:00.0000000 +00:00 | 2024-07-15 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 | 2030-07-13 00:00:00.0000000 +00:00 | 2030-07-13 00:00:00.0000000 +00:00 |  | 2030-07-13 00:00:00.0000000 +00:00 | 2030-07-13 00:00:00.0000000 +00:00
HWK1310 | Y | 2012-01-13 00:00:00.0000000 +00:00 | 2012-10-10 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2012-01-13 00:00:00.0000000 +00:00 | 2012-10-10 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2012-01-13 00:00:00.0000000 +00:00 | 2012-07-25 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2014-06-05 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2012-01-13 12:00:00.0000000 +00:00 | 2012-10-10 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2016-09-23 18:00:00.0000000 +00:00 | 2014-03-16 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 | 2012-01-13 00:00:00.0000000 +00:00 | 2012-01-13 00:00:00.0000000 +00:00 | 2012-10-10 00:00:00.0000000 +00:00 | 2012-10-10 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-01-15 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2019-07-22 00:00:00.0000000 +00:00 | 2019-07-22 00:00:00.0000000 +00:00 |  | 2019-07-22 00:00:00.0000000 +00:00 | 2019-07-22 00:00:00.0000000 +00:00
HWK1668 | Y | 2007-08-07 00:00:00.0000000 +00:00 | 2020-01-16 00:00:00.0000000 +00:00 | 2023-10-17 00:00:00.0000000 +00:00 | 2024-07-15 00:00:00.0000000 +00:00 | 2026-07-14 00:00:00.0000000 +00:00 | 2007-08-07 00:00:00.0000000 +00:00 | 2009-04-15 00:00:00.0000000 +00:00 | 2011-01-15 00:00:00.0000000 +00:00 | 2011-07-16 00:00:00.0000000 +00:00 | 2012-07-14 00:00:00.0000000 +00:00 | 2007-08-07 00:00:00.0000000 +00:00 | 2019-10-17 00:00:00.0000000 +00:00 | 2021-07-18 00:00:00.0000000 +00:00 | 2024-01-16 00:00:00.0000000 +00:00 | 2025-01-14 00:00:00.0000000 +00:00 | 2007-08-07 12:00:00.0000000 +00:00 |  |  |  |  | 2023-10-17 00:00:00.0000000 +00:00 | 2026-07-14 00:00:00.0000000 +00:00 | 2007-08-07 00:00:00.0000000 +00:00 | 2007-08-07 00:00:00.0000000 +00:00 | 2020-01-16 00:00:00.0000000 +00:00 | 2020-01-16 00:00:00.0000000 +00:00 | 2009-11-30 00:00:00.0000000 +00:00 | 2022-05-16 00:00:00.0000000 +00:00 |  | 2022-05-16 00:00:00.0000000 +00:00 | 2022-05-16 00:00:00.0000000 +00:00 | [5 empty] | 2023-10-17 00:00:00.0000000 +00:00 | 2023-10-17 00:00:00.0000000 +00:00 | 2024-07-15 00:00:00.0000000 +00:00 | 2024-07-15 00:00:00.0000000 +00:00 | 2026-07-14 00:00:00.0000000 +00:00 | 2026-07-14 00:00:00.0000000 +00:00 | 2029-07-13 00:00:00.0000000 +00:00 | 2029-07-13 00:00:00.0000000 +00:00 |  | 2029-07-13 00:00:00.0000000 +00:00 | 2029-07-13 00:00:00.0000000 +00:00
HWK1669 | Y | 2014-09-22 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2019-04-15 00:00:00.0000000 +00:00 | 2021-04-05 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-05-19 00:00:00.0000000 +00:00 | 2019-05-10 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-22 17:00:00.0000000 +00:00 | 2014-12-30 17:00:00.0000000 +00:00 |  |  |  | 2018-07-15 00:00:00.0000000 +00:00 | [21 empty] | 2020-05-10 00:00:00.0000000 +00:00 | 2022-04-06 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-29 12:02:10.7333727 -04:00
HWK1669A | Y | 2015-06-24 00:00:00.0000000 +00:00 | 2016-07-14 00:00:00.0000000 +00:00 | 2018-11-12 00:00:00.0000000 +00:00 | 2019-07-29 00:00:00.0000000 +00:00 | 2021-07-28 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2017-11-24 00:00:00.0000000 +00:00 | 2018-07-10 00:00:00.0000000 +00:00 | 2020-07-10 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-24 00:00:00.0000000 +00:00 | 2016-07-14 18:00:00.0000000 +00:00 |  |  |  | 2018-11-12 00:00:00.0000000 +00:00 | 2021-07-28 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2016-07-14 00:00:00.0000000 +00:00 | 2016-07-14 00:00:00.0000000 +00:00 | 2016-12-12 00:00:00.0000000 +00:00 | 2018-03-01 00:00:00.0000000 +00:00 |  | 2018-03-01 00:00:00.0000000 +00:00 | 2018-03-01 00:00:00.0000000 +00:00 | [5 empty] | 2018-11-12 00:00:00.0000000 +00:00 | 2018-11-12 00:00:00.0000000 +00:00 | 2019-07-29 00:00:00.0000000 +00:00 | 2019-07-29 00:00:00.0000000 +00:00 | 2021-07-28 00:00:00.0000000 +00:00 | 2021-07-28 00:00:00.0000000 +00:00 | 2023-07-27 00:00:00.0000000 +00:00 | 2023-07-27 00:00:00.0000000 +00:00 |  | 2023-07-27 00:00:00.0000000 +00:00 | 2023-07-27 00:00:00.0000000 +00:00 |  | 2017-08-30 14:34:30.9379529 -04:00
HWK1670 | Y | 2016-01-14 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2019-07-28 00:00:00.0000000 +00:00 | 2020-07-27 00:00:00.0000000 +00:00 | 2016-01-14 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2017-06-27 00:00:00.0000000 +00:00 | 2018-02-22 00:00:00.0000000 +00:00 | 2019-02-22 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-14 17:00:00.0000000 +00:00 | 2016-04-15 18:00:00.0000000 +00:00 |  |  |  | 2018-11-30 00:00:00.0000000 +00:00 | 2020-07-27 00:00:00.0000000 +00:00 | 2016-01-14 17:00:00.0000000 +00:00 | 2016-01-14 00:00:00.0000000 +00:00 | 2016-04-15 18:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-10-17 00:00:00.0000000 +00:00 | 2017-04-21 00:00:00.0000000 +00:00 | 2017-04-21 00:00:00.0000000 +00:00 | 2017-04-21 00:00:00.0000000 +00:00 | 2017-04-21 00:00:00.0000000 +00:00 | [5 empty] | 2018-11-30 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2019-07-28 00:00:00.0000000 +00:00 | 2019-07-28 00:00:00.0000000 +00:00 | 2020-07-27 00:00:00.0000000 +00:00 | 2020-07-27 00:00:00.0000000 +00:00 | 2023-07-26 00:00:00.0000000 +00:00 | 2023-07-26 00:00:00.0000000 +00:00 |  | 2023-07-26 00:00:00.0000000 +00:00 | 2023-07-26 00:00:00.0000000 +00:00 |  | 2017-08-30 14:34:46.3735521 -04:00
HWK1672 | Y | [47 empty] | 2017-10-04 07:00:20.0170000 +00:00
HWK2013GB | Y | 2014-04-09 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2019-08-20 00:00:00.0000000 +00:00 | 2021-08-19 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2016-12-16 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | 2019-07-02 00:00:00.0000000 +00:00 | [5 empty] | 2014-04-09 17:00:00.0000000 +00:00 | 2014-11-14 17:00:00.0000000 +00:00 |  |  |  | 2018-11-30 00:00:00.0000000 +00:00 | 2021-08-19 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2015-10-12 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 |  | 2018-01-15 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2018-11-30 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2019-08-20 00:00:00.0000000 +00:00 | 2019-08-20 00:00:00.0000000 +00:00 | 2021-08-19 00:00:00.0000000 +00:00 | 2021-08-19 00:00:00.0000000 +00:00 | 2024-08-18 00:00:00.0000000 +00:00 | 2024-08-18 00:00:00.0000000 +00:00 |  | 2024-08-18 00:00:00.0000000 +00:00 | 2024-08-18 00:00:00.0000000 +00:00 |  | 2017-08-30 14:35:07.4182308 -04:00
HWK2048 | Y | 2017-04-07 00:00:00.0000000 +00:00 | 2017-08-04 00:00:00.0000000 +00:00 | 2019-02-27 00:00:00.0000000 +00:00 | 2019-10-20 00:00:00.0000000 +00:00 | 2021-10-18 00:00:00.0000000 +00:00 | 2017-04-07 00:00:00.0000000 +00:00 | 2018-05-02 00:00:00.0000000 +00:00 | 2019-11-25 00:00:00.0000000 +00:00 | 2020-07-17 00:00:00.0000000 +00:00 | 2022-07-16 00:00:00.0000000 +00:00 | [5 empty] | 2017-04-07 00:00:00.0000000 +00:00 | 2017-08-04 17:00:00.0000000 +00:00 |  |  |  | 2019-02-27 00:00:00.0000000 +00:00 | 2021-10-18 00:00:00.0000000 +00:00 | 2017-04-07 00:00:00.0000000 +00:00 | 2017-04-07 00:00:00.0000000 +00:00 | 2017-08-04 17:00:00.0000000 +00:00 | 2017-08-04 00:00:00.0000000 +00:00 | 2018-06-21 00:00:00.0000000 +00:00 | 2018-06-21 00:00:00.0000000 +00:00 |  | 2018-06-21 00:00:00.0000000 +00:00 | 2018-06-21 00:00:00.0000000 +00:00 | [5 empty] | 2019-02-27 00:00:00.0000000 +00:00 | 2019-02-27 00:00:00.0000000 +00:00 | 2019-10-20 00:00:00.0000000 +00:00 | 2019-10-20 00:00:00.0000000 +00:00 | 2021-10-18 00:00:00.0000000 +00:00 | 2021-10-18 00:00:00.0000000 +00:00 | 2024-10-17 00:00:00.0000000 +00:00 | 2024-10-17 00:00:00.0000000 +00:00 |  | 2024-10-17 00:00:00.0000000 +00:00 | 2024-10-17 00:00:00.0000000 +00:00 |  | 2017-09-01 11:48:46.1972577 -04:00
HWK300-01 | Y | 2011-03-21 00:00:00.0000000 +00:00 | 2012-03-22 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2018-05-12 00:00:00.0000000 +00:00 | 2011-03-21 00:00:00.0000000 +00:00 | 2011-09-17 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-16 00:00:00.0000000 +00:00 | 2011-03-21 00:00:00.0000000 +00:00 | 2012-04-15 00:00:00.0000000 +00:00 | 2014-09-27 00:00:00.0000000 +00:00 | 2015-06-28 00:00:00.0000000 +00:00 | 2016-07-25 00:00:00.0000000 +00:00 | 2011-03-21 00:00:00.0000000 +00:00 | 2012-03-22 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 |  | 2014-12-26 00:00:00.0000000 +00:00 | 2018-05-12 00:00:00.0000000 +00:00 | 2011-03-21 00:00:00.0000000 +00:00 | 2011-03-21 00:00:00.0000000 +00:00 | 2012-03-22 00:00:00.0000000 +00:00 | 2012-03-22 00:00:00.0000000 +00:00 | 2012-09-10 00:00:00.0000000 +00:00 | 2014-06-18 00:00:00.0000000 +00:00 | 2014-06-18 00:00:00.0000000 +00:00 | 2014-06-18 00:00:00.0000000 +00:00 | 2014-06-18 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-26 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2018-05-12 00:00:00.0000000 +00:00 | 2018-05-12 00:00:00.0000000 +00:00 | 2024-10-17 00:00:00.0000000 +00:00 | 2024-10-17 00:00:00.0000000 +00:00 |  | 2024-10-17 00:00:00.0000000 +00:00 | 2024-10-17 00:00:00.0000000 +00:00 |  | 2017-08-29 12:19:27.6130255 -04:00
HWK476C | Y | 2010-05-06 00:00:00.0000000 +00:00 | 2022-01-02 00:00:00.0000000 +00:00 | 2023-11-30 00:00:00.0000000 +00:00 | 2024-07-05 00:00:00.0000000 +00:00 | 2026-07-04 00:00:00.0000000 +00:00 | 2010-05-06 00:00:00.0000000 +00:00 | 2010-11-03 00:00:00.0000000 +00:00 | 2012-01-13 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2011-02-11 00:00:00.0000000 +00:00 | 2018-01-11 00:00:00.0000000 +00:00 | 2019-03-23 00:00:00.0000000 +00:00 | 2019-07-23 00:00:00.0000000 +00:00 | 2020-07-24 00:00:00.0000000 +00:00 | 2010-05-06 12:00:00.0000000 +00:00 |  |  |  |  | 2023-11-30 00:00:00.0000000 +00:00 | 2026-07-04 00:00:00.0000000 +00:00 | 2010-05-06 00:00:00.0000000 +00:00 | 2010-05-06 00:00:00.0000000 +00:00 | 2022-01-02 00:00:00.0000000 +00:00 | 2022-01-02 00:00:00.0000000 +00:00 | 2011-12-12 00:00:00.0000000 +00:00 | 2022-12-15 00:00:00.0000000 +00:00 |  | 2022-12-15 00:00:00.0000000 +00:00 | 2022-12-15 00:00:00.0000000 +00:00 | [5 empty] | 2023-11-30 00:00:00.0000000 +00:00 | 2023-11-30 00:00:00.0000000 +00:00 | 2024-07-05 00:00:00.0000000 +00:00 | 2024-07-05 00:00:00.0000000 +00:00 | 2026-07-04 00:00:00.0000000 +00:00 | 2026-07-04 00:00:00.0000000 +00:00 | 2029-07-03 00:00:00.0000000 +00:00 | 2029-07-03 00:00:00.0000000 +00:00 |  | 2029-07-03 00:00:00.0000000 +00:00 | 2029-07-03 00:00:00.0000000 +00:00
HWK614D | Y | 2003-05-15 00:00:00.0000000 +00:00 | 2012-12-03 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2022-07-29 00:00:00.0000000 +00:00 | 2003-05-15 00:00:00.0000000 +00:00 | 2008-08-15 00:00:00.0000000 +00:00 | 2010-02-14 00:00:00.0000000 +00:00 | 2010-08-15 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2003-05-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2019-12-18 00:00:00.0000000 +00:00 | 2029-03-19 00:00:00.0000000 +00:00 | 2031-03-20 00:00:00.0000000 +00:00 | 2003-05-15 00:00:00.0000000 +00:00 | 2012-12-03 00:00:00.0000000 +00:00 | 2017-09-21 00:00:00.0000000 +00:00 |  |  | 2022-06-28 00:00:00.0000000 +00:00 | 2022-07-29 00:00:00.0000000 +00:00 | 2003-05-15 00:00:00.0000000 +00:00 | 2003-05-15 00:00:00.0000000 +00:00 | 2012-12-03 00:00:00.0000000 +00:00 | 2012-12-03 00:00:00.0000000 +00:00 | 2009-08-17 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | [5 empty] | 2017-09-30 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2022-07-29 00:00:00.0000000 +00:00 | 2022-07-29 00:00:00.0000000 +00:00 | 2025-07-28 00:00:00.0000000 +00:00 | 2025-07-28 00:00:00.0000000 +00:00 |  | 2025-07-28 00:00:00.0000000 +00:00 | 2025-07-28 00:00:00.0000000 +00:00 |  | 2017-09-21 10:03:23.3351585 -04:00
HWK639W | Y | 2007-04-17 00:00:00.0000000 +00:00 | 2012-04-12 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2007-04-17 00:00:00.0000000 +00:00 | 2007-10-30 00:00:00.0000000 +00:00 | 2009-01-15 00:00:00.0000000 +00:00 | 2009-06-15 00:00:00.0000000 +00:00 | 2010-12-08 00:00:00.0000000 +00:00 | 2007-04-17 00:00:00.0000000 +00:00 | 2009-02-13 00:00:00.0000000 +00:00 | 2012-08-01 00:00:00.0000000 +00:00 | 2012-06-30 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2007-04-17 00:00:00.0000000 +00:00 | 2012-04-12 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2007-04-17 00:00:00.0000000 +00:00 | 2007-04-17 00:00:00.0000000 +00:00 | 2012-04-12 00:00:00.0000000 +00:00 | 2012-04-12 00:00:00.0000000 +00:00 | 2008-10-13 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-30 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 |  | 2019-06-15 00:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 |  | 2017-08-29 12:25:26.5861855 -04:00
HWK639WA | Y | 2014-12-01 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2021-04-28 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2017-04-01 00:00:00.0000000 +00:00 | 2018-09-23 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-01 17:00:00.0000000 +00:00 | 2015-01-30 17:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 |  |  | 2017-04-17 00:00:00.0000000 +00:00 | 2021-04-28 00:00:00.0000000 +00:00 | 2014-12-01 17:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-01-30 17:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2015-08-06 00:00:00.0000000 +00:00 | 2015-08-06 00:00:00.0000000 +00:00 | 2015-08-06 00:00:00.0000000 +00:00 | 2015-08-06 00:00:00.0000000 +00:00 | 2015-08-06 00:00:00.0000000 +00:00 | [5 empty] | 2017-04-17 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2021-04-28 00:00:00.0000000 +00:00 | 2021-04-28 00:00:00.0000000 +00:00 | 2024-04-27 00:00:00.0000000 +00:00 | 2024-04-27 00:00:00.0000000 +00:00 |  | 2024-04-27 00:00:00.0000000 +00:00 | 2024-04-27 00:00:00.0000000 +00:00 |  | 2017-08-30 14:36:12.8825933 -04:00
HWK700B | Y | 2001-02-12 00:00:00.0000000 +00:00 | 2008-06-18 00:00:00.0000000 +00:00 | 2021-10-30 00:00:00.0000000 +00:00 | 2022-10-30 00:00:00.0000000 +00:00 | 2025-10-30 00:00:00.0000000 +00:00 | 2001-02-12 00:00:00.0000000 +00:00 | 2008-06-18 00:00:00.0000000 +00:00 | 2010-01-15 00:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2001-02-12 00:00:00.0000000 +00:00 | 2008-06-18 00:00:00.0000000 +00:00 | 2019-04-14 00:00:00.0000000 +00:00 | 2019-10-12 00:00:00.0000000 +00:00 | 2021-10-12 00:00:00.0000000 +00:00 | 2001-02-12 00:00:00.0000000 +00:00 | 2008-06-18 00:00:00.0000000 +00:00 |  |  |  | 2021-10-30 00:00:00.0000000 +00:00 | 2025-10-12 00:00:00.0000000 +00:00 | 2001-02-12 00:00:00.0000000 +00:00 | 2001-02-12 00:00:00.0000000 +00:00 | 2008-06-18 00:00:00.0000000 +00:00 | 2008-06-18 00:00:00.0000000 +00:00 | 2009-06-15 00:00:00.0000000 +00:00 | 2020-01-01 00:00:00.0000000 +00:00 |  | 2020-01-01 00:00:00.0000000 +00:00 | 2020-01-01 00:00:00.0000000 +00:00 | [5 empty] | 2021-10-30 00:00:00.0000000 +00:00 | 2021-10-30 00:00:00.0000000 +00:00 | 2022-10-30 00:00:00.0000000 +00:00 | 2022-10-30 00:00:00.0000000 +00:00 | 2025-10-30 00:00:00.0000000 +00:00 | 2025-10-30 00:00:00.0000000 +00:00 | 2028-10-30 00:00:00.0000000 +00:00 | 2028-10-30 00:00:00.0000000 +00:00 |  | 2028-10-30 00:00:00.0000000 +00:00 | 2028-10-30 00:00:00.0000000 +00:00
HWK732B | Y | 2000-03-21 00:00:00.0000000 +00:00 | 2005-08-15 00:00:00.0000000 +00:00 | 2023-11-30 00:00:00.0000000 +00:00 | 2024-07-30 00:00:00.0000000 +00:00 | 2027-07-29 00:00:00.0000000 +00:00 | 2000-03-21 00:00:00.0000000 +00:00 | 2005-08-15 00:00:00.0000000 +00:00 | 2008-02-15 00:00:00.0000000 +00:00 | 2008-09-15 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2000-03-21 00:00:00.0000000 +00:00 | 2011-08-29 00:00:00.0000000 +00:00 | 2024-01-28 00:00:00.0000000 +00:00 | 2024-08-28 00:00:00.0000000 +00:00 | 2026-08-29 00:00:00.0000000 +00:00 | 2000-03-21 12:00:00.0000000 +00:00 | 2005-08-15 12:00:00.0000000 +00:00 |  |  |  | 2023-11-30 00:00:00.0000000 +00:00 | 2027-07-29 00:00:00.0000000 +00:00 | 2000-03-21 00:00:00.0000000 +00:00 | 2000-03-21 00:00:00.0000000 +00:00 | 2005-08-15 00:00:00.0000000 +00:00 | 2005-08-15 00:00:00.0000000 +00:00 | 2006-10-16 00:00:00.0000000 +00:00 | 2022-08-15 00:00:00.0000000 +00:00 |  | 2022-08-15 00:00:00.0000000 +00:00 | 2022-08-15 00:00:00.0000000 +00:00 | [5 empty] | 2023-11-30 00:00:00.0000000 +00:00 | 2023-11-30 00:00:00.0000000 +00:00 | 2024-07-30 00:00:00.0000000 +00:00 | 2024-07-30 00:00:00.0000000 +00:00 | 2027-07-29 00:00:00.0000000 +00:00 | 2027-07-29 00:00:00.0000000 +00:00 | 2030-07-28 00:00:00.0000000 +00:00 | 2030-07-28 00:00:00.0000000 +00:00 |  | 2030-07-28 00:00:00.0000000 +00:00 | 2030-07-28 00:00:00.0000000 +00:00
HWK779W | Y | 2011-12-19 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2012-08-08 00:00:00.0000000 +00:00 | 2013-03-08 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2014-07-03 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2012-08-08 00:00:00.0000000 +00:00 | 2015-10-07 00:00:00.0000000 +00:00 | 2016-01-31 00:00:00.0000000 +00:00 | 2017-01-31 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 |  |  |  | 2018-10-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 | 2013-01-08 00:00:00.0000000 +00:00 | 2017-08-29 00:00:00.0000000 +00:00 | 2017-08-29 00:00:00.0000000 +00:00 | 2017-08-29 00:00:00.0000000 +00:00 | 2017-08-29 00:00:00.0000000 +00:00 | [5 empty] | 2018-10-30 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2021-07-29 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2024-07-28 00:00:00.0000000 +00:00 | 2024-07-28 00:00:00.0000000 +00:00 |  | 2017-10-13 09:52:54.2744893 -04:00
HWK797W | Y | 2013-07-16 00:00:00.0000000 +00:00 | 2016-08-24 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2020-07-14 00:00:00.0000000 +00:00 | 2013-07-16 00:00:00.0000000 +00:00 | 2014-11-01 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2020-07-14 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-08-01 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2018-07-06 00:00:00.0000000 +00:00 | 2013-07-16 17:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 |  |  |  | 2018-11-30 00:00:00.0000000 +00:00 | 2020-07-14 00:00:00.0000000 +00:00 | 2013-07-16 00:00:00.0000000 +00:00 | 2013-07-16 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-10-12 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 |  | 2018-03-15 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | [5 empty] | 2018-11-30 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2020-07-14 00:00:00.0000000 +00:00 | 2020-07-14 00:00:00.0000000 +00:00 | 2023-07-13 00:00:00.0000000 +00:00 | 2023-07-13 00:00:00.0000000 +00:00 |  | 2023-07-13 00:00:00.0000000 +00:00 | 2023-07-13 00:00:00.0000000 +00:00
HWK855 | Y | 2008-05-15 00:00:00.0000000 +00:00 | 2021-07-04 00:00:00.0000000 +00:00 | 2023-11-30 00:00:00.0000000 +00:00 | 2024-07-04 00:00:00.0000000 +00:00 | 2027-07-03 00:00:00.0000000 +00:00 | 2008-05-15 00:00:00.0000000 +00:00 | 2009-07-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2008-05-15 00:00:00.0000000 +00:00 | 2009-07-15 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2008-05-15 12:00:00.0000000 +00:00 |  |  |  |  | 2023-11-30 00:00:00.0000000 +00:00 | 2027-07-03 00:00:00.0000000 +00:00 | 2008-05-15 00:00:00.0000000 +00:00 | 2008-05-15 00:00:00.0000000 +00:00 | 2021-07-04 00:00:00.0000000 +00:00 | 2021-07-04 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2022-05-15 00:00:00.0000000 +00:00 |  | 2022-05-15 00:00:00.0000000 +00:00 | 2022-05-15 00:00:00.0000000 +00:00 | [5 empty] | 2023-11-30 00:00:00.0000000 +00:00 | 2023-11-30 00:00:00.0000000 +00:00 | 2024-07-04 00:00:00.0000000 +00:00 | 2024-07-04 00:00:00.0000000 +00:00 | 2027-07-03 00:00:00.0000000 +00:00 | 2027-07-03 00:00:00.0000000 +00:00 | 2030-07-02 00:00:00.0000000 +00:00 | 2030-07-02 00:00:00.0000000 +00:00 |  | 2030-07-02 00:00:00.0000000 +00:00 | 2030-07-02 00:00:00.0000000 +00:00
HWK876 | Y | 2001-09-24 00:00:00.0000000 +00:00 | 2008-06-10 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2019-04-26 00:00:00.0000000 +00:00 | 2022-04-25 00:00:00.0000000 +00:00 | 2001-09-24 00:00:00.0000000 +00:00 | 2002-06-28 00:00:00.0000000 +00:00 | 2004-06-28 00:00:00.0000000 +00:00 | 2004-12-28 00:00:00.0000000 +00:00 | 2006-12-28 00:00:00.0000000 +00:00 | 2001-09-24 00:00:00.0000000 +00:00 | 2007-06-16 00:00:00.0000000 +00:00 | 2028-07-18 00:00:00.0000000 +00:00 | 2038-02-27 00:00:00.0000000 +00:00 | 2041-02-26 00:00:00.0000000 +00:00 | 2001-09-24 00:00:00.0000000 +00:00 | 2008-06-10 00:00:00.0000000 +00:00 |  |  |  | 2018-06-30 00:00:00.0000000 +00:00 | 2022-04-25 00:00:00.0000000 +00:00 | 2001-09-24 00:00:00.0000000 +00:00 | 2001-09-24 00:00:00.0000000 +00:00 | 2008-06-10 00:00:00.0000000 +00:00 | 2008-06-10 00:00:00.0000000 +00:00 | 2003-08-30 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2018-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2019-04-26 00:00:00.0000000 +00:00 | 2019-04-19 00:00:00.0000000 +00:00 | 2022-04-25 00:00:00.0000000 +00:00 | 2022-04-25 00:00:00.0000000 +00:00 | 2025-04-24 00:00:00.0000000 +00:00 | 2025-04-24 00:00:00.0000000 +00:00 |  | 2025-04-24 00:00:00.0000000 +00:00 | 2025-04-24 00:00:00.0000000 +00:00
HWK900 | Y | 2017-12-11 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2021-10-31 00:00:00.0000000 +00:00 | 2022-07-25 00:00:00.0000000 +00:00 | 2024-01-24 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2021-10-31 00:00:00.0000000 +00:00 | 2022-07-25 00:00:00.0000000 +00:00 | 2024-01-24 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-11 00:00:00.0000000 +00:00 |  |  |  |  | 2021-10-31 00:00:00.0000000 +00:00 | 2024-01-24 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 |  | 2019-08-30 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 | [5 empty] | 2021-10-31 00:00:00.0000000 +00:00 | 2021-10-31 00:00:00.0000000 +00:00 | 2022-07-25 00:00:00.0000000 +00:00 | 2022-07-25 00:00:00.0000000 +00:00 | 2024-01-24 00:00:00.0000000 +00:00 | 2024-01-24 00:00:00.0000000 +00:00 | 2027-01-23 00:00:00.0000000 +00:00 | 2027-01-23 00:00:00.0000000 +00:00 |  | 2027-01-23 00:00:00.0000000 +00:00 | 2027-01-23 00:00:00.0000000 +00:00 | 2017-12-11 13:00:20.9170000 +00:00 | 2017-12-12 10:11:15.3641978 -05:00
HWKF029B | Y | 2012-05-23 00:00:00.0000000 +00:00 | 2012-08-30 00:00:00.0000000 +00:00 | 2014-05-22 00:00:00.0000000 +00:00 | 2015-03-11 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2012-08-30 00:00:00.0000000 +00:00 | 2012-12-09 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2013-11-05 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2012-08-30 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2015-11-09 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2012-08-30 00:00:00.0000000 +00:00 | 2014-05-22 00:00:00.0000000 +00:00 | 2015-03-11 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | [6 empty] | 2013-08-30 00:00:00.0000000 +00:00 |  |  |  |  | 2013-12-29 00:00:00.0000000 +00:00 | [8 empty] | 2017-02-03 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00
HWKF2007A | Y | 2014-01-13 00:00:00.0000000 +00:00 | 2014-02-05 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-04-23 00:00:00.0000000 +00:00 | 2015-06-16 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-02-05 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2014-10-10 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-02-05 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-02-05 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-04-23 00:00:00.0000000 +00:00 | 2015-05-28 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2015-05-28 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-02-05 00:00:00.0000000 +00:00 | 2014-02-05 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-04-23 00:00:00.0000000 +00:00 | 2014-04-23 00:00:00.0000000 +00:00 | 2015-05-28 00:00:00.0000000 +00:00 | 2015-05-28 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2017-09-27 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 |  | 2017-09-07 10:59:47.2767246 -04:00
HWKF488R | Y | 2015-06-30 00:00:00.0000000 +00:00 | 2017-12-01 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2019-10-02 00:00:00.0000000 +00:00 | 2020-10-02 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2017-07-03 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2019-05-04 00:00:00.0000000 +00:00 | 2020-05-04 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-30 18:00:00.0000000 +00:00 | 2017-07-05 20:00:00.0000000 +00:00 |  |  |  | 2018-11-30 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-28 00:00:00.0000000 +00:00 | 2017-12-28 00:00:00.0000000 +00:00 |  |  |  | 2018-03-08 00:00:00.0000000 +00:00 | 2018-03-08 00:00:00.0000000 +00:00 | [9 empty] | 2021-10-11 00:00:00.0000000 +00:00 | 2021-10-11 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-05 10:04:48.5327637 -04:00
HWKKP005 | Y | 2011-09-12 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-09-16 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 | 2011-09-12 00:00:00.0000000 +00:00 | 2012-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-12 00:00:00.0000000 +00:00 | 2011-09-12 00:00:00.0000000 +00:00 | 2012-06-28 00:00:00.0000000 +00:00 | 2017-01-10 00:00:00.0000000 +00:00 | 2017-11-14 00:00:00.0000000 +00:00 | 2018-11-11 00:00:00.0000000 +00:00 | 2011-09-12 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 |  |  |  | 2017-12-15 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 | 2011-09-12 00:00:00.0000000 +00:00 | 2011-09-21 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 | 2012-06-11 00:00:00.0000000 +00:00 | 2015-06-04 00:00:00.0000000 +00:00 | 2015-06-04 00:00:00.0000000 +00:00 | 2015-06-04 00:00:00.0000000 +00:00 | 2015-06-04 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-15 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-09-16 00:00:00.0000000 +00:00 | 2018-09-16 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 | 2024-09-14 00:00:00.0000000 +00:00 | 2024-09-14 00:00:00.0000000 +00:00 |  | 2024-09-14 00:00:00.0000000 +00:00 | 2024-09-14 00:00:00.0000000 +00:00 |  | 2017-08-30 14:36:52.0428541 -04:00
HWKP2027 | Y | 2011-08-16 00:00:00.0000000 +00:00 | 2012-11-01 00:00:00.0000000 +00:00 | 2015-04-15 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 | 2011-08-16 00:00:00.0000000 +00:00 | 2012-04-04 00:00:00.0000000 +00:00 | 2012-12-19 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2014-05-03 00:00:00.0000000 +00:00 | 2011-08-16 00:00:00.0000000 +00:00 | 2012-11-01 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2014-11-25 00:00:00.0000000 +00:00 | 2015-11-26 00:00:00.0000000 +00:00 | 2011-08-16 12:00:00.0000000 +00:00 | 2012-04-04 00:00:00.0000000 +00:00 | 2015-04-15 00:00:00.0000000 +00:00 | 2016-09-26 17:00:00.0000000 +00:00 |  | 2017-04-25 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 | 2011-08-16 00:00:00.0000000 +00:00 | 2011-08-16 00:00:00.0000000 +00:00 | 2012-04-04 00:00:00.0000000 +00:00 | 2012-04-04 00:00:00.0000000 +00:00 | 2012-08-20 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-15 00:00:00.0000000 +00:00 | 2015-04-15 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 | 2020-09-24 00:00:00.0000000 +00:00 | 2020-09-24 00:00:00.0000000 +00:00 |  | 2020-09-24 00:00:00.0000000 +00:00 | 2020-09-24 00:00:00.0000000 +00:00 |  | 2017-08-30 14:39:07.3162069 -04:00
HWKP2029 | Y | 2013-06-19 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 | 2017-11-01 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2013-12-01 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2015-07-17 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2014-06-15 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2016-07-03 00:00:00.0000000 +00:00 | 2013-06-19 12:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 |  | 2016-12-28 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 | 2013-06-19 12:00:00.0000000 +00:00 | 2013-06-19 12:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-28 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 | 2022-03-24 00:00:00.0000000 +00:00 | 2022-03-24 00:00:00.0000000 +00:00 |  | 2022-03-24 00:00:00.0000000 +00:00 | 2022-03-24 00:00:00.0000000 +00:00 |  | 2017-09-15 10:45:35.6315726 -04:00
HWM1163 | Y | 2006-06-21 00:00:00.0000000 +00:00 | 2007-01-22 00:00:00.0000000 +00:00 | 2023-12-15 00:00:00.0000000 +00:00 | 2024-06-14 00:00:00.0000000 +00:00 | 2026-06-13 00:00:00.0000000 +00:00 | 2006-06-21 00:00:00.0000000 +00:00 | 2007-02-12 00:00:00.0000000 +00:00 | 2008-04-13 00:00:00.0000000 +00:00 | 2008-10-13 00:00:00.0000000 +00:00 | 2010-04-15 00:00:00.0000000 +00:00 | 2006-06-21 00:00:00.0000000 +00:00 | 2007-02-12 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2015-03-18 00:00:00.0000000 +00:00 | 2024-09-27 00:00:00.0000000 +00:00 | 2006-06-21 12:00:00.0000000 +00:00 | 2007-02-12 12:00:00.0000000 +00:00 |  |  |  | 2046-04-05 00:00:00.0000000 +00:00 | 2026-12-10 00:00:00.0000000 +00:00 | 2006-06-21 12:00:00.0000000 +00:00 |  | 2007-02-12 12:00:00.0000000 +00:00 |  | 2008-02-08 00:00:00.0000000 +00:00 | 2022-06-15 00:00:00.0000000 +00:00 |  | 2022-06-15 00:00:00.0000000 +00:00 | [6 empty] | 2023-12-15 00:00:00.0000000 +00:00 |  | 2024-06-14 00:00:00.0000000 +00:00 |  | 2026-06-13 00:00:00.0000000 +00:00 |  | 2013-04-15 00:00:00.0000000 +00:00 | 2029-06-13 00:00:00.0000000 +00:00 |  | 2029-06-13 00:00:00.0000000 +00:00 |  |  | 2017-11-17 15:13:33.4554917 -05:00
HWM1683 | Y | 2007-04-27 00:00:00.0000000 +00:00 | 2007-07-23 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2007-04-27 00:00:00.0000000 +00:00 | 2007-07-23 00:00:00.0000000 +00:00 | 2008-04-15 00:00:00.0000000 +00:00 | 2008-10-14 00:00:00.0000000 +00:00 | 2010-04-08 00:00:00.0000000 +00:00 | 2007-04-27 00:00:00.0000000 +00:00 | 2007-07-23 00:00:00.0000000 +00:00 | 2014-04-08 00:00:00.0000000 +00:00 | 2014-10-07 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2007-04-27 00:00:00.0000000 +00:00 | 2007-07-23 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 |  | 2012-06-17 00:00:00.0000000 +00:00 | 2018-09-16 00:00:00.0000000 +00:00 | 2007-04-27 00:00:00.0000000 +00:00 | 2007-04-27 00:00:00.0000000 +00:00 | 2007-07-23 00:00:00.0000000 +00:00 | 2007-07-23 00:00:00.0000000 +00:00 |  | 2007-09-27 00:00:00.0000000 +00:00 | 2012-04-04 00:00:00.0000000 +00:00 | 2012-04-04 00:00:00.0000000 +00:00 | 2012-04-04 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-30 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2017-09-10 00:00:00.0000000 +00:00 | 2018-03-29 00:00:00.0000000 +00:00 | 2015-05-31 00:00:00.0000000 +00:00 | 2021-03-30 00:00:00.0000000 +00:00 |  | 2022-11-02 00:00:00.0000000 +00:00 | 2021-03-28 00:00:00.0000000 +00:00 |  | 2017-11-29 14:36:29.6770897 -05:00
HWM2025 | Y | 2017-01-12 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2022-06-14 00:00:00.0000000 +00:00 | 2017-01-12 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2022-06-14 00:00:00.0000000 +00:00 | [5 empty] | 2017-01-12 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 |  |  |  | 2019-10-30 00:00:00.0000000 +00:00 |  | 2017-01-12 00:00:00.0000000 +00:00 |  | 2017-07-15 00:00:00.0000000 +00:00 |  | 2018-02-12 00:00:00.0000000 +00:00 | 2018-02-12 00:00:00.0000000 +00:00 |  | 2018-02-12 00:00:00.0000000 +00:00 | [6 empty] | 2019-10-30 00:00:00.0000000 +00:00 |  | 2020-06-15 00:00:00.0000000 +00:00 |  | 2022-06-14 00:00:00.0000000 +00:00 |  | 2025-06-14 00:00:00.0000000 +00:00 | 2025-06-14 00:00:00.0000000 +00:00 |  | 2025-06-14 00:00:00.0000000 +00:00 |  |  | 2017-08-31 13:56:56.5893294 -04:00
HWM215 | Y | 2008-04-09 00:00:00.0000000 +00:00 | 2009-09-10 00:00:00.0000000 +00:00 | 2012-12-28 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2016-01-30 00:00:00.0000000 +00:00 | 2008-04-09 00:00:00.0000000 +00:00 | 2008-08-08 00:00:00.0000000 +00:00 | 2009-08-04 00:00:00.0000000 +00:00 | 2010-02-01 00:00:00.0000000 +00:00 | 2011-02-02 00:00:00.0000000 +00:00 | 2008-04-09 00:00:00.0000000 +00:00 | 2009-09-10 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2014-02-16 00:00:00.0000000 +00:00 | 2023-10-11 00:00:00.0000000 +00:00 | 2008-04-09 12:00:00.0000000 +00:00 | 2009-09-10 07:00:00.0000000 +00:00 | 2012-12-28 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2016-01-30 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2015-08-06 00:00:00.0000000 +00:00 | 2008-04-09 00:00:00.0000000 +00:00 | 2008-04-09 00:00:00.0000000 +00:00 | 2009-09-10 00:00:00.0000000 +00:00 | 2009-09-10 00:00:00.0000000 +00:00 | 2009-02-05 00:00:00.0000000 +00:00 | 2011-05-20 00:00:00.0000000 +00:00 | 2011-05-20 00:00:00.0000000 +00:00 | 2011-05-20 00:00:00.0000000 +00:00 | 2011-05-20 00:00:00.0000000 +00:00 | [5 empty] | 2012-12-28 00:00:00.0000000 +00:00 | 2012-12-28 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2016-01-30 00:00:00.0000000 +00:00 | 2014-02-01 00:00:00.0000000 +00:00 | 2019-01-29 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00 | 2019-01-29 00:00:00.0000000 +00:00
HWMBRT5A | Y | 2011-03-15 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2016-11-13 00:00:00.0000000 +00:00 | 2011-03-15 00:00:00.0000000 +00:00 | 2011-07-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2011-03-15 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2013-01-24 00:00:00.0000000 +00:00 | 2013-11-04 00:00:00.0000000 +00:00 | 2015-10-31 00:00:00.0000000 +00:00 | 2011-03-15 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2016-10-12 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2016-10-12 00:00:00.0000000 +00:00 | 2011-03-15 00:00:00.0000000 +00:00 | 2011-03-15 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 |  | 2012-05-17 00:00:00.0000000 +00:00 | 2012-05-17 00:00:00.0000000 +00:00 | 2012-05-17 00:00:00.0000000 +00:00 | 2012-05-17 00:00:00.0000000 +00:00 | [5 empty] | 2013-04-29 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2016-10-10 00:00:00.0000000 +00:00 | 2016-11-13 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 |  | 2019-10-10 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00
HWMM008 | Y | 2012-08-28 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2016-05-15 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2012-08-28 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2012-08-28 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2012-08-28 12:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2016-05-16 18:00:00.0000000 +00:00 |  | 2015-07-11 00:00:00.0000000 +00:00 | 2017-06-14 00:00:00.0000000 +00:00 | 2012-08-28 12:00:00.0000000 +00:00 | 2012-08-28 12:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-27 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2016-05-16 18:00:00.0000000 +00:00 | 2016-05-16 18:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2019-11-27 00:00:00.0000000 +00:00 | 2019-11-27 00:00:00.0000000 +00:00 |  | 2019-11-27 00:00:00.0000000 +00:00 | 2019-11-27 00:00:00.0000000 +00:00 |  | 2017-08-31 15:54:37.7407633 -04:00
HWMNYPL | Y | 2017-04-27 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2019-10-15 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2022-06-14 00:00:00.0000000 +00:00 | 2017-04-27 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2019-10-15 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2022-06-14 00:00:00.0000000 +00:00 | [5 empty] | 2017-04-27 00:00:00.0000000 +00:00 | [10 empty] | 2019-05-07 00:00:00.0000000 +00:00 | 2019-05-07 00:00:00.0000000 +00:00 | [14 empty] | 2025-06-12 00:00:00.0000000 +00:00 | 2025-06-12 00:00:00.0000000 +00:00
HWMP116 | Y | 2006-01-30 00:00:00.0000000 +00:00 | 2006-07-25 00:00:00.0000000 +00:00 | 2012-08-17 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2016-01-31 00:00:00.0000000 +00:00 | 2006-01-30 00:00:00.0000000 +00:00 | 2006-08-01 00:00:00.0000000 +00:00 | 2008-02-15 00:00:00.0000000 +00:00 | 2008-08-15 00:00:00.0000000 +00:00 | 2010-08-15 00:00:00.0000000 +00:00 | 2006-01-30 00:00:00.0000000 +00:00 | 2006-08-01 00:00:00.0000000 +00:00 | 2011-06-22 00:00:00.0000000 +00:00 | 2012-06-11 00:00:00.0000000 +00:00 | 2014-06-11 00:00:00.0000000 +00:00 | 2006-01-30 00:00:00.0000000 +00:00 | 2006-07-25 00:00:00.0000000 +00:00 | 2012-08-17 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2016-01-31 00:00:00.0000000 +00:00 | 2012-06-17 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2006-01-30 00:00:00.0000000 +00:00 | 2006-01-30 00:00:00.0000000 +00:00 | 2006-07-25 00:00:00.0000000 +00:00 | 2006-07-25 00:00:00.0000000 +00:00 |  | 2010-11-23 00:00:00.0000000 +00:00 | 2010-11-23 00:00:00.0000000 +00:00 | 2010-11-23 00:00:00.0000000 +00:00 | 2010-11-23 00:00:00.0000000 +00:00 | [5 empty] | 2012-08-17 00:00:00.0000000 +00:00 | 2012-08-17 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2016-01-31 00:00:00.0000000 +00:00 | 2016-01-31 00:00:00.0000000 +00:00 | 2013-08-14 00:00:00.0000000 +00:00 | 2019-01-30 00:00:00.0000000 +00:00 |  | 2019-01-30 00:00:00.0000000 +00:00 | 2019-01-30 00:00:00.0000000 +00:00 |  | 2017-09-01 16:02:28.9502798 -04:00
HWMP2012 | Y | 2004-02-27 00:00:00.0000000 +00:00 | 2005-10-07 00:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2013-04-16 00:00:00.0000000 +00:00 | 2017-10-06 00:00:00.0000000 +00:00 | 2004-02-27 00:00:00.0000000 +00:00 | 2005-10-07 00:00:00.0000000 +00:00 | 2007-03-17 00:00:00.0000000 +00:00 | 2007-09-14 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2004-02-27 00:00:00.0000000 +00:00 | 2005-10-07 00:00:00.0000000 +00:00 | 2012-04-15 00:00:00.0000000 +00:00 | 2012-10-13 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2004-02-27 00:00:00.0000000 +00:00 | 2005-10-07 00:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2013-04-16 00:00:00.0000000 +00:00 | 2017-10-06 00:00:00.0000000 +00:00 | 2012-09-14 00:00:00.0000000 +00:00 | 2017-09-03 00:00:00.0000000 +00:00 | 2004-02-27 00:00:00.0000000 +00:00 | 2004-02-27 00:00:00.0000000 +00:00 | 2005-10-07 00:00:00.0000000 +00:00 | 2005-10-07 00:00:00.0000000 +00:00 |  | 2011-06-22 00:00:00.0000000 +00:00 | 2011-06-22 00:00:00.0000000 +00:00 | 2011-06-22 00:00:00.0000000 +00:00 | 2011-06-22 00:00:00.0000000 +00:00 | [5 empty] | 2012-10-17 00:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2013-04-16 00:00:00.0000000 +00:00 | 2013-04-16 00:00:00.0000000 +00:00 | 2017-10-06 00:00:00.0000000 +00:00 | 2017-10-06 00:00:00.0000000 +00:00 | 2012-09-13 00:00:00.0000000 +00:00 | 2020-10-05 00:00:00.0000000 +00:00 |  | 2020-10-05 00:00:00.0000000 +00:00 | 2020-10-05 00:00:00.0000000 +00:00 |  | 2017-11-17 10:48:45.8560936 -05:00
HWMP2012-ER | Y | 2017-06-30 00:00:00.0000000 +00:00 | 2017-07-26 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-11-15 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2017-07-26 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-11-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-06-30 00:00:00.0000000 +00:00 | 2017-07-26 00:00:00.0000000 +00:00 |  |  |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2017-06-30 00:00:00.0000000 +00:00 |  | 2017-07-26 00:00:00.0000000 +00:00 |  |  | 2017-10-20 00:00:00.0000000 +00:00 |  | 2017-10-20 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-15 00:00:00.0000000 +00:00 |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2018-11-15 00:00:00.0000000 +00:00 |  | 2019-11-15 00:00:00.0000000 +00:00 | 2019-11-15 00:00:00.0000000 +00:00 |  | 2019-11-15 00:00:00.0000000 +00:00 |  |  | 2017-09-01 16:09:59.4541355 -04:00
HWMP2017 | Y | 2011-04-06 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2011-04-06 00:00:00.0000000 +00:00 | 2011-10-06 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-14 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2011-04-06 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 | 2015-02-27 00:00:00.0000000 +00:00 | 2011-04-06 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2016-04-17 00:00:00.0000000 +00:00 | 2011-04-06 00:00:00.0000000 +00:00 | 2011-04-06 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 |  | 2013-06-14 00:00:00.0000000 +00:00 | 2013-06-14 00:00:00.0000000 +00:00 | 2013-06-14 00:00:00.0000000 +00:00 | 2013-06-14 00:00:00.0000000 +00:00 | [5 empty] | 2014-02-19 00:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2018-01-14 00:00:00.0000000 +00:00 | 2019-05-24 00:00:00.0000000 +00:00 |  | 2019-05-24 00:00:00.0000000 +00:00 | 2019-05-24 00:00:00.0000000 +00:00
HWMP2019 | Y | 2006-10-26 00:00:00.0000000 +00:00 | 2007-01-25 00:00:00.0000000 +00:00 | 2009-07-14 00:00:00.0000000 +00:00 | 2010-06-21 00:00:00.0000000 +00:00 | 2017-11-22 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 | 2007-01-25 00:00:00.0000000 +00:00 | 2008-02-15 00:00:00.0000000 +00:00 | 2008-08-15 00:00:00.0000000 +00:00 | 2010-02-15 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 | 2007-01-25 00:00:00.0000000 +00:00 | 2009-07-14 00:00:00.0000000 +00:00 | 2010-09-28 00:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 | 2007-01-25 00:00:00.0000000 +00:00 | 2009-07-14 00:00:00.0000000 +00:00 | 2010-06-21 00:00:00.0000000 +00:00 |  | 2009-07-14 00:00:00.0000000 +00:00 | 2016-06-24 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 | 2007-01-25 00:00:00.0000000 +00:00 | 2007-01-25 00:00:00.0000000 +00:00 |  | 2008-07-08 00:00:00.0000000 +00:00 | 2008-07-08 00:00:00.0000000 +00:00 | 2008-07-08 00:00:00.0000000 +00:00 | 2008-07-08 00:00:00.0000000 +00:00 | [5 empty] | 2009-07-14 00:00:00.0000000 +00:00 | 2009-07-14 00:00:00.0000000 +00:00 | 2010-06-21 00:00:00.0000000 +00:00 | 2010-06-21 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2020-11-22 00:00:00.0000000 +00:00 |  | 2016-06-19 00:00:00.0000000 +00:00 | 2016-06-19 00:00:00.0000000 +00:00
HWMP2020 | Y | 2010-04-09 00:00:00.0000000 +00:00 | 2011-08-24 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 | 2015-03-09 00:00:00.0000000 +00:00 | 2018-11-04 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2010-12-16 00:00:00.0000000 +00:00 | 2012-01-31 00:00:00.0000000 +00:00 | 2012-08-02 00:00:00.0000000 +00:00 | 2014-08-03 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2011-02-10 00:00:00.0000000 +00:00 | 2012-03-27 00:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2014-09-18 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2011-08-24 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 | 2015-03-09 00:00:00.0000000 +00:00 |  | 2014-03-24 00:00:00.0000000 +00:00 | 2018-08-22 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2011-08-24 00:00:00.0000000 +00:00 | 2011-08-24 00:00:00.0000000 +00:00 |  | 2013-05-03 00:00:00.0000000 +00:00 | 2013-05-03 00:00:00.0000000 +00:00 | 2013-05-03 00:00:00.0000000 +00:00 | 2013-05-03 00:00:00.0000000 +00:00 | [5 empty] | 2014-03-24 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 | 2015-03-09 00:00:00.0000000 +00:00 | 2015-03-09 00:00:00.0000000 +00:00 | 2018-11-04 00:00:00.0000000 +00:00 | 2018-11-04 00:00:00.0000000 +00:00 | 2017-03-03 00:00:00.0000000 +00:00 | 2021-11-04 00:00:00.0000000 +00:00 |  | 2021-11-04 00:00:00.0000000 +00:00 | 2021-11-04 00:00:00.0000000 +00:00
HWMWTCA6A | Y | 2003-03-07 00:00:00.0000000 +00:00 | 2003-07-28 00:00:00.0000000 +00:00 | 2012-03-20 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2003-03-07 00:00:00.0000000 +00:00 | 2003-07-10 00:00:00.0000000 +00:00 | 2004-01-10 00:00:00.0000000 +00:00 | 2004-05-10 00:00:00.0000000 +00:00 | 2005-05-10 00:00:00.0000000 +00:00 | 2003-03-07 00:00:00.0000000 +00:00 | 2003-02-18 00:00:00.0000000 +00:00 | 2011-06-08 00:00:00.0000000 +00:00 | 2012-08-23 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 | 2003-03-07 00:00:00.0000000 +00:00 | 2003-07-28 00:00:00.0000000 +00:00 | 2012-03-20 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2011-12-03 00:00:00.0000000 +00:00 | 2017-08-03 00:00:00.0000000 +00:00 | 2003-03-07 00:00:00.0000000 +00:00 | 2003-03-07 00:00:00.0000000 +00:00 | 2003-07-28 00:00:00.0000000 +00:00 | 2003-07-28 00:00:00.0000000 +00:00 |  | 2010-07-13 00:00:00.0000000 +00:00 | 2010-07-13 00:00:00.0000000 +00:00 | 2010-07-13 00:00:00.0000000 +00:00 | 2010-07-13 00:00:00.0000000 +00:00 | [5 empty] | 2012-03-20 00:00:00.0000000 +00:00 | 2012-03-20 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2013-08-05 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2008-05-09 00:00:00.0000000 +00:00 | 2020-05-30 00:00:00.0000000 +00:00 |  | 2020-05-30 00:00:00.0000000 +00:00 | 2020-05-30 00:00:00.0000000 +00:00 |  | 2017-09-01 16:12:33.8755405 -04:00
HWMWTCA7B | Y | 2004-01-23 00:00:00.0000000 +00:00 | 2005-09-26 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2017-01-12 00:00:00.0000000 +00:00 | 2020-01-12 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-05-15 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 | 2005-08-15 00:00:00.0000000 +00:00 | 2007-08-15 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2005-09-26 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2004-01-23 12:00:00.0000000 +00:00 | 2004-05-15 12:00:00.0000000 +00:00 |  |  |  | 2029-06-12 00:00:00.0000000 +00:00 | [21 empty] | 2021-01-12 00:00:00.0000000 +00:00 | 2032-04-14 00:00:00.0000000 +00:00
HWMWTCA7E | Y | 2004-01-23 00:00:00.0000000 +00:00 | 2004-07-26 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2019-04-10 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-05-15 00:00:00.0000000 +00:00 | 2005-03-16 00:00:00.0000000 +00:00 | 2005-08-15 00:00:00.0000000 +00:00 | 2007-08-15 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-07-26 00:00:00.0000000 +00:00 | 2014-06-17 00:00:00.0000000 +00:00 | 2015-10-31 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-07-26 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 |  | 2014-06-17 00:00:00.0000000 +00:00 | 2019-04-10 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-07-26 00:00:00.0000000 +00:00 | 2004-07-26 00:00:00.0000000 +00:00 |  | 2011-11-15 00:00:00.0000000 +00:00 | 2011-11-15 00:00:00.0000000 +00:00 | 2011-11-15 00:00:00.0000000 +00:00 | 2011-11-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-16 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2019-04-10 00:00:00.0000000 +00:00 | 2019-04-10 00:00:00.0000000 +00:00 | 2010-08-15 00:00:00.0000000 +00:00 | 2022-04-10 00:00:00.0000000 +00:00 |  | 2022-04-10 00:00:00.0000000 +00:00 | 2022-04-10 00:00:00.0000000 +00:00 |  | 2017-08-29 12:50:16.1459236 -04:00
HWMWTCA7F | Y | 2004-01-23 00:00:00.0000000 +00:00 | 2004-12-06 00:00:00.0000000 +00:00 | 2015-02-11 00:00:00.0000000 +00:00 | 2017-01-09 00:00:00.0000000 +00:00 | 2019-07-07 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-05-15 00:00:00.0000000 +00:00 | 2005-02-15 00:00:00.0000000 +00:00 | 2005-08-15 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-10-15 00:00:00.0000000 +00:00 | 2013-09-24 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-12-06 00:00:00.0000000 +00:00 | 2015-02-11 00:00:00.0000000 +00:00 | 2017-01-09 00:00:00.0000000 +00:00 |  | 2025-03-05 00:00:00.0000000 +00:00 | 2019-07-07 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-01-23 00:00:00.0000000 +00:00 | 2004-12-06 00:00:00.0000000 +00:00 | 2004-12-06 00:00:00.0000000 +00:00 |  | 2013-11-06 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | [5 empty] | 2015-02-11 00:00:00.0000000 +00:00 | 2015-02-11 00:00:00.0000000 +00:00 | 2017-01-09 00:00:00.0000000 +00:00 | 2017-01-09 00:00:00.0000000 +00:00 | 2019-07-07 00:00:00.0000000 +00:00 | 2019-07-07 00:00:00.0000000 +00:00 | 2010-02-13 00:00:00.0000000 +00:00 | 2022-07-05 00:00:00.0000000 +00:00 |  | 2022-07-05 00:00:00.0000000 +00:00 | 2022-07-05 00:00:00.0000000 +00:00
HWMWTCA7G | Y | 2005-07-15 00:00:00.0000000 +00:00 | 2005-11-30 00:00:00.0000000 +00:00 | 2015-02-11 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2005-07-15 00:00:00.0000000 +00:00 | 2005-09-15 00:00:00.0000000 +00:00 | 2006-02-15 00:00:00.0000000 +00:00 | 2006-08-15 00:00:00.0000000 +00:00 | 2008-02-15 00:00:00.0000000 +00:00 | 2005-07-15 00:00:00.0000000 +00:00 | 2005-09-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2005-07-15 12:00:00.0000000 +00:00 | 2005-11-30 17:00:00.0000000 +00:00 | 2015-02-11 17:00:00.0000000 +00:00 |  |  | 2023-02-07 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-17 10:54:34.4161547 -05:00
HWMWTCA9 | Y | 2013-10-15 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2016-02-16 00:00:00.0000000 +00:00 | 2018-02-16 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-02-15 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2017-08-17 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-05-17 00:00:00.0000000 +00:00 | 2015-11-16 00:00:00.0000000 +00:00 | 2017-11-16 00:00:00.0000000 +00:00 | 2013-10-15 12:00:00.0000000 +00:00 |  |  |  |  | 2015-08-17 00:00:00.0000000 +00:00 | 2018-02-16 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-17 14:07:48.2561612 -05:00
HWMWTCB1 | Y | 2017-08-03 00:00:00.0000000 +00:00 | 2018-06-01 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2019-09-11 00:00:00.0000000 +00:00 | 2021-09-10 00:00:00.0000000 +00:00 | 2017-08-03 00:00:00.0000000 +00:00 | 2018-04-09 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2019-06-28 00:00:00.0000000 +00:00 | 2021-06-28 00:00:00.0000000 +00:00 | [5 empty] | 2017-08-03 00:00:00.0000000 +00:00 | [10 empty] | 2018-10-08 00:00:00.0000000 +00:00 | 2018-10-08 00:00:00.0000000 +00:00 | [14 empty] | 2024-06-27 00:00:00.0000000 +00:00 | 2024-09-10 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-01 16:15:32.4630482 -04:00
HWMWTCB2 | Y | 2017-06-21 00:00:00.0000000 +00:00 | 2018-06-01 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2019-09-11 00:00:00.0000000 +00:00 | 2021-09-10 00:00:00.0000000 +00:00 | 2017-06-21 00:00:00.0000000 +00:00 | 2018-06-01 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2019-09-11 00:00:00.0000000 +00:00 | 2021-09-10 00:00:00.0000000 +00:00 | [5 empty] | 2017-06-21 00:00:00.0000000 +00:00 | [10 empty] | 2018-10-08 00:00:00.0000000 +00:00 | 2018-10-08 00:00:00.0000000 +00:00 | [14 empty] | 2024-09-10 00:00:00.0000000 +00:00 | 2024-09-10 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-01 16:16:20.6780071 -04:00
HWMWTCB5A | Y | 2017-03-09 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-08-19 00:00:00.0000000 +00:00 | 2020-03-19 00:00:00.0000000 +00:00 | 2017-03-09 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-08-19 00:00:00.0000000 +00:00 | 2020-03-19 00:00:00.0000000 +00:00 | [5 empty] | 2017-03-09 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 |  |  |  | 2017-12-29 00:00:00.0000000 +00:00 |  | 2017-03-09 00:00:00.0000000 +00:00 |  | 2017-06-28 00:00:00.0000000 +00:00 |  | 2017-07-28 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-08-19 00:00:00.0000000 +00:00 |  | 2020-03-19 00:00:00.0000000 +00:00 |  | 2023-03-19 00:00:00.0000000 +00:00 | 2023-03-19 00:00:00.0000000 +00:00 |  | 2023-03-19 00:00:00.0000000 +00:00 |  | 2017-11-01 13:00:20.3100000 +00:00 | 2017-11-09 12:12:14.5407497 -05:00
HWMWTCB6 | Y | [47 empty] | 2017-10-12 13:00:19.2200000 +00:00
HWMWTCB7 | Y | [47 empty] | 2017-10-12 13:00:20.4730000 +00:00
HWP14MLM | Y | 2013-01-10 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 | 2017-12-24 00:00:00.0000000 +00:00 | 2013-01-10 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-01-05 00:00:00.0000000 +00:00 | 2013-01-10 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-04-17 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2013-01-10 12:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 |  | 2015-12-12 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 | 2013-01-10 12:00:00.0000000 +00:00 | 2013-01-10 12:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-01-14 00:00:00.0000000 +00:00 | 2014-01-14 00:00:00.0000000 +00:00 | 2014-01-14 00:00:00.0000000 +00:00 | 2014-01-14 00:00:00.0000000 +00:00 | 2014-01-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-15 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 | 2018-05-08 00:00:00.0000000 +00:00 | 2020-12-23 00:00:00.0000000 +00:00 |  | 2020-08-20 00:00:00.0000000 +00:00 | 2020-08-20 00:00:00.0000000 +00:00
HWP14MTA | Y | 2013-01-10 00:00:00.0000000 +00:00 | 2013-12-17 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2016-09-20 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2013-01-10 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2016-01-05 00:00:00.0000000 +00:00 | 2013-01-10 00:00:00.0000000 +00:00 | 2013-10-16 00:00:00.0000000 +00:00 | 2014-04-18 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2016-04-07 00:00:00.0000000 +00:00 | 2013-01-10 12:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2016-09-20 00:00:00.0000000 +00:00 |  | 2017-06-28 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2013-01-10 12:00:00.0000000 +00:00 | 2013-01-10 12:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-26 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2016-09-20 00:00:00.0000000 +00:00 | 2016-09-20 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2018-06-12 00:00:00.0000000 +00:00 | 2021-07-01 00:00:00.0000000 +00:00 |  | 2021-07-01 00:00:00.0000000 +00:00 | 2021-07-01 00:00:00.0000000 +00:00
HWP14QC | Y | 2013-04-03 00:00:00.0000000 +00:00 | 2015-07-01 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-03-13 00:00:00.0000000 +00:00 | 2018-06-10 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2013-04-03 12:00:00.0000000 +00:00 | 2015-07-01 17:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-03-13 17:00:00.0000000 +00:00 |  | 2016-04-29 00:00:00.0000000 +00:00 | 2018-06-10 00:00:00.0000000 +00:00 | 2013-04-03 12:00:00.0000000 +00:00 | 2013-04-03 12:00:00.0000000 +00:00 | 2015-07-01 17:00:00.0000000 +00:00 | 2015-07-01 17:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-04-29 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-03-13 17:00:00.0000000 +00:00 | 2017-03-13 17:00:00.0000000 +00:00 | 2018-06-10 00:00:00.0000000 +00:00 | 2018-06-10 00:00:00.0000000 +00:00 | 2018-12-14 00:00:00.0000000 +00:00 | 2021-06-10 00:00:00.0000000 +00:00 |  | 2021-06-10 00:00:00.0000000 +00:00 | 2021-06-10 00:00:00.0000000 +00:00 |  | 2017-11-03 10:05:47.8491324 -04:00
HWP14QLM | Y | 2013-04-03 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-06-12 00:00:00.0000000 +00:00 | 2014-11-12 00:00:00.0000000 +00:00 | 2015-11-11 00:00:00.0000000 +00:00 | 2013-04-03 12:00:00.0000000 +00:00 | 2013-11-12 17:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2013-04-03 12:00:00.0000000 +00:00 | 2013-04-03 12:00:00.0000000 +00:00 | 2013-11-12 17:00:00.0000000 +00:00 | 2013-11-12 17:00:00.0000000 +00:00 | 2014-04-29 00:00:00.0000000 +00:00 | 2014-11-03 00:00:00.0000000 +00:00 | 2014-11-03 00:00:00.0000000 +00:00 | 2014-11-03 00:00:00.0000000 +00:00 | 2014-11-03 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-02 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2018-12-13 00:00:00.0000000 +00:00 | 2020-06-24 00:00:00.0000000 +00:00 |  | 2020-06-24 00:00:00.0000000 +00:00 | 2020-06-24 00:00:00.0000000 +00:00
HWP14QTA | Y | 2013-04-03 00:00:00.0000000 +00:00 | 2013-11-08 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-11-10 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-11-08 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-11-10 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2017-11-10 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-11-08 00:00:00.0000000 +00:00 | 2013-11-08 00:00:00.0000000 +00:00 | 2014-04-28 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-30 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-11-10 00:00:00.0000000 +00:00 | 2017-11-10 00:00:00.0000000 +00:00 | 2018-12-13 00:00:00.0000000 +00:00 | 2020-11-09 00:00:00.0000000 +00:00 |  | 2020-11-09 00:00:00.0000000 +00:00 | 2020-11-09 00:00:00.0000000 +00:00 |  | 2017-11-14 09:31:50.0199629 -05:00
HWP14RLM | Y | 2013-01-08 00:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2017-11-06 00:00:00.0000000 +00:00 | 2013-01-08 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-10-14 00:00:00.0000000 +00:00 | 2015-04-15 00:00:00.0000000 +00:00 | 2016-04-13 00:00:00.0000000 +00:00 | [5 empty] | 2013-01-08 17:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2017-11-06 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2017-11-06 00:00:00.0000000 +00:00 | 2013-01-08 17:00:00.0000000 +00:00 | 2013-01-08 17:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 |  | 2014-03-13 00:00:00.0000000 +00:00 | 2014-03-13 00:00:00.0000000 +00:00 | 2014-03-13 00:00:00.0000000 +00:00 | 2014-03-13 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-30 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2017-11-06 00:00:00.0000000 +00:00 | 2017-11-06 00:00:00.0000000 +00:00 | 2017-10-29 00:00:00.0000000 +00:00 | 2019-11-05 00:00:00.0000000 +00:00 |  | 2019-11-05 00:00:00.0000000 +00:00 | 2019-11-05 00:00:00.0000000 +00:00 |  | 2017-11-20 07:51:21.7771750 -05:00
HWP14RTA | Y | 2013-01-08 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2018-06-04 00:00:00.0000000 +00:00 | 2013-01-08 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-10-14 00:00:00.0000000 +00:00 | 2015-04-15 00:00:00.0000000 +00:00 | 2016-04-13 00:00:00.0000000 +00:00 | [5 empty] | 2013-01-08 17:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 |  | 2015-12-24 00:00:00.0000000 +00:00 | 2018-06-04 00:00:00.0000000 +00:00 | 2013-01-08 17:00:00.0000000 +00:00 | 2013-01-08 17:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 |  | 2015-03-17 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-24 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2018-06-04 00:00:00.0000000 +00:00 | 2018-06-04 00:00:00.0000000 +00:00 | 2017-12-17 00:00:00.0000000 +00:00 | 2021-06-03 00:00:00.0000000 +00:00 |  | 2021-06-03 00:00:00.0000000 +00:00 | 2021-06-03 00:00:00.0000000 +00:00
HWP15KCL | Y | 2014-06-16 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-12-22 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2019-06-10 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-11-11 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-09-07 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-16 17:00:00.0000000 +00:00 | 2014-12-01 17:00:00.0000000 +00:00 | 2015-12-22 00:00:00.0000000 +00:00 | 2017-04-17 17:00:00.0000000 +00:00 |  | 2015-11-22 00:00:00.0000000 +00:00 | 2019-06-10 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-22 00:00:00.0000000 +00:00 | 2015-12-22 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2019-06-19 00:00:00.0000000 +00:00 | 2019-06-19 00:00:00.0000000 +00:00 | 2022-06-09 00:00:00.0000000 +00:00 | 2022-06-09 00:00:00.0000000 +00:00 |  | 2022-06-09 00:00:00.0000000 +00:00 | 2022-06-09 00:00:00.0000000 +00:00
HWP15KTA | Y | 2014-06-13 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2016-02-24 00:00:00.0000000 +00:00 | 2016-11-06 00:00:00.0000000 +00:00 | 2017-11-05 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-13 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-03-27 17:00:00.0000000 +00:00 |  | 2016-03-11 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-31 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | 2021-08-13 00:00:00.0000000 +00:00 | 2021-08-13 00:00:00.0000000 +00:00 |  | 2021-08-13 00:00:00.0000000 +00:00 | 2021-08-13 00:00:00.0000000 +00:00
HWP15QLA | Y
HWP15QTA | Y | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2018-06-03 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2016-02-04 00:00:00.0000000 +00:00 | 2016-09-12 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-03-06 17:00:00.0000000 +00:00 |  | 2016-02-04 00:00:00.0000000 +00:00 | 2018-06-03 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-31 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2018-06-03 00:00:00.0000000 +00:00 | 2018-06-03 00:00:00.0000000 +00:00 | 2021-06-02 00:00:00.0000000 +00:00 | 2021-06-02 00:00:00.0000000 +00:00 |  | 2021-06-02 00:00:00.0000000 +00:00 | 2021-06-02 00:00:00.0000000 +00:00 |  | 2017-08-30 14:39:50.2105527 -04:00
HWP15RSC | Y | 2014-06-13 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2019-03-31 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2019-03-31 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-13 08:00:00.0000000 +00:00 | 2014-11-14 08:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 |  | 2016-09-30 00:00:00.0000000 +00:00 | 2019-03-31 00:00:00.0000000 +00:00 | 2014-06-13 08:00:00.0000000 +00:00 |  | 2014-11-14 08:00:00.0000000 +00:00 |  | 2016-03-19 00:00:00.0000000 +00:00 | 2016-03-19 00:00:00.0000000 +00:00 | 2016-03-19 00:00:00.0000000 +00:00 | 2016-03-19 00:00:00.0000000 +00:00 | [6 empty] | 2016-09-30 00:00:00.0000000 +00:00 |  | 2017-10-02 00:00:00.0000000 +00:00 |  | 2019-03-31 00:00:00.0000000 +00:00 |  | 2020-03-25 00:00:00.0000000 +00:00 | 2020-03-25 00:00:00.0000000 +00:00 |  | 2020-03-25 00:00:00.0000000 +00:00 |  |  | 2017-11-17 14:23:58.4962838 -05:00
HWP15XMCL | Y | 2014-06-11 00:00:00.0000000 +00:00 | 2014-09-26 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-03-20 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2014-06-11 00:00:00.0000000 +00:00 | 2014-10-01 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-11 17:00:00.0000000 +00:00 | 2014-09-26 17:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-03-20 17:00:00.0000000 +00:00 |  |  | 2019-09-15 00:00:00.0000000 +00:00 | 2014-06-11 17:00:00.0000000 +00:00 | 2014-06-11 17:00:00.0000000 +00:00 | 2014-09-26 17:00:00.0000000 +00:00 | 2014-09-26 17:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-31 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-03-20 17:00:00.0000000 +00:00 | 2017-03-20 17:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2017-04-28 00:00:00.0000000 +00:00 | 2022-09-15 00:00:00.0000000 +00:00 |  | 2022-09-15 00:00:00.0000000 +00:00 | 2022-09-15 00:00:00.0000000 +00:00
HWP15XMTA | Y | 2014-06-10 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2017-03-20 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2014-06-10 00:00:00.0000000 +00:00 | 2014-10-01 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-10 17:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2017-03-20 00:00:00.0000000 +00:00 |  |  | 2018-09-15 00:00:00.0000000 +00:00 | 2014-06-10 17:00:00.0000000 +00:00 | 2014-06-10 17:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-24 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2017-03-20 00:00:00.0000000 +00:00 | 2017-03-20 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2021-09-14 00:00:00.0000000 +00:00 |  | 2021-09-14 00:00:00.0000000 +00:00 | 2021-09-14 00:00:00.0000000 +00:00
HWP16KC | Y | 2015-07-13 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2018-01-02 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-02-14 00:00:00.0000000 +00:00 | 2016-07-14 00:00:00.0000000 +00:00 | 2017-08-28 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-13 17:00:00.0000000 +00:00 | 2015-10-15 18:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 |  |  | 2017-02-01 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2015-07-13 17:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-10-15 18:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | [5 empty] | 2017-02-01 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2018-01-02 00:00:00.0000000 +00:00 | 2018-01-02 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2022-12-05 00:00:00.0000000 +00:00 | 2022-06-29 00:00:00.0000000 +00:00 |  | 2022-06-29 00:00:00.0000000 +00:00 | 2022-06-29 00:00:00.0000000 +00:00 |  | 2017-10-16 13:28:19.5361672 -04:00
HWP16MTAL | Y | 2014-09-17 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2017-06-19 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2014-09-17 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-10-15 00:00:00.0000000 +00:00 | 2017-07-11 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-17 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2017-06-19 00:00:00.0000000 +00:00 |  | 2016-06-29 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2014-09-17 00:00:00.0000000 +00:00 | 2014-09-17 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 |  | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | [5 empty] | 2016-06-29 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2017-06-19 00:00:00.0000000 +00:00 | 2017-06-19 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2019-07-12 00:00:00.0000000 +00:00 | 2022-06-18 00:00:00.0000000 +00:00 |  | 2022-06-18 00:00:00.0000000 +00:00 | 2022-06-18 00:00:00.0000000 +00:00
HWP16XTA | Y | 2015-04-12 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2017-05-02 00:00:00.0000000 +00:00 | 2017-11-18 00:00:00.0000000 +00:00 | 2019-05-16 00:00:00.0000000 +00:00 | 2015-04-10 00:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2016-08-08 00:00:00.0000000 +00:00 | 2017-04-08 00:00:00.0000000 +00:00 | 2017-11-04 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-10 00:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2017-05-02 00:00:00.0000000 +00:00 |  |  | 2017-05-02 00:00:00.0000000 +00:00 |  | 2015-04-10 00:00:00.0000000 +00:00 |  | 2015-07-06 00:00:00.0000000 +00:00 |  | 2016-02-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | [6 empty] | 2017-05-02 00:00:00.0000000 +00:00 |  | 2017-11-18 00:00:00.0000000 +00:00 |  | 2019-05-16 00:00:00.0000000 +00:00 |  | 2022-05-16 00:00:00.0000000 +00:00 | 2022-05-16 00:00:00.0000000 +00:00 |  | 2022-05-16 00:00:00.0000000 +00:00
HWP2010R | Y | 2009-08-11 00:00:00.0000000 +00:00 | 2009-10-05 00:00:00.0000000 +00:00 | 2010-02-17 00:00:00.0000000 +00:00 | 2011-01-03 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2009-08-11 00:00:00.0000000 +00:00 | 2009-10-15 00:00:00.0000000 +00:00 | 2010-01-15 00:00:00.0000000 +00:00 | 2010-07-12 00:00:00.0000000 +00:00 | 2012-07-11 00:00:00.0000000 +00:00 | 2009-08-11 00:00:00.0000000 +00:00 | 2009-10-05 00:00:00.0000000 +00:00 | 2010-02-17 00:00:00.0000000 +00:00 | 2011-01-03 00:00:00.0000000 +00:00 | 2013-01-02 00:00:00.0000000 +00:00 | 2009-08-11 12:00:00.0000000 +00:00 | 2009-10-05 18:00:00.0000000 +00:00 | 2010-02-17 17:00:00.0000000 +00:00 | 2011-01-03 17:00:00.0000000 +00:00 | 2013-06-28 18:00:00.0000000 +00:00 | 2010-02-17 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2009-08-11 00:00:00.0000000 +00:00 | 2009-08-11 00:00:00.0000000 +00:00 | 2009-10-05 00:00:00.0000000 +00:00 | 2009-10-05 00:00:00.0000000 +00:00 |  | 2009-11-30 00:00:00.0000000 +00:00 | 2009-11-30 00:00:00.0000000 +00:00 | 2009-11-30 00:00:00.0000000 +00:00 | 2009-11-30 00:00:00.0000000 +00:00 | [5 empty] | 2010-02-17 00:00:00.0000000 +00:00 | 2010-02-17 00:00:00.0000000 +00:00 | 2011-01-03 00:00:00.0000000 +00:00 | 2011-01-03 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00
HWP2012QC | Y | 2011-10-24 00:00:00.0000000 +00:00 | 2011-11-07 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2013-10-21 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2011-10-24 00:00:00.0000000 +00:00 | 2011-11-07 00:00:00.0000000 +00:00 | 2012-05-08 00:00:00.0000000 +00:00 | 2012-11-06 00:00:00.0000000 +00:00 | 2014-10-29 00:00:00.0000000 +00:00 | 2011-10-24 00:00:00.0000000 +00:00 | 2011-11-07 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2016-06-22 00:00:00.0000000 +00:00 | 2011-10-24 12:00:00.0000000 +00:00 | 2011-11-07 12:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2013-10-21 00:00:00.0000000 +00:00 | 2015-10-20 17:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 |  | 2011-10-24 12:00:00.0000000 +00:00 |  | 2011-11-07 12:00:00.0000000 +00:00 |  | 2012-01-16 00:00:00.0000000 +00:00 | 2012-01-16 00:00:00.0000000 +00:00 |  | 2012-01-16 00:00:00.0000000 +00:00 | [6 empty] | 2012-03-07 00:00:00.0000000 +00:00 |  | 2013-10-21 00:00:00.0000000 +00:00 |  | 2015-10-20 17:00:00.0000000 +00:00 | 2017-10-29 00:00:00.0000000 +00:00 | 2018-10-20 00:00:00.0000000 +00:00 |  |  | 2018-10-20 00:00:00.0000000 +00:00
HWP2012R | Y | 2011-10-18 00:00:00.0000000 +00:00 | 2011-11-28 00:00:00.0000000 +00:00 | 2012-01-19 00:00:00.0000000 +00:00 | 2013-03-18 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 | 2011-11-28 00:00:00.0000000 +00:00 | 2012-01-16 00:00:00.0000000 +00:00 | 2012-07-16 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | [5 empty] | 2011-10-18 18:00:00.0000000 +00:00 | 2011-11-28 17:00:00.0000000 +00:00 | 2012-01-19 17:00:00.0000000 +00:00 | 2013-03-18 18:00:00.0000000 +00:00 | 2014-11-07 17:00:00.0000000 +00:00 | 2012-01-19 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 |  | 2011-10-18 18:00:00.0000000 +00:00 |  | 2011-11-28 17:00:00.0000000 +00:00 |  | 2011-12-15 00:00:00.0000000 +00:00 | 2011-12-15 00:00:00.0000000 +00:00 |  | 2011-12-15 00:00:00.0000000 +00:00 | [6 empty] | 2012-01-19 17:00:00.0000000 +00:00 |  | 2013-03-18 18:00:00.0000000 +00:00 |  | 2014-11-07 17:00:00.0000000 +00:00 |  | 2018-03-16 00:00:00.0000000 +00:00 |  |  | 2018-03-16 00:00:00.0000000 +00:00 |  | 2017-09-29 07:46:15.4139648 -04:00
HWP2013LM | Y | 2011-10-19 00:00:00.0000000 +00:00 | 2013-04-23 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2012-10-14 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2015-04-05 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2012-10-14 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2015-04-05 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2013-04-23 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 |  | 2015-03-11 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2013-04-23 00:00:00.0000000 +00:00 | 2013-04-23 00:00:00.0000000 +00:00 |  | 2014-08-19 00:00:00.0000000 +00:00 | 2014-08-19 00:00:00.0000000 +00:00 | 2014-08-19 00:00:00.0000000 +00:00 | 2014-08-19 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-31 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2018-03-13 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 |  | 2019-07-01 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 |  | 2017-11-29 14:38:18.9714763 -05:00
HWP2013MX | Y | 2012-07-27 00:00:00.0000000 +00:00 | 2012-09-04 00:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 | 2018-03-22 00:00:00.0000000 +00:00 | 2012-07-27 00:00:00.0000000 +00:00 | 2012-09-14 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2012-07-27 00:00:00.0000000 +00:00 | 2012-09-14 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2014-03-12 00:00:00.0000000 +00:00 | 2016-03-10 00:00:00.0000000 +00:00 | 2012-07-27 00:00:00.0000000 +00:00 | 2012-09-04 00:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 |  | 2013-02-08 00:00:00.0000000 +00:00 | 2018-03-22 00:00:00.0000000 +00:00 | 2012-07-27 00:00:00.0000000 +00:00 | 2012-07-27 00:00:00.0000000 +00:00 | 2012-09-04 00:00:00.0000000 +00:00 | 2012-09-04 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | [5 empty] | 2013-02-08 00:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 | 2018-03-22 00:00:00.0000000 +00:00 | 2018-03-22 00:00:00.0000000 +00:00 | 2018-08-10 00:00:00.0000000 +00:00 | 2021-03-21 00:00:00.0000000 +00:00 |  | 2021-03-21 00:00:00.0000000 +00:00 | 2021-03-21 00:00:00.0000000 +00:00 |  | 2017-11-16 15:08:17.5360482 -05:00
HWP2013TA | Y | 2011-10-19 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2016-04-18 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2012-10-14 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2015-04-05 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2012-10-14 00:00:00.0000000 +00:00 | 2013-10-10 00:00:00.0000000 +00:00 | 2015-01-27 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2016-04-18 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2013-10-05 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2011-10-19 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 |  | 2014-04-06 00:00:00.0000000 +00:00 | 2014-04-06 00:00:00.0000000 +00:00 | 2014-04-06 00:00:00.0000000 +00:00 | 2014-04-06 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-31 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2016-04-18 00:00:00.0000000 +00:00 | 2016-04-18 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2018-04-03 00:00:00.0000000 +00:00 | 2019-12-10 00:00:00.0000000 +00:00 |  | 2019-12-10 00:00:00.0000000 +00:00 | 2019-12-10 00:00:00.0000000 +00:00
HWP2016M1 | Y | [48 empty] | 2017-09-01 16:20:27.6888795 -04:00
HWP2016M2 | Y | [48 empty] | 2017-09-01 16:21:28.5887617 -04:00
HWP2016M3 | Y | [48 empty] | 2017-09-01 16:22:18.4963666 -04:00
HWPEDSF1 | Y | 2011-06-03 00:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2014-11-18 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2011-06-03 00:00:00.0000000 +00:00 | 2011-12-31 00:00:00.0000000 +00:00 | 2014-11-18 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2017-06-29 00:00:00.0000000 +00:00 | 2011-06-03 00:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 | 2016-08-13 00:00:00.0000000 +00:00 | 2011-06-03 12:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2014-11-18 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 |  | 2014-11-18 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2011-06-03 00:00:00.0000000 +00:00 | 2011-06-03 12:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2012-10-17 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | [5 empty] | 2014-11-18 00:00:00.0000000 +00:00 | 2014-11-18 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2020-06-28 00:00:00.0000000 +00:00 | 2021-04-29 00:00:00.0000000 +00:00 |  |  | 2021-04-29 00:00:00.0000000 +00:00
HWPEDSF3A | Y | 2013-03-04 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 | 2018-08-20 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2015-02-15 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 | 2016-08-14 00:00:00.0000000 +00:00 | 2013-03-04 12:00:00.0000000 +00:00 | 2013-03-04 17:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 |  | 2016-01-28 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2013-03-04 12:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2013-03-04 17:00:00.0000000 +00:00 |  | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-28 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2018-08-20 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | 2021-08-19 00:00:00.0000000 +00:00 |  | 2021-06-29 00:00:00.0000000 +00:00 | 2021-08-19 00:00:00.0000000 +00:00
HWPEDSF3-R | Y | 2011-06-15 00:00:00.0000000 +00:00 | 2011-07-12 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-07-12 00:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2013-12-31 00:00:00.0000000 +00:00 | 2014-08-29 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-07-12 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2013-12-04 00:00:00.0000000 +00:00 | 2014-08-02 00:00:00.0000000 +00:00 | 2011-06-15 12:00:00.0000000 +00:00 | 2011-07-12 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2014-01-20 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-07-12 00:00:00.0000000 +00:00 | 2011-07-12 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | [5 empty] | 2013-06-03 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2014-01-20 00:00:00.0000000 +00:00 | 2014-01-20 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 |  | 2017-11-20 11:12:20.1723371 -05:00
HWPEDSF4 | Y | 2013-12-30 00:00:00.0000000 +00:00 | 2014-08-07 00:00:00.0000000 +00:00 | 2017-12-14 00:00:00.0000000 +00:00 | 2018-08-26 00:00:00.0000000 +00:00 | 2020-02-25 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2014-08-07 00:00:00.0000000 +00:00 | 2016-07-07 00:00:00.0000000 +00:00 | 2017-01-04 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2015-12-29 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2017-12-20 00:00:00.0000000 +00:00 | 2013-12-30 17:00:00.0000000 +00:00 | 2014-08-07 17:00:00.0000000 +00:00 |  |  |  | 2017-10-31 00:00:00.0000000 +00:00 |  | 2013-12-30 17:00:00.0000000 +00:00 |  | 2014-08-07 17:00:00.0000000 +00:00 |  | 2015-12-18 00:00:00.0000000 +00:00 | 2017-06-23 00:00:00.0000000 +00:00 | 2017-06-23 00:00:00.0000000 +00:00 | 2017-06-23 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-14 00:00:00.0000000 +00:00 |  | 2018-08-26 00:00:00.0000000 +00:00 |  | 2020-02-25 00:00:00.0000000 +00:00 |  | 2021-06-27 00:00:00.0000000 +00:00 | 2023-02-23 00:00:00.0000000 +00:00 |  | 2023-02-23 00:00:00.0000000 +00:00
HWPEDSF5 | Y | 2017-01-26 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2019-10-02 00:00:00.0000000 +00:00 | 2020-04-03 00:00:00.0000000 +00:00 | 2021-05-02 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2019-12-17 00:00:00.0000000 +00:00 | 2020-06-18 00:00:00.0000000 +00:00 | 2021-07-17 00:00:00.0000000 +00:00 | [5 empty] | 2017-01-26 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | [5 empty] | 2017-01-26 00:00:00.0000000 +00:00 |  | 2017-08-01 00:00:00.0000000 +00:00 |  | 2018-08-18 00:00:00.0000000 +00:00 | 2018-08-18 00:00:00.0000000 +00:00 |  | 2018-08-18 00:00:00.0000000 +00:00 | [6 empty] | 2019-10-02 00:00:00.0000000 +00:00 |  | 2020-04-03 00:00:00.0000000 +00:00 |  | 2021-05-02 00:00:00.0000000 +00:00 |  | 2024-07-17 00:00:00.0000000 +00:00 | 2024-05-02 00:00:00.0000000 +00:00 |  | 2024-05-02 00:00:00.0000000 +00:00 |  |  | 2017-09-05 14:57:43.8062478 -04:00
HWPLZ001K | Y | 2009-02-02 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2013-06-04 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2017-05-17 00:00:00.0000000 +00:00 | 2009-02-02 00:00:00.0000000 +00:00 | 2009-12-15 00:00:00.0000000 +00:00 | 2011-01-13 00:00:00.0000000 +00:00 | 2011-06-08 00:00:00.0000000 +00:00 | 2012-06-12 00:00:00.0000000 +00:00 | 2009-02-02 00:00:00.0000000 +00:00 | 2010-09-15 00:00:00.0000000 +00:00 | 2013-09-01 00:00:00.0000000 +00:00 | 2014-08-30 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2009-02-02 12:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2013-06-04 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2017-05-17 17:00:00.0000000 +00:00 | 2018-03-29 00:00:00.0000000 +00:00 | 2019-07-23 00:00:00.0000000 +00:00 | 2009-02-02 00:00:00.0000000 +00:00 | 2009-02-02 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-07-12 00:00:00.0000000 +00:00 | 2011-07-11 00:00:00.0000000 +00:00 | 2011-07-11 00:00:00.0000000 +00:00 | 2011-07-11 00:00:00.0000000 +00:00 | 2011-07-11 00:00:00.0000000 +00:00 | [5 empty] | 2013-06-04 00:00:00.0000000 +00:00 | 2013-06-04 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2017-05-17 00:00:00.0000000 +00:00 | 2017-05-17 00:00:00.0000000 +00:00 | 2020-05-16 00:00:00.0000000 +00:00 | 2020-05-16 00:00:00.0000000 +00:00 |  | 2020-05-16 00:00:00.0000000 +00:00 | 2020-05-16 00:00:00.0000000 +00:00
HWPLZ003M | Y | 2009-01-27 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2018-06-26 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2009-08-01 00:00:00.0000000 +00:00 | 2011-01-15 00:00:00.0000000 +00:00 | 2011-07-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2012-08-01 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | 2009-01-27 12:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2016-06-27 18:00:00.0000000 +00:00 |  | 2015-12-04 00:00:00.0000000 +00:00 | 2018-06-28 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2009-01-27 12:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2010-06-14 00:00:00.0000000 +00:00 | 2014-06-12 00:00:00.0000000 +00:00 | 2014-06-12 00:00:00.0000000 +00:00 | 2014-06-12 00:00:00.0000000 +00:00 | 2014-06-12 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-03 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2016-06-27 18:00:00.0000000 +00:00 | 2018-06-26 00:00:00.0000000 +00:00 | 2018-06-26 00:00:00.0000000 +00:00 | 2019-12-02 00:00:00.0000000 +00:00 | 2020-06-26 00:00:00.0000000 +00:00 |  | 2020-06-26 00:00:00.0000000 +00:00 | 2020-06-26 00:00:00.0000000 +00:00
HWPLZ004M | Y | 2009-01-27 00:00:00.0000000 +00:00 | 2010-07-13 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2010-07-13 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2016-06-11 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2011-01-14 00:00:00.0000000 +00:00 | 2011-05-14 00:00:00.0000000 +00:00 | 2011-11-14 00:00:00.0000000 +00:00 | 2012-11-11 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2010-07-13 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 |  | 2013-03-15 00:00:00.0000000 +00:00 | 2017-03-24 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2010-07-13 00:00:00.0000000 +00:00 | 2010-07-13 00:00:00.0000000 +00:00 |  | 2012-03-15 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | [5 empty] | 2013-03-15 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2019-06-10 00:00:00.0000000 +00:00 | 2021-05-29 00:00:00.0000000 +00:00 |  | 2021-05-29 00:00:00.0000000 +00:00 | 2021-05-29 00:00:00.0000000 +00:00
HWPLZ004X | Y | 2015-06-16 00:00:00.0000000 +00:00 | 2016-10-07 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2018-11-26 00:00:00.0000000 +00:00 | 2020-05-24 00:00:00.0000000 +00:00 | 2015-06-16 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-12-24 00:00:00.0000000 +00:00 | 2018-07-14 00:00:00.0000000 +00:00 | 2019-07-13 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-16 00:00:00.0000000 +00:00 | 2016-10-07 00:00:00.0000000 +00:00 |  |  |  | 2018-03-30 00:00:00.0000000 +00:00 |  | 2015-06-16 00:00:00.0000000 +00:00 |  | 2016-10-07 00:00:00.0000000 +00:00 |  | 2017-02-24 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | [6 empty] | 2018-03-30 00:00:00.0000000 +00:00 |  | 2018-11-26 00:00:00.0000000 +00:00 |  | 2020-05-24 00:00:00.0000000 +00:00 |  | 2022-07-12 00:00:00.0000000 +00:00 | 2023-05-24 00:00:00.0000000 +00:00 |  | 2023-05-24 00:00:00.0000000 +00:00 |  |  | 2017-10-18 12:45:01.1060896 -04:00
HWPLZ008M | Y | 2009-01-27 00:00:00.0000000 +00:00 | 2010-11-08 00:00:00.0000000 +00:00 | 2013-08-09 00:00:00.0000000 +00:00 | 2014-10-20 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2009-07-15 00:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2011-01-15 00:00:00.0000000 +00:00 | 2012-01-15 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2010-11-08 00:00:00.0000000 +00:00 | 2012-12-15 00:00:00.0000000 +00:00 | 2013-06-23 00:00:00.0000000 +00:00 | 2014-06-23 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2010-11-08 00:00:00.0000000 +00:00 | 2013-08-09 00:00:00.0000000 +00:00 | 2014-10-20 00:00:00.0000000 +00:00 |  | 2014-04-01 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2010-11-08 00:00:00.0000000 +00:00 | 2010-11-08 00:00:00.0000000 +00:00 |  | 2013-01-03 00:00:00.0000000 +00:00 | 2013-01-03 00:00:00.0000000 +00:00 | 2013-01-03 00:00:00.0000000 +00:00 | 2013-01-03 00:00:00.0000000 +00:00 | [5 empty] | 2013-08-09 00:00:00.0000000 +00:00 | 2013-08-09 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2014-10-20 00:00:00.0000000 +00:00 | 2015-04-09 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2015-01-14 00:00:00.0000000 +00:00 | 2020-10-29 00:00:00.0000000 +00:00 |  | 2018-04-08 00:00:00.0000000 +00:00 | 2018-10-18 00:00:00.0000000 +00:00
HWPLZ008Q | Y | 2009-01-12 00:00:00.0000000 +00:00 | 2011-12-12 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2009-01-12 00:00:00.0000000 +00:00 | 2013-02-21 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2014-08-23 00:00:00.0000000 +00:00 | 2015-08-19 00:00:00.0000000 +00:00 | 2009-01-12 00:00:00.0000000 +00:00 | 2011-12-12 00:00:00.0000000 +00:00 | 2013-11-24 00:00:00.0000000 +00:00 | 2014-05-27 00:00:00.0000000 +00:00 | 2015-05-23 00:00:00.0000000 +00:00 | 2009-01-12 00:00:00.0000000 +00:00 | 2011-12-12 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-12-14 17:00:00.0000000 +00:00 | 2017-06-30 17:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 |  | 2009-01-12 00:00:00.0000000 +00:00 |  | 2011-12-12 00:00:00.0000000 +00:00 | 2013-09-26 00:00:00.0000000 +00:00 | 2013-09-26 00:00:00.0000000 +00:00 | 2013-09-26 00:00:00.0000000 +00:00 |  | 2013-09-26 00:00:00.0000000 +00:00 | [6 empty] | 2015-02-05 00:00:00.0000000 +00:00 |  | 2015-12-14 17:00:00.0000000 +00:00 |  | 2017-06-30 17:00:00.0000000 +00:00 | 2018-08-19 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 |  |  | 2020-06-30 00:00:00.0000000 +00:00 |  | 2017-08-30 16:14:36.2582433 -04:00
HWPLZ009K | Y | 2011-12-19 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2016-06-20 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2012-07-19 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2013-05-12 00:00:00.0000000 +00:00 | 2014-05-13 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2012-08-02 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2015-05-24 00:00:00.0000000 +00:00 | 2016-05-24 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2016-06-20 00:00:00.0000000 +00:00 |  | 2015-07-15 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2011-12-19 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2013-04-29 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-30 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2016-06-20 00:00:00.0000000 +00:00 | 2016-06-20 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2020-12-14 00:00:00.0000000 +00:00 | 2020-12-14 00:00:00.0000000 +00:00 |  | 2020-12-14 00:00:00.0000000 +00:00 | 2020-12-14 00:00:00.0000000 +00:00
HWPLZ009M | Y | 2009-01-27 00:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2013-11-16 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2009-07-15 00:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2011-01-15 00:00:00.0000000 +00:00 | 2012-01-15 00:00:00.0000000 +00:00 | 2009-01-27 00:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2013-10-05 00:00:00.0000000 +00:00 | 2014-04-07 00:00:00.0000000 +00:00 | 2015-04-07 00:00:00.0000000 +00:00 | 2009-01-27 12:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2014-03-04 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2019-08-25 00:00:00.0000000 +00:00 | 2019-06-01 00:00:00.0000000 +00:00 | 2009-01-27 12:00:00.0000000 +00:00 | 2009-01-27 12:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2010-05-01 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 | [5 empty] | 2014-03-04 00:00:00.0000000 +00:00 | 2014-03-04 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2015-01-14 00:00:00.0000000 +00:00 | 2018-11-23 00:00:00.0000000 +00:00 |  | 2018-11-23 00:00:00.0000000 +00:00 | 2018-11-23 00:00:00.0000000 +00:00
HWPLZ009Q | Y | 2012-07-09 00:00:00.0000000 +00:00 | 2013-01-31 00:00:00.0000000 +00:00 | 2015-04-13 00:00:00.0000000 +00:00 | 2016-09-28 00:00:00.0000000 +00:00 | 2017-09-27 00:00:00.0000000 +00:00 | 2012-07-09 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-06-12 00:00:00.0000000 +00:00 | 2012-07-09 00:00:00.0000000 +00:00 | 2012-11-02 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-05-10 00:00:00.0000000 +00:00 | 2016-04-06 00:00:00.0000000 +00:00 | 2012-07-09 12:00:00.0000000 +00:00 | 2013-01-31 12:00:00.0000000 +00:00 | 2015-04-13 00:00:00.0000000 +00:00 | 2016-09-28 00:00:00.0000000 +00:00 | 2017-09-26 00:00:00.0000000 +00:00 | 2015-04-13 00:00:00.0000000 +00:00 | 2017-09-27 00:00:00.0000000 +00:00 | 2012-07-09 12:00:00.0000000 +00:00 | 2012-07-09 12:00:00.0000000 +00:00 | 2013-01-31 12:00:00.0000000 +00:00 | 2013-01-31 12:00:00.0000000 +00:00 | 2013-09-26 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-13 00:00:00.0000000 +00:00 | 2015-04-13 00:00:00.0000000 +00:00 | 2016-09-28 00:00:00.0000000 +00:00 | 2016-09-28 00:00:00.0000000 +00:00 | 2017-09-27 00:00:00.0000000 +00:00 | 2017-09-27 00:00:00.0000000 +00:00 | 2018-06-12 00:00:00.0000000 +00:00 | 2020-09-27 00:00:00.0000000 +00:00 |  | 2020-09-27 00:00:00.0000000 +00:00 | 2020-09-27 00:00:00.0000000 +00:00 |  | 2017-09-27 09:42:20.4719382 -04:00
HWPLZ010K | Y | 2012-01-31 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 | 2016-09-19 00:00:00.0000000 +00:00 | 2018-03-08 00:00:00.0000000 +00:00 | 2012-01-31 00:00:00.0000000 +00:00 | 2012-12-26 00:00:00.0000000 +00:00 | 2014-01-09 00:00:00.0000000 +00:00 | 2014-06-25 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2012-01-31 00:00:00.0000000 +00:00 | 2012-12-26 00:00:00.0000000 +00:00 | 2015-03-25 00:00:00.0000000 +00:00 | 2016-04-06 00:00:00.0000000 +00:00 | 2017-04-06 00:00:00.0000000 +00:00 | 2012-01-31 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 | 2016-09-19 00:00:00.0000000 +00:00 |  | 2016-06-13 00:00:00.0000000 +00:00 | 2018-03-08 00:00:00.0000000 +00:00 | 2012-01-31 00:00:00.0000000 +00:00 | 2012-01-31 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2013-06-13 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 | [5 empty] | 2015-03-27 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 | 2016-09-19 00:00:00.0000000 +00:00 | 2016-09-19 00:00:00.0000000 +00:00 | 2018-03-08 00:00:00.0000000 +00:00 | 2018-03-08 00:00:00.0000000 +00:00 | 2020-09-17 00:00:00.0000000 +00:00 | 2020-09-17 00:00:00.0000000 +00:00 |  | 2020-09-07 00:00:00.0000000 +00:00 | 2021-03-07 00:00:00.0000000 +00:00
HWPLZ010M | Y | 2015-10-05 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2022-06-14 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2022-06-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-05 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 |  |  |  | 2019-10-30 00:00:00.0000000 +00:00 |  | 2015-10-05 00:00:00.0000000 +00:00 |  | 2017-09-11 00:00:00.0000000 +00:00 |  | 2018-08-30 00:00:00.0000000 +00:00 | 2018-08-30 00:00:00.0000000 +00:00 |  | 2018-08-30 00:00:00.0000000 +00:00 | [6 empty] | 2019-10-30 00:00:00.0000000 +00:00 |  | 2020-06-15 00:00:00.0000000 +00:00 |  | 2022-06-14 00:00:00.0000000 +00:00 |  | 2025-06-24 00:00:00.0000000 +00:00 | 2025-06-24 00:00:00.0000000 +00:00 |  | 2025-06-24 00:00:00.0000000 +00:00
HWPLZ010Q | Y | 2012-07-10 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2012-07-10 00:00:00.0000000 +00:00 | 2012-09-29 00:00:00.0000000 +00:00 | 2014-01-23 00:00:00.0000000 +00:00 | 2014-08-13 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2012-07-10 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2014-08-31 00:00:00.0000000 +00:00 | 2015-07-25 00:00:00.0000000 +00:00 | 2016-07-25 00:00:00.0000000 +00:00 | 2012-07-10 12:00:00.0000000 +00:00 | 2012-09-29 12:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2017-03-27 17:00:00.0000000 +00:00 |  | 2015-06-29 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2012-07-10 12:00:00.0000000 +00:00 | 2012-07-10 12:00:00.0000000 +00:00 | 2012-09-29 12:00:00.0000000 +00:00 | 2012-09-29 12:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-29 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2017-03-27 17:00:00.0000000 +00:00 | 2017-03-27 17:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2018-08-13 00:00:00.0000000 +00:00 | 2021-06-18 00:00:00.0000000 +00:00 |  | 2021-06-18 00:00:00.0000000 +00:00 | 2021-06-18 00:00:00.0000000 +00:00 |  | 2017-10-12 13:44:17.1854669 -04:00
HWPLZ011K | Y | 2012-01-27 00:00:00.0000000 +00:00 | 2013-04-22 00:00:00.0000000 +00:00 | 2016-09-13 00:00:00.0000000 +00:00 | 2018-05-14 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 | 2012-01-27 00:00:00.0000000 +00:00 | 2013-04-22 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2012-01-27 00:00:00.0000000 +00:00 | 2012-06-01 00:00:00.0000000 +00:00 | 2015-07-19 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2017-01-02 00:00:00.0000000 +00:00 | 2012-01-27 00:00:00.0000000 +00:00 | 2013-04-22 17:00:00.0000000 +00:00 | 2016-09-13 00:00:00.0000000 +00:00 |  |  | 2016-09-13 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 | 2012-01-27 00:00:00.0000000 +00:00 | 2012-01-27 00:00:00.0000000 +00:00 | 2013-04-22 17:00:00.0000000 +00:00 | 2013-04-22 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-13 00:00:00.0000000 +00:00 | 2016-09-13 00:00:00.0000000 +00:00 | 2018-05-14 00:00:00.0000000 +00:00 | 2018-05-14 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 | 2022-11-12 00:00:00.0000000 +00:00 | 2022-11-12 00:00:00.0000000 +00:00 |  | 2022-11-12 00:00:00.0000000 +00:00 | 2022-11-12 00:00:00.0000000 +00:00 |  | 2017-08-29 12:56:36.7755826 -04:00
HWPLZ012M | Y | 2013-05-14 00:00:00.0000000 +00:00 | 2014-02-24 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2018-10-20 00:00:00.0000000 +00:00 | 2013-05-14 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2018-01-07 00:00:00.0000000 +00:00 | 2013-05-14 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2018-01-07 00:00:00.0000000 +00:00 | 2013-05-14 12:00:00.0000000 +00:00 | 2014-02-24 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2017-04-24 17:00:00.0000000 +00:00 |  | 2016-10-12 00:00:00.0000000 +00:00 | 2018-10-20 00:00:00.0000000 +00:00 | 2013-05-14 12:00:00.0000000 +00:00 | 2013-05-14 12:00:00.0000000 +00:00 | 2014-02-24 00:00:00.0000000 +00:00 | 2014-02-24 00:00:00.0000000 +00:00 |  | 2015-08-04 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-30 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2017-04-24 17:00:00.0000000 +00:00 | 2017-04-24 17:00:00.0000000 +00:00 | 2018-10-20 00:00:00.0000000 +00:00 | 2018-10-20 00:00:00.0000000 +00:00 | 2019-12-23 00:00:00.0000000 +00:00 | 2021-10-20 00:00:00.0000000 +00:00 |  | 2021-10-20 00:00:00.0000000 +00:00 | 2021-10-20 00:00:00.0000000 +00:00
HWPLZ014Q | Y | 2013-12-18 00:00:00.0000000 +00:00 | 2014-07-02 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-10-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-10-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2013-12-18 12:00:00.0000000 +00:00 | 2014-07-02 17:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 |  |  | 2018-06-15 00:00:00.0000000 +00:00 | 2013-12-18 12:00:00.0000000 +00:00 | 2013-12-18 12:00:00.0000000 +00:00 | 2014-07-02 17:00:00.0000000 +00:00 | 2014-07-02 17:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-31 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2017-04-17 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2020-09-14 00:00:00.0000000 +00:00 | 2021-06-14 00:00:00.0000000 +00:00 |  | 2021-06-14 00:00:00.0000000 +00:00 | 2021-06-14 00:00:00.0000000 +00:00 |  | 2017-10-12 13:45:21.7359531 -04:00
HWPLZ016K | Y | 2013-06-20 00:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-07-10 00:00:00.0000000 +00:00 | 2018-07-09 00:00:00.0000000 +00:00 | 2013-06-20 00:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2017-07-16 00:00:00.0000000 +00:00 | [5 empty] | 2013-06-20 17:00:00.0000000 +00:00 | 2014-06-06 17:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-07-10 17:00:00.0000000 +00:00 |  | 2016-01-16 00:00:00.0000000 +00:00 | 2018-07-09 00:00:00.0000000 +00:00 | 2013-06-20 00:00:00.0000000 +00:00 | 2013-06-20 17:00:00.0000000 +00:00 | 2014-06-06 00:00:00.0000000 +00:00 | 2014-06-06 17:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-31 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-07-10 00:00:00.0000000 +00:00 | 2017-07-10 17:00:00.0000000 +00:00 | 2018-07-09 00:00:00.0000000 +00:00 | 2018-07-09 00:00:00.0000000 +00:00 | 2021-07-08 00:00:00.0000000 +00:00 | 2021-07-08 00:00:00.0000000 +00:00 |  | 2021-07-08 00:00:00.0000000 +00:00 | 2021-07-08 00:00:00.0000000 +00:00
HWPR16M | Y | 2016-05-25 00:00:00.0000000 +00:00 | 2016-06-09 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2017-06-19 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2016-05-25 00:00:00.0000000 +00:00 | 2016-06-09 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2017-03-08 00:00:00.0000000 +00:00 | 2018-03-08 00:00:00.0000000 +00:00 | [5 empty] | 2016-05-25 00:00:00.0000000 +00:00 | 2016-06-09 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2017-06-19 00:00:00.0000000 +00:00 |  | 2016-08-31 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2016-05-25 00:00:00.0000000 +00:00 | 2016-05-25 00:00:00.0000000 +00:00 | 2016-06-09 00:00:00.0000000 +00:00 | 2016-06-09 00:00:00.0000000 +00:00 |  | 2016-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2017-06-19 00:00:00.0000000 +00:00 | 2017-06-19 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2020-03-08 00:00:00.0000000 +00:00 | 2022-06-18 00:00:00.0000000 +00:00 |  | 2022-06-18 00:00:00.0000000 +00:00 | 2022-06-18 00:00:00.0000000 +00:00 |  | 2017-11-29 14:39:38.8752425 -05:00
HWPR17CW | Y | 2016-07-27 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-10-15 00:00:00.0000000 +00:00 | 2019-04-07 00:00:00.0000000 +00:00 | 2016-07-27 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2019-08-29 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-27 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 |  | 2016-12-15 00:00:00.0000000 +00:00 | 2019-04-07 00:00:00.0000000 +00:00 | 2016-07-27 00:00:00.0000000 +00:00 | 2016-07-27 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-10-15 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 | 2019-10-13 00:00:00.0000000 +00:00 | 2019-04-07 00:00:00.0000000 +00:00 | 2022-08-29 00:00:00.0000000 +00:00 | 2022-04-07 00:00:00.0000000 +00:00 |  | 2022-10-12 00:00:00.0000000 +00:00 | 2022-04-07 00:00:00.0000000 +00:00 |  | 2017-12-01 14:15:56.1522697 -05:00
HWPR17K | Y | 2016-08-09 00:00:00.0000000 +00:00 | 2016-09-09 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 | 2019-06-01 00:00:00.0000000 +00:00 | 2016-08-09 00:00:00.0000000 +00:00 | 2016-09-09 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2018-07-14 00:00:00.0000000 +00:00 | [5 empty] | 2016-08-09 18:00:00.0000000 +00:00 | 2016-09-09 17:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 |  | 2016-12-20 00:00:00.0000000 +00:00 | 2019-06-01 00:00:00.0000000 +00:00 | 2016-08-09 18:00:00.0000000 +00:00 | 2016-08-09 00:00:00.0000000 +00:00 | 2016-09-09 17:00:00.0000000 +00:00 | 2016-09-09 00:00:00.0000000 +00:00 | 2016-10-17 00:00:00.0000000 +00:00 | 2016-10-15 00:00:00.0000000 +00:00 | 2016-10-15 00:00:00.0000000 +00:00 | 2016-10-15 00:00:00.0000000 +00:00 | 2016-10-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-19 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 | 2019-06-01 00:00:00.0000000 +00:00 | 2019-06-01 00:00:00.0000000 +00:00 | 2022-05-11 00:00:00.0000000 +00:00 | 2022-05-31 00:00:00.0000000 +00:00 |  | 2022-05-31 00:00:00.0000000 +00:00 | 2022-05-31 00:00:00.0000000 +00:00 |  | 2017-10-16 13:34:14.5599287 -04:00
HWPR17M | Y | 2016-07-28 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 | 2019-04-07 00:00:00.0000000 +00:00 | 2016-07-28 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2018-08-30 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-28 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 |  | 2016-12-15 00:00:00.0000000 +00:00 | 2019-04-07 00:00:00.0000000 +00:00 | 2016-07-28 00:00:00.0000000 +00:00 | 2016-07-28 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 | 2019-08-29 00:00:00.0000000 +00:00 | 2019-08-29 00:00:00.0000000 +00:00 | 2020-08-30 00:00:00.0000000 +00:00 | 2022-04-06 00:00:00.0000000 +00:00 |  | 2022-08-29 00:00:00.0000000 +00:00 | 2022-08-29 00:00:00.0000000 +00:00 |  | 2017-11-30 10:12:46.7643109 -05:00
HWPR17Q | Y | 2016-07-29 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2019-06-08 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-10-11 00:00:00.0000000 +00:00 | 2019-04-08 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-29 18:00:00.0000000 +00:00 | 2016-08-15 18:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 |  | 2017-01-15 00:00:00.0000000 +00:00 |  | 2016-07-29 18:00:00.0000000 +00:00 |  | 2016-08-15 18:00:00.0000000 +00:00 |  | 2016-10-18 00:00:00.0000000 +00:00 | 2016-10-18 00:00:00.0000000 +00:00 | 2016-10-18 00:00:00.0000000 +00:00 | 2016-10-18 00:00:00.0000000 +00:00 | [6 empty] | 2016-12-19 00:00:00.0000000 +00:00 |  | 2017-12-11 00:00:00.0000000 +00:00 |  | 2019-06-08 00:00:00.0000000 +00:00 |  | 2022-09-04 00:00:00.0000000 +00:00 | 2022-06-07 00:00:00.0000000 +00:00 |  | 2022-06-07 00:00:00.0000000 +00:00 |  |  | 2017-12-08 11:43:07.6914477 -05:00
HWPR17R | Y | 2016-07-26 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2016-08-18 00:00:00.0000000 +00:00 | 2016-10-31 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2018-08-13 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 18:00:00.0000000 +00:00 | 2016-08-29 18:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 |  | 2016-12-19 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2016-07-26 18:00:00.0000000 +00:00 | 2016-07-26 18:00:00.0000000 +00:00 | 2016-08-29 18:00:00.0000000 +00:00 | 2016-08-29 18:00:00.0000000 +00:00 |  | 2016-10-20 00:00:00.0000000 +00:00 | 2016-10-20 00:00:00.0000000 +00:00 | 2016-10-20 00:00:00.0000000 +00:00 | 2016-10-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-19 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2019-02-08 00:00:00.0000000 +00:00 | 2022-03-28 00:00:00.0000000 +00:00 |  | 2022-03-28 00:00:00.0000000 +00:00 | 2022-03-28 00:00:00.0000000 +00:00 |  | 2017-09-11 08:15:34.2811103 -04:00
HWPR17X | Y | 2016-07-28 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2019-07-13 00:00:00.0000000 +00:00 | 2016-07-28 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-28 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 |  |  | 2016-12-19 00:00:00.0000000 +00:00 | 2019-07-13 00:00:00.0000000 +00:00 | 2016-07-28 00:00:00.0000000 +00:00 |  | 2016-08-15 00:00:00.0000000 +00:00 |  | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | [6 empty] | 2016-12-19 00:00:00.0000000 +00:00 |  | 2018-01-15 00:00:00.0000000 +00:00 |  | 2019-07-13 00:00:00.0000000 +00:00 |  | 2021-08-12 00:00:00.0000000 +00:00 | 2022-11-12 00:00:00.0000000 +00:00 |  | 2022-11-12 00:00:00.0000000 +00:00 |  |  | 2017-11-16 15:08:31.4122447 -05:00
HWPR18K1 | Y | 2017-07-28 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-28 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 |  |  | 2017-12-30 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-30 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2022-09-24 00:00:00.0000000 +00:00 | 2022-09-24 00:00:00.0000000 +00:00 |  | 2022-09-24 00:00:00.0000000 +00:00 | 2022-09-24 00:00:00.0000000 +00:00 |  | 2017-12-14 10:24:45.5704936 -05:00
HWPR18K2 | Y | 2017-07-28 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-28 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 |  |  | 2017-12-30 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 | 2017-07-28 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | [5 empty] | 2017-12-30 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2022-09-24 00:00:00.0000000 +00:00 | 2022-09-24 00:00:00.0000000 +00:00 |  | 2022-09-24 00:00:00.0000000 +00:00 | 2022-09-24 00:00:00.0000000 +00:00 |  | 2017-12-14 10:21:55.6856111 -05:00
HWPR18M | Y | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-08-01 00:00:00.0000000 +00:00 | 2020-01-28 00:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-08-01 00:00:00.0000000 +00:00 | 2020-01-28 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 |  |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2017-07-14 00:00:00.0000000 +00:00 |  | 2017-08-14 00:00:00.0000000 +00:00 |  | 2017-09-13 00:00:00.0000000 +00:00 | 2017-09-13 00:00:00.0000000 +00:00 | 2017-09-13 00:00:00.0000000 +00:00 | 2017-09-13 00:00:00.0000000 +00:00 | [6 empty] | 2017-11-30 00:00:00.0000000 +00:00 |  | 2018-08-01 00:00:00.0000000 +00:00 |  | 2020-01-28 00:00:00.0000000 +00:00 |  | 2023-01-28 00:00:00.0000000 +00:00 | 2023-01-28 00:00:00.0000000 +00:00 |  | 2023-01-28 00:00:00.0000000 +00:00 |  |  | 2017-11-30 13:20:56.0966434 -05:00
HWPR18Q1 | Y | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2020-03-23 00:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2020-03-23 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-14 17:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 |  |  | 2017-12-29 00:00:00.0000000 +00:00 |  | 2017-07-14 17:00:00.0000000 +00:00 |  | 2017-08-14 00:00:00.0000000 +00:00 |  | 2017-10-05 00:00:00.0000000 +00:00 | 2017-10-05 00:00:00.0000000 +00:00 | 2017-10-05 00:00:00.0000000 +00:00 | 2017-10-05 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-09-26 00:00:00.0000000 +00:00 |  | 2020-03-23 00:00:00.0000000 +00:00 |  | 2023-03-23 00:00:00.0000000 +00:00 | 2023-03-23 00:00:00.0000000 +00:00 |  | 2022-03-30 00:00:00.0000000 +00:00 |  |  | 2017-12-14 09:13:08.5205707 -05:00
HWPR18Q2 | Y | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2020-03-23 00:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2020-03-23 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-14 17:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 |  |  | 2017-12-29 00:00:00.0000000 +00:00 |  | 2017-07-14 17:00:00.0000000 +00:00 |  | 2017-08-14 00:00:00.0000000 +00:00 |  | 2017-10-05 00:00:00.0000000 +00:00 | 2017-10-05 00:00:00.0000000 +00:00 | 2017-10-05 00:00:00.0000000 +00:00 | 2017-10-05 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-09-26 00:00:00.0000000 +00:00 |  | 2020-03-23 00:00:00.0000000 +00:00 |  | 2023-03-23 00:00:00.0000000 +00:00 | 2023-03-23 00:00:00.0000000 +00:00 |  | 2022-03-30 00:00:00.0000000 +00:00 |  |  | 2017-12-14 09:04:20.2588618 -05:00
HWPR18R | Y | 2017-07-21 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-08-06 00:00:00.0000000 +00:00 | 2019-08-05 00:00:00.0000000 +00:00 | 2017-07-21 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-08-06 00:00:00.0000000 +00:00 | 2019-08-05 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-21 17:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 |  |  | 2017-12-07 00:00:00.0000000 +00:00 |  | 2017-07-21 17:00:00.0000000 +00:00 |  | 2017-08-14 00:00:00.0000000 +00:00 |  |  | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | [6 empty] | 2017-11-30 00:00:00.0000000 +00:00 |  | 2018-08-06 00:00:00.0000000 +00:00 |  | 2019-08-05 00:00:00.0000000 +00:00 |  | 2022-08-03 00:00:00.0000000 +00:00 | 2022-08-03 00:00:00.0000000 +00:00 |  | 2022-08-03 00:00:00.0000000 +00:00 |  |  | 2017-12-07 15:31:59.7510525 -05:00
HWPR18X | Y | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2020-03-23 00:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2020-03-23 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-14 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 |  |  | 2017-12-07 00:00:00.0000000 +00:00 |  | 2017-07-14 00:00:00.0000000 +00:00 |  | 2017-08-14 00:00:00.0000000 +00:00 |  | 2017-09-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | 2017-09-15 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-07 00:00:00.0000000 +00:00 |  | 2018-09-26 00:00:00.0000000 +00:00 |  | 2020-03-23 00:00:00.0000000 +00:00 |  | 2023-03-22 00:00:00.0000000 +00:00 | 2023-03-22 00:00:00.0000000 +00:00 |  | 2023-03-22 00:00:00.0000000 +00:00 |  |  | 2017-10-18 12:38:04.5337728 -04:00
HWPS199 | Y | 2015-04-23 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2018-10-27 00:00:00.0000000 +00:00 | 2015-04-23 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-12-18 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-23 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 |  | 2016-04-29 00:00:00.0000000 +00:00 | 2018-10-27 00:00:00.0000000 +00:00 | 2015-04-23 00:00:00.0000000 +00:00 | 2015-04-23 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2016-01-20 00:00:00.0000000 +00:00 | 2016-01-20 00:00:00.0000000 +00:00 | 2016-01-20 00:00:00.0000000 +00:00 | 2016-01-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-04-29 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2018-10-27 00:00:00.0000000 +00:00 | 2018-10-27 00:00:00.0000000 +00:00 | 2020-12-17 00:00:00.0000000 +00:00 | 2021-10-26 00:00:00.0000000 +00:00 |  | 2021-10-26 00:00:00.0000000 +00:00 | 2021-10-26 00:00:00.0000000 +00:00 |  | 2017-11-13 09:24:55.0415743 -05:00
HWQ100FJM | Y | 2015-11-16 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-07-23 00:00:00.0000000 +00:00 | 2020-08-06 00:00:00.0000000 +00:00 | 2015-11-16 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 | 2017-09-12 00:00:00.0000000 +00:00 | 2018-05-14 00:00:00.0000000 +00:00 | 2019-05-13 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-16 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 |  |  |  | 2017-12-30 00:00:00.0000000 +00:00 |  | 2015-11-16 00:00:00.0000000 +00:00 |  | 2016-05-02 00:00:00.0000000 +00:00 |  | 2017-05-03 00:00:00.0000000 +00:00 | 2017-05-03 00:00:00.0000000 +00:00 | 2017-05-03 00:00:00.0000000 +00:00 | 2017-05-03 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-30 00:00:00.0000000 +00:00 |  | 2018-07-23 00:00:00.0000000 +00:00 |  | 2020-08-06 00:00:00.0000000 +00:00 |  | 2022-05-12 00:00:00.0000000 +00:00 | 2023-08-05 00:00:00.0000000 +00:00 |  | 2023-08-05 00:00:00.0000000 +00:00 |  |  | 2017-10-12 13:47:43.7345902 -04:00
HWQ100SBA | Y | 2017-01-24 00:00:00.0000000 +00:00 | 2017-08-03 00:00:00.0000000 +00:00 | 2019-04-04 00:00:00.0000000 +00:00 | 2019-11-30 00:00:00.0000000 +00:00 | 2022-11-29 00:00:00.0000000 +00:00 | 2017-01-24 00:00:00.0000000 +00:00 | 2017-08-03 00:00:00.0000000 +00:00 | 2019-04-04 00:00:00.0000000 +00:00 | 2019-11-30 00:00:00.0000000 +00:00 | 2022-11-29 00:00:00.0000000 +00:00 | [5 empty] | 2017-01-24 00:00:00.0000000 +00:00 | 2017-08-03 00:00:00.0000000 +00:00 |  |  |  | 2019-04-04 00:00:00.0000000 +00:00 |  | 2017-01-24 00:00:00.0000000 +00:00 |  | 2017-08-03 00:00:00.0000000 +00:00 |  | 2018-02-15 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 |  | 2018-02-15 00:00:00.0000000 +00:00 | [6 empty] | 2019-04-04 00:00:00.0000000 +00:00 |  | 2019-10-02 00:00:00.0000000 +00:00 |  | 2022-11-29 00:00:00.0000000 +00:00 |  | 2025-11-28 00:00:00.0000000 +00:00 | 2025-11-28 00:00:00.0000000 +00:00 |  | 2025-11-28 00:00:00.0000000 +00:00 |  |  | 2017-09-01 08:59:28.4974206 -04:00
HWQ100SBS | Y
HWQ1079 | Y
HWQ1126B | Y | 2000-01-17 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2020-07-11 00:00:00.0000000 +00:00 | 2022-07-10 00:00:00.0000000 +00:00 | 2000-01-17 00:00:00.0000000 +00:00 | 2002-03-04 00:00:00.0000000 +00:00 | 2002-09-06 00:00:00.0000000 +00:00 | 2003-03-03 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 | 2000-01-17 00:00:00.0000000 +00:00 | 2014-01-16 00:00:00.0000000 +00:00 | 2019-08-01 00:00:00.0000000 +00:00 | 2020-01-26 00:00:00.0000000 +00:00 | 2023-01-21 00:00:00.0000000 +00:00 | 2000-01-17 12:00:00.0000000 +00:00 | [5 empty] | 2023-07-12 00:00:00.0000000 +00:00 |  |  |  |  | 2002-03-13 00:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 | [14 empty] | 2007-03-01 00:00:00.0000000 +00:00 | 2025-07-09 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-14 08:53:36.5791173 -04:00
HWQ1126C | Y | 2000-01-17 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 |  |  |  | 2000-01-17 00:00:00.0000000 +00:00 | 2004-02-02 00:00:00.0000000 +00:00 | 2004-08-09 00:00:00.0000000 +00:00 | 2005-02-07 00:00:00.0000000 +00:00 | 2006-02-03 00:00:00.0000000 +00:00 | 2000-01-17 00:00:00.0000000 +00:00 | 2011-01-07 00:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 | 2023-06-05 00:00:00.0000000 +00:00 | 2024-05-31 00:00:00.0000000 +00:00 | 2000-01-17 12:00:00.0000000 +00:00 | [32 empty] | 2017-09-14 08:54:14.2662538 -04:00
HWQ1182A | Y | 2010-07-22 00:00:00.0000000 +00:00 | 2010-10-28 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2014-05-05 00:00:00.0000000 +00:00 | 2018-10-01 00:00:00.0000000 +00:00 | 2010-07-22 00:00:00.0000000 +00:00 | 2011-01-14 00:00:00.0000000 +00:00 | 2012-01-12 00:00:00.0000000 +00:00 | 2012-07-12 00:00:00.0000000 +00:00 | 2013-07-12 00:00:00.0000000 +00:00 | 2010-07-22 00:00:00.0000000 +00:00 | 2010-10-28 00:00:00.0000000 +00:00 | 2014-05-10 00:00:00.0000000 +00:00 | 2015-03-16 00:00:00.0000000 +00:00 | 2016-04-13 00:00:00.0000000 +00:00 | 2010-07-22 12:00:00.0000000 +00:00 | 2010-10-28 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2014-05-05 17:00:00.0000000 +00:00 |  | 2013-07-29 00:00:00.0000000 +00:00 | 2020-03-19 00:00:00.0000000 +00:00 | 2010-07-22 00:00:00.0000000 +00:00 | 2010-07-22 12:00:00.0000000 +00:00 | 2010-10-28 00:00:00.0000000 +00:00 | 2010-10-28 00:00:00.0000000 +00:00 | 2011-10-30 00:00:00.0000000 +00:00 | 2012-01-10 00:00:00.0000000 +00:00 | 2012-01-10 00:00:00.0000000 +00:00 | 2012-01-01 00:00:00.0000000 +00:00 | 2012-01-10 00:00:00.0000000 +00:00 | [5 empty] | 2013-07-29 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2014-05-05 00:00:00.0000000 +00:00 | 2014-05-05 17:00:00.0000000 +00:00 | 2018-10-01 00:00:00.0000000 +00:00 | 2018-10-01 00:00:00.0000000 +00:00 | 2016-07-12 00:00:00.0000000 +00:00 | 2021-10-01 00:00:00.0000000 +00:00 |  | 2021-10-01 00:00:00.0000000 +00:00 | 2021-10-01 00:00:00.0000000 +00:00
HWQ1182B | Y | 2014-01-06 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 | 2021-08-30 00:00:00.0000000 +00:00 | 2024-08-27 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2017-12-10 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 | 2024-08-27 00:00:00.0000000 +00:00 | [5 empty] | 2014-01-06 17:00:00.0000000 +00:00 | 2015-06-01 18:00:00.0000000 +00:00 |  |  |  | 2018-11-30 00:00:00.0000000 +00:00 |  | 2014-01-06 17:00:00.0000000 +00:00 |  | 2015-06-01 18:00:00.0000000 +00:00 |  | 2016-08-25 00:00:00.0000000 +00:00 | 2016-08-25 00:00:00.0000000 +00:00 | 2016-08-25 00:00:00.0000000 +00:00 | 2016-08-25 00:00:00.0000000 +00:00 | [6 empty] | 2018-11-30 00:00:00.0000000 +00:00 |  | 2021-08-30 00:00:00.0000000 +00:00 |  | 2024-08-27 00:00:00.0000000 +00:00 |  | 2027-08-27 00:00:00.0000000 +00:00 | 2027-08-27 00:00:00.0000000 +00:00 |  | 2027-08-27 00:00:00.0000000 +00:00 |  |  | 2017-10-16 14:05:28.9209685 -04:00
HWQ1184A | Y | 2011-03-04 00:00:00.0000000 +00:00 | 2015-01-26 00:00:00.0000000 +00:00 | 2018-12-13 00:00:00.0000000 +00:00 | 2019-10-26 00:00:00.0000000 +00:00 | 2021-04-22 00:00:00.0000000 +00:00 | 2011-03-04 00:00:00.0000000 +00:00 | 2012-01-13 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2011-03-04 00:00:00.0000000 +00:00 | 2012-04-02 00:00:00.0000000 +00:00 | 2014-08-16 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2016-02-12 00:00:00.0000000 +00:00 | 2011-03-04 12:00:00.0000000 +00:00 | 2012-01-09 00:00:00.0000000 +00:00 |  |  |  | 2020-01-04 00:00:00.0000000 +00:00 |  | 2011-03-04 12:00:00.0000000 +00:00 |  | 2012-01-09 00:00:00.0000000 +00:00 |  |  | 2017-11-22 00:00:00.0000000 +00:00 |  | 2017-11-22 00:00:00.0000000 +00:00 | [6 empty] | 2018-12-13 00:00:00.0000000 +00:00 |  | 2019-10-26 00:00:00.0000000 +00:00 |  | 2021-04-22 00:00:00.0000000 +00:00 |  | 2017-07-12 00:00:00.0000000 +00:00 | 2024-04-20 00:00:00.0000000 +00:00 |  | 2024-04-20 00:00:00.0000000 +00:00 |  |  | 2017-11-03 09:24:52.8896744 -04:00
HWQ1187 | Y | 2011-05-31 00:00:00.0000000 +00:00 | 2016-03-01 00:00:00.0000000 +00:00 | 2018-02-23 00:00:00.0000000 +00:00 | 2018-10-22 00:00:00.0000000 +00:00 | 2018-10-22 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | [5 empty] | 2014-10-27 18:00:00.0000000 +00:00 | 2016-03-01 17:00:00.0000000 +00:00 |  |  |  | 2016-03-01 00:00:00.0000000 +00:00
HWQ1188 | Y
HWQ1190 | Y
HWQ1190A | Y | 2015-11-13 00:00:00.0000000 +00:00 | 2016-08-11 00:00:00.0000000 +00:00 | 2019-03-17 00:00:00.0000000 +00:00 | 2020-11-16 00:00:00.0000000 +00:00 | 2023-11-14 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 | 2016-08-11 00:00:00.0000000 +00:00 | 2019-03-17 00:00:00.0000000 +00:00 | 2020-11-16 00:00:00.0000000 +00:00 | 2023-11-14 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-13 00:00:00.0000000 +00:00 | 2016-08-11 17:00:00.0000000 +00:00 |  |  |  | 2019-03-17 00:00:00.0000000 +00:00 | 2023-11-14 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 |  | 2016-08-11 17:00:00.0000000 +00:00 |  | 2018-03-27 00:00:00.0000000 +00:00 | 2018-03-27 00:00:00.0000000 +00:00 |  | 2018-03-27 00:00:00.0000000 +00:00 | [6 empty] | 2019-03-17 00:00:00.0000000 +00:00 |  | 2020-11-16 00:00:00.0000000 +00:00 |  | 2023-11-14 00:00:00.0000000 +00:00 |  | 2026-11-13 00:00:00.0000000 +00:00 | 2026-11-13 00:00:00.0000000 +00:00 |  | 2026-11-13 00:00:00.0000000 +00:00 |  |  | 2017-09-05 08:44:31.0131119 -04:00
HWQ1190B | Y | 2015-11-13 00:00:00.0000000 +00:00 | 2016-10-26 00:00:00.0000000 +00:00 | 2019-08-16 00:00:00.0000000 +00:00 | 2020-04-15 00:00:00.0000000 +00:00 | 2023-04-12 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 | 2016-10-26 00:00:00.0000000 +00:00 | 2019-08-16 00:00:00.0000000 +00:00 | 2020-04-15 00:00:00.0000000 +00:00 | 2023-04-12 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-13 00:00:00.0000000 +00:00 | 2016-10-26 17:00:00.0000000 +00:00 |  |  |  | 2019-08-16 00:00:00.0000000 +00:00 | 2023-04-12 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 |  | 2016-10-26 17:00:00.0000000 +00:00 |  | 2018-08-16 00:00:00.0000000 +00:00 | 2018-08-16 00:00:00.0000000 +00:00 |  | 2018-08-16 00:00:00.0000000 +00:00 | [6 empty] | 2019-08-16 00:00:00.0000000 +00:00 |  | 2020-04-15 00:00:00.0000000 +00:00 |  | 2023-04-12 00:00:00.0000000 +00:00 |  | 2026-04-11 00:00:00.0000000 +00:00 | 2026-04-11 00:00:00.0000000 +00:00 |  | 2026-04-11 00:00:00.0000000 +00:00 |  |  | 2017-09-05 08:48:00.5226802 -04:00
HWQ1190C | Y | 2017-06-28 00:00:00.0000000 +00:00 | 2018-07-10 00:00:00.0000000 +00:00 | 2020-06-19 00:00:00.0000000 +00:00 | 2021-03-15 00:00:00.0000000 +00:00 | 2024-03-12 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2018-07-10 00:00:00.0000000 +00:00 | 2020-06-19 00:00:00.0000000 +00:00 | 2021-03-15 00:00:00.0000000 +00:00 | 2024-03-12 00:00:00.0000000 +00:00 | [5 empty] | 2017-06-28 00:00:00.0000000 +00:00 | [10 empty] | 2019-10-20 00:00:00.0000000 +00:00 | 2019-10-20 00:00:00.0000000 +00:00 | [14 empty] | 2027-03-12 00:00:00.0000000 +00:00 | 2027-03-12 00:00:00.0000000 +00:00 |  |  |  | 2017-11-28 07:00:21.1800000 +00:00 | 2017-11-28 08:57:09.8667677 -05:00
HWQ1197 | Y | [47 empty] | 2017-09-09 15:33:14.4070000 +00:00 | 2017-11-30 14:50:00.0411071 -05:00
HWQ121B3 | Y | 2010-08-04 00:00:00.0000000 +00:00 | 2014-02-04 00:00:00.0000000 +00:00 | 2018-10-01 00:00:00.0000000 +00:00 | 2019-08-12 00:00:00.0000000 +00:00 | 2021-12-08 00:00:00.0000000 +00:00 | 2010-08-04 00:00:00.0000000 +00:00 | 2012-01-10 00:00:00.0000000 +00:00 | 2014-01-08 00:00:00.0000000 +00:00 | 2014-07-09 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2010-08-04 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2019-01-13 00:00:00.0000000 +00:00 | 2019-07-14 00:00:00.0000000 +00:00 | 2021-07-13 00:00:00.0000000 +00:00 | 2010-08-04 12:00:00.0000000 +00:00 | 2014-02-04 17:00:00.0000000 +00:00 |  |  |  | 2018-10-01 00:00:00.0000000 +00:00 | 2021-12-08 00:00:00.0000000 +00:00 | 2010-08-04 12:00:00.0000000 +00:00 |  | 2014-02-04 17:00:00.0000000 +00:00 |  | 2013-02-15 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | [6 empty] | 2018-10-01 00:00:00.0000000 +00:00 |  | 2019-08-12 00:00:00.0000000 +00:00 |  | 2021-12-08 00:00:00.0000000 +00:00 |  | 2019-07-08 00:00:00.0000000 +00:00 | 2024-12-08 00:00:00.0000000 +00:00 |  | 2024-12-08 00:00:00.0000000 +00:00
HWQ121B4 | Y | 2006-10-26 00:00:00.0000000 +00:00 | 2012-08-22 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2016-02-08 00:00:00.0000000 +00:00 | 2018-06-06 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 | 2012-08-22 00:00:00.0000000 +00:00 | 2015-04-01 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2017-12-01 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2014-09-27 00:00:00.0000000 +00:00 | 2015-03-31 00:00:00.0000000 +00:00 | 2019-03-21 00:00:00.0000000 +00:00 | 2006-10-26 17:00:00.0000000 +00:00 | 2012-08-22 17:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2016-02-08 17:00:00.0000000 +00:00 |  | 2015-05-14 00:00:00.0000000 +00:00 | 2018-06-06 00:00:00.0000000 +00:00 | 2006-10-26 17:00:00.0000000 +00:00 | 2006-10-26 17:00:00.0000000 +00:00 | 2012-08-22 17:00:00.0000000 +00:00 | 2012-08-22 17:00:00.0000000 +00:00 | 2014-01-16 00:00:00.0000000 +00:00 | 2014-01-16 00:00:00.0000000 +00:00 | 2014-01-16 00:00:00.0000000 +00:00 | 2014-01-16 00:00:00.0000000 +00:00 | 2014-01-16 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-14 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2016-02-08 17:00:00.0000000 +00:00 | 2016-02-08 17:00:00.0000000 +00:00 | 2018-06-06 00:00:00.0000000 +00:00 | 2018-06-06 00:00:00.0000000 +00:00 | 2020-12-01 00:00:00.0000000 +00:00 | 2021-06-06 00:00:00.0000000 +00:00 |  | 2021-06-06 00:00:00.0000000 +00:00 | 2021-06-06 00:00:00.0000000 +00:00 |  | 2017-09-05 11:11:08.2246540 -04:00
HWQ1682 | Y | 2006-10-26 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2022-01-24 00:00:00.0000000 +00:00 | 2022-07-30 00:00:00.0000000 +00:00 | 2024-07-30 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2010-01-06 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2012-07-01 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 | 2019-01-25 00:00:00.0000000 +00:00 | 2022-01-24 00:00:00.0000000 +00:00 | 2022-07-30 00:00:00.0000000 +00:00 | 2024-07-30 00:00:00.0000000 +00:00 | 2006-10-26 00:00:00.0000000 +00:00 |  |  |  |  | 2023-01-24 00:00:00.0000000 +00:00 | 2024-07-30 00:00:00.0000000 +00:00 | [20 empty] | 2025-04-30 00:00:00.0000000 +00:00 | 2027-08-15 00:00:00.0000000 +00:00
HWQ213C | Y | 2012-05-14 00:00:00.0000000 +00:00 | 2013-02-20 00:00:00.0000000 +00:00 | 2015-04-20 00:00:00.0000000 +00:00 | 2016-05-09 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2012-10-02 00:00:00.0000000 +00:00 | 2013-05-21 00:00:00.0000000 +00:00 | 2013-09-01 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2013-02-20 00:00:00.0000000 +00:00 | 2015-03-19 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2013-02-20 00:00:00.0000000 +00:00 | 2015-04-20 00:00:00.0000000 +00:00 | 2016-05-09 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2015-04-20 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2013-02-20 00:00:00.0000000 +00:00 | 2013-02-20 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2014-06-04 00:00:00.0000000 +00:00 | 2014-06-04 00:00:00.0000000 +00:00 | 2014-06-04 00:00:00.0000000 +00:00 | 2014-06-04 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-20 00:00:00.0000000 +00:00 | 2015-04-20 00:00:00.0000000 +00:00 | 2016-05-09 00:00:00.0000000 +00:00 | 2016-05-09 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | 2020-11-16 00:00:00.0000000 +00:00 |  | 2020-11-16 00:00:00.0000000 +00:00 | 2020-11-16 00:00:00.0000000 +00:00 |  | 2017-11-29 12:03:33.6118105 -05:00
HWQ233 | Y | 2008-08-29 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2022-01-15 00:00:00.0000000 +00:00 | 2022-07-16 00:00:00.0000000 +00:00 | 2023-07-17 00:00:00.0000000 +00:00 | 2008-08-29 00:00:00.0000000 +00:00 | 2010-07-15 00:00:00.0000000 +00:00 | 2012-01-16 00:00:00.0000000 +00:00 | 2012-07-16 00:00:00.0000000 +00:00 | 2013-07-17 00:00:00.0000000 +00:00 | 2008-08-29 00:00:00.0000000 +00:00 | 2019-01-13 00:00:00.0000000 +00:00 | 2021-07-16 00:00:00.0000000 +00:00 | 2022-01-14 00:00:00.0000000 +00:00 | 2023-01-15 00:00:00.0000000 +00:00 | 2008-08-29 12:00:00.0000000 +00:00 | [10 empty] | 2011-02-15 00:00:00.0000000 +00:00 | 2020-09-15 00:00:00.0000000 +00:00 | [14 empty] | 2016-07-15 00:00:00.0000000 +00:00 | 2026-07-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-03 10:22:17.2958980 -04:00
HWQ242CW | Y | 2002-03-27 00:00:00.0000000 +00:00 | 2027-03-23 00:00:00.0000000 +00:00 | 2028-09-21 00:00:00.0000000 +00:00 | 2029-03-23 00:00:00.0000000 +00:00 | 2030-09-21 00:00:00.0000000 +00:00 | 2002-03-27 00:00:00.0000000 +00:00 | 2010-03-15 00:00:00.0000000 +00:00 | 2011-09-14 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-09-13 00:00:00.0000000 +00:00 | 2002-03-27 00:00:00.0000000 +00:00 | 2019-09-04 00:00:00.0000000 +00:00 | 2021-03-05 00:00:00.0000000 +00:00 | 2021-09-04 00:00:00.0000000 +00:00 | 2023-03-05 00:00:00.0000000 +00:00 | 2002-03-27 12:00:00.0000000 +00:00 |  |  |  |  | 2028-09-21 00:00:00.0000000 +00:00 | 2030-09-21 00:00:00.0000000 +00:00 | [20 empty] | 2031-01-03 00:00:00.0000000 +00:00 | 2050-11-26 00:00:00.0000000 +00:00
HWQ274F1 | Y | 2017-07-19 00:00:00.0000000 +00:00 | 2017-08-09 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-12-04 00:00:00.0000000 +00:00 | 2020-12-02 00:00:00.0000000 +00:00 | 2017-07-19 00:00:00.0000000 +00:00 | 2017-08-09 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-12-04 00:00:00.0000000 +00:00 | 2020-12-02 00:00:00.0000000 +00:00 | 2000-08-10 00:00:00.0000000 +00:00 | 2001-04-01 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-09-16 00:00:00.0000000 +00:00 | 2017-09-16 00:00:00.0000000 +00:00 | 2017-07-19 00:00:00.0000000 +00:00 | 2017-08-09 00:00:00.0000000 +00:00 |  |  |  | 2017-12-30 00:00:00.0000000 +00:00 | 2020-12-02 00:00:00.0000000 +00:00 | 2017-07-19 00:00:00.0000000 +00:00 |  | 2017-08-09 00:00:00.0000000 +00:00 |  | 2017-10-23 00:00:00.0000000 +00:00 | 2017-10-23 00:00:00.0000000 +00:00 | 2017-10-23 00:00:00.0000000 +00:00 | 2017-10-23 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-30 00:00:00.0000000 +00:00 |  | 2018-12-04 00:00:00.0000000 +00:00 |  | 2020-12-02 00:00:00.0000000 +00:00 |  | 2023-12-02 00:00:00.0000000 +00:00 | 2023-12-02 00:00:00.0000000 +00:00 |  | 2023-12-02 00:00:00.0000000 +00:00 |  |  | 2017-11-03 09:24:52.8584344 -04:00
HWQ411B | Y | 1999-06-07 00:00:00.0000000 +00:00 | 2012-06-27 00:00:00.0000000 +00:00 | 2013-12-04 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2018-09-30 00:00:00.0000000 +00:00 | 1999-06-07 00:00:00.0000000 +00:00 | 2006-08-31 00:00:00.0000000 +00:00 | 2008-03-18 00:00:00.0000000 +00:00 | 2008-09-22 00:00:00.0000000 +00:00 | 2010-11-14 00:00:00.0000000 +00:00 | 1999-06-07 00:00:00.0000000 +00:00 | 2007-03-20 00:00:00.0000000 +00:00 | 2014-01-05 00:00:00.0000000 +00:00 | 2014-10-11 00:00:00.0000000 +00:00 | 2016-12-02 00:00:00.0000000 +00:00 | 1999-06-07 12:00:00.0000000 +00:00 | 2007-02-20 12:00:00.0000000 +00:00 | 2013-12-04 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 |  | 2013-12-04 00:00:00.0000000 +00:00 | 2018-09-30 00:00:00.0000000 +00:00 | 1999-06-07 12:00:00.0000000 +00:00 | 1999-06-07 12:00:00.0000000 +00:00 | 2007-02-20 12:00:00.0000000 +00:00 | 2007-02-20 12:00:00.0000000 +00:00 | 2007-12-30 00:00:00.0000000 +00:00 | 2013-05-04 00:00:00.0000000 +00:00 | 2013-05-04 00:00:00.0000000 +00:00 | 2013-05-04 00:00:00.0000000 +00:00 | 2013-05-04 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-04 00:00:00.0000000 +00:00 | 2013-12-04 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2018-07-25 00:00:00.0000000 +00:00 | 2018-07-25 00:00:00.0000000 +00:00 | 2013-11-14 00:00:00.0000000 +00:00 | 2021-07-25 00:00:00.0000000 +00:00 |  | 2021-07-25 00:00:00.0000000 +00:00 | 2021-07-25 00:00:00.0000000 +00:00 |  | 2017-09-19 09:22:06.7435072 -04:00
HWQ631B2 | Y | 2006-03-15 00:00:00.0000000 +00:00 | 2008-06-23 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2020-07-15 00:00:00.0000000 +00:00 | 2022-07-13 00:00:00.0000000 +00:00 | 2006-03-15 00:00:00.0000000 +00:00 | 2007-07-02 00:00:00.0000000 +00:00 | 2009-01-03 00:00:00.0000000 +00:00 | 2009-07-02 00:00:00.0000000 +00:00 | 2011-07-03 00:00:00.0000000 +00:00 | 2006-03-15 00:00:00.0000000 +00:00 | 2008-10-11 00:00:00.0000000 +00:00 | 2020-05-04 00:00:00.0000000 +00:00 | 2020-10-31 00:00:00.0000000 +00:00 | 2022-11-01 00:00:00.0000000 +00:00 | 2006-03-15 00:00:00.0000000 +00:00 | 2008-06-23 00:00:00.0000000 +00:00 |  |  |  | 2020-01-15 00:00:00.0000000 +00:00 | 2012-06-13 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-15 10:34:45.4446208 -04:00
HWQ631B3 | Y | 2007-03-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2021-02-23 00:00:00.0000000 +00:00 | 2021-08-25 00:00:00.0000000 +00:00 | 2023-08-24 00:00:00.0000000 +00:00 | 2007-03-15 00:00:00.0000000 +00:00 | 2013-07-11 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2018-02-17 00:00:00.0000000 +00:00 | 2007-03-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2020-07-15 00:00:00.0000000 +00:00 | 2021-07-15 00:00:00.0000000 +00:00 | 2007-03-15 12:00:00.0000000 +00:00 |  |  |  |  | 2021-02-23 00:00:00.0000000 +00:00 | 2023-08-24 00:00:00.0000000 +00:00
HWQ708 | Y | 2004-09-13 00:00:00.0000000 +00:00 | 2019-11-23 00:00:00.0000000 +00:00 | 2022-08-30 00:00:00.0000000 +00:00 | 2023-07-14 00:00:00.0000000 +00:00 | 2025-01-12 00:00:00.0000000 +00:00 | 2004-09-13 00:00:00.0000000 +00:00 | 2005-03-15 00:00:00.0000000 +00:00 | 2007-03-15 00:00:00.0000000 +00:00 | 2007-09-15 00:00:00.0000000 +00:00 | 2009-03-14 00:00:00.0000000 +00:00 | 2004-09-13 00:00:00.0000000 +00:00 | 2011-11-23 00:00:00.0000000 +00:00 | 2021-03-18 00:00:00.0000000 +00:00 | 2021-09-18 00:00:00.0000000 +00:00 | 2025-07-04 00:00:00.0000000 +00:00 | 2004-09-13 00:00:00.0000000 +00:00 |  |  |  |  | 2022-08-30 00:00:00.0000000 +00:00 |  | 2004-09-13 00:00:00.0000000 +00:00 |  |  |  | 2006-12-15 00:00:00.0000000 +00:00 | 2021-11-30 00:00:00.0000000 +00:00 | [14 empty] | 2012-03-12 00:00:00.0000000 +00:00 | 2028-01-10 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-14 09:29:17.5046114 -04:00
HWQ724B | Y | 2005-02-09 00:00:00.0000000 +00:00 | 2013-02-13 00:00:00.0000000 +00:00 | 2018-12-12 00:00:00.0000000 +00:00 | 2019-09-20 00:00:00.0000000 +00:00 | 2022-09-20 00:00:00.0000000 +00:00 | 2005-02-09 00:00:00.0000000 +00:00 | 2013-02-13 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2018-08-20 00:00:00.0000000 +00:00 | 2021-08-18 00:00:00.0000000 +00:00 | 2005-02-09 00:00:00.0000000 +00:00 | 2013-07-25 00:00:00.0000000 +00:00 | 2018-11-19 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 | 2022-01-18 00:00:00.0000000 +00:00 | 2005-02-09 17:00:00.0000000 +00:00 | 2013-02-13 17:00:00.0000000 +00:00 |  |  |  | 2018-12-12 00:00:00.0000000 +00:00 | 2022-09-20 00:00:00.0000000 +00:00 | 2005-02-09 17:00:00.0000000 +00:00 |  | 2013-02-13 17:00:00.0000000 +00:00 |  | 2015-12-10 00:00:00.0000000 +00:00 | 2015-12-10 00:00:00.0000000 +00:00 | 2015-12-10 00:00:00.0000000 +00:00 | 2015-12-10 00:00:00.0000000 +00:00 | [6 empty] | 2018-12-12 00:00:00.0000000 +00:00 |  | 2019-09-20 00:00:00.0000000 +00:00 |  | 2022-09-20 00:00:00.0000000 +00:00 |  | 2024-08-18 00:00:00.0000000 +00:00 | 2025-09-20 00:00:00.0000000 +00:00 |  | 2025-09-20 00:00:00.0000000 +00:00
HWQ787B3 | Y | 2011-01-11 00:00:00.0000000 +00:00 | 2013-06-17 00:00:00.0000000 +00:00 | 2016-03-29 00:00:00.0000000 +00:00 | 2018-05-22 00:00:00.0000000 +00:00 | 2019-04-20 00:00:00.0000000 +00:00 | 2011-01-11 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-14 00:00:00.0000000 +00:00 | 2011-01-11 00:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2014-07-02 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-12-29 00:00:00.0000000 +00:00 | 2011-01-11 12:00:00.0000000 +00:00 | 2013-06-17 00:00:00.0000000 +00:00 | 2016-03-29 00:00:00.0000000 +00:00 |  |  | 2016-03-29 00:00:00.0000000 +00:00 |  | 2011-01-11 12:00:00.0000000 +00:00 |  | 2013-06-17 00:00:00.0000000 +00:00 |  | 2013-11-20 00:00:00.0000000 +00:00 | 2013-11-20 00:00:00.0000000 +00:00 | 2013-11-20 00:00:00.0000000 +00:00 | 2013-11-20 00:00:00.0000000 +00:00 | [6 empty] | 2016-03-29 00:00:00.0000000 +00:00 |  | 2018-05-22 00:00:00.0000000 +00:00 |  | 2019-04-20 00:00:00.0000000 +00:00 |  | 2018-07-12 00:00:00.0000000 +00:00 | 2022-04-18 00:00:00.0000000 +00:00 |  | 2022-04-18 00:00:00.0000000 +00:00
HWQ788 | Y | 2012-02-10 00:00:00.0000000 +00:00 | 2014-10-01 00:00:00.0000000 +00:00 |  |  |  | 2012-02-10 00:00:00.0000000 +00:00 | 2014-10-01 00:00:00.0000000 +00:00 |  |  |  | 2012-02-10 00:00:00.0000000 +00:00 | 2013-12-29 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-03-30 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2012-02-10 12:00:00.0000000 +00:00 | 2014-10-01 00:00:00.0000000 +00:00 | [9 empty] | 2016-03-24 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00
HWQ985 | Y | 2008-09-02 00:00:00.0000000 +00:00 | 2010-12-21 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2018-03-14 00:00:00.0000000 +00:00 | 2008-09-02 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2011-01-17 00:00:00.0000000 +00:00 | 2011-10-16 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2008-09-02 00:00:00.0000000 +00:00 | 2010-07-14 00:00:00.0000000 +00:00 | 2014-12-12 00:00:00.0000000 +00:00 | 2015-09-10 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 | 2008-09-02 12:00:00.0000000 +00:00 | 2010-12-21 12:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 |  | 2014-04-14 00:00:00.0000000 +00:00 | 2018-03-14 00:00:00.0000000 +00:00 | 2008-09-02 12:00:00.0000000 +00:00 | 2008-09-02 12:00:00.0000000 +00:00 | 2010-12-21 12:00:00.0000000 +00:00 | 2010-12-21 12:00:00.0000000 +00:00 | 2010-03-15 00:00:00.0000000 +00:00 | 2012-04-30 00:00:00.0000000 +00:00 | 2012-04-30 00:00:00.0000000 +00:00 | 2012-04-30 00:00:00.0000000 +00:00 | 2012-04-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-04-14 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2018-03-14 00:00:00.0000000 +00:00 | 2018-03-14 00:00:00.0000000 +00:00 | 2016-04-13 00:00:00.0000000 +00:00 | 2021-03-13 00:00:00.0000000 +00:00 |  | 2021-03-13 00:00:00.0000000 +00:00 | 2021-03-13 00:00:00.0000000 +00:00
HWQF027C | Y | 2008-11-25 00:00:00.0000000 +00:00 | 2009-12-09 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2012-07-14 00:00:00.0000000 +00:00 | 2017-02-22 00:00:00.0000000 +00:00 | 2008-11-25 00:00:00.0000000 +00:00 | 2009-08-03 00:00:00.0000000 +00:00 | 2010-09-29 00:00:00.0000000 +00:00 | 2011-04-04 00:00:00.0000000 +00:00 | 2013-05-07 00:00:00.0000000 +00:00 | 2008-11-25 00:00:00.0000000 +00:00 | 2009-11-20 00:00:00.0000000 +00:00 | 2011-07-30 00:00:00.0000000 +00:00 | 2013-05-06 00:00:00.0000000 +00:00 | 2019-09-01 00:00:00.0000000 +00:00 | 2008-11-25 00:00:00.0000000 +00:00 | 2009-12-09 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2012-07-14 00:00:00.0000000 +00:00 | 2017-02-22 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2017-02-22 00:00:00.0000000 +00:00 |  |  |  |  | 2009-10-20 00:00:00.0000000 +00:00 | 2010-03-10 00:00:00.0000000 +00:00 | 2010-03-10 00:00:00.0000000 +00:00 |  |  | 2010-05-12 00:00:00.0000000 +00:00 | 2010-11-10 00:00:00.0000000 +00:00 | 2010-11-10 00:00:00.0000000 +00:00 | [9 empty] | 2018-02-22 00:00:00.0000000 +00:00 | 2018-02-22 00:00:00.0000000 +00:00
HWQF027D | Y | 2015-08-25 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2016-03-08 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2015-08-25 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-02 00:00:00.0000000 +00:00 | 2016-03-08 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2015-08-25 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-02 00:00:00.0000000 +00:00 | 2016-03-08 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2015-08-25 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2016-03-08 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2015-12-02 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2015-08-25 00:00:00.0000000 +00:00 | 2015-08-25 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2016-03-08 00:00:00.0000000 +00:00 | 2016-03-08 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | 2018-02-27 00:00:00.0000000 +00:00 |  |  | 2018-02-27 00:00:00.0000000 +00:00 |  | 2017-09-05 12:01:58.2513715 -04:00
HWQF030 | Y | 2015-11-23 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 | 2020-02-28 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 | 2020-02-28 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-23 17:00:00.0000000 +00:00 | [10 empty] | 2018-11-30 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 |  |  |  | 2019-03-29 00:00:00.0000000 +00:00 | 2019-03-29 00:00:00.0000000 +00:00 | [9 empty] | 2022-06-30 00:00:00.0000000 +00:00 | 2022-06-30 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-10 15:13:37.4441945 -04:00
HWR00504 | Y | 2009-10-05 00:00:00.0000000 +00:00 | 2012-07-23 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2017-02-24 00:00:00.0000000 +00:00 | 2018-02-21 00:00:00.0000000 +00:00 | 2009-10-05 00:00:00.0000000 +00:00 | 2009-12-07 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2017-02-24 00:00:00.0000000 +00:00 | 2018-02-21 00:00:00.0000000 +00:00 | 2009-10-05 00:00:00.0000000 +00:00 | 2011-04-15 00:00:00.0000000 +00:00 | 2013-04-19 00:00:00.0000000 +00:00 | 2013-11-01 00:00:00.0000000 +00:00 | 2014-06-28 00:00:00.0000000 +00:00 | 2009-10-05 12:00:00.0000000 +00:00 | 2012-07-23 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2017-02-24 17:00:00.0000000 +00:00 |  | 2015-06-26 00:00:00.0000000 +00:00 | 2018-02-21 00:00:00.0000000 +00:00 |  | 2009-10-05 12:00:00.0000000 +00:00 |  | 2012-07-23 00:00:00.0000000 +00:00 | 2015-01-22 00:00:00.0000000 +00:00 | 2015-01-22 00:00:00.0000000 +00:00 | 2015-01-22 00:00:00.0000000 +00:00 |  | 2015-01-22 00:00:00.0000000 +00:00 | [6 empty] | 2015-06-26 00:00:00.0000000 +00:00 |  | 2017-02-24 17:00:00.0000000 +00:00 |  | 2018-02-21 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 |  |  | 2019-02-15 00:00:00.0000000 +00:00 |  | 2017-10-24 11:03:27.3416454 -04:00
HWR00505 | Y | 2009-10-05 00:00:00.0000000 +00:00 | 2012-07-23 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2017-10-15 00:00:00.0000000 +00:00 | 2019-04-07 00:00:00.0000000 +00:00 | 2009-10-05 00:00:00.0000000 +00:00 | 2012-07-23 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2017-10-15 00:00:00.0000000 +00:00 | 2018-10-14 00:00:00.0000000 +00:00 | 2009-10-05 00:00:00.0000000 +00:00 | 2011-04-15 00:00:00.0000000 +00:00 | 2013-04-03 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2009-10-05 12:00:00.0000000 +00:00 | 2012-07-23 18:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 |  |  | 2015-06-26 00:00:00.0000000 +00:00 | 2019-11-30 00:00:00.0000000 +00:00 | 2009-10-05 12:00:00.0000000 +00:00 |  | 2012-07-23 18:00:00.0000000 +00:00 |  | 2013-07-22 00:00:00.0000000 +00:00 | 2013-07-22 00:00:00.0000000 +00:00 | 2013-07-22 00:00:00.0000000 +00:00 | 2013-07-22 00:00:00.0000000 +00:00 | [6 empty] | 2015-06-26 00:00:00.0000000 +00:00 |  | 2017-10-15 00:00:00.0000000 +00:00 |  | 2019-04-07 00:00:00.0000000 +00:00 |  | 2019-11-05 00:00:00.0000000 +00:00 | 2019-11-05 00:00:00.0000000 +00:00 |  | 2019-11-05 00:00:00.0000000 +00:00 |  |  | 2017-11-30 08:55:24.5612668 -05:00
HWR00508 | Y | 2010-08-18 00:00:00.0000000 +00:00 | 2014-04-01 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 | 2018-12-10 00:00:00.0000000 +00:00 | 2020-12-09 00:00:00.0000000 +00:00 | 2010-08-18 00:00:00.0000000 +00:00 | 2012-01-15 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 | 2018-12-10 00:00:00.0000000 +00:00 | 2020-12-09 00:00:00.0000000 +00:00 | 2010-08-18 00:00:00.0000000 +00:00 | 2012-06-14 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2013-12-13 00:00:00.0000000 +00:00 | 2014-12-13 00:00:00.0000000 +00:00 | 2010-08-18 12:00:00.0000000 +00:00 | 2014-04-01 17:00:00.0000000 +00:00 |  |  |  | 2018-12-30 00:00:00.0000000 +00:00 | 2021-12-30 00:00:00.0000000 +00:00 | 2010-08-18 12:00:00.0000000 +00:00 |  | 2014-04-01 17:00:00.0000000 +00:00 |  | 2017-12-04 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 |  | 2017-12-04 00:00:00.0000000 +00:00 | [6 empty] | 2018-03-16 00:00:00.0000000 +00:00 |  | 2018-12-10 00:00:00.0000000 +00:00 |  | 2020-12-09 00:00:00.0000000 +00:00 |  | 2021-12-03 00:00:00.0000000 +00:00 | 2021-12-03 00:00:00.0000000 +00:00 |  | 2021-12-03 00:00:00.0000000 +00:00 |  |  | 2017-11-17 15:08:47.8882401 -05:00
HWR00510 | Y | 2013-04-30 00:00:00.0000000 +00:00 | 2013-08-06 00:00:00.0000000 +00:00 | 2020-10-15 00:00:00.0000000 +00:00 | 2021-07-15 00:00:00.0000000 +00:00 | 2023-01-15 00:00:00.0000000 +00:00 | 2013-04-30 00:00:00.0000000 +00:00 | 2013-08-06 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-07-13 00:00:00.0000000 +00:00 | [5 empty] | 2013-04-30 18:00:00.0000000 +00:00 | 2013-08-06 18:00:00.0000000 +00:00 | [10 empty] | 2018-07-05 00:00:00.0000000 +00:00 | [14 empty] | 2018-01-30 00:00:00.0000000 +00:00 | 2025-01-14 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-24 08:54:04.3490425 -05:00
HWR00511 | Y | 2013-01-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2019-02-28 00:00:00.0000000 +00:00 | 2019-10-28 00:00:00.0000000 +00:00 | 2021-04-25 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-07-13 00:00:00.0000000 +00:00 | [5 empty] | 2013-01-15 17:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | [9 empty] | 2015-01-15 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | [14 empty] | 2018-04-10 00:00:00.0000000 +00:00 | 2024-04-24 00:00:00.0000000 +00:00
HWR00512 | Y | 2017-08-01 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2020-06-02 00:00:00.0000000 +00:00 | 2021-10-15 00:00:00.0000000 +00:00 | 2022-10-15 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2020-06-15 00:00:00.0000000 +00:00 | 2021-10-15 00:00:00.0000000 +00:00 | 2022-10-15 00:00:00.0000000 +00:00 | [16 empty] | 2019-01-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | [14 empty] | 2025-10-15 00:00:00.0000000 +00:00 | 2025-10-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-12 09:30:14.8969932 -04:00
HWR005B | Y | 2006-11-21 00:00:00.0000000 +00:00 | 2017-11-02 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 | 2023-09-14 00:00:00.0000000 +00:00 | 2006-11-21 00:00:00.0000000 +00:00 | 2017-11-02 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 | 2023-09-14 00:00:00.0000000 +00:00 | 2006-11-21 00:00:00.0000000 +00:00 | 2012-04-14 00:00:00.0000000 +00:00 | 2012-11-16 00:00:00.0000000 +00:00 | 2013-05-16 00:00:00.0000000 +00:00 | 2014-05-16 00:00:00.0000000 +00:00 | 2006-11-21 00:00:00.0000000 +00:00 | [10 empty] | 2018-06-12 00:00:00.0000000 +00:00 | 2018-05-29 00:00:00.0000000 +00:00 | [14 empty] | 2024-09-09 00:00:00.0000000 +00:00 | 2024-09-09 00:00:00.0000000 +00:00
HWR005B1 | Y | 2007-07-03 00:00:00.0000000 +00:00 | 2010-02-24 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 | 2020-09-14 00:00:00.0000000 +00:00 | 2023-09-14 00:00:00.0000000 +00:00 | 2007-07-03 00:00:00.0000000 +00:00 | 2010-02-24 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 | 2020-09-14 00:00:00.0000000 +00:00 | 2023-09-14 00:00:00.0000000 +00:00 | 2007-07-03 00:00:00.0000000 +00:00 | 2010-02-24 00:00:00.0000000 +00:00 | 2014-05-22 00:00:00.0000000 +00:00 | 2014-11-19 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2007-07-03 00:00:00.0000000 +00:00 | 2010-02-24 00:00:00.0000000 +00:00 |  |  |  | 2020-01-17 00:00:00.0000000 +00:00 | 2023-09-14 00:00:00.0000000 +00:00 | 2007-07-03 00:00:00.0000000 +00:00 |  | 2010-02-24 00:00:00.0000000 +00:00 |  | 2019-02-14 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 |  | 2019-02-14 00:00:00.0000000 +00:00 | [6 empty] | 2020-01-17 00:00:00.0000000 +00:00 |  | 2020-09-14 00:00:00.0000000 +00:00 |  | 2023-09-14 00:00:00.0000000 +00:00 |  | 2024-09-09 00:00:00.0000000 +00:00 | 2024-09-09 00:00:00.0000000 +00:00 |  | 2024-09-09 00:00:00.0000000 +00:00
HWR100PAD | Y | 2013-01-11 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 | 2016-11-21 00:00:00.0000000 +00:00 | 2017-11-20 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2014-04-12 00:00:00.0000000 +00:00 | 2014-10-09 00:00:00.0000000 +00:00 | 2015-10-08 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 |  |  |  |  | 2013-01-11 17:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 | 2016-11-21 00:00:00.0000000 +00:00 |  | 2015-12-11 00:00:00.0000000 +00:00 | 2017-11-20 00:00:00.0000000 +00:00 | 2013-01-11 17:00:00.0000000 +00:00 | 2013-01-11 17:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 |  | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-11 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 | 2016-11-21 00:00:00.0000000 +00:00 | 2016-11-21 00:00:00.0000000 +00:00 | 2017-11-20 00:00:00.0000000 +00:00 | 2017-11-20 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 | 2020-11-19 00:00:00.0000000 +00:00 |  | 2020-11-19 00:00:00.0000000 +00:00 | 2020-11-19 00:00:00.0000000 +00:00 |  | 2017-11-28 08:24:21.1971729 -05:00
HWR1132B | Y | 1998-02-01 00:00:00.0000000 +00:00 | 2008-02-26 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2016-11-01 00:00:00.0000000 +00:00 | 2020-10-30 00:00:00.0000000 +00:00 | 1998-02-01 00:00:00.0000000 +00:00 | 2001-06-15 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2016-11-01 00:00:00.0000000 +00:00 | 2020-10-30 00:00:00.0000000 +00:00 | 1998-02-01 00:00:00.0000000 +00:00 | 2008-02-26 00:00:00.0000000 +00:00 | 2016-04-07 00:00:00.0000000 +00:00 | 2016-10-05 00:00:00.0000000 +00:00 | 2018-10-04 00:00:00.0000000 +00:00 | 1998-02-01 00:00:00.0000000 +00:00 | 2008-02-26 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2016-11-01 00:00:00.0000000 +00:00 |  | 2015-12-21 00:00:00.0000000 +00:00 | 2020-10-30 00:00:00.0000000 +00:00 |  | 1998-02-01 00:00:00.0000000 +00:00 |  | 2008-02-26 00:00:00.0000000 +00:00 | 2012-02-07 00:00:00.0000000 +00:00 | 2012-02-07 00:00:00.0000000 +00:00 | 2012-02-07 00:00:00.0000000 +00:00 |  | 2012-02-07 00:00:00.0000000 +00:00 | [6 empty] | 2015-12-21 00:00:00.0000000 +00:00 |  | 2016-11-01 00:00:00.0000000 +00:00 |  | 2020-10-30 00:00:00.0000000 +00:00 | 2021-10-25 00:00:00.0000000 +00:00 | 2021-10-25 00:00:00.0000000 +00:00 |  |  | 2021-10-25 00:00:00.0000000 +00:00 |  | 2017-11-30 14:59:59.8599594 -05:00
HWR1140A | Y | 2006-03-22 00:00:00.0000000 +00:00 | 2016-12-16 00:00:00.0000000 +00:00 | 2019-01-13 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 | 2006-03-22 00:00:00.0000000 +00:00 | 2016-12-16 00:00:00.0000000 +00:00 | 2019-01-13 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 | 2006-03-22 00:00:00.0000000 +00:00 | 2019-10-26 00:00:00.0000000 +00:00 | 2020-11-15 00:00:00.0000000 +00:00 | 2023-08-07 00:00:00.0000000 +00:00 | 2025-07-28 00:00:00.0000000 +00:00 | 2006-03-22 12:00:00.0000000 +00:00 | 2016-12-16 00:00:00.0000000 +00:00 |  |  |  | 2019-01-13 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 | 2006-03-22 12:00:00.0000000 +00:00 |  | 2016-12-16 00:00:00.0000000 +00:00 |  | 2018-07-16 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 |  | 2018-07-16 00:00:00.0000000 +00:00 | [6 empty] | 2019-01-13 00:00:00.0000000 +00:00 |  | 2019-06-30 00:00:00.0000000 +00:00 |  | 2020-06-30 00:00:00.0000000 +00:00 |  | 2023-06-30 00:00:00.0000000 +00:00 | 2023-06-30 00:00:00.0000000 +00:00 |  | 2023-06-30 00:00:00.0000000 +00:00 |  |  | 2017-09-18 10:36:11.1082137 -04:00
HWR200-01 | Y | 2012-12-11 00:00:00.0000000 +00:00 | 2012-02-28 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2017-03-03 00:00:00.0000000 +00:00 | 2011-05-27 00:00:00.0000000 +00:00 | 2012-02-28 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2017-07-07 00:00:00.0000000 +00:00 | [5 empty] | 2009-11-09 00:00:00.0000000 +00:00 | 2012-02-28 00:00:00.0000000 +00:00 |  |  |  | 2015-04-16 00:00:00.0000000 +00:00 | 2017-03-03 00:00:00.0000000 +00:00 | [20 empty] | 2018-07-03 00:00:00.0000000 +00:00 | 2018-02-27 00:00:00.0000000 +00:00
HWR300-03 | Y | 2009-08-13 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2009-08-13 00:00:00.0000000 +00:00 | 2010-03-12 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2016-11-24 00:00:00.0000000 +00:00 | 2017-11-13 00:00:00.0000000 +00:00 | 2009-08-13 00:00:00.0000000 +00:00 | 2011-03-15 00:00:00.0000000 +00:00 | 2012-01-10 00:00:00.0000000 +00:00 | 2012-07-13 00:00:00.0000000 +00:00 | 2013-04-08 00:00:00.0000000 +00:00 | 2009-08-13 17:00:00.0000000 +00:00 | 2012-08-15 18:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2016-11-14 17:00:00.0000000 +00:00 |  | 2015-06-03 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 |  | 2009-08-13 17:00:00.0000000 +00:00 |  | 2012-08-15 18:00:00.0000000 +00:00 | 2015-01-08 00:00:00.0000000 +00:00 | 2015-01-08 00:00:00.0000000 +00:00 | 2015-01-18 00:00:00.0000000 +00:00 |  | 2015-01-18 00:00:00.0000000 +00:00 | [6 empty] | 2015-06-03 00:00:00.0000000 +00:00 |  | 2016-11-14 17:00:00.0000000 +00:00 |  | 2017-11-13 00:00:00.0000000 +00:00 | 2018-11-08 00:00:00.0000000 +00:00 | 2018-11-08 00:00:00.0000000 +00:00 |  |  | 2018-11-08 00:00:00.0000000 +00:00
HWR669C | Y | 1998-02-01 00:00:00.0000000 +00:00 | 2008-06-19 00:00:00.0000000 +00:00 | 2018-01-01 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 | 1998-02-01 00:00:00.0000000 +00:00 | 2007-04-02 00:00:00.0000000 +00:00 | 2018-01-01 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 | 1998-02-01 00:00:00.0000000 +00:00 | 2007-12-10 00:00:00.0000000 +00:00 | 2015-12-20 00:00:00.0000000 +00:00 | 2016-06-23 00:00:00.0000000 +00:00 | 2018-06-22 00:00:00.0000000 +00:00 | 1998-02-01 00:00:00.0000000 +00:00 | 2008-06-19 00:00:00.0000000 +00:00 |  |  |  | 2018-01-01 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 | 1998-02-01 00:00:00.0000000 +00:00 |  | 2008-06-19 00:00:00.0000000 +00:00 |  | 2014-10-15 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | [6 empty] | 2018-01-01 00:00:00.0000000 +00:00 |  | 2018-06-30 00:00:00.0000000 +00:00 |  | 2021-06-30 00:00:00.0000000 +00:00 |  | 2024-06-30 00:00:00.0000000 +00:00 | 2024-06-30 00:00:00.0000000 +00:00 |  | 2024-06-30 00:00:00.0000000 +00:00
HWR703 | Y | 2017-10-10 00:00:00.0000000 +00:00 | 2019-10-10 00:00:00.0000000 +00:00 | 2021-01-15 00:00:00.0000000 +00:00 | 2021-07-15 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 | 2019-10-10 00:00:00.0000000 +00:00 | 2021-01-15 00:00:00.0000000 +00:00 | 2021-07-15 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-10-10 00:00:00.0000000 +00:00 |  |  |  |  | 2021-01-15 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 |  | 2019-10-10 00:00:00.0000000 +00:00 |  | 2020-10-15 00:00:00.0000000 +00:00 | 2020-10-15 00:00:00.0000000 +00:00 |  | 2020-10-15 00:00:00.0000000 +00:00 | [6 empty] | 2021-01-15 00:00:00.0000000 +00:00 |  | 2021-07-15 00:00:00.0000000 +00:00 | 2021-07-15 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2025-07-15 00:00:00.0000000 +00:00 | 2025-07-15 00:00:00.0000000 +00:00 |  | 2025-07-15 00:00:00.0000000 +00:00 | 2025-07-15 00:00:00.0000000 +00:00 | 2017-10-10 13:00:21.1100000 +00:00 | 2017-10-13 11:56:39.4531894 -04:00
HWR890 | Y | 2004-06-18 00:00:00.0000000 +00:00 | 2014-03-18 00:00:00.0000000 +00:00 | 2018-12-29 00:00:00.0000000 +00:00 | 2019-08-27 00:00:00.0000000 +00:00 | 2021-02-21 00:00:00.0000000 +00:00 | 2004-06-18 00:00:00.0000000 +00:00 | 2014-03-18 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2020-02-21 00:00:00.0000000 +00:00 | 2004-06-18 00:00:00.0000000 +00:00 | 2014-03-18 00:00:00.0000000 +00:00 | 2015-09-18 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2004-06-18 17:00:00.0000000 +00:00 | 2014-03-18 17:00:00.0000000 +00:00 | [10 empty] | 2018-09-28 00:00:00.0000000 +00:00 | [14 empty] | 2020-08-19 00:00:00.0000000 +00:00 | 2024-02-20 00:00:00.0000000 +00:00 |  |  |  |  | 2017-12-15 12:26:44.5331770 -05:00
HWR919 | Y | 2006-03-01 00:00:00.0000000 +00:00 | 2012-07-24 00:00:00.0000000 +00:00 | 2019-11-01 00:00:00.0000000 +00:00 | 2020-07-15 00:00:00.0000000 +00:00 | 2022-07-14 00:00:00.0000000 +00:00 | 2006-03-01 00:00:00.0000000 +00:00 | 2007-07-17 00:00:00.0000000 +00:00 | 2019-11-01 00:00:00.0000000 +00:00 | 2020-07-15 00:00:00.0000000 +00:00 | 2022-07-14 00:00:00.0000000 +00:00 | 2006-03-01 00:00:00.0000000 +00:00 | 2011-04-30 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2015-05-22 00:00:00.0000000 +00:00 | 2006-03-01 17:00:00.0000000 +00:00 | 2012-07-24 18:00:00.0000000 +00:00 |  |  |  | 2019-11-01 00:00:00.0000000 +00:00 | 2022-07-14 00:00:00.0000000 +00:00 | 2006-03-01 17:00:00.0000000 +00:00 |  | 2012-07-24 18:00:00.0000000 +00:00 |  | 2013-12-03 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | [6 empty] | 2019-11-01 00:00:00.0000000 +00:00 |  | 2020-07-15 00:00:00.0000000 +00:00 |  | 2022-07-14 00:00:00.0000000 +00:00 |  | 2023-07-07 00:00:00.0000000 +00:00 | 2023-07-07 00:00:00.0000000 +00:00 |  | 2023-07-07 00:00:00.0000000 +00:00 |  |  | 2017-09-13 14:13:58.0981296 -04:00
HWRC054-R | Y | 2010-04-08 00:00:00.0000000 +00:00 | 2010-07-18 00:00:00.0000000 +00:00 | 2011-03-17 00:00:00.0000000 +00:00 | 2012-01-09 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2010-04-08 00:00:00.0000000 +00:00 | 2010-07-18 00:00:00.0000000 +00:00 | 2011-01-16 00:00:00.0000000 +00:00 | 2011-07-16 00:00:00.0000000 +00:00 | 2012-04-12 00:00:00.0000000 +00:00 | 2010-04-08 00:00:00.0000000 +00:00 | 2002-04-06 00:00:00.0000000 +00:00 | 2003-01-28 00:00:00.0000000 +00:00 | 2003-07-28 00:00:00.0000000 +00:00 | 2004-04-24 00:00:00.0000000 +00:00 | 2010-04-08 12:00:00.0000000 +00:00 | 2010-07-18 18:00:00.0000000 +00:00 | 2011-03-17 00:00:00.0000000 +00:00 | 2012-01-09 08:00:00.0000000 +00:00 | 2013-06-28 17:00:00.0000000 +00:00 | 2011-03-11 00:00:00.0000000 +00:00 | 2015-06-05 17:00:00.0000000 +00:00 |  |  |  |  | 2010-10-28 00:00:00.0000000 +00:00 | 2010-10-28 00:00:00.0000000 +00:00 | 2010-10-28 00:00:00.0000000 +00:00 | [7 empty] | 2011-03-17 00:00:00.0000000 +00:00 |  | 2012-01-09 00:00:00.0000000 +00:00 |  | 2013-06-28 00:00:00.0000000 +00:00 |  | 2017-10-28 00:00:00.0000000 +00:00 | 2017-10-28 00:00:00.0000000 +00:00
HWRC055 | Y | 2018-06-15 00:00:00.0000000 +00:00 | 2019-03-15 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 | 2021-06-29 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-03-15 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 | 2021-06-29 00:00:00.0000000 +00:00 | 2005-09-12 00:00:00.0000000 +00:00 | 2012-02-20 00:00:00.0000000 +00:00 | 2013-01-05 00:00:00.0000000 +00:00 | 2013-07-05 00:00:00.0000000 +00:00 | 2014-04-02 00:00:00.0000000 +00:00 | [11 empty] | 2019-10-15 00:00:00.0000000 +00:00 | 2019-10-15 00:00:00.0000000 +00:00 | [14 empty] | 2024-06-29 00:00:00.0000000 +00:00 | 2024-06-29 00:00:00.0000000 +00:00
HWRF05R | Y | 2015-08-04 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2018-05-08 00:00:00.0000000 +00:00 | 2019-01-08 00:00:00.0000000 +00:00 | 2021-01-08 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2017-07-17 00:00:00.0000000 +00:00 | 2018-03-08 00:00:00.0000000 +00:00 | 2020-03-20 00:00:00.0000000 +00:00 | [5 empty] | 2015-08-04 18:00:00.0000000 +00:00 | 2016-10-24 10:00:00.0000000 +00:00 |  |  |  | 2018-06-26 00:00:00.0000000 +00:00 | 2021-02-26 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2017-01-19 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2017-04-26 00:00:00.0000000 +00:00 | 2018-01-11 00:00:00.0000000 +00:00 |  | 2018-01-11 00:00:00.0000000 +00:00 | 2018-01-11 00:00:00.0000000 +00:00 | 2018-06-26 00:00:00.0000000 +00:00 | 2018-06-26 00:00:00.0000000 +00:00 | 2019-02-26 00:00:00.0000000 +00:00 | 2019-02-26 00:00:00.0000000 +00:00 | 2021-02-26 00:00:00.0000000 +00:00 | 2021-02-26 00:00:00.0000000 +00:00 | 2021-03-05 00:00:00.0000000 +00:00 | 2022-01-07 00:00:00.0000000 +00:00 |  | 2022-02-25 00:00:00.0000000 +00:00 | 2022-02-25 00:00:00.0000000 +00:00 |  | 2017-11-28 10:01:54.3339988 -05:00
HWS16CW1 | Y | 2015-07-08 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-11-10 00:00:00.0000000 +00:00 | 2018-02-12 00:00:00.0000000 +00:00 | 2019-08-10 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-11-10 00:00:00.0000000 +00:00 | 2016-05-09 00:00:00.0000000 +00:00 | 2017-05-10 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-08 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-11-10 00:00:00.0000000 +00:00 |  |  | 2015-11-10 00:00:00.0000000 +00:00 |  | 2015-07-08 00:00:00.0000000 +00:00 |  | 2015-09-07 00:00:00.0000000 +00:00 |  | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | [6 empty] | 2015-11-10 00:00:00.0000000 +00:00 |  | 2018-02-12 00:00:00.0000000 +00:00 |  | 2019-08-10 00:00:00.0000000 +00:00 |  | 2018-05-04 00:00:00.0000000 +00:00 | 2022-08-09 00:00:00.0000000 +00:00 |  | 2022-08-09 00:00:00.0000000 +00:00 |  |  | 2017-10-16 15:00:56.5168109 -04:00
HWS16CW2 | Y | 2015-07-08 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 | 2018-02-12 00:00:00.0000000 +00:00 | 2019-08-10 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 | 2016-01-21 00:00:00.0000000 +00:00 | 2017-01-21 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-08 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 |  |  | 2015-11-13 00:00:00.0000000 +00:00 |  | 2015-07-08 00:00:00.0000000 +00:00 |  | 2015-09-07 00:00:00.0000000 +00:00 |  | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | [6 empty] | 2015-11-13 00:00:00.0000000 +00:00 |  | 2018-02-12 00:00:00.0000000 +00:00 |  | 2019-08-10 00:00:00.0000000 +00:00 |  | 2018-01-16 00:00:00.0000000 +00:00 | 2022-08-09 00:00:00.0000000 +00:00 |  | 2022-08-09 00:00:00.0000000 +00:00 |  |  | 2017-10-16 15:01:17.7091703 -04:00
HWS16XCW2 | Y
HWS17CW1 | Y | 2016-11-17 17:00:00.0000000 +00:00 | 2016-11-19 17:00:00.0000000 +00:00 | 2017-01-27 17:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2020-04-30 00:00:00.0000000 +00:00 | 2016-11-17 00:00:00.0000000 +00:00 | 2016-11-19 00:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 | 2019-04-30 00:00:00.0000000 +00:00 | [5 empty] | 2016-11-17 17:00:00.0000000 +00:00 | 2016-11-19 17:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 |  |  | 2017-01-27 00:00:00.0000000 +00:00 | 2020-04-30 00:00:00.0000000 +00:00 | 2016-11-17 17:00:00.0000000 +00:00 | 2016-11-17 00:00:00.0000000 +00:00 | 2016-11-19 17:00:00.0000000 +00:00 | 2016-11-19 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-01-27 17:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2018-10-31 00:00:00.0000000 +00:00 | 2020-04-30 00:00:00.0000000 +00:00 | 2020-04-30 00:00:00.0000000 +00:00 | 2023-04-29 00:00:00.0000000 +00:00 | 2023-04-29 00:00:00.0000000 +00:00 |  | 2023-04-29 00:00:00.0000000 +00:00 | 2023-04-29 00:00:00.0000000 +00:00 |  | 2017-10-12 08:07:46.4072961 -04:00
HWS17CW2 | Y | 2016-08-31 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 | 2018-08-28 00:00:00.0000000 +00:00 | 2020-02-22 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2017-07-31 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | [5 empty] | 2016-08-31 17:00:00.0000000 +00:00 | 2016-10-03 17:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 |  |  | 2017-01-27 00:00:00.0000000 +00:00 |  | 2016-08-31 17:00:00.0000000 +00:00 |  | 2016-10-03 17:00:00.0000000 +00:00 |  |  | 2016-11-03 00:00:00.0000000 +00:00 | 2016-11-03 00:00:00.0000000 +00:00 | 2016-11-03 00:00:00.0000000 +00:00 | [6 empty] | 2017-01-27 00:00:00.0000000 +00:00 |  | 2018-08-28 00:00:00.0000000 +00:00 |  | 2020-02-22 00:00:00.0000000 +00:00 |  | 2018-11-26 00:00:00.0000000 +00:00 | 2023-02-21 00:00:00.0000000 +00:00 |  | 2023-02-21 00:00:00.0000000 +00:00 |  |  | 2017-12-06 10:27:33.4756124 -05:00
HWS18CW1 | Y | 2017-04-24 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | [5 empty] | 2017-04-24 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 |  |  |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2017-04-24 00:00:00.0000000 +00:00 |  | 2017-08-15 00:00:00.0000000 +00:00 |  | 2017-09-12 00:00:00.0000000 +00:00 | 2017-09-12 00:00:00.0000000 +00:00 | 2017-09-12 00:00:00.0000000 +00:00 | 2017-09-12 00:00:00.0000000 +00:00 | [6 empty] | 2017-11-30 00:00:00.0000000 +00:00 |  | 2018-09-26 00:00:00.0000000 +00:00 |  | 2019-09-25 00:00:00.0000000 +00:00 |  | 2022-09-25 00:00:00.0000000 +00:00 | 2022-09-25 00:00:00.0000000 +00:00 |  | 2022-09-25 00:00:00.0000000 +00:00 |  |  | 2017-10-24 13:59:38.0245751 -04:00
HWS18CW2 | Y | 2017-04-24 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-09-26 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | [5 empty] | 2017-04-24 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 |  |  |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2017-04-24 00:00:00.0000000 +00:00 |  | 2017-08-15 00:00:00.0000000 +00:00 |  | 2017-09-12 00:00:00.0000000 +00:00 | 2017-09-12 00:00:00.0000000 +00:00 | 2017-09-12 00:00:00.0000000 +00:00 | 2017-09-12 00:00:00.0000000 +00:00 | [6 empty] | 2017-11-30 00:00:00.0000000 +00:00 |  | 2018-09-26 00:00:00.0000000 +00:00 |  | 2019-09-25 00:00:00.0000000 +00:00 |  | 2022-09-25 00:00:00.0000000 +00:00 | 2022-09-25 00:00:00.0000000 +00:00 |  | 2022-09-25 00:00:00.0000000 +00:00 |  |  | 2017-10-24 14:01:06.7458193 -04:00
HWS2011R | Y | 2010-05-04 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-09-16 00:00:00.0000000 +00:00 | 2011-07-25 00:00:00.0000000 +00:00 | 2012-07-24 00:00:00.0000000 +00:00 | 2010-05-04 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-11-01 00:00:00.0000000 +00:00 | 2011-05-16 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2010-05-04 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-09-16 00:00:00.0000000 +00:00 | 2011-05-31 00:00:00.0000000 +00:00 | 2012-05-30 00:00:00.0000000 +00:00 | 2010-05-04 17:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-09-16 00:00:00.0000000 +00:00 | 2011-07-25 00:00:00.0000000 +00:00 | 2012-07-24 00:00:00.0000000 +00:00 | 2010-09-16 00:00:00.0000000 +00:00 | 2012-07-24 00:00:00.0000000 +00:00 | 2010-05-04 00:00:00.0000000 +00:00 | 2010-05-04 00:00:00.0000000 +00:00 | 2010-06-01 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 |  | 2010-08-10 00:00:00.0000000 +00:00 | 2010-08-10 00:00:00.0000000 +00:00 | 2010-08-10 00:00:00.0000000 +00:00 | 2010-08-10 00:00:00.0000000 +00:00 | [5 empty] | 2010-09-16 00:00:00.0000000 +00:00 | 2010-09-16 00:00:00.0000000 +00:00 | 2011-07-25 00:00:00.0000000 +00:00 | 2011-07-25 00:00:00.0000000 +00:00 | 2012-07-24 00:00:00.0000000 +00:00 | 2012-07-24 00:00:00.0000000 +00:00 |  | 2015-07-23 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 |  | 2017-11-27 11:44:36.8379660 -05:00
HWS2013CW | Y | 2012-07-02 00:00:00.0000000 +00:00 | 2012-10-16 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2012-10-16 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2013-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2013-07-15 12:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2016-02-16 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-12-15 00:00:00.0000000 +00:00 | 2012-12-15 00:00:00.0000000 +00:00 | 2012-12-15 00:00:00.0000000 +00:00 | 2012-12-15 00:00:00.0000000 +00:00 | 2012-12-15 00:00:00.0000000 +00:00 | [5 empty] | 2013-01-16 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 |  | 2018-06-29 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00
HWS2013M | Y | 2012-07-02 00:00:00.0000000 +00:00 | 2012-07-14 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2013-08-10 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2012-10-04 00:00:00.0000000 +00:00 | 2012-10-16 00:00:00.0000000 +00:00 | 2013-01-17 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-11-11 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2012-10-16 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2012-10-04 17:00:00.0000000 +00:00 | 2012-10-16 17:00:00.0000000 +00:00 | 2013-01-17 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2012-11-16 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2012-10-04 17:00:00.0000000 +00:00 | 2012-10-04 17:00:00.0000000 +00:00 | 2012-10-16 17:00:00.0000000 +00:00 | 2012-10-16 17:00:00.0000000 +00:00 | 2012-12-14 00:00:00.0000000 +00:00 | 2012-10-20 00:00:00.0000000 +00:00 | 2012-10-20 00:00:00.0000000 +00:00 | 2012-10-20 00:00:00.0000000 +00:00 | 2012-10-20 00:00:00.0000000 +00:00 | [5 empty] | 2012-11-15 00:00:00.0000000 +00:00 | 2013-01-17 00:00:00.0000000 +00:00 | 2013-08-10 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2016-06-18 00:00:00.0000000 +00:00 | 2016-01-26 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2016-01-26 00:00:00.0000000 +00:00 | 2016-01-26 00:00:00.0000000 +00:00 |  | 2017-12-01 16:49:26.0687324 -05:00
HWS2013Q | Y | 2012-10-04 00:00:00.0000000 +00:00 | 2012-10-09 00:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-12-29 00:00:00.0000000 +00:00 | 2012-10-04 00:00:00.0000000 +00:00 | 2012-10-20 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2012-10-04 00:00:00.0000000 +00:00 | 2012-10-20 00:00:00.0000000 +00:00 | 2013-02-18 00:00:00.0000000 +00:00 | 2013-08-19 00:00:00.0000000 +00:00 | 2014-08-18 00:00:00.0000000 +00:00 | 2012-10-04 12:00:00.0000000 +00:00 | 2012-10-09 17:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2014-03-17 17:00:00.0000000 +00:00 | 2014-12-29 17:00:00.0000000 +00:00 | 2013-01-16 00:00:00.0000000 +00:00 | 2014-12-29 00:00:00.0000000 +00:00 |  | 2012-10-04 12:00:00.0000000 +00:00 |  | 2012-10-09 17:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 |  | 2012-11-30 00:00:00.0000000 +00:00 | [6 empty] | 2013-01-16 00:00:00.0000000 +00:00 |  | 2014-03-17 17:00:00.0000000 +00:00 |  | 2014-12-29 17:00:00.0000000 +00:00 | 2017-07-14 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 |  |  | 2017-12-29 00:00:00.0000000 +00:00
HWS2013R | Y | 2012-07-02 00:00:00.0000000 +00:00 | 2012-11-02 00:00:00.0000000 +00:00 | 2013-01-17 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2014-11-21 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2012-10-22 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | [5 empty] | 2012-07-02 18:00:00.0000000 +00:00 | 2012-11-02 18:00:00.0000000 +00:00 | 2013-01-17 17:00:00.0000000 +00:00 | 2013-09-23 18:00:00.0000000 +00:00 | 2014-11-21 17:00:00.0000000 +00:00 | 2013-01-17 00:00:00.0000000 +00:00 | 2015-01-20 00:00:00.0000000 +00:00 | 2012-07-02 18:00:00.0000000 +00:00 | 2012-07-02 18:00:00.0000000 +00:00 | 2012-11-02 18:00:00.0000000 +00:00 | 2012-11-02 18:00:00.0000000 +00:00 |  | 2012-12-10 00:00:00.0000000 +00:00 | 2012-12-10 00:00:00.0000000 +00:00 | 2012-12-10 00:00:00.0000000 +00:00 | 2012-12-10 00:00:00.0000000 +00:00 | [5 empty] | 2013-01-17 17:00:00.0000000 +00:00 | 2013-01-17 17:00:00.0000000 +00:00 | 2013-09-23 18:00:00.0000000 +00:00 | 2013-09-23 18:00:00.0000000 +00:00 | 2014-11-21 17:00:00.0000000 +00:00 | 2014-11-21 17:00:00.0000000 +00:00 |  | 2017-11-20 00:00:00.0000000 +00:00 |  | 2017-11-20 00:00:00.0000000 +00:00 | 2017-11-20 00:00:00.0000000 +00:00
HWS2014CW | Y | 2013-08-28 00:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2013-12-19 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2013-08-28 00:00:00.0000000 +00:00 | 2013-10-08 00:00:00.0000000 +00:00 | 2014-02-06 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2013-08-28 00:00:00.0000000 +00:00 | 2013-10-08 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2015-09-09 00:00:00.0000000 +00:00 | 2013-08-28 12:00:00.0000000 +00:00 | 2013-10-08 12:00:00.0000000 +00:00 | 2013-12-19 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2013-08-28 12:00:00.0000000 +00:00 | 2013-08-28 12:00:00.0000000 +00:00 | 2013-10-08 12:00:00.0000000 +00:00 | 2013-10-08 12:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-19 00:00:00.0000000 +00:00 | 2013-12-19 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2018-08-06 00:00:00.0000000 +00:00 | 2019-06-13 00:00:00.0000000 +00:00 |  | 2019-06-13 00:00:00.0000000 +00:00 | 2019-06-13 00:00:00.0000000 +00:00 |  | 2017-09-01 17:01:46.0769242 -04:00
HWS2014K | Y | 2013-08-27 00:00:00.0000000 +00:00 | 2013-09-03 00:00:00.0000000 +00:00 | 2013-12-22 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | 2015-07-24 00:00:00.0000000 +00:00 | 2013-08-27 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-17 00:00:00.0000000 +00:00 | 2013-08-27 00:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-17 00:00:00.0000000 +00:00 | 2013-08-27 12:00:00.0000000 +00:00 | 2013-09-03 17:00:00.0000000 +00:00 | 2013-12-22 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | 2015-07-24 00:00:00.0000000 +00:00 | 2013-11-25 00:00:00.0000000 +00:00 | 2015-07-21 00:00:00.0000000 +00:00 | 2013-08-27 00:00:00.0000000 +00:00 | 2013-08-27 00:00:00.0000000 +00:00 | 2013-09-03 00:00:00.0000000 +00:00 | 2013-09-03 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | 2013-11-11 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-22 00:00:00.0000000 +00:00 | 2013-12-22 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | 2015-07-24 00:00:00.0000000 +00:00 | 2015-07-24 00:00:00.0000000 +00:00 | 2018-07-17 00:00:00.0000000 +00:00 | 2018-07-24 00:00:00.0000000 +00:00 |  | 2018-07-24 00:00:00.0000000 +00:00 | 2018-07-24 00:00:00.0000000 +00:00
HWS2014M | Y | 2013-08-28 00:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2013-12-10 00:00:00.0000000 +00:00 | 2014-07-21 00:00:00.0000000 +00:00 | 2015-07-22 00:00:00.0000000 +00:00 | 2013-08-28 00:00:00.0000000 +00:00 | 2013-10-08 00:00:00.0000000 +00:00 | 2014-02-06 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2013-08-28 00:00:00.0000000 +00:00 | 2013-10-08 00:00:00.0000000 +00:00 | 2014-03-11 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2015-09-09 00:00:00.0000000 +00:00 | 2013-08-28 12:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2013-12-10 00:00:00.0000000 +00:00 | 2014-07-21 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2014-01-12 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2013-08-28 12:00:00.0000000 +00:00 | 2013-08-28 12:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 | 2013-11-09 00:00:00.0000000 +00:00 | 2013-11-09 00:00:00.0000000 +00:00 | 2013-11-09 00:00:00.0000000 +00:00 | 2013-11-09 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-10 00:00:00.0000000 +00:00 | 2013-12-10 00:00:00.0000000 +00:00 | 2014-07-21 17:00:00.0000000 +00:00 | 2014-07-21 00:00:00.0000000 +00:00 | 2015-03-31 17:00:00.0000000 +00:00 | 2015-07-22 00:00:00.0000000 +00:00 | 2018-08-06 00:00:00.0000000 +00:00 | 2018-07-21 00:00:00.0000000 +00:00 |  | 2018-07-21 00:00:00.0000000 +00:00 | 2018-07-21 00:00:00.0000000 +00:00
HWS2014Q | Y | 2013-08-27 00:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2014-01-29 00:00:00.0000000 +00:00 | 2014-10-20 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2013-08-27 00:00:00.0000000 +00:00 | 2013-10-01 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2013-08-27 00:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2013-12-20 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2015-06-19 00:00:00.0000000 +00:00 | 2013-08-27 12:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2014-01-29 00:00:00.0000000 +00:00 | 2014-10-20 00:00:00.0000000 +00:00 | 2015-10-19 18:00:00.0000000 +00:00 | 2014-01-29 00:00:00.0000000 +00:00 | 2015-10-18 00:00:00.0000000 +00:00 |  | 2013-08-27 12:00:00.0000000 +00:00 |  | 2013-09-05 00:00:00.0000000 +00:00 | 2013-11-01 00:00:00.0000000 +00:00 | 2013-11-01 00:00:00.0000000 +00:00 | 2013-11-01 00:00:00.0000000 +00:00 |  | 2013-11-01 00:00:00.0000000 +00:00 | [6 empty] | 2014-01-29 00:00:00.0000000 +00:00 |  | 2014-10-20 00:00:00.0000000 +00:00 |  | 2015-10-19 18:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2018-10-17 00:00:00.0000000 +00:00 |  |  | 2018-10-17 00:00:00.0000000 +00:00 |  | 2017-09-12 16:15:45.7622554 -04:00
HWS2014R | Y | 2013-08-26 00:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2013-12-10 00:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2015-08-10 00:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-07-14 00:00:00.0000000 +00:00 | [5 empty] | 2013-08-26 18:00:00.0000000 +00:00 | 2013-09-05 18:00:00.0000000 +00:00 | 2013-12-10 00:00:00.0000000 +00:00 | 2014-08-11 17:00:00.0000000 +00:00 | 2015-08-10 17:00:00.0000000 +00:00 | 2013-12-10 00:00:00.0000000 +00:00 | 2015-08-10 00:00:00.0000000 +00:00 | 2013-08-26 18:00:00.0000000 +00:00 | 2013-08-26 18:00:00.0000000 +00:00 | 2013-09-05 18:00:00.0000000 +00:00 | 2013-09-05 18:00:00.0000000 +00:00 |  | 2013-10-11 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-10 00:00:00.0000000 +00:00 | 2013-12-10 00:00:00.0000000 +00:00 | 2014-08-11 17:00:00.0000000 +00:00 | 2014-08-11 17:00:00.0000000 +00:00 | 2015-08-10 17:00:00.0000000 +00:00 | 2015-08-10 17:00:00.0000000 +00:00 | 2016-02-10 00:00:00.0000000 +00:00 | 2018-08-09 00:00:00.0000000 +00:00 |  | 2018-08-09 00:00:00.0000000 +00:00 | 2018-08-09 00:00:00.0000000 +00:00 |  | 2017-09-29 08:07:22.5550577 -04:00
HWS2014X | Y | 2013-09-04 00:00:00.0000000 +00:00 | 2013-09-04 00:00:00.0000000 +00:00 | 2013-12-24 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2016-08-11 00:00:00.0000000 +00:00 | 2013-09-04 00:00:00.0000000 +00:00 | 2013-09-04 00:00:00.0000000 +00:00 | 2014-02-12 00:00:00.0000000 +00:00 | 2014-05-14 00:00:00.0000000 +00:00 | 2015-05-25 00:00:00.0000000 +00:00 | 2013-09-04 00:00:00.0000000 +00:00 | 2013-09-04 00:00:00.0000000 +00:00 | 2014-02-12 00:00:00.0000000 +00:00 | 2014-10-24 00:00:00.0000000 +00:00 | 2015-11-04 00:00:00.0000000 +00:00 | 2013-09-04 12:00:00.0000000 +00:00 | 2013-09-04 12:00:00.0000000 +00:00 | 2013-12-24 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2016-08-11 00:00:00.0000000 +00:00 | 2013-12-24 00:00:00.0000000 +00:00 | 2016-08-11 00:00:00.0000000 +00:00 | 2013-09-04 12:00:00.0000000 +00:00 | 2013-09-04 12:00:00.0000000 +00:00 | 2013-09-04 12:00:00.0000000 +00:00 | 2013-09-04 12:00:00.0000000 +00:00 | 2013-12-22 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-24 00:00:00.0000000 +00:00 | 2013-12-24 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2016-08-11 00:00:00.0000000 +00:00 | 2016-08-11 00:00:00.0000000 +00:00 | 2018-05-24 00:00:00.0000000 +00:00 | 2019-08-11 00:00:00.0000000 +00:00 |  | 2019-08-11 00:00:00.0000000 +00:00 | 2019-08-11 00:00:00.0000000 +00:00
HWS2015CW | Y | 2014-06-24 00:00:00.0000000 +00:00 | 2014-07-21 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2016-03-14 00:00:00.0000000 +00:00 | 2017-02-28 00:00:00.0000000 +00:00 | 2014-06-24 00:00:00.0000000 +00:00 | 2014-07-21 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-24 17:00:00.0000000 +00:00 | 2014-07-21 17:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2016-03-14 18:00:00.0000000 +00:00 | 2017-02-28 17:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2017-02-28 00:00:00.0000000 +00:00 | 2014-06-24 17:00:00.0000000 +00:00 | 2014-06-24 17:00:00.0000000 +00:00 | 2014-07-21 17:00:00.0000000 +00:00 | 2014-07-21 17:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2016-03-14 18:00:00.0000000 +00:00 | 2016-03-14 18:00:00.0000000 +00:00 | 2017-02-28 17:00:00.0000000 +00:00 | 2017-02-28 17:00:00.0000000 +00:00 | 2020-02-27 00:00:00.0000000 +00:00 | 2020-02-27 00:00:00.0000000 +00:00 |  | 2020-02-27 00:00:00.0000000 +00:00 | 2020-02-27 00:00:00.0000000 +00:00 |  | 2017-08-30 14:41:49.8405707 -04:00
HWS2015K | Y | 2014-06-20 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-11-30 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-07-20 00:00:00.0000000 +00:00 | 2016-07-20 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-20 17:00:00.0000000 +00:00 | 2014-07-15 17:00:00.0000000 +00:00 | 2014-11-30 00:00:00.0000000 +00:00 | 2015-10-26 18:00:00.0000000 +00:00 | 2016-11-22 17:00:00.0000000 +00:00 | 2014-11-30 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-11-30 00:00:00.0000000 +00:00 | 2014-11-30 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2019-11-21 00:00:00.0000000 +00:00 | 2019-11-21 00:00:00.0000000 +00:00 |  | 2019-11-21 00:00:00.0000000 +00:00 | 2019-11-21 00:00:00.0000000 +00:00 |  | 2017-08-30 14:42:02.7802122 -04:00
HWS2015M | Y | 2014-07-11 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-09-18 00:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2014-07-11 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-07-11 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-09-18 00:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2014-06-07 00:00:00.0000000 +00:00 | 2016-06-18 00:00:00.0000000 +00:00 | 2014-07-11 00:00:00.0000000 +00:00 | 2014-07-11 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 |  | 2014-07-31 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-18 00:00:00.0000000 +00:00 | 2014-09-18 00:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2019-06-27 00:00:00.0000000 +00:00 |  | 2019-06-27 00:00:00.0000000 +00:00 | 2019-06-27 00:00:00.0000000 +00:00
HWS2015Q | Y | 2014-07-02 00:00:00.0000000 +00:00 | 2014-08-01 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | 2017-05-19 00:00:00.0000000 +00:00 | 2014-07-02 00:00:00.0000000 +00:00 | 2014-08-18 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-04-26 00:00:00.0000000 +00:00 | 2016-04-24 00:00:00.0000000 +00:00 | [5 empty] | 2014-07-02 08:00:00.0000000 +00:00 | 2014-08-01 17:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-10-05 18:00:00.0000000 +00:00 | 2017-05-19 17:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2017-05-27 00:00:00.0000000 +00:00 |  | 2014-07-02 08:00:00.0000000 +00:00 |  | 2014-08-01 17:00:00.0000000 +00:00 | 2014-08-30 00:00:00.0000000 +00:00 | 2014-08-30 00:00:00.0000000 +00:00 | 2014-08-30 00:00:00.0000000 +00:00 |  | 2014-08-30 00:00:00.0000000 +00:00 | [6 empty] | 2014-09-15 00:00:00.0000000 +00:00 |  | 2015-10-05 18:00:00.0000000 +00:00 |  | 2017-05-19 17:00:00.0000000 +00:00 | 2019-04-24 00:00:00.0000000 +00:00 | 2020-05-19 00:00:00.0000000 +00:00 |  |  | 2020-05-19 00:00:00.0000000 +00:00
HWS2015R | Y | 2014-06-26 00:00:00.0000000 +00:00 | 2014-07-30 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2014-07-30 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-26 17:00:00.0000000 +00:00 | 2014-07-30 17:00:00.0000000 +00:00 | 2014-09-10 17:00:00.0000000 +00:00 | 2015-08-17 17:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2014-06-26 17:00:00.0000000 +00:00 | 2014-07-30 00:00:00.0000000 +00:00 | 2014-07-30 17:00:00.0000000 +00:00 |  | 2014-08-20 00:00:00.0000000 +00:00 | 2014-08-20 00:00:00.0000000 +00:00 | 2014-08-20 00:00:00.0000000 +00:00 | 2014-08-20 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-10 00:00:00.0000000 +00:00 | 2014-09-10 17:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-17 17:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 |  | 2019-08-14 00:00:00.0000000 +00:00 |  | 2019-08-14 00:00:00.0000000 +00:00 | 2019-08-14 00:00:00.0000000 +00:00 |  | 2017-11-27 12:41:20.4088661 -05:00
HWS2015X | Y | 2014-06-20 00:00:00.0000000 +00:00 | 2014-08-21 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2014-06-20 00:00:00.0000000 +00:00 | 2014-08-21 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-05-25 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-20 17:00:00.0000000 +00:00 | 2014-08-01 17:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2014-06-20 17:00:00.0000000 +00:00 | 2014-06-20 17:00:00.0000000 +00:00 | 2014-08-01 17:00:00.0000000 +00:00 | 2014-08-01 17:00:00.0000000 +00:00 | 2014-09-03 00:00:00.0000000 +00:00 | 2014-09-03 00:00:00.0000000 +00:00 | 2014-09-03 00:00:00.0000000 +00:00 | 2014-09-03 00:00:00.0000000 +00:00 | 2014-09-03 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2016-10-24 00:00:00.0000000 +00:00 | 2019-05-23 00:00:00.0000000 +00:00 | 2019-10-23 00:00:00.0000000 +00:00 |  | 2019-10-23 00:00:00.0000000 +00:00 | 2019-10-23 00:00:00.0000000 +00:00
HWS2016CW1 | Y | [48 empty] | 2017-09-01 16:28:32.8259924 -04:00
HWS2016K1 | Y | 2015-07-14 00:00:00.0000000 +00:00 | 2015-08-06 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2020-05-13 00:00:00.0000000 +00:00 | 2015-07-14 00:00:00.0000000 +00:00 | 2015-08-19 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2019-07-16 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-14 17:00:00.0000000 +00:00 | 2015-08-06 17:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2017-05-15 17:00:00.0000000 +00:00 |  | 2015-12-19 00:00:00.0000000 +00:00 | 2020-05-13 00:00:00.0000000 +00:00 | 2015-07-14 00:00:00.0000000 +00:00 | 2015-07-14 00:00:00.0000000 +00:00 | 2015-08-06 00:00:00.0000000 +00:00 | 2015-08-06 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-21 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2020-05-13 00:00:00.0000000 +00:00 | 2020-05-13 00:00:00.0000000 +00:00 | 2023-05-12 00:00:00.0000000 +00:00 | 2023-05-12 00:00:00.0000000 +00:00 |  | 2023-05-12 00:00:00.0000000 +00:00 | 2023-05-12 00:00:00.0000000 +00:00 |  | 2017-08-30 14:42:23.5636915 -04:00
HWS2016K2 | Y | 2015-07-14 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2020-06-04 00:00:00.0000000 +00:00 | 2015-07-14 00:00:00.0000000 +00:00 | 2015-08-19 00:00:00.0000000 +00:00 | 2016-01-16 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2019-07-16 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-14 17:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2017-06-05 17:00:00.0000000 +00:00 |  | 2015-12-20 00:00:00.0000000 +00:00 | 2020-06-04 00:00:00.0000000 +00:00 | 2015-07-14 00:00:00.0000000 +00:00 | 2015-07-14 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-29 00:00:00.0000000 +00:00 | 2015-10-29 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2020-06-04 00:00:00.0000000 +00:00 | 2020-06-04 00:00:00.0000000 +00:00 | 2023-06-03 00:00:00.0000000 +00:00 | 2023-06-03 00:00:00.0000000 +00:00 |  | 2023-06-03 00:00:00.0000000 +00:00 | 2023-06-03 00:00:00.0000000 +00:00 |  | 2017-08-30 14:42:37.0221275 -04:00
HWS2016M | Y | 2015-07-08 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2019-03-08 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2016-05-25 00:00:00.0000000 +00:00 | 2017-05-26 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-08 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 |  | 2015-11-24 00:00:00.0000000 +00:00 | 2019-03-08 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-24 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2019-03-08 00:00:00.0000000 +00:00 | 2019-03-08 00:00:00.0000000 +00:00 | 2021-03-08 00:00:00.0000000 +00:00 | 2021-03-08 00:00:00.0000000 +00:00 |  | 2021-03-08 00:00:00.0000000 +00:00 | 2021-03-08 00:00:00.0000000 +00:00 |  | 2017-11-17 11:04:09.4209246 -05:00
HWS2016Q1 | Y | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-26 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2019-02-09 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-26 00:00:00.0000000 +00:00 | 2019-08-19 00:00:00.0000000 +00:00 | 2019-08-19 00:00:00.0000000 +00:00 | 2019-08-19 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-26 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 |  | 2016-09-26 00:00:00.0000000 +00:00 | 2019-02-09 00:00:00.0000000 +00:00 |  | 2015-07-10 00:00:00.0000000 +00:00 |  | 2015-08-26 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 |  | 2016-02-15 00:00:00.0000000 +00:00 | [6 empty] | 2016-09-26 00:00:00.0000000 +00:00 |  | 2017-08-14 00:00:00.0000000 +00:00 |  | 2019-02-09 00:00:00.0000000 +00:00 | 2022-08-19 00:00:00.0000000 +00:00 | 2022-02-09 00:00:00.0000000 +00:00 |  |  | 2022-02-09 00:00:00.0000000 +00:00
HWS2016Q2 | Y | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-26 00:00:00.0000000 +00:00 | 2016-10-05 00:00:00.0000000 +00:00 | 2017-09-18 00:00:00.0000000 +00:00 | 2019-02-09 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-26 00:00:00.0000000 +00:00 | 2016-10-05 00:00:00.0000000 +00:00 | 2017-06-10 00:00:00.0000000 +00:00 | 2018-12-05 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-10 17:00:00.0000000 +00:00 | 2015-08-26 00:00:00.0000000 +00:00 | 2016-10-06 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 |  | 2016-10-06 00:00:00.0000000 +00:00 | 2019-02-09 00:00:00.0000000 +00:00 |  | 2015-07-10 17:00:00.0000000 +00:00 |  | 2015-08-26 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 |  | 2016-02-15 00:00:00.0000000 +00:00 | [6 empty] | 2016-10-06 00:00:00.0000000 +00:00 |  | 2017-08-14 00:00:00.0000000 +00:00 |  | 2019-02-09 00:00:00.0000000 +00:00 | 2021-12-05 00:00:00.0000000 +00:00 | 2022-02-09 00:00:00.0000000 +00:00 |  |  | 2022-02-09 00:00:00.0000000 +00:00 |  | 2017-09-05 13:45:18.0118579 -04:00
HWS2016R1 | Y | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2017-07-31 00:00:00.0000000 +00:00 | 2020-07-29 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2017-08-29 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-10 17:00:00.0000000 +00:00 | 2015-08-17 17:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2017-07-31 00:00:00.0000000 +00:00 |  | 2015-10-20 00:00:00.0000000 +00:00 | 2020-07-29 00:00:00.0000000 +00:00 |  | 2015-07-10 17:00:00.0000000 +00:00 |  | 2015-08-17 17:00:00.0000000 +00:00 |  | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | [6 empty] | 2015-10-20 00:00:00.0000000 +00:00 | 2017-07-31 00:00:00.0000000 +00:00 | 2017-07-31 00:00:00.0000000 +00:00 |  | 2020-07-29 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2023-07-28 00:00:00.0000000 +00:00 |  |  | 2023-07-28 00:00:00.0000000 +00:00 |  | 2017-09-29 07:49:49.1575420 -04:00
HWS2016R2 | Y | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-11-04 00:00:00.0000000 +00:00 | 2017-07-31 00:00:00.0000000 +00:00 | 2020-07-29 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2017-08-29 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-10 17:00:00.0000000 +00:00 | 2015-08-17 17:00:00.0000000 +00:00 | 2015-11-04 00:00:00.0000000 +00:00 | 2017-07-31 17:00:00.0000000 +00:00 |  | 2015-11-04 00:00:00.0000000 +00:00 | 2020-07-29 00:00:00.0000000 +00:00 |  | 2015-07-10 17:00:00.0000000 +00:00 |  | 2015-08-17 17:00:00.0000000 +00:00 |  | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | [6 empty] | 2015-11-04 00:00:00.0000000 +00:00 | 2017-07-31 00:00:00.0000000 +00:00 | 2017-07-31 17:00:00.0000000 +00:00 |  | 2020-07-29 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2023-07-28 00:00:00.0000000 +00:00 |  |  | 2023-07-28 00:00:00.0000000 +00:00 |  | 2017-09-29 07:50:27.7170758 -04:00
HWS2016X | Y | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2018-03-19 00:00:00.0000000 +00:00 | 2019-09-14 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 |  |  | 2015-11-24 00:00:00.0000000 +00:00 | 2019-09-14 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2015-10-07 00:00:00.0000000 +00:00 | 2015-10-07 00:00:00.0000000 +00:00 | 2015-10-07 00:00:00.0000000 +00:00 | 2015-10-07 00:00:00.0000000 +00:00 | 2015-10-07 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-24 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2018-03-19 00:00:00.0000000 +00:00 | 2018-03-19 00:00:00.0000000 +00:00 | 2019-09-14 00:00:00.0000000 +00:00 | 2019-09-14 00:00:00.0000000 +00:00 | 2020-08-20 00:00:00.0000000 +00:00 | 2022-09-13 00:00:00.0000000 +00:00 |  | 2022-09-13 00:00:00.0000000 +00:00 | 2022-09-13 00:00:00.0000000 +00:00 |  | 2017-10-18 14:09:51.0807370 -04:00
HWS2016XM | Y | 2015-07-08 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2020-02-12 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2017-05-24 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-08 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 |  | 2015-10-23 00:00:00.0000000 +00:00 | 2020-02-12 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-23 00:00:00.0000000 +00:00 | 2015-10-23 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | 2020-02-12 00:00:00.0000000 +00:00 | 2020-02-12 00:00:00.0000000 +00:00 | 2018-05-19 00:00:00.0000000 +00:00 | 2023-02-12 00:00:00.0000000 +00:00 |  | 2023-02-12 00:00:00.0000000 +00:00 | 2023-02-12 00:00:00.0000000 +00:00
HWS2017M | Y | 2016-09-13 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 | 2018-04-19 00:00:00.0000000 +00:00 | 2019-10-15 00:00:00.0000000 +00:00 | 2016-09-13 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-12-31 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2018-08-30 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-13 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 |  |  | 2016-12-21 00:00:00.0000000 +00:00 |  | 2016-09-13 00:00:00.0000000 +00:00 |  | 2016-10-03 00:00:00.0000000 +00:00 |  | 2016-11-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | [6 empty] | 2016-12-21 00:00:00.0000000 +00:00 |  | 2018-04-19 00:00:00.0000000 +00:00 |  | 2019-10-15 00:00:00.0000000 +00:00 |  | 2020-08-30 00:00:00.0000000 +00:00 | 2021-10-15 00:00:00.0000000 +00:00 |  | 2021-10-15 00:00:00.0000000 +00:00 |  |  | 2017-09-13 14:22:33.0862425 -04:00
HWS2017Q1 | Y | 2016-10-03 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 | 2017-10-09 00:00:00.0000000 +00:00 | 2019-04-06 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 | 2019-08-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-10-03 17:00:00.0000000 +00:00 | 2016-10-03 17:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 | 2017-10-09 00:00:00.0000000 +00:00 |  | 2016-12-21 00:00:00.0000000 +00:00 | 2019-04-06 00:00:00.0000000 +00:00 | 2016-10-03 17:00:00.0000000 +00:00 | 2016-10-03 17:00:00.0000000 +00:00 | 2016-10-03 17:00:00.0000000 +00:00 | 2016-10-03 17:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-21 00:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 | 2017-10-09 00:00:00.0000000 +00:00 | 2017-10-09 00:00:00.0000000 +00:00 | 2019-04-06 00:00:00.0000000 +00:00 | 2019-04-06 00:00:00.0000000 +00:00 | 2022-08-20 00:00:00.0000000 +00:00 | 2022-04-06 00:00:00.0000000 +00:00 |  | 2022-04-06 00:00:00.0000000 +00:00 | 2022-04-06 00:00:00.0000000 +00:00 |  | 2017-12-04 13:43:41.2114159 -05:00
HWS2017Q2 | Y | 2016-10-03 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2017-12-20 00:00:00.0000000 +00:00 | 2018-08-13 00:00:00.0000000 +00:00 | 2020-08-13 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 | 2018-08-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-10-03 17:00:00.0000000 +00:00 | 2016-10-03 17:00:00.0000000 +00:00 | 2017-12-08 00:00:00.0000000 +00:00 |  |  | 2017-12-20 00:00:00.0000000 +00:00 |  | 2016-10-03 17:00:00.0000000 +00:00 |  | 2016-10-03 17:00:00.0000000 +00:00 |  | 2016-11-15 00:00:00.0000000 +00:00 | 2017-06-15 00:00:00.0000000 +00:00 | 2017-06-15 00:00:00.0000000 +00:00 | 2017-06-15 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-20 00:00:00.0000000 +00:00 |  | 2018-08-13 00:00:00.0000000 +00:00 |  | 2020-08-13 00:00:00.0000000 +00:00 |  | 2021-08-20 00:00:00.0000000 +00:00 | 2023-08-13 00:00:00.0000000 +00:00 |  | 2023-08-13 00:00:00.0000000 +00:00 |  |  | 2017-12-12 10:13:06.1180777 -05:00
HWS2017X | Y | 2016-08-31 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2019-06-13 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2019-06-13 00:00:00.0000000 +00:00 | [5 empty] | 2016-08-31 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 |  | 2016-12-21 00:00:00.0000000 +00:00 | 2019-06-13 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2016-10-31 00:00:00.0000000 +00:00 | 2016-10-31 00:00:00.0000000 +00:00 | 2016-10-31 00:00:00.0000000 +00:00 | 2016-10-31 00:00:00.0000000 +00:00 | 2016-10-31 00:00:00.0000000 +00:00 | [5 empty] | 2016-12-21 00:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2019-06-13 00:00:00.0000000 +00:00 | 2019-06-13 00:00:00.0000000 +00:00 | 2022-06-12 00:00:00.0000000 +00:00 | 2022-06-12 00:00:00.0000000 +00:00 |  | 2022-06-12 00:00:00.0000000 +00:00 | 2022-06-12 00:00:00.0000000 +00:00
HWS2018M | Y | 2017-05-03 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-06-14 00:00:00.0000000 +00:00 | 2017-05-03 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-06-14 00:00:00.0000000 +00:00 | [5 empty] | 2017-05-03 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 |  |  |  | 2017-11-30 00:00:00.0000000 +00:00 | 2019-06-14 00:00:00.0000000 +00:00 | 2017-05-03 00:00:00.0000000 +00:00 |  | 2017-06-01 00:00:00.0000000 +00:00 |  | 2017-08-15 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | [6 empty] | 2017-11-30 00:00:00.0000000 +00:00 |  | 2018-06-15 00:00:00.0000000 +00:00 |  | 2019-06-14 00:00:00.0000000 +00:00 |  | 2022-06-12 00:00:00.0000000 +00:00 | 2022-09-23 00:00:00.0000000 +00:00 |  | 2022-09-23 00:00:00.0000000 +00:00 |  |  | 2017-12-01 13:01:13.2465351 -05:00
HWS2018Q1 | Y | 2017-04-24 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-12-15 00:00:00.0000000 +00:00 | 2019-12-15 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-04-24 17:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 |  |  | 2017-12-29 00:00:00.0000000 +00:00 |  | 2017-04-24 17:00:00.0000000 +00:00 |  | 2017-06-01 00:00:00.0000000 +00:00 |  | 2017-10-30 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-12-15 00:00:00.0000000 +00:00 |  | 2019-12-15 00:00:00.0000000 +00:00 |  | 2022-06-15 00:00:00.0000000 +00:00 | 2022-12-15 00:00:00.0000000 +00:00 |  | 2022-12-15 00:00:00.0000000 +00:00 |  |  | 2017-12-12 09:39:27.6076665 -05:00
HWS2018Q2 | Y | 2017-04-24 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-12-15 00:00:00.0000000 +00:00 | 2019-12-15 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-04-24 17:00:00.0000000 +00:00 | 2017-06-01 17:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 |  |  | 2017-12-29 00:00:00.0000000 +00:00 | 2020-04-09 00:00:00.0000000 +00:00 | 2017-04-24 17:00:00.0000000 +00:00 |  | 2017-06-01 17:00:00.0000000 +00:00 |  | 2017-10-30 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-12-15 00:00:00.0000000 +00:00 |  | 2019-12-15 00:00:00.0000000 +00:00 |  | 2022-06-15 00:00:00.0000000 +00:00 | 2022-12-15 00:00:00.0000000 +00:00 |  | 2022-12-15 00:00:00.0000000 +00:00 |  |  | 2017-12-12 09:41:10.4663034 -05:00
HWS2018X | Y | 2017-05-03 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-12-12 00:00:00.0000000 +00:00 | 2018-10-15 00:00:00.0000000 +00:00 | 2020-04-11 00:00:00.0000000 +00:00 | 2017-05-03 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2018-10-15 00:00:00.0000000 +00:00 | 2019-10-14 00:00:00.0000000 +00:00 | [5 empty] | 2017-05-03 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-12-12 00:00:00.0000000 +00:00 |  |  | 2017-12-12 00:00:00.0000000 +00:00 |  | 2017-05-03 00:00:00.0000000 +00:00 |  | 2017-06-01 00:00:00.0000000 +00:00 |  | 2017-08-30 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-12 00:00:00.0000000 +00:00 |  | 2018-10-15 00:00:00.0000000 +00:00 |  | 2020-04-11 00:00:00.0000000 +00:00 |  | 2022-10-12 00:00:00.0000000 +00:00 | 2023-04-11 00:00:00.0000000 +00:00 |  | 2023-04-11 00:00:00.0000000 +00:00 |  |  | 2017-10-12 13:49:43.0971990 -04:00
HWSRT2009 | Y | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2008-10-15 00:00:00.0000000 +00:00 | 2010-02-13 00:00:00.0000000 +00:00 | 2010-08-23 00:00:00.0000000 +00:00 | 2011-08-24 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2009-05-19 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 | 2016-09-24 00:00:00.0000000 +00:00 | 2008-08-25 12:00:00.0000000 +00:00 | 2009-12-17 12:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2014-02-09 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2008-08-25 12:00:00.0000000 +00:00 | 2008-08-25 12:00:00.0000000 +00:00 | 2009-12-17 12:00:00.0000000 +00:00 | 2009-12-17 12:00:00.0000000 +00:00 | 2009-08-10 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | [5 empty] | 2014-02-19 00:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2014-08-23 00:00:00.0000000 +00:00 | 2018-11-04 00:00:00.0000000 +00:00 |  | 2018-11-04 00:00:00.0000000 +00:00 | 2018-11-04 00:00:00.0000000 +00:00
HWSRT200A | Y | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2013-02-19 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2012-01-12 00:00:00.0000000 +00:00 | 2012-08-01 00:00:00.0000000 +00:00 | 2013-07-31 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2014-02-19 00:00:00.0000000 +00:00 | 2014-03-21 00:00:00.0000000 +00:00 | 2015-03-20 00:00:00.0000000 +00:00 | 2008-08-25 12:00:00.0000000 +00:00 | 2009-12-17 12:00:00.0000000 +00:00 | 2013-02-19 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2013-02-19 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2008-08-25 12:00:00.0000000 +00:00 | 2008-08-25 12:00:00.0000000 +00:00 | 2009-12-17 12:00:00.0000000 +00:00 | 2009-12-17 12:00:00.0000000 +00:00 | 2010-08-26 00:00:00.0000000 +00:00 | 2011-01-07 00:00:00.0000000 +00:00 | 2011-01-07 00:00:00.0000000 +00:00 | 2011-01-07 00:00:00.0000000 +00:00 | 2011-01-07 00:00:00.0000000 +00:00 | [5 empty] | 2013-02-19 00:00:00.0000000 +00:00 | 2013-02-19 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2016-07-30 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 |  | 2019-06-29 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00
HWSRT200B | Y | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2015-11-04 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2012-01-12 00:00:00.0000000 +00:00 | 2012-08-01 00:00:00.0000000 +00:00 | 2013-07-31 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 | 2014-01-26 00:00:00.0000000 +00:00 | 2015-01-25 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2015-11-04 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 | 2015-11-04 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2010-10-25 00:00:00.0000000 +00:00 | 2011-01-07 00:00:00.0000000 +00:00 | 2011-01-07 00:00:00.0000000 +00:00 | 2011-01-07 00:00:00.0000000 +00:00 | 2011-01-07 00:00:00.0000000 +00:00 | [5 empty] | 2012-11-30 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2015-11-04 00:00:00.0000000 +00:00 | 2015-11-04 00:00:00.0000000 +00:00 | 2016-07-30 00:00:00.0000000 +00:00 | 2018-11-03 00:00:00.0000000 +00:00 |  | 2018-11-03 00:00:00.0000000 +00:00 | 2018-11-03 00:00:00.0000000 +00:00 |  | 2017-10-18 14:10:20.2433926 -04:00
HWSRT200C | Y | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2014-03-04 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2017-01-18 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2014-01-16 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2015-09-11 00:00:00.0000000 +00:00 | 2008-08-25 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-03-09 00:00:00.0000000 +00:00 | 2016-03-09 00:00:00.0000000 +00:00 | 2008-08-25 12:00:00.0000000 +00:00 | 2009-12-17 12:00:00.0000000 +00:00 | 2014-03-04 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2017-01-18 00:00:00.0000000 +00:00 | 2014-03-04 00:00:00.0000000 +00:00 | 2017-01-18 00:00:00.0000000 +00:00 | 2008-08-25 12:00:00.0000000 +00:00 | 2008-08-25 12:00:00.0000000 +00:00 | 2009-12-17 12:00:00.0000000 +00:00 | 2009-12-17 12:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2013-12-12 00:00:00.0000000 +00:00 | 2013-12-12 00:00:00.0000000 +00:00 | [5 empty] | 2014-03-04 00:00:00.0000000 +00:00 | 2014-03-04 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2017-01-18 00:00:00.0000000 +00:00 | 2017-01-18 00:00:00.0000000 +00:00 | 2018-09-10 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00 |  | 2020-01-17 00:00:00.0000000 +00:00 | 2020-01-17 00:00:00.0000000 +00:00
HWSRT200D | Y | 2017-06-12 00:00:00.0000000 +00:00 | 2018-01-02 00:00:00.0000000 +00:00 | 2020-10-31 00:00:00.0000000 +00:00 | 2021-07-17 00:00:00.0000000 +00:00 | 2023-01-06 00:00:00.0000000 +00:00 | 2017-06-12 00:00:00.0000000 +00:00 | 2018-01-02 00:00:00.0000000 +00:00 | 2020-10-31 00:00:00.0000000 +00:00 | 2021-07-17 00:00:00.0000000 +00:00 | 2023-01-06 00:00:00.0000000 +00:00 | [5 empty] | 2017-06-12 17:00:00.0000000 +00:00 |  |  |  |  | 2020-10-31 00:00:00.0000000 +00:00 | 2023-01-06 00:00:00.0000000 +00:00 | 2017-06-12 00:00:00.0000000 +00:00 | 2017-06-12 00:00:00.0000000 +00:00 | 2018-01-02 00:00:00.0000000 +00:00 | 2018-01-02 00:00:00.0000000 +00:00 | 2020-05-04 00:00:00.0000000 +00:00 | 2020-05-04 00:00:00.0000000 +00:00 |  | 2020-05-04 00:00:00.0000000 +00:00 | 2020-05-04 00:00:00.0000000 +00:00 | [5 empty] | 2020-10-31 00:00:00.0000000 +00:00 | 2020-10-31 00:00:00.0000000 +00:00 | 2021-07-17 00:00:00.0000000 +00:00 | 2021-07-17 00:00:00.0000000 +00:00 | 2023-01-06 00:00:00.0000000 +00:00 | 2023-01-06 00:00:00.0000000 +00:00 | 2026-01-05 00:00:00.0000000 +00:00 | 2026-01-05 00:00:00.0000000 +00:00 |  | 2026-01-05 00:00:00.0000000 +00:00 | 2026-01-05 00:00:00.0000000 +00:00 |  | 2017-08-30 14:42:56.8437223 -04:00
HWTRK1 | Y | 2017-05-04 00:00:00.0000000 +00:00 | 2018-01-29 00:00:00.0000000 +00:00 | 2020-10-30 00:00:00.0000000 +00:00 | 2021-07-19 00:00:00.0000000 +00:00 | 2023-07-18 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 | 2018-01-29 00:00:00.0000000 +00:00 | 2020-10-30 00:00:00.0000000 +00:00 | 2021-07-19 00:00:00.0000000 +00:00 | 2023-07-18 00:00:00.0000000 +00:00 | [5 empty] | 2017-05-04 17:00:00.0000000 +00:00 |  |  |  |  | 2020-10-30 00:00:00.0000000 +00:00 | 2023-07-18 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 | 2018-01-29 00:00:00.0000000 +00:00 | 2018-01-29 00:00:00.0000000 +00:00 | 2019-01-28 00:00:00.0000000 +00:00 | 2019-01-28 00:00:00.0000000 +00:00 |  | 2019-01-28 00:00:00.0000000 +00:00 | 2019-01-28 00:00:00.0000000 +00:00 | [5 empty] | 2020-10-30 00:00:00.0000000 +00:00 | 2020-10-30 00:00:00.0000000 +00:00 | 2021-07-19 00:00:00.0000000 +00:00 | 2021-07-19 00:00:00.0000000 +00:00 | 2023-07-18 00:00:00.0000000 +00:00 | 2023-07-18 00:00:00.0000000 +00:00 | 2026-07-17 00:00:00.0000000 +00:00 | 2026-07-17 00:00:00.0000000 +00:00 |  | 2026-07-17 00:00:00.0000000 +00:00 | 2026-07-17 00:00:00.0000000 +00:00
HWTRQX1 | Y | 2017-05-16 00:00:00.0000000 +00:00 | 2018-04-15 00:00:00.0000000 +00:00 | 2020-04-14 00:00:00.0000000 +00:00 | 2021-03-30 00:00:00.0000000 +00:00 | 2023-03-30 00:00:00.0000000 +00:00 | 2017-05-16 00:00:00.0000000 +00:00 | 2018-04-15 00:00:00.0000000 +00:00 | 2020-04-14 00:00:00.0000000 +00:00 | 2021-03-30 00:00:00.0000000 +00:00 | 2023-03-30 00:00:00.0000000 +00:00 | [5 empty] | 2017-05-16 17:00:00.0000000 +00:00 | [10 empty] | 2019-04-15 00:00:00.0000000 +00:00 | 2019-04-15 00:00:00.0000000 +00:00 | [14 empty] | 2026-03-30 00:00:00.0000000 +00:00 | 2026-03-30 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-26 11:22:00.1199223 -04:00
HWTRR1 | Y | 2017-05-16 00:00:00.0000000 +00:00 | 2018-03-12 00:00:00.0000000 +00:00 | 2019-03-12 00:00:00.0000000 +00:00 | 2020-08-10 00:00:00.0000000 +00:00 | 2021-08-10 00:00:00.0000000 +00:00 | 2017-05-16 00:00:00.0000000 +00:00 | 2018-03-12 00:00:00.0000000 +00:00 | 2019-03-12 00:00:00.0000000 +00:00 | 2020-08-10 00:00:00.0000000 +00:00 | 2021-08-10 00:00:00.0000000 +00:00 | [5 empty] | 2017-05-16 00:00:00.0000000 +00:00 | [10 empty] | 2018-12-17 00:00:00.0000000 +00:00 | 2018-12-17 00:00:00.0000000 +00:00 | [14 empty] | 2022-08-05 00:00:00.0000000 +00:00 | 2022-08-05 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-20 11:58:38.6777134 -05:00
HWX100SBS | Y | 2014-01-31 00:00:00.0000000 +00:00 | 2014-04-28 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2018-01-11 00:00:00.0000000 +00:00 | 2014-01-31 00:00:00.0000000 +00:00 | 2014-04-28 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-11-16 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | [5 empty] | 2014-01-31 17:00:00.0000000 +00:00 | 2014-04-28 18:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 |  | 2015-09-30 00:00:00.0000000 +00:00 | 2018-01-11 00:00:00.0000000 +00:00 | 2014-01-31 17:00:00.0000000 +00:00 | 2014-01-31 17:00:00.0000000 +00:00 | 2014-04-28 18:00:00.0000000 +00:00 | 2014-04-28 18:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2018-01-11 00:00:00.0000000 +00:00 | 2018-01-11 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 | 2021-01-10 00:00:00.0000000 +00:00 |  | 2021-01-10 00:00:00.0000000 +00:00 | 2021-01-10 00:00:00.0000000 +00:00
HWX1048 | Y | 2017-08-03 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2020-12-28 00:00:00.0000000 +00:00 | 2021-09-06 00:00:00.0000000 +00:00 | 2023-03-05 00:00:00.0000000 +00:00 | 2017-08-03 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2020-12-28 00:00:00.0000000 +00:00 | 2021-09-06 00:00:00.0000000 +00:00 | 2023-03-05 00:00:00.0000000 +00:00 | [5 empty] | 2017-08-03 00:00:00.0000000 +00:00 | [10 empty] | 2020-02-17 00:00:00.0000000 +00:00 | 2020-02-17 00:00:00.0000000 +00:00 | [14 empty] | 2026-03-04 00:00:00.0000000 +00:00 | 2026-03-04 00:00:00.0000000 +00:00
HWX421AW | Y | 2006-08-09 00:00:00.0000000 +00:00 | 2020-04-15 00:00:00.0000000 +00:00 | 2023-11-23 00:00:00.0000000 +00:00 | 2024-07-05 00:00:00.0000000 +00:00 | 2027-07-05 00:00:00.0000000 +00:00 | 2006-08-09 00:00:00.0000000 +00:00 | 2007-07-31 00:00:00.0000000 +00:00 | 2009-02-15 00:00:00.0000000 +00:00 | 2009-09-02 00:00:00.0000000 +00:00 | 2011-02-23 00:00:00.0000000 +00:00 | 2006-08-09 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2020-02-01 00:00:00.0000000 +00:00 | 2020-08-18 00:00:00.0000000 +00:00 | 2022-02-08 00:00:00.0000000 +00:00 | 2006-08-09 00:00:00.0000000 +00:00 | [10 empty] | 2008-08-07 00:00:00.0000000 +00:00 | 2022-10-19 00:00:00.0000000 +00:00 | [14 empty] | 2014-02-24 00:00:00.0000000 +00:00 | 2030-07-04 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-18 10:54:46.4551273 -04:00
HWX710A | Y | 1998-05-15 00:00:00.0000000 +00:00 | 2002-02-20 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2021-07-31 00:00:00.0000000 +00:00 | 1998-05-15 00:00:00.0000000 +00:00 | 2002-02-15 00:00:00.0000000 +00:00 | 2002-08-15 00:00:00.0000000 +00:00 | 2003-03-15 00:00:00.0000000 +00:00 | 2004-03-15 00:00:00.0000000 +00:00 | 1998-05-15 00:00:00.0000000 +00:00 | 2002-02-15 00:00:00.0000000 +00:00 | 2012-07-10 00:00:00.0000000 +00:00 | 2013-10-20 00:00:00.0000000 +00:00 | 2016-10-18 00:00:00.0000000 +00:00 | 1998-05-15 12:00:00.0000000 +00:00 | 2002-02-15 12:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 |  | 2016-11-30 00:00:00.0000000 +00:00 | 2021-07-31 00:00:00.0000000 +00:00 | 1998-05-15 12:00:00.0000000 +00:00 | 1998-05-15 12:00:00.0000000 +00:00 | 2002-02-15 12:00:00.0000000 +00:00 | 2002-02-15 12:00:00.0000000 +00:00 | 2002-06-28 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | [5 empty] | 2016-11-30 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2021-07-31 00:00:00.0000000 +00:00 | 2021-07-31 00:00:00.0000000 +00:00 | 2007-03-14 00:00:00.0000000 +00:00 | 2024-07-30 00:00:00.0000000 +00:00 |  | 2024-07-30 00:00:00.0000000 +00:00 | 2024-07-30 00:00:00.0000000 +00:00
HWXF2000A | Y | 2008-10-23 00:00:00.0000000 +00:00 | 2010-01-06 00:00:00.0000000 +00:00 | 2011-05-05 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2008-10-23 00:00:00.0000000 +00:00 | 2009-06-03 00:00:00.0000000 +00:00 | 2010-05-15 00:00:00.0000000 +00:00 | 2010-11-12 00:00:00.0000000 +00:00 | 2012-04-10 00:00:00.0000000 +00:00 | 2008-10-23 00:00:00.0000000 +00:00 | 2010-01-06 00:00:00.0000000 +00:00 | 2010-12-18 00:00:00.0000000 +00:00 | 2011-10-30 00:00:00.0000000 +00:00 | 2013-03-28 00:00:00.0000000 +00:00 | 2008-10-23 00:00:00.0000000 +00:00 | 2010-01-06 00:00:00.0000000 +00:00 |  | 2012-01-26 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2011-05-05 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | [6 empty] | 2010-05-06 00:00:00.0000000 +00:00 |  |  |  |  | 2010-11-06 00:00:00.0000000 +00:00 | [8 empty] | 2016-02-15 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00
HWXF2000B | Y | 2015-07-31 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2018-02-12 00:00:00.0000000 +00:00 | 2018-10-03 00:00:00.0000000 +00:00 | 2020-04-10 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2017-03-03 00:00:00.0000000 +00:00 | 2018-10-03 00:00:00.0000000 +00:00 | 2020-04-10 00:00:00.0000000 +00:00 | [5 empty] | 2015-07-31 18:00:00.0000000 +00:00 | 2016-08-10 18:00:00.0000000 +00:00 |  |  |  | 2018-02-12 00:00:00.0000000 +00:00 | 2020-10-09 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2016-11-10 00:00:00.0000000 +00:00 | 2016-11-10 00:00:00.0000000 +00:00 | 2016-11-10 00:00:00.0000000 +00:00 | 2016-11-10 00:00:00.0000000 +00:00 | 2016-11-29 00:00:00.0000000 +00:00 | 2017-02-02 00:00:00.0000000 +00:00 | 2017-02-02 00:00:00.0000000 +00:00 | 2017-02-02 00:00:00.0000000 +00:00 | 2017-02-02 00:00:00.0000000 +00:00 | 2018-02-12 00:00:00.0000000 +00:00 | 2018-02-12 00:00:00.0000000 +00:00 | 2018-10-03 00:00:00.0000000 +00:00 | 2018-10-03 00:00:00.0000000 +00:00 | 2020-10-09 00:00:00.0000000 +00:00 | 2020-10-09 00:00:00.0000000 +00:00 | 2021-04-09 00:00:00.0000000 +00:00 | 2021-04-09 00:00:00.0000000 +00:00 |  | 2021-10-08 00:00:00.0000000 +00:00 | 2021-10-08 00:00:00.0000000 +00:00 |  | 2017-09-06 10:50:18.1737654 -04:00
HWXF2144W | Y | 2015-11-18 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2016-10-28 00:00:00.0000000 +00:00 | 2017-10-19 00:00:00.0000000 +00:00 | 2019-10-21 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2016-10-28 00:00:00.0000000 +00:00 | 2017-05-29 00:00:00.0000000 +00:00 | 2019-10-21 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-18 17:00:00.0000000 +00:00 | 2016-08-17 18:00:00.0000000 +00:00 | 2017-01-09 00:00:00.0000000 +00:00 | 2017-10-19 00:00:00.0000000 +00:00 |  | 2017-01-09 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2016-08-17 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-09-16 00:00:00.0000000 +00:00 | 2016-10-07 00:00:00.0000000 +00:00 | 2016-10-07 00:00:00.0000000 +00:00 | 2016-10-28 00:00:00.0000000 +00:00 | 2016-10-28 00:00:00.0000000 +00:00 | 2016-10-28 00:00:00.0000000 +00:00 | 2017-01-09 00:00:00.0000000 +00:00 | 2017-01-09 00:00:00.0000000 +00:00 | 2017-10-23 00:00:00.0000000 +00:00 | 2017-10-23 00:00:00.0000000 +00:00 | 2019-04-19 00:00:00.0000000 +00:00 | 2019-04-19 00:00:00.0000000 +00:00 | 2020-11-30 00:00:00.0000000 +00:00 | 2020-11-30 00:00:00.0000000 +00:00 |  | 2020-04-30 00:00:00.0000000 +00:00 | 2020-04-30 00:00:00.0000000 +00:00 |  | 2017-09-06 10:34:52.1766018 -04:00
HWXFPLZA | Y | 2010-04-05 00:00:00.0000000 +00:00 | 2011-06-02 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2014-08-04 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2010-04-05 00:00:00.0000000 +00:00 | 2011-06-02 00:00:00.0000000 +00:00 | 2013-06-02 00:00:00.0000000 +00:00 | 2013-10-18 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2010-04-05 00:00:00.0000000 +00:00 | 2011-06-02 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2014-07-30 00:00:00.0000000 +00:00 | 2015-10-27 00:00:00.0000000 +00:00 | 2010-04-05 12:00:00.0000000 +00:00 | 2011-06-02 12:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2014-08-04 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2010-04-05 12:00:00.0000000 +00:00 | 2010-04-05 12:00:00.0000000 +00:00 | 2011-06-02 12:00:00.0000000 +00:00 | 2011-06-02 12:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2013-07-19 00:00:00.0000000 +00:00 | 2013-07-19 00:00:00.0000000 +00:00 | 2013-07-19 00:00:00.0000000 +00:00 | 2013-07-19 00:00:00.0000000 +00:00 | [5 empty] | 2014-02-28 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2014-08-04 00:00:00.0000000 +00:00 | 2014-08-04 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2018-01-14 00:00:00.0000000 +00:00 | 2018-12-23 00:00:00.0000000 +00:00 |  | 2018-12-23 00:00:00.0000000 +00:00 | 2018-12-23 00:00:00.0000000 +00:00
HWXP093B | Y | 2007-08-22 00:00:00.0000000 +00:00 | 2011-02-01 00:00:00.0000000 +00:00 | 2013-03-21 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2007-08-22 00:00:00.0000000 +00:00 | 2008-02-09 00:00:00.0000000 +00:00 | 2009-02-04 00:00:00.0000000 +00:00 | 2009-05-03 00:00:00.0000000 +00:00 | 2009-10-31 00:00:00.0000000 +00:00 | 2007-08-22 00:00:00.0000000 +00:00 | 2008-09-23 00:00:00.0000000 +00:00 | 2011-09-09 00:00:00.0000000 +00:00 | 2022-03-06 00:00:00.0000000 +00:00 | 2022-09-03 00:00:00.0000000 +00:00 | 2007-08-22 12:00:00.0000000 +00:00 | 2011-02-01 00:00:00.0000000 +00:00 | 2013-03-21 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2013-03-21 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2007-08-22 12:00:00.0000000 +00:00 | 2007-08-22 12:00:00.0000000 +00:00 | 2011-02-01 00:00:00.0000000 +00:00 | 2011-02-01 00:00:00.0000000 +00:00 | 2009-01-18 00:00:00.0000000 +00:00 | 2012-06-18 00:00:00.0000000 +00:00 | 2012-06-18 00:00:00.0000000 +00:00 | 2012-06-18 00:00:00.0000000 +00:00 | 2012-06-18 00:00:00.0000000 +00:00 | [5 empty] | 2013-03-21 00:00:00.0000000 +00:00 | 2013-03-21 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2012-10-30 00:00:00.0000000 +00:00 | 2018-12-30 00:00:00.0000000 +00:00 |  | 2018-12-30 00:00:00.0000000 +00:00 | 2018-12-30 00:00:00.0000000 +00:00
HWXP136A | Y | 2007-08-08 00:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2007-08-08 00:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 | 2009-02-13 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2011-09-15 00:00:00.0000000 +00:00 | 2007-08-08 00:00:00.0000000 +00:00 | 2008-05-19 00:00:00.0000000 +00:00 | 2014-03-18 00:00:00.0000000 +00:00 | 2014-10-18 00:00:00.0000000 +00:00 | 2016-10-17 00:00:00.0000000 +00:00 | 2007-08-08 12:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2007-08-08 12:00:00.0000000 +00:00 | 2007-08-08 12:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 | 2008-03-17 00:00:00.0000000 +00:00 | 2008-07-30 00:00:00.0000000 +00:00 | 2011-10-31 00:00:00.0000000 +00:00 | 2011-10-31 00:00:00.0000000 +00:00 | 2011-10-31 00:00:00.0000000 +00:00 | 2011-10-31 00:00:00.0000000 +00:00 | [5 empty] | 2013-07-29 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2020-10-01 00:00:00.0000000 +00:00 |  | 2020-12-28 00:00:00.0000000 +00:00 | 2020-12-28 00:00:00.0000000 +00:00 |  | 2017-10-18 13:49:51.3341170 -04:00
HWXP136B | Y | 2014-10-14 00:00:00.0000000 +00:00 | 2015-01-16 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-12-01 00:00:00.0000000 +00:00 | 2019-11-30 00:00:00.0000000 +00:00 | 2014-10-14 00:00:00.0000000 +00:00 | 2015-01-16 00:00:00.0000000 +00:00 | 2016-08-05 00:00:00.0000000 +00:00 | 2017-06-15 00:00:00.0000000 +00:00 | 2019-06-14 00:00:00.0000000 +00:00 | [5 empty] | 2014-10-14 17:00:00.0000000 +00:00 | 2015-01-16 17:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-12-01 00:00:00.0000000 +00:00 |  | 2016-07-26 00:00:00.0000000 +00:00 | 2019-11-30 00:00:00.0000000 +00:00 | 2014-10-14 17:00:00.0000000 +00:00 | 2014-10-14 17:00:00.0000000 +00:00 | 2015-01-16 17:00:00.0000000 +00:00 | 2015-01-16 17:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-12-01 00:00:00.0000000 +00:00 | 2017-12-01 00:00:00.0000000 +00:00 | 2019-11-30 00:00:00.0000000 +00:00 | 2019-11-30 00:00:00.0000000 +00:00 | 2022-06-12 00:00:00.0000000 +00:00 | 2022-11-29 00:00:00.0000000 +00:00 |  | 2022-11-29 00:00:00.0000000 +00:00 | 2022-11-29 00:00:00.0000000 +00:00 |  | 2017-08-30 14:46:40.2561498 -04:00
HWXP136C | Y | 2015-04-27 00:00:00.0000000 +00:00 | 2016-07-19 00:00:00.0000000 +00:00 | 2018-04-25 00:00:00.0000000 +00:00 | 2020-08-15 00:00:00.0000000 +00:00 | 2023-08-14 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2020-09-11 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-27 17:00:00.0000000 +00:00 | 2016-07-19 18:00:00.0000000 +00:00 |  |  |  | 2018-04-25 00:00:00.0000000 +00:00 |  | 2015-04-27 17:00:00.0000000 +00:00 |  | 2016-07-19 18:00:00.0000000 +00:00 |  | 2016-10-14 00:00:00.0000000 +00:00 | 2017-05-20 00:00:00.0000000 +00:00 | 2017-05-20 00:00:00.0000000 +00:00 | 2017-05-20 00:00:00.0000000 +00:00 | [6 empty] | 2018-04-25 00:00:00.0000000 +00:00 |  | 2020-08-15 00:00:00.0000000 +00:00 |  | 2023-08-14 00:00:00.0000000 +00:00 |  | 2023-09-10 00:00:00.0000000 +00:00 | 2026-08-13 00:00:00.0000000 +00:00 |  | 2026-08-13 00:00:00.0000000 +00:00 |  |  | 2017-08-30 15:28:12.1614437 -04:00
HWXP138 | Y | 1998-03-03 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2022-10-14 00:00:00.0000000 +00:00 | 2024-09-16 00:00:00.0000000 +00:00 | 2026-09-14 00:00:00.0000000 +00:00 | 1998-03-03 00:00:00.0000000 +00:00 | 2002-05-15 00:00:00.0000000 +00:00 | 2003-11-14 00:00:00.0000000 +00:00 | 2004-06-21 00:00:00.0000000 +00:00 | 2005-06-20 00:00:00.0000000 +00:00 | 1998-03-03 00:00:00.0000000 +00:00 | 2003-08-28 00:00:00.0000000 +00:00 | 2022-08-20 00:00:00.0000000 +00:00 | 2023-03-28 00:00:00.0000000 +00:00 | 2025-03-21 00:00:00.0000000 +00:00 | 1998-03-03 00:00:00.0000000 +00:00 | [10 empty] | 2003-02-17 00:00:00.0000000 +00:00 | 2020-10-15 00:00:00.0000000 +00:00 | [14 empty] | 2008-06-18 00:00:00.0000000 +00:00 | 2029-09-11 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-01 10:50:27.0027207 -04:00
HWXP2007 | Y | 2008-12-01 00:00:00.0000000 +00:00 | 2009-09-03 00:00:00.0000000 +00:00 | 2018-12-15 00:00:00.0000000 +00:00 | 2019-08-15 00:00:00.0000000 +00:00 | 2021-08-14 00:00:00.0000000 +00:00 | 2008-12-01 00:00:00.0000000 +00:00 | 2009-09-03 00:00:00.0000000 +00:00 | 2010-01-17 00:00:00.0000000 +00:00 | 2010-08-12 00:00:00.0000000 +00:00 | 2011-08-13 00:00:00.0000000 +00:00 | 2008-12-01 00:00:00.0000000 +00:00 | 2009-12-15 00:00:00.0000000 +00:00 | 2015-11-10 00:00:00.0000000 +00:00 | 2016-06-04 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2008-12-01 12:00:00.0000000 +00:00 | 2009-09-03 12:00:00.0000000 +00:00 |  |  |  | 2018-12-15 00:00:00.0000000 +00:00 |  | 2008-12-01 12:00:00.0000000 +00:00 |  | 2009-09-03 12:00:00.0000000 +00:00 |  | 2009-11-13 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | [6 empty] | 2018-12-15 00:00:00.0000000 +00:00 |  | 2019-08-15 00:00:00.0000000 +00:00 |  | 2021-08-14 00:00:00.0000000 +00:00 |  | 2014-08-12 00:00:00.0000000 +00:00 | 2024-08-13 00:00:00.0000000 +00:00 |  | 2024-08-13 00:00:00.0000000 +00:00
HWXP2022 | Y | 2008-09-01 00:00:00.0000000 +00:00 | 2009-01-20 00:00:00.0000000 +00:00 | 2011-01-06 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | 2008-09-01 00:00:00.0000000 +00:00 | 2009-02-16 00:00:00.0000000 +00:00 | 2010-01-15 00:00:00.0000000 +00:00 | 2010-09-15 00:00:00.0000000 +00:00 | 2011-03-14 00:00:00.0000000 +00:00 | 2008-09-01 00:00:00.0000000 +00:00 | 2009-02-16 00:00:00.0000000 +00:00 | 2010-03-01 00:00:00.0000000 +00:00 | 2010-10-30 00:00:00.0000000 +00:00 | 2014-01-28 00:00:00.0000000 +00:00 | 2008-09-01 00:00:00.0000000 +00:00 | 2009-01-20 00:00:00.0000000 +00:00 | 2011-01-06 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 |  | 2011-01-06 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | 2008-09-01 00:00:00.0000000 +00:00 | 2008-09-01 00:00:00.0000000 +00:00 | 2009-01-20 00:00:00.0000000 +00:00 | 2009-01-20 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | [5 empty] | 2011-01-06 00:00:00.0000000 +00:00 | 2011-01-06 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | 2014-03-12 00:00:00.0000000 +00:00 | 2021-09-16 00:00:00.0000000 +00:00 |  | 2021-09-16 00:00:00.0000000 +00:00 | 2021-09-16 00:00:00.0000000 +00:00
HWXPRATT | Y | [47 empty] | 2017-09-18 07:00:25.7030000 +00:00
HWXRCPLZ | Y | 2007-07-30 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2007-07-30 00:00:00.0000000 +00:00 | 2007-12-15 00:00:00.0000000 +00:00 | 2009-01-15 00:00:00.0000000 +00:00 | 2009-09-14 00:00:00.0000000 +00:00 | 2010-09-15 00:00:00.0000000 +00:00 | 2007-07-30 00:00:00.0000000 +00:00 | 2009-06-04 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 | 2014-11-06 00:00:00.0000000 +00:00 | 2015-11-07 00:00:00.0000000 +00:00 | 2007-07-30 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2012-12-19 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 |  | 2014-03-15 00:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2007-07-30 00:00:00.0000000 +00:00 | 2007-07-30 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2008-08-15 00:00:00.0000000 +00:00 | 2011-08-31 00:00:00.0000000 +00:00 | 2011-08-31 00:00:00.0000000 +00:00 | 2011-08-31 00:00:00.0000000 +00:00 | 2011-08-31 00:00:00.0000000 +00:00 | [5 empty] | 2014-03-15 00:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2013-09-14 00:00:00.0000000 +00:00 | 2020-12-28 00:00:00.0000000 +00:00 |  | 2020-12-28 00:00:00.0000000 +00:00 | 2020-12-28 00:00:00.0000000 +00:00 |  | 2017-11-14 08:53:09.5001361 -05:00
HWXRCPLZA | Y | 2013-04-24 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2018-03-12 00:00:00.0000000 +00:00 | 2018-08-20 00:00:00.0000000 +00:00 | 2020-02-17 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2013-07-24 00:00:00.0000000 +00:00 | 2013-12-22 00:00:00.0000000 +00:00 | 2014-10-04 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-08-01 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2015-07-29 00:00:00.0000000 +00:00 | 2013-04-24 12:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 |  |  |  | 2018-03-12 00:00:00.0000000 +00:00 |  | 2013-04-24 12:00:00.0000000 +00:00 |  | 2016-06-13 00:00:00.0000000 +00:00 |  | 2013-10-21 00:00:00.0000000 +00:00 | 2016-10-10 00:00:00.0000000 +00:00 | 2016-10-10 00:00:00.0000000 +00:00 | 2016-10-10 00:00:00.0000000 +00:00 | [6 empty] | 2018-03-12 00:00:00.0000000 +00:00 |  | 2018-08-20 00:00:00.0000000 +00:00 |  | 2020-02-17 00:00:00.0000000 +00:00 |  | 2015-12-18 00:00:00.0000000 +00:00 | 2021-02-16 00:00:00.0000000 +00:00 |  | 2021-02-16 00:00:00.0000000 +00:00
HWXS311V1 | Y | 2010-05-03 00:00:00.0000000 +00:00 | 2011-01-11 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 | 2010-05-03 00:00:00.0000000 +00:00 | 2010-11-15 00:00:00.0000000 +00:00 | 2012-01-16 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2010-05-03 00:00:00.0000000 +00:00 | 2010-11-06 00:00:00.0000000 +00:00 | 2015-03-08 00:00:00.0000000 +00:00 | 2005-10-06 00:00:00.0000000 +00:00 | 2006-10-05 00:00:00.0000000 +00:00 | 2010-05-03 12:00:00.0000000 +00:00 | 2011-01-10 12:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 |  | 2015-01-30 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 | 2010-05-03 12:00:00.0000000 +00:00 | 2010-05-03 12:00:00.0000000 +00:00 | 2011-01-10 12:00:00.0000000 +00:00 | 2011-01-10 12:00:00.0000000 +00:00 | 2011-05-16 00:00:00.0000000 +00:00 | 2012-10-01 00:00:00.0000000 +00:00 | 2012-10-01 00:00:00.0000000 +00:00 | 2012-10-01 00:00:00.0000000 +00:00 | 2012-10-01 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-30 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 | 2016-08-13 00:00:00.0000000 +00:00 | 2021-06-15 00:00:00.0000000 +00:00 |  | 2021-06-15 00:00:00.0000000 +00:00 | 2021-06-15 00:00:00.0000000 +00:00 |  | 2017-10-18 13:50:39.8867850 -04:00
HWXS411 | Y | 2013-12-09 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2018-11-10 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-18 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-09 17:00:00.0000000 +00:00 | 2014-09-08 17:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 |  | 2016-04-29 00:00:00.0000000 +00:00 | 2018-11-10 00:00:00.0000000 +00:00 | 2013-12-09 17:00:00.0000000 +00:00 | 2013-12-09 17:00:00.0000000 +00:00 | 2014-09-08 17:00:00.0000000 +00:00 | 2014-09-08 17:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | [5 empty] | 2016-04-29 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2018-11-10 00:00:00.0000000 +00:00 | 2018-11-10 00:00:00.0000000 +00:00 | 2019-06-18 00:00:00.0000000 +00:00 | 2021-11-09 00:00:00.0000000 +00:00 |  | 2021-11-09 00:00:00.0000000 +00:00 | 2021-11-09 00:00:00.0000000 +00:00 |  | 2017-10-18 15:39:35.7572441 -04:00
HWXS511 | Y | 2014-04-04 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2017-05-19 00:00:00.0000000 +00:00 | 2018-03-19 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2014-04-04 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2017-01-14 00:00:00.0000000 +00:00 | 2017-08-13 00:00:00.0000000 +00:00 | 2018-08-12 00:00:00.0000000 +00:00 | [5 empty] | 2014-04-04 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2017-05-19 00:00:00.0000000 +00:00 |  |  | 2017-05-19 00:00:00.0000000 +00:00 |  | 2014-04-04 00:00:00.0000000 +00:00 |  | 2014-09-10 00:00:00.0000000 +00:00 |  | 2016-03-10 00:00:00.0000000 +00:00 | 2016-03-10 00:00:00.0000000 +00:00 | 2016-03-10 00:00:00.0000000 +00:00 | 2016-03-10 00:00:00.0000000 +00:00 | [6 empty] | 2017-05-19 00:00:00.0000000 +00:00 |  | 2018-03-19 00:00:00.0000000 +00:00 |  | 2019-09-15 00:00:00.0000000 +00:00 |  | 2021-08-11 00:00:00.0000000 +00:00 | 2022-09-14 00:00:00.0000000 +00:00 |  | 2022-09-14 00:00:00.0000000 +00:00
HWXS611 | Y | 2017-05-03 00:00:00.0000000 +00:00 | 2018-01-09 00:00:00.0000000 +00:00 | 2020-01-10 00:00:00.0000000 +00:00 | 2020-07-16 00:00:00.0000000 +00:00 | 2022-01-10 00:00:00.0000000 +00:00 | 2017-05-03 00:00:00.0000000 +00:00 | 2018-01-09 00:00:00.0000000 +00:00 | 2020-01-10 00:00:00.0000000 +00:00 | 2020-07-16 00:00:00.0000000 +00:00 | 2022-01-10 00:00:00.0000000 +00:00 | [5 empty] | 2017-05-03 00:00:00.0000000 +00:00 | [10 empty] | 2019-02-05 00:00:00.0000000 +00:00 | 2019-02-05 00:00:00.0000000 +00:00 | [14 empty] | 2025-01-09 00:00:00.0000000 +00:00 | 2025-01-09 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-18 14:55:15.6657670 -04:00
HYDREST04 | Y | 2014-03-27 00:00:00.0000000 +00:00 | 2014-05-14 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2017-03-20 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2014-05-14 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-03-15 00:00:00.0000000 +00:00 | 2016-03-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-03-27 08:00:00.0000000 +00:00 | 2014-05-14 08:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2017-03-20 00:00:00.0000000 +00:00 |  | 2014-08-27 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2014-05-14 00:00:00.0000000 +00:00 | 2014-05-14 00:00:00.0000000 +00:00 | 2014-06-23 00:00:00.0000000 +00:00 | 2014-06-23 00:00:00.0000000 +00:00 | 2014-06-23 00:00:00.0000000 +00:00 | 2014-06-23 00:00:00.0000000 +00:00 | 2014-06-23 00:00:00.0000000 +00:00 | [5 empty] | 2014-08-27 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2017-03-20 00:00:00.0000000 +00:00 | 2017-03-20 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 | 2021-06-16 00:00:00.0000000 +00:00 | 2021-06-16 00:00:00.0000000 +00:00 |  | 2021-06-16 00:00:00.0000000 +00:00 | 2021-06-16 00:00:00.0000000 +00:00 |  | 2017-09-15 09:43:04.9135238 -04:00
HYDREST05 | Y | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-10-15 00:00:00.0000000 +00:00 | 2018-05-23 00:00:00.0000000 +00:00 | 2019-11-19 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2018-04-15 00:00:00.0000000 +00:00 | 2019-04-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-11-22 00:00:00.0000000 +00:00 |  |  | 2017-11-22 00:00:00.0000000 +00:00 |  | 2017-01-13 00:00:00.0000000 +00:00 |  | 2017-01-20 00:00:00.0000000 +00:00 |  | 2017-06-15 00:00:00.0000000 +00:00 | 2017-06-15 00:00:00.0000000 +00:00 | 2017-06-15 00:00:00.0000000 +00:00 | 2017-06-15 00:00:00.0000000 +00:00 | [6 empty] | 2017-10-15 00:00:00.0000000 +00:00 |  | 2018-04-15 00:00:00.0000000 +00:00 |  | 2019-04-15 00:00:00.0000000 +00:00 |  | 2020-04-15 00:00:00.0000000 +00:00 | 2022-11-18 00:00:00.0000000 +00:00 |  | 2020-04-15 00:00:00.0000000 +00:00 |  |  | 2017-11-29 15:20:52.6747768 -05:00
HYDREST06 | Y | 2017-08-14 00:00:00.0000000 +00:00 | 2018-04-15 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2018-04-15 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2017-08-14 00:00:00.0000000 +00:00 | [10 empty] | 2018-09-14 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | [14 empty] | 2023-06-30 00:00:00.0000000 +00:00 | 2023-06-30 00:00:00.0000000 +00:00 |  |  |  | 2017-09-09 15:33:16.8900000 +00:00 | 2017-10-24 11:38:59.4559911 -04:00
IFPM01CW | Y | 2017-08-25 00:00:00.0000000 +00:00 | 2017-08-25 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 | 2018-05-09 00:00:00.0000000 +00:00 | 2021-05-08 00:00:00.0000000 +00:00 | 2017-08-25 00:00:00.0000000 +00:00 | 2017-08-25 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 | 2018-05-09 00:00:00.0000000 +00:00 | 2021-05-08 00:00:00.0000000 +00:00 | [5 empty] | 2017-08-25 00:00:00.0000000 +00:00 | 2017-08-25 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 |  |  | 2017-09-11 00:00:00.0000000 +00:00 |  | 2017-08-25 00:00:00.0000000 +00:00 |  | 2017-08-25 00:00:00.0000000 +00:00 |  | 2017-09-04 00:00:00.0000000 +00:00 | 2017-09-04 00:00:00.0000000 +00:00 | 2017-09-04 00:00:00.0000000 +00:00 | 2017-09-04 00:00:00.0000000 +00:00 | [6 empty] | 2017-09-11 00:00:00.0000000 +00:00 |  | 2018-05-09 00:00:00.0000000 +00:00 |  | 2021-05-08 00:00:00.0000000 +00:00 |  | 2024-05-07 00:00:00.0000000 +00:00 | 2024-05-07 00:00:00.0000000 +00:00 |  | 2024-05-07 00:00:00.0000000 +00:00 |  | 2017-09-09 15:33:20.6300000 +00:00 | 2017-11-28 13:25:40.9634341 -05:00
JJ1FACREN | Y | [48 empty] | 2017-11-28 11:23:53.6467735 -05:00
LBC05BVRF1 | Y | 2007-05-24 00:00:00.0000000 +00:00 | 2009-02-26 00:00:00.0000000 +00:00 | 2009-05-28 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-12-05 00:00:00.0000000 +00:00 | 2007-05-24 00:00:00.0000000 +00:00 | 2009-02-26 00:00:00.0000000 +00:00 | 2009-05-28 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2011-11-30 00:00:00.0000000 +00:00 | 2007-05-24 00:00:00.0000000 +00:00 | 2009-02-26 00:00:00.0000000 +00:00 | 2009-05-28 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-06-05 00:00:00.0000000 +00:00 | 2007-05-24 00:00:00.0000000 +00:00 | 2009-02-26 00:00:00.0000000 +00:00 |  | 2011-08-15 00:00:00.0000000 +00:00 | 2012-12-05 00:00:00.0000000 +00:00 | 2009-05-08 00:00:00.0000000 +00:00 | 2012-10-16 00:00:00.0000000 +00:00
LBC10CDHC1 | Y | 2014-04-14 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2019-01-31 00:00:00.0000000 +00:00 | 2020-05-08 00:00:00.0000000 +00:00 | 2021-11-03 00:00:00.0000000 +00:00 | 2014-03-18 00:00:00.0000000 +00:00 | 2015-04-09 00:00:00.0000000 +00:00 | 2015-11-20 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2016-07-02 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2015-08-30 00:00:00.0000000 +00:00 | 2017-03-09 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-12-11 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 |  |  |  | 2017-12-01 00:00:00.0000000 +00:00 |  | 2014-04-14 00:00:00.0000000 +00:00 |  | 2015-10-19 00:00:00.0000000 +00:00 |  |  |  | 2016-04-12 00:00:00.0000000 +00:00 | 2016-04-12 00:00:00.0000000 +00:00 |  |  |  | 2017-09-07 00:00:00.0000000 +00:00 | 2017-08-31 00:00:00.0000000 +00:00 |  | 2019-01-31 00:00:00.0000000 +00:00 |  | 2020-05-08 00:00:00.0000000 +00:00 |  | 2021-11-03 00:00:00.0000000 +00:00 |  | 2018-07-02 00:00:00.0000000 +00:00 | 2022-05-03 00:00:00.0000000 +00:00 |  | 2022-05-03 00:00:00.0000000 +00:00 |  |  | 2017-12-12 16:16:51.4024008 -05:00
LBC10LDHC | Y | 2009-10-21 00:00:00.0000000 +00:00 | 2010-11-04 00:00:00.0000000 +00:00 | 2011-06-30 00:00:00.0000000 +00:00 | 2012-08-09 00:00:00.0000000 +00:00 | 2013-05-15 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2010-05-04 00:00:00.0000000 +00:00 | 2010-10-02 00:00:00.0000000 +00:00 | 2011-02-15 00:00:00.0000000 +00:00 | 2011-08-22 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2010-11-04 00:00:00.0000000 +00:00 | 2011-06-30 00:00:00.0000000 +00:00 | 2012-08-09 00:00:00.0000000 +00:00 | 2013-09-01 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2010-11-04 00:00:00.0000000 +00:00 | 2011-06-30 00:00:00.0000000 +00:00 | 2012-08-09 00:00:00.0000000 +00:00 | 2013-05-15 00:00:00.0000000 +00:00 | 2011-06-30 00:00:00.0000000 +00:00 | 2013-09-01 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 |  | 2010-11-04 00:00:00.0000000 +00:00 |  |  | 2010-12-04 00:00:00.0000000 +00:00 |  | 2010-12-04 00:00:00.0000000 +00:00 |  |  | 2011-01-31 00:00:00.0000000 +00:00 |  | 2011-01-31 00:00:00.0000000 +00:00 |  | 2011-06-30 00:00:00.0000000 +00:00 |  | 2012-08-09 00:00:00.0000000 +00:00 |  | 2013-05-15 00:00:00.0000000 +00:00 |  |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00
LBC10NUHC | Y | 2009-11-09 00:00:00.0000000 +00:00 | 2013-01-23 00:00:00.0000000 +00:00 | 2021-07-31 00:00:00.0000000 +00:00 | 2023-11-18 00:00:00.0000000 +00:00 | 2026-11-28 00:00:00.0000000 +00:00 | 2009-11-16 00:00:00.0000000 +00:00 | 2010-09-22 00:00:00.0000000 +00:00 | 2011-07-23 00:00:00.0000000 +00:00 | 2011-10-25 00:00:00.0000000 +00:00 | 2012-05-07 00:00:00.0000000 +00:00 | 2009-11-16 00:00:00.0000000 +00:00 | 2013-01-30 00:00:00.0000000 +00:00 | 2017-04-09 00:00:00.0000000 +00:00 | 2018-03-28 00:00:00.0000000 +00:00 | 2019-02-06 00:00:00.0000000 +00:00 | 2009-11-09 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 |  |  |  | 2018-08-23 00:00:00.0000000 +00:00 |  | 2009-11-09 00:00:00.0000000 +00:00 |  | 2012-12-17 00:00:00.0000000 +00:00 |  |  |  | 2015-05-11 00:00:00.0000000 +00:00 | 2015-05-11 00:00:00.0000000 +00:00 |  |  |  | 2016-03-16 00:00:00.0000000 +00:00 | 2016-03-16 00:00:00.0000000 +00:00 |  | 2021-07-31 00:00:00.0000000 +00:00 |  | 2023-11-18 00:00:00.0000000 +00:00 |  | 2026-11-28 00:00:00.0000000 +00:00 |  | 2014-05-07 00:00:00.0000000 +00:00 | 2027-05-28 00:00:00.0000000 +00:00 |  | 2027-05-28 00:00:00.0000000 +00:00
LBC11BBHC | Y | 2010-11-17 00:00:00.0000000 +00:00 | 2012-12-13 00:00:00.0000000 +00:00 | 2014-03-19 00:00:00.0000000 +00:00 | 2015-03-25 00:00:00.0000000 +00:00 | 2017-01-31 00:00:00.0000000 +00:00 | 2010-11-17 00:00:00.0000000 +00:00 | 2011-12-02 00:00:00.0000000 +00:00 | 2012-07-26 00:00:00.0000000 +00:00 | 2013-03-01 00:00:00.0000000 +00:00 | 2013-09-09 00:00:00.0000000 +00:00 | 2010-11-17 00:00:00.0000000 +00:00 | 2012-09-19 00:00:00.0000000 +00:00 | 2013-10-16 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2016-07-31 00:00:00.0000000 +00:00 | 2010-11-17 00:00:00.0000000 +00:00 | 2012-12-13 00:00:00.0000000 +00:00 | 2014-05-09 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 | 2014-01-09 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | 2010-11-17 00:00:00.0000000 +00:00 |  | 2012-12-13 00:00:00.0000000 +00:00 |  |  |  |  | 2013-05-13 00:00:00.0000000 +00:00 |  |  |  |  | 2014-01-13 00:00:00.0000000 +00:00 |  | 2014-05-09 00:00:00.0000000 +00:00 |  | 2015-06-24 00:00:00.0000000 +00:00 |  | 2017-01-27 00:00:00.0000000 +00:00 |  |  | 2017-06-27 00:00:00.0000000 +00:00 |  | 2017-06-27 00:00:00.0000000 +00:00
LBC11BBRF | Y | 2013-01-02 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2013-01-02 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2013-04-08 00:00:00.0000000 +00:00 | 2013-09-08 00:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2013-01-02 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2013-07-11 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2013-01-02 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 |  | 2015-06-24 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2013-07-11 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00
LBC11UPRF | Y | 2010-12-01 00:00:00.0000000 +00:00 | 2010-12-30 00:00:00.0000000 +00:00 | 2011-09-29 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2017-08-21 00:00:00.0000000 +00:00 | 2010-12-01 00:00:00.0000000 +00:00 | 2010-12-30 00:00:00.0000000 +00:00 | 2011-02-14 00:00:00.0000000 +00:00 | 2011-05-16 00:00:00.0000000 +00:00 | 2011-11-08 00:00:00.0000000 +00:00 | 2010-12-01 00:00:00.0000000 +00:00 | 2010-12-30 00:00:00.0000000 +00:00 | 2011-04-17 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2014-10-18 00:00:00.0000000 +00:00 | 2010-12-01 00:00:00.0000000 +00:00 | 2010-12-30 00:00:00.0000000 +00:00 |  | 2014-12-16 00:00:00.0000000 +00:00 | 2016-12-08 00:00:00.0000000 +00:00 | 2011-04-17 00:00:00.0000000 +00:00 | 2016-01-11 00:00:00.0000000 +00:00 | 2010-12-01 00:00:00.0000000 +00:00 |  | 2010-12-30 00:00:00.0000000 +00:00 |  |  |  |  | 2011-03-30 00:00:00.0000000 +00:00 |  |  |  |  | 2011-06-30 00:00:00.0000000 +00:00 |  | 2011-09-29 00:00:00.0000000 +00:00 |  | 2014-12-16 00:00:00.0000000 +00:00 |  | 2016-12-08 00:00:00.0000000 +00:00 |  |  | 2018-02-01 00:00:00.0000000 +00:00 |  | 2017-06-08 00:00:00.0000000 +00:00 |  |  | 2017-10-30 15:02:43.1585687 -04:00
LBC12ARRF | Y | 2012-05-28 00:00:00.0000000 +00:00 | 2013-02-14 00:00:00.0000000 +00:00 | 2013-06-26 00:00:00.0000000 +00:00 | 2014-04-16 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2012-05-28 00:00:00.0000000 +00:00 | 2013-03-25 00:00:00.0000000 +00:00 | 2014-01-20 00:00:00.0000000 +00:00 | 2014-08-22 00:00:00.0000000 +00:00 | 2015-05-03 00:00:00.0000000 +00:00 | 2012-05-28 00:00:00.0000000 +00:00 | 2013-03-25 00:00:00.0000000 +00:00 | 2014-01-20 00:00:00.0000000 +00:00 | 2014-08-22 00:00:00.0000000 +00:00 | 2015-05-03 00:00:00.0000000 +00:00 | 2012-05-28 00:00:00.0000000 +00:00 | 2013-02-14 00:00:00.0000000 +00:00 | 2013-06-26 00:00:00.0000000 +00:00 | 2014-04-16 00:00:00.0000000 +00:00 | 2014-11-20 00:00:00.0000000 +00:00 | 2014-01-20 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00
LBC12EPRF | Y | 2013-01-22 00:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2016-07-24 00:00:00.0000000 +00:00 | 2013-01-22 00:00:00.0000000 +00:00 | 2013-04-18 00:00:00.0000000 +00:00 | 2013-08-12 00:00:00.0000000 +00:00 | 2014-02-04 00:00:00.0000000 +00:00 | 2014-08-04 00:00:00.0000000 +00:00 | 2013-01-22 00:00:00.0000000 +00:00 | 2013-09-15 00:00:00.0000000 +00:00 | 2014-04-12 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2016-03-19 00:00:00.0000000 +00:00 | 2013-01-22 00:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 |  | 2015-08-31 00:00:00.0000000 +00:00 | 2016-01-13 00:00:00.0000000 +00:00 | 2014-01-06 00:00:00.0000000 +00:00 | 2016-07-24 00:00:00.0000000 +00:00
LBC12P2FS | Y | 2012-02-13 00:00:00.0000000 +00:00 | 2015-07-16 00:00:00.0000000 +00:00 | 2016-02-26 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2012-02-13 00:00:00.0000000 +00:00 | 2013-02-05 00:00:00.0000000 +00:00 | 2014-02-04 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2012-02-13 00:00:00.0000000 +00:00 | 2015-05-22 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2012-02-13 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2016-02-26 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 |  | 2015-11-06 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2012-02-13 00:00:00.0000000 +00:00 | 2012-02-13 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 |  | 2015-09-05 00:00:00.0000000 +00:00 | 2015-09-05 00:00:00.0000000 +00:00 | 2015-09-05 00:00:00.0000000 +00:00 | 2015-09-05 00:00:00.0000000 +00:00 |  | 2015-11-15 00:00:00.0000000 +00:00 | 2015-11-15 00:00:00.0000000 +00:00 | 2015-11-15 00:00:00.0000000 +00:00 | 2015-11-15 00:00:00.0000000 +00:00 | 2016-02-26 00:00:00.0000000 +00:00 | 2016-02-26 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-12-21 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 |  | 2019-05-01 00:00:00.0000000 +00:00 |  | 2020-01-01 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00
LBC12STHC | Y | 2012-02-13 00:00:00.0000000 +00:00 | 2014-09-25 00:00:00.0000000 +00:00 | 2019-04-29 00:00:00.0000000 +00:00 | 2020-03-20 00:00:00.0000000 +00:00 | 2021-10-29 00:00:00.0000000 +00:00 | 2012-02-13 00:00:00.0000000 +00:00 | 2012-12-01 00:00:00.0000000 +00:00 | 2013-10-16 00:00:00.0000000 +00:00 | 2014-06-27 00:00:00.0000000 +00:00 | 2015-04-04 00:00:00.0000000 +00:00 | 2012-02-13 00:00:00.0000000 +00:00 | 2014-12-20 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2018-05-02 00:00:00.0000000 +00:00 | 2019-02-07 00:00:00.0000000 +00:00 | 2012-02-13 00:00:00.0000000 +00:00 | 2014-09-25 00:00:00.0000000 +00:00 |  |  |  | 2017-06-18 00:00:00.0000000 +00:00 |  | 2012-02-13 00:00:00.0000000 +00:00 |  | 2014-09-25 00:00:00.0000000 +00:00 |  |  | 2015-02-10 00:00:00.0000000 +00:00 |  | 2015-02-10 00:00:00.0000000 +00:00 |  |  | 2015-10-27 00:00:00.0000000 +00:00 |  | 2015-10-27 00:00:00.0000000 +00:00 |  | 2019-04-29 00:00:00.0000000 +00:00 |  | 2020-03-20 00:00:00.0000000 +00:00 |  | 2021-10-29 00:00:00.0000000 +00:00 |  | 2017-04-03 00:00:00.0000000 +00:00 | 2022-10-29 00:00:00.0000000 +00:00 |  | 2022-10-29 00:00:00.0000000 +00:00
LBC12WIRF | Y | 2014-04-18 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2019-08-02 00:00:00.0000000 +00:00 | 2020-08-07 00:00:00.0000000 +00:00 | 2021-12-10 00:00:00.0000000 +00:00 | 2014-04-18 00:00:00.0000000 +00:00 | 2014-12-18 00:00:00.0000000 +00:00 | 2015-07-19 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 | 2016-12-14 00:00:00.0000000 +00:00 | 2014-04-18 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2017-11-14 00:00:00.0000000 +00:00 | 2019-02-07 00:00:00.0000000 +00:00 | 2014-04-18 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 |  |  |  | 2019-08-02 00:00:00.0000000 +00:00 |  | 2014-04-18 00:00:00.0000000 +00:00 |  | 2014-12-18 00:00:00.0000000 +00:00 |  | 2015-03-16 00:00:00.0000000 +00:00 | 2018-02-01 00:00:00.0000000 +00:00 |  | 2018-02-01 00:00:00.0000000 +00:00 |  | 2015-05-20 00:00:00.0000000 +00:00 | 2018-08-02 00:00:00.0000000 +00:00 |  | 2018-08-02 00:00:00.0000000 +00:00 |  | 2019-08-02 00:00:00.0000000 +00:00 |  | 2020-08-07 00:00:00.0000000 +00:00 |  | 2021-12-10 00:00:00.0000000 +00:00 |  | 2018-12-14 00:00:00.0000000 +00:00 | 2022-12-02 00:00:00.0000000 +00:00 |  | 2022-12-02 00:00:00.0000000 +00:00
LBC13BPRF | Y | 2013-04-25 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2019-07-26 00:00:00.0000000 +00:00 | 2020-03-20 00:00:00.0000000 +00:00 | 2022-03-18 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2014-01-26 00:00:00.0000000 +00:00 | 2015-04-23 00:00:00.0000000 +00:00 | 2015-11-28 00:00:00.0000000 +00:00 | 2017-05-22 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2016-08-02 00:00:00.0000000 +00:00 | 2017-04-12 00:00:00.0000000 +00:00 | 2018-06-13 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 |  |  |  | 2020-09-25 00:00:00.0000000 +00:00 |  | 2013-04-25 00:00:00.0000000 +00:00 |  | 2014-09-10 00:00:00.0000000 +00:00 |  |  | 2018-06-08 00:00:00.0000000 +00:00 |  | 2018-02-02 00:00:00.0000000 +00:00 |  |  | 2018-12-14 00:00:00.0000000 +00:00 |  | 2019-01-25 00:00:00.0000000 +00:00 |  | 2019-08-16 00:00:00.0000000 +00:00 |  | 2020-03-20 00:00:00.0000000 +00:00 |  | 2022-03-18 00:00:00.0000000 +00:00 |  | 2019-05-22 00:00:00.0000000 +00:00 | 2022-09-16 00:00:00.0000000 +00:00 |  | 2022-09-16 00:00:00.0000000 +00:00 |  |  | 2017-10-30 15:53:45.5886658 -04:00
LBC13NLBR | Y | 2012-10-26 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2021-07-01 00:00:00.0000000 +00:00 | 2025-04-01 00:00:00.0000000 +00:00 | 2029-06-24 00:00:00.0000000 +00:00 | 2012-10-26 00:00:00.0000000 +00:00 | 2013-10-06 00:00:00.0000000 +00:00 | 2014-10-07 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2016-08-07 00:00:00.0000000 +00:00 | 2012-10-26 00:00:00.0000000 +00:00 | 2014-09-28 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2019-06-17 00:00:00.0000000 +00:00 | 2012-10-26 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 |  |  |  | 2021-07-01 00:00:00.0000000 +00:00 | 2029-06-24 00:00:00.0000000 +00:00 | 2012-10-26 00:00:00.0000000 +00:00 |  | 2014-11-17 00:00:00.0000000 +00:00 |  |  |  | 2015-09-10 00:00:00.0000000 +00:00 | 2015-09-10 00:00:00.0000000 +00:00 |  |  |  | 2016-04-06 00:00:00.0000000 +00:00 | 2016-04-06 00:00:00.0000000 +00:00 |  | 2021-07-01 00:00:00.0000000 +00:00 |  | 2025-04-01 00:00:00.0000000 +00:00 |  | 2029-06-24 00:00:00.0000000 +00:00 |  |  | 2029-12-24 00:00:00.0000000 +00:00 |  | 2029-12-24 00:00:00.0000000 +00:00 |  |  | 2017-11-16 14:44:50.5697126 -05:00
LBC14ARHC | Y | 2013-07-15 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2019-03-01 00:00:00.0000000 +00:00 | 2019-11-29 17:00:00.0000000 +00:00 | 2020-11-29 17:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-08-24 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2017-01-12 00:00:00.0000000 +00:00 | 2018-03-21 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2017-04-08 00:00:00.0000000 +00:00 | 2018-08-16 00:00:00.0000000 +00:00 | 2020-03-21 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 |  |  |  | 2017-03-24 00:00:00.0000000 +00:00 |  | 2013-07-15 00:00:00.0000000 +00:00 |  | 2015-06-30 00:00:00.0000000 +00:00 |  |  |  | 2016-09-07 00:00:00.0000000 +00:00 | 2016-09-07 00:00:00.0000000 +00:00 |  |  | 2018-07-01 00:00:00.0000000 +00:00 |  | 2018-07-01 00:00:00.0000000 +00:00 |  | 2019-03-01 00:00:00.0000000 +00:00 |  | 2019-11-29 17:00:00.0000000 +00:00 |  | 2020-11-29 17:00:00.0000000 +00:00 |  | 2020-03-20 00:00:00.0000000 +00:00 | 2021-06-01 00:00:00.0000000 +00:00 |  | 2021-06-01 00:00:00.0000000 +00:00 |  |  | 2017-10-30 12:10:01.6124880 -04:00
LBC14BVHC | Y | 2013-10-07 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2018-04-03 00:00:00.0000000 +00:00 | 2018-10-03 00:00:00.0000000 +00:00 | 2020-04-03 00:00:00.0000000 +00:00 | 2013-10-07 00:00:00.0000000 +00:00 | 2014-05-26 00:00:00.0000000 +00:00 | 2014-11-05 00:00:00.0000000 +00:00 | 2015-04-25 00:00:00.0000000 +00:00 | 2015-08-30 00:00:00.0000000 +00:00 | 2013-10-07 00:00:00.0000000 +00:00 | 2014-12-05 00:00:00.0000000 +00:00 | 2017-09-09 00:00:00.0000000 +00:00 | 2018-10-27 00:00:00.0000000 +00:00 | 2019-03-03 00:00:00.0000000 +00:00 | 2013-10-07 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 |  |  |  | 2018-03-14 00:00:00.0000000 +00:00 |  | 2013-10-07 00:00:00.0000000 +00:00 |  | 2015-01-29 00:00:00.0000000 +00:00 |  |  |  | 2015-04-24 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 |  |  |  | 2016-07-15 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 |  | 2018-04-03 00:00:00.0000000 +00:00 |  | 2018-10-03 00:00:00.0000000 +00:00 |  | 2020-04-03 00:00:00.0000000 +00:00 |  | 2017-08-29 00:00:00.0000000 +00:00 | 2020-10-03 00:00:00.0000000 +00:00 |  | 2020-10-03 00:00:00.0000000 +00:00
LBC14CNHC | Y | 2014-09-23 00:00:00.0000000 +00:00 | 2015-10-14 00:00:00.0000000 +00:00 | 2018-01-19 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | 2019-12-13 00:00:00.0000000 +00:00 | 2014-09-23 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2015-12-10 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2017-06-15 00:00:00.0000000 +00:00 | 2014-09-23 00:00:00.0000000 +00:00 | 2015-06-28 00:00:00.0000000 +00:00 | 2017-08-10 00:00:00.0000000 +00:00 | 2018-03-28 00:00:00.0000000 +00:00 | 2018-11-24 00:00:00.0000000 +00:00 | 2014-09-23 00:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 |  |  |  | 2018-05-31 00:00:00.0000000 +00:00 | 2019-09-24 00:00:00.0000000 +00:00 | 2014-09-23 00:00:00.0000000 +00:00 |  | 2015-09-24 00:00:00.0000000 +00:00 |  |  |  | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 |  |  |  | 2017-01-27 00:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 |  | 2018-01-19 00:00:00.0000000 +00:00 |  | 2018-07-20 00:00:00.0000000 +00:00 |  | 2019-12-13 00:00:00.0000000 +00:00 |  | 2019-06-15 00:00:00.0000000 +00:00 | 2020-05-22 00:00:00.0000000 +00:00 |  | 2020-05-22 00:00:00.0000000 +00:00 |  |  | 2017-08-31 09:18:56.5593952 -04:00
LBC14CYHC | Y | 2013-08-29 00:00:00.0000000 +00:00 | 2015-03-09 00:00:00.0000000 +00:00 | 2018-09-28 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 | 2020-09-30 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2016-05-20 00:00:00.0000000 +00:00 | 2017-05-19 00:00:00.0000000 +00:00 | 2018-11-19 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2015-03-31 00:00:00.0000000 +00:00 | 2016-12-13 00:00:00.0000000 +00:00 | 2017-10-06 00:00:00.0000000 +00:00 | 2018-02-18 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 |  |  |  | 2018-09-28 00:00:00.0000000 +00:00 |  | 2013-08-29 00:00:00.0000000 +00:00 |  | 2015-06-02 00:00:00.0000000 +00:00 |  | 2014-11-18 00:00:00.0000000 +00:00 |  | 2015-12-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 |  | 2015-05-18 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2018-09-28 00:00:00.0000000 +00:00 |  | 2019-09-30 00:00:00.0000000 +00:00 |  | 2020-09-30 00:00:00.0000000 +00:00 |  | 2019-11-19 00:00:00.0000000 +00:00 | 2021-09-30 00:00:00.0000000 +00:00 |  | 2021-09-30 00:00:00.0000000 +00:00
LBC14LDRF | Y | 2013-08-29 00:00:00.0000000 +00:00 | 2015-03-31 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-05-18 00:00:00.0000000 +00:00 | 2019-05-31 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2014-07-12 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2015-10-01 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2015-03-04 00:00:00.0000000 +00:00 | 2016-08-07 00:00:00.0000000 +00:00 | 2017-09-16 00:00:00.0000000 +00:00 | 2018-01-29 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 |  |  |  | 2018-05-29 00:00:00.0000000 +00:00 |  | 2013-08-29 00:00:00.0000000 +00:00 |  | 2015-03-17 00:00:00.0000000 +00:00 |  |  | 2016-01-01 00:00:00.0000000 +00:00 | 2016-01-01 00:00:00.0000000 +00:00 | 2016-01-01 00:00:00.0000000 +00:00 |  |  | 2016-06-22 00:00:00.0000000 +00:00 | 2016-06-22 00:00:00.0000000 +00:00 | 2016-06-22 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2018-05-18 00:00:00.0000000 +00:00 |  | 2019-05-31 00:00:00.0000000 +00:00 |  | 2017-09-30 00:00:00.0000000 +00:00 | 2020-05-31 00:00:00.0000000 +00:00 |  | 2020-05-31 00:00:00.0000000 +00:00 |  |  | 2017-11-30 08:52:53.3914591 -05:00
LBC14MDBR | Y | 2013-10-11 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2015-11-18 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2015-04-23 00:00:00.0000000 +00:00 | 2015-10-09 00:00:00.0000000 +00:00 | 2016-02-21 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2014-07-14 00:00:00.0000000 +00:00 | 2015-02-20 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 |  | 2015-06-25 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-02-20 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | [6 empty] | 2014-05-08 00:00:00.0000000 +00:00 |  |  |  | 2014-07-09 00:00:00.0000000 +00:00
LBC14NLHC | Y | 2013-08-29 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2021-07-01 00:00:00.0000000 +00:00 | 2025-04-01 00:00:00.0000000 +00:00 | 2029-06-24 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2015-07-26 00:00:00.0000000 +00:00 | 2016-05-29 00:00:00.0000000 +00:00 | 2017-03-21 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2015-07-16 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | 2018-05-05 00:00:00.0000000 +00:00 | 2019-02-25 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 |  |  |  | 2017-06-14 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 |  | 2015-06-29 00:00:00.0000000 +00:00 |  |  |  | 2015-12-04 00:00:00.0000000 +00:00 | 2015-12-04 00:00:00.0000000 +00:00 |  |  |  | 2016-07-14 00:00:00.0000000 +00:00 | 2016-07-14 00:00:00.0000000 +00:00 |  | 2021-07-01 00:00:00.0000000 +00:00 |  | 2025-04-01 00:00:00.0000000 +00:00 |  | 2029-06-24 00:00:00.0000000 +00:00 |  |  | 2029-12-24 00:00:00.0000000 +00:00 |  | 2029-12-24 00:00:00.0000000 +00:00 |  |  | 2017-11-16 08:08:41.3147322 -05:00
LBC15BWHC | Y | 2014-10-02 00:00:00.0000000 +00:00 | 2016-01-31 00:00:00.0000000 +00:00 | 2018-09-28 00:00:00.0000000 +00:00 | 2019-05-31 00:00:00.0000000 +00:00 | 2020-09-30 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2015-12-25 00:00:00.0000000 +00:00 | 2016-05-24 00:00:00.0000000 +00:00 | 2016-10-10 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2017-05-30 00:00:00.0000000 +00:00 | 2017-10-28 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2016-01-31 00:00:00.0000000 +00:00 | [5 empty] | 2014-10-02 00:00:00.0000000 +00:00 |  | 2016-01-31 00:00:00.0000000 +00:00 |  | 2015-07-20 00:00:00.0000000 +00:00 | 2016-06-02 00:00:00.0000000 +00:00 | 2016-06-02 00:00:00.0000000 +00:00 | 2016-06-02 00:00:00.0000000 +00:00 |  | 2015-09-21 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 |  | 2018-02-28 00:00:00.0000000 +00:00 |  | 2018-09-28 00:00:00.0000000 +00:00 |  | 2019-05-31 00:00:00.0000000 +00:00 |  | 2020-09-30 00:00:00.0000000 +00:00 |  |  | 2021-09-30 00:00:00.0000000 +00:00 |  | 2021-09-30 00:00:00.0000000 +00:00 |  |  | 2017-09-08 11:08:20.8717891 -04:00
LBC15CHHC | Y | 2026-08-18 00:00:00.0000000 +00:00 | 2027-01-13 00:00:00.0000000 +00:00 | 2027-09-29 00:00:00.0000000 +00:00 | 2017-03-14 00:00:00.0000000 +00:00 | 2017-11-29 00:00:00.0000000 +00:00 | 2015-03-20 00:00:00.0000000 +00:00 | 2015-09-12 00:00:00.0000000 +00:00 | 2016-03-14 00:00:00.0000000 +00:00 | 2016-06-16 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2026-08-18 00:00:00.0000000 +00:00 | 2027-01-13 00:00:00.0000000 +00:00 | 2027-09-29 00:00:00.0000000 +00:00 | 2028-06-17 00:00:00.0000000 +00:00 | 2028-12-01 00:00:00.0000000 +00:00 | 2015-03-20 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 |  |  |  | 2027-12-13 00:00:00.0000000 +00:00 | [21 empty] | 2018-09-15 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00
LBC15FBHC | Y | 2015-01-13 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2018-09-03 00:00:00.0000000 +00:00 | 2019-04-24 00:00:00.0000000 +00:00 | 2020-04-23 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-04-29 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2016-03-05 00:00:00.0000000 +00:00 | 2016-08-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 |  |  |  | 2018-09-03 00:00:00.0000000 +00:00 | [21 empty] | 2018-08-13 00:00:00.0000000 +00:00 | 2023-04-23 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-24 16:08:25.7314567 -05:00
LBC15FLRF | Y | 2014-12-03 00:00:00.0000000 +00:00 | 2015-10-28 00:00:00.0000000 +00:00 | 2019-02-22 00:00:00.0000000 +00:00 | 2020-02-22 00:00:00.0000000 +00:00 | 2021-06-23 00:00:00.0000000 +00:00 | 2014-12-03 00:00:00.0000000 +00:00 | 2015-07-11 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2014-12-03 00:00:00.0000000 +00:00 | 2015-08-03 00:00:00.0000000 +00:00 | 2017-01-12 00:00:00.0000000 +00:00 | 2017-06-08 00:00:00.0000000 +00:00 | 2018-01-04 00:00:00.0000000 +00:00 | 2014-12-03 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 |  |  |  | 2019-02-22 00:00:00.0000000 +00:00 |  | 2014-12-03 00:00:00.0000000 +00:00 |  | 2015-10-20 00:00:00.0000000 +00:00 |  | 2015-08-31 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 |  | 2015-10-15 00:00:00.0000000 +00:00 | 2018-02-23 00:00:00.0000000 +00:00 |  | 2018-02-23 00:00:00.0000000 +00:00 |  | 2019-02-22 00:00:00.0000000 +00:00 |  | 2020-02-22 00:00:00.0000000 +00:00 |  | 2021-06-23 00:00:00.0000000 +00:00 |  | 2018-10-03 00:00:00.0000000 +00:00 | 2022-06-22 00:00:00.0000000 +00:00 |  | 2022-06-22 00:00:00.0000000 +00:00 |  |  | 2017-11-30 08:51:39.3817435 -05:00
LBC15GSRF | Y | 2014-12-30 00:00:00.0000000 +00:00 | 2015-03-24 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2016-05-24 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-03-24 00:00:00.0000000 +00:00 | 2015-10-10 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-03-24 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2017-01-25 17:00:00.0000000 +00:00 | 2017-10-25 00:00:00.0000000 +00:00 | 2015-10-10 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-03-24 00:00:00.0000000 +00:00 | 2015-03-24 00:00:00.0000000 +00:00 |  | 2015-05-29 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 |  | 2015-08-27 00:00:00.0000000 +00:00 | 2015-08-27 00:00:00.0000000 +00:00 | 2015-08-27 00:00:00.0000000 +00:00 | 2015-08-27 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 |  | 2017-01-25 17:00:00.0000000 +00:00 |  | 2018-02-15 00:00:00.0000000 +00:00 | 2018-05-24 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 |  |  | 2018-06-15 00:00:00.0000000 +00:00 |  | 2017-10-30 15:05:19.2126836 -04:00
LBC15MPHC | Y | 2014-10-16 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2019-04-15 00:00:00.0000000 +00:00 | 2020-11-18 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2016-03-15 00:00:00.0000000 +00:00 | 2017-03-26 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2015-08-10 00:00:00.0000000 +00:00 | 2017-05-26 00:00:00.0000000 +00:00 | 2017-10-24 00:00:00.0000000 +00:00 | 2018-11-04 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 |  |  |  | 2018-09-30 00:00:00.0000000 +00:00 |  | 2014-10-16 00:00:00.0000000 +00:00 |  | 2015-06-29 00:00:00.0000000 +00:00 |  |  | 2016-03-11 00:00:00.0000000 +00:00 | 2016-03-11 00:00:00.0000000 +00:00 | 2016-03-11 00:00:00.0000000 +00:00 |  |  | 2017-10-13 00:00:00.0000000 +00:00 |  | 2017-10-13 00:00:00.0000000 +00:00 |  | 2018-08-27 00:00:00.0000000 +00:00 |  | 2019-04-15 00:00:00.0000000 +00:00 |  | 2020-11-18 00:00:00.0000000 +00:00 |  | 2019-03-26 00:00:00.0000000 +00:00 | 2021-02-12 00:00:00.0000000 +00:00 |  | 2021-02-12 00:00:00.0000000 +00:00 |  |  | 2017-08-31 09:25:20.0500720 -04:00
LBC16MBHC | Y | 2015-07-23 00:00:00.0000000 +00:00 | 2015-09-01 00:00:00.0000000 +00:00 | 2015-11-28 00:00:00.0000000 +00:00 | 2016-04-09 00:00:00.0000000 +00:00 | 2017-12-17 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2015-09-01 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2016-02-12 00:00:00.0000000 +00:00 | 2016-07-04 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2015-09-01 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2017-05-07 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2015-09-01 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-09-07 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2017-07-24 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-05 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 |  |  |  | 2015-10-05 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | [9 empty] | 2018-09-07 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-13 08:59:56.7536889 -04:00
LBC16MD2F | Y | 2015-10-13 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2019-09-27 00:00:00.0000000 +00:00 | 2020-08-27 00:00:00.0000000 +00:00 | 2022-08-29 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2016-02-22 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 | 2017-08-23 00:00:00.0000000 +00:00 | 2018-08-21 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2016-04-07 00:00:00.0000000 +00:00 | 2017-07-21 00:00:00.0000000 +00:00 | 2018-06-12 00:00:00.0000000 +00:00 | 2019-06-10 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 |  |  |  | 2020-04-28 00:00:00.0000000 +00:00 |  | 2015-10-13 00:00:00.0000000 +00:00 |  | 2016-07-15 00:00:00.0000000 +00:00 |  |  | 2018-03-16 00:00:00.0000000 +00:00 |  | 2018-03-16 00:00:00.0000000 +00:00 |  |  | 2018-12-14 00:00:00.0000000 +00:00 |  | 2018-12-14 00:00:00.0000000 +00:00 |  | 2019-09-27 00:00:00.0000000 +00:00 |  | 2020-08-27 00:00:00.0000000 +00:00 |  | 2022-08-29 00:00:00.0000000 +00:00 |  | 2020-08-20 00:00:00.0000000 +00:00 | 2022-12-23 00:00:00.0000000 +00:00 |  | 2022-12-23 00:00:00.0000000 +00:00 |  |  | 2017-11-30 08:53:18.0383824 -05:00
LBC16MPHC | Y | 2015-08-20 00:00:00.0000000 +00:00 | 2016-01-13 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2019-04-15 00:00:00.0000000 +00:00 | 2020-11-18 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-05-15 00:00:00.0000000 +00:00 | 2016-10-23 00:00:00.0000000 +00:00 | 2017-04-29 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2017-04-27 00:00:00.0000000 +00:00 | 2018-07-22 00:00:00.0000000 +00:00 | 2019-07-10 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2016-04-12 00:00:00.0000000 +00:00 |  |  |  | 2018-10-22 00:00:00.0000000 +00:00 |  | 2015-08-20 00:00:00.0000000 +00:00 |  | 2016-04-12 00:00:00.0000000 +00:00 |  |  |  | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 |  |  | 2017-10-13 00:00:00.0000000 +00:00 |  | 2017-10-13 00:00:00.0000000 +00:00 |  | 2018-08-27 00:00:00.0000000 +00:00 |  | 2019-04-15 00:00:00.0000000 +00:00 |  | 2020-11-18 00:00:00.0000000 +00:00 |  | 2019-04-29 00:00:00.0000000 +00:00 | 2021-02-12 00:00:00.0000000 +00:00 |  | 2021-02-12 00:00:00.0000000 +00:00
LBC16PSGD | Y | 2015-08-24 00:00:00.0000000 +00:00 | 2015-10-06 00:00:00.0000000 +00:00 | 2016-01-26 00:00:00.0000000 +00:00 | 2016-06-18 00:00:00.0000000 +00:00 | 2016-12-27 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2015-10-06 00:00:00.0000000 +00:00 | 2016-02-04 00:00:00.0000000 +00:00 | 2016-04-21 00:00:00.0000000 +00:00 | 2016-10-30 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2015-10-06 00:00:00.0000000 +00:00 | 2016-02-04 00:00:00.0000000 +00:00 | 2016-04-21 00:00:00.0000000 +00:00 | 2016-10-30 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2015-10-06 00:00:00.0000000 +00:00 |  | 2016-06-30 00:00:00.0000000 +00:00 | 2016-12-02 00:00:00.0000000 +00:00 | 2016-02-04 00:00:00.0000000 +00:00 | 2016-10-30 00:00:00.0000000 +00:00
LBC17MPGD | Y | 2017-01-13 17:00:00.0000000 +00:00 | 2017-07-05 17:00:00.0000000 +00:00 | 2018-09-15 17:00:00.0000000 +00:00 | 2019-04-15 17:00:00.0000000 +00:00 | 2020-04-15 17:00:00.0000000 +00:00 | [10 empty] | 2017-01-13 17:00:00.0000000 +00:00 | 2017-07-05 17:00:00.0000000 +00:00 |  |  |  | 2018-09-15 00:00:00.0000000 +00:00 | 2020-04-15 00:00:00.0000000 +00:00 | 2017-01-13 17:00:00.0000000 +00:00 |  | 2017-07-05 17:00:00.0000000 +00:00 |  |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00 |  |  | 2018-04-13 00:00:00.0000000 +00:00 |  | 2018-04-13 00:00:00.0000000 +00:00 |  | 2018-09-15 17:00:00.0000000 +00:00 |  | 2019-04-15 17:00:00.0000000 +00:00 |  | 2020-04-15 17:00:00.0000000 +00:00 |  |  | 2020-12-11 00:00:00.0000000 +00:00 |  | 2020-12-11 00:00:00.0000000 +00:00
LBC17MRAD | Y | 2017-01-17 00:00:00.0000000 +00:00 | 2017-07-11 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2018-12-31 00:00:00.0000000 +00:00 | 2019-07-31 00:00:00.0000000 +00:00 | 2017-01-10 00:00:00.0000000 +00:00 | 2017-01-10 00:00:00.0000000 +00:00 | 2018-08-30 00:00:00.0000000 +00:00 | 2019-01-10 00:00:00.0000000 +00:00 | 2019-01-10 00:00:00.0000000 +00:00 | [5 empty] | 2017-01-17 00:00:00.0000000 +00:00 | 2017-07-11 00:00:00.0000000 +00:00 |  |  |  | 2018-05-31 00:00:00.0000000 +00:00 |  | 2017-01-17 00:00:00.0000000 +00:00 |  | 2017-07-11 00:00:00.0000000 +00:00 |  | 2017-09-05 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 | 2017-09-01 00:00:00.0000000 +00:00 |  | 2018-02-15 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 |  | 2017-11-30 00:00:00.0000000 +00:00 |  | 2018-05-31 00:00:00.0000000 +00:00 |  | 2018-12-31 00:00:00.0000000 +00:00 |  | 2019-07-31 00:00:00.0000000 +00:00 |  | 2020-01-20 00:00:00.0000000 +00:00 | 2020-01-31 00:00:00.0000000 +00:00 |  | 2020-01-31 00:00:00.0000000 +00:00 |  |  | 2017-12-01 10:42:28.0793499 -05:00
LBC17PCFS | Y | 2017-02-14 00:00:00.0000000 +00:00 | 2018-03-21 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2019-12-30 00:00:00.0000000 +00:00 | 2020-01-30 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2018-03-21 00:00:00.0000000 +00:00 | 2019-02-28 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 | 2020-03-26 00:00:00.0000000 +00:00 | [5 empty] | 2017-02-14 00:00:00.0000000 +00:00 | [6 empty] | 2017-02-14 00:00:00.0000000 +00:00 |  | 2018-03-21 00:00:00.0000000 +00:00 |  | 2018-07-23 00:00:00.0000000 +00:00 | 2018-07-23 00:00:00.0000000 +00:00 |  | 2018-07-23 00:00:00.0000000 +00:00 |  | 2018-07-23 00:00:00.0000000 +00:00 | 2018-07-23 00:00:00.0000000 +00:00 |  | 2018-07-23 00:00:00.0000000 +00:00 |  | 2018-10-30 00:00:00.0000000 +00:00 |  | 2019-12-30 00:00:00.0000000 +00:00 |  | 2020-01-30 00:00:00.0000000 +00:00 |  | 2021-03-26 00:00:00.0000000 +00:00 | 2021-01-30 00:00:00.0000000 +00:00 |  | 2021-01-30 00:00:00.0000000 +00:00
LBCA07FBH3 | Y | 2007-07-31 00:00:00.0000000 +00:00 | 2008-09-22 00:00:00.0000000 +00:00 | 2009-04-14 00:00:00.0000000 +00:00 | 2011-10-11 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2007-07-31 00:00:00.0000000 +00:00 | 2008-09-22 00:00:00.0000000 +00:00 | 2009-04-14 00:00:00.0000000 +00:00 | 2011-10-11 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00 | 2007-07-31 00:00:00.0000000 +00:00 | 2008-09-22 00:00:00.0000000 +00:00 | 2009-04-14 00:00:00.0000000 +00:00 | 2010-11-06 00:00:00.0000000 +00:00 | 2016-01-31 00:00:00.0000000 +00:00 | 2007-07-31 00:00:00.0000000 +00:00 | 2008-09-22 00:00:00.0000000 +00:00 |  | 2011-10-11 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2009-04-14 00:00:00.0000000 +00:00 | 2017-01-04 00:00:00.0000000 +00:00
LBK13EFBR | Y | 2013-07-15 00:00:00.0000000 +00:00 | 2014-09-14 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2019-02-11 00:00:00.0000000 +00:00 | 2022-02-12 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2015-09-19 00:00:00.0000000 +00:00 | 2017-09-10 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-09-14 00:00:00.0000000 +00:00 | 2016-10-06 00:00:00.0000000 +00:00 | 2017-11-21 00:00:00.0000000 +00:00 | 2019-11-13 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 |  |  |  | 2018-06-30 00:00:00.0000000 +00:00 | 2022-02-12 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 |  | 2014-09-15 00:00:00.0000000 +00:00 |  |  |  | 2015-01-23 00:00:00.0000000 +00:00 | 2015-01-23 00:00:00.0000000 +00:00 |  |  |  | 2015-11-02 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2018-09-14 00:00:00.0000000 +00:00 |  | 2020-12-11 00:00:00.0000000 +00:00 |  | 2019-09-10 00:00:00.0000000 +00:00 | 2023-02-10 00:00:00.0000000 +00:00 |  | 2021-09-10 00:00:00.0000000 +00:00 |  |  | 2017-10-30 15:55:29.8807213 -04:00
LBK14DRRF | Y | 2013-08-29 00:00:00.0000000 +00:00 | 2014-04-30 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2016-06-21 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2014-03-26 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2015-03-18 00:00:00.0000000 +00:00 | 2015-08-10 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2014-04-30 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2015-07-14 00:00:00.0000000 +00:00 | 2015-11-22 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2014-04-08 00:00:00.0000000 +00:00 | 2014-08-22 00:00:00.0000000 +00:00 | 2016-06-21 00:00:00.0000000 +00:00 | 2016-12-05 17:00:00.0000000 +00:00 | 2014-09-20 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 |  | 2014-04-08 00:00:00.0000000 +00:00 |  |  | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 |  |  | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 |  | 2014-08-22 00:00:00.0000000 +00:00 |  | 2016-06-21 00:00:00.0000000 +00:00 | 2016-06-21 00:00:00.0000000 +00:00 | 2016-12-05 00:00:00.0000000 +00:00 | 2016-12-05 00:00:00.0000000 +00:00 | 2017-08-09 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 |  | 2017-12-19 00:00:00.0000000 +00:00 | 2017-12-19 00:00:00.0000000 +00:00
LBK15BDHC | Y | 2015-01-02 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 | 2019-02-22 00:00:00.0000000 +00:00 | 2020-02-28 00:00:00.0000000 +00:00 | 2021-06-28 00:00:00.0000000 +00:00 | 2015-01-02 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2015-09-02 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2016-07-27 00:00:00.0000000 +00:00 | 2015-01-02 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2017-10-25 00:00:00.0000000 +00:00 | 2018-11-26 00:00:00.0000000 +00:00 | 2019-12-07 00:00:00.0000000 +00:00 | 2015-01-02 00:00:00.0000000 +00:00 | 2015-12-14 00:00:00.0000000 +00:00 |  |  |  | 2019-02-22 00:00:00.0000000 +00:00 |  | 2015-01-02 00:00:00.0000000 +00:00 |  | 2015-12-14 00:00:00.0000000 +00:00 |  | 2015-06-12 00:00:00.0000000 +00:00 | 2016-06-16 00:00:00.0000000 +00:00 | 2016-06-16 00:00:00.0000000 +00:00 | 2016-06-16 00:00:00.0000000 +00:00 |  | 2015-08-14 00:00:00.0000000 +00:00 | 2018-03-23 00:00:00.0000000 +00:00 |  | 2018-02-23 00:00:00.0000000 +00:00 |  | 2019-02-22 00:00:00.0000000 +00:00 |  | 2020-02-28 00:00:00.0000000 +00:00 |  | 2021-06-28 00:00:00.0000000 +00:00 |  | 2018-07-27 00:00:00.0000000 +00:00 | 2022-06-28 00:00:00.0000000 +00:00 |  | 2022-06-28 00:00:00.0000000 +00:00 |  |  | 2017-12-15 08:56:35.5393048 -05:00
LBK15BRRF | Y | 2014-12-30 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2015-05-03 00:00:00.0000000 +00:00 | 2017-05-10 00:00:00.0000000 +00:00 | 2018-08-30 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2015-12-22 00:00:00.0000000 +00:00 | 2016-06-10 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2017-09-07 00:00:00.0000000 +00:00 | 2014-12-30 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 |  | 2017-03-24 17:00:00.0000000 +00:00 |  | 2015-01-13 00:00:00.0000000 +00:00 | 2018-08-18 00:00:00.0000000 +00:00 | [20 empty] | 2018-06-10 00:00:00.0000000 +00:00 | 2020-08-29 00:00:00.0000000 +00:00
LBK15WTHC | Y | 2014-11-10 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2018-07-25 00:00:00.0000000 +00:00 | 2019-04-30 00:00:00.0000000 +00:00 | 2020-10-30 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2016-02-10 00:00:00.0000000 +00:00 | 2016-07-10 00:00:00.0000000 +00:00 | 2017-05-12 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2017-05-16 00:00:00.0000000 +00:00 | 2018-04-16 00:00:00.0000000 +00:00 | 2019-02-16 00:00:00.0000000 +00:00 | 2014-11-10 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 |  |  |  | 2018-07-25 00:00:00.0000000 +00:00 |  | 2014-11-10 00:00:00.0000000 +00:00 |  | 2015-12-15 00:00:00.0000000 +00:00 |  |  | 2016-03-22 00:00:00.0000000 +00:00 | 2016-03-22 00:00:00.0000000 +00:00 | 2016-03-22 00:00:00.0000000 +00:00 |  |  | 2018-01-31 00:00:00.0000000 +00:00 |  | 2018-01-31 00:00:00.0000000 +00:00 |  | 2018-07-25 00:00:00.0000000 +00:00 |  | 2019-04-30 00:00:00.0000000 +00:00 |  | 2020-10-30 00:00:00.0000000 +00:00 |  | 2019-05-12 00:00:00.0000000 +00:00 | 2021-12-30 00:00:00.0000000 +00:00 |  | 2021-12-30 00:00:00.0000000 +00:00 |  |  | 2017-12-15 09:43:54.7825146 -05:00
LBK16CIBR | Y | 2015-10-15 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2020-11-20 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2017-08-10 00:00:00.0000000 +00:00 | 2018-08-12 00:00:00.0000000 +00:00 | 2019-09-06 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2018-01-16 00:00:00.0000000 +00:00 | 2017-12-23 00:00:00.0000000 +00:00 | 2018-12-26 00:00:00.0000000 +00:00 | 2015-10-13 18:00:00.0000000 +00:00 | 2016-06-13 18:00:00.0000000 +00:00 |  |  |  | 2018-12-14 00:00:00.0000000 +00:00 |  | 2015-10-13 18:00:00.0000000 +00:00 |  | 2016-06-13 18:00:00.0000000 +00:00 |  |  |  | 2017-01-13 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 |  |  | 2017-10-20 00:00:00.0000000 +00:00 |  | 2017-10-20 00:00:00.0000000 +00:00 |  | 2018-09-14 00:00:00.0000000 +00:00 |  | 2019-05-17 00:00:00.0000000 +00:00 |  | 2020-11-20 00:00:00.0000000 +00:00 |  | 2021-09-03 00:00:00.0000000 +00:00 | 2021-06-04 00:00:00.0000000 +00:00 |  | 2021-06-04 00:00:00.0000000 +00:00 |  |  | 2017-10-30 15:54:46.9568306 -04:00
LBKA05RUG | Y | 2004-10-14 00:00:00.0000000 +00:00 | 2005-07-15 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2004-10-14 00:00:00.0000000 +00:00 | 2005-03-10 00:00:00.0000000 +00:00 | 2005-11-15 00:00:00.0000000 +00:00 | 2006-07-15 00:00:00.0000000 +00:00 | 2007-03-14 00:00:00.0000000 +00:00 | 2004-10-14 00:00:00.0000000 +00:00 | 2005-03-10 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2021-04-16 00:00:00.0000000 +00:00 | 2022-06-12 00:00:00.0000000 +00:00 | 2004-10-14 00:00:00.0000000 +00:00 | 2005-07-15 00:00:00.0000000 +00:00 |  | 2016-08-23 00:00:00.0000000 +00:00 |  | 2015-11-23 00:00:00.0000000 +00:00 | 2019-04-15 00:00:00.0000000 +00:00 | 2004-10-04 00:00:00.0000000 +00:00 | 2004-10-14 00:00:00.0000000 +00:00 | 2005-07-15 00:00:00.0000000 +00:00 | 2005-07-15 00:00:00.0000000 +00:00 | 2005-06-10 00:00:00.0000000 +00:00 | 2009-09-01 00:00:00.0000000 +00:00 |  | 2009-09-01 00:00:00.0000000 +00:00 | 2009-09-01 00:00:00.0000000 +00:00 | 2005-09-10 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 |  | 2014-09-01 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2008-03-14 00:00:00.0000000 +00:00 | 2020-09-15 00:00:00.0000000 +00:00 |  | 2019-02-28 00:00:00.0000000 +00:00 | 2020-09-15 00:00:00.0000000 +00:00 |  | 2017-08-31 09:22:08.8371931 -04:00
LBM08DKRF | Y | 2008-01-03 00:00:00.0000000 +00:00 | 2008-10-29 00:00:00.0000000 +00:00 | 2009-05-27 00:00:00.0000000 +00:00 | 2009-10-30 00:00:00.0000000 +00:00 | 2010-04-16 00:00:00.0000000 +00:00 | 2008-01-03 00:00:00.0000000 +00:00 | 2008-05-13 00:00:00.0000000 +00:00 | 2008-09-10 00:00:00.0000000 +00:00 | 2008-11-02 00:00:00.0000000 +00:00 | 2009-04-19 00:00:00.0000000 +00:00 | 2008-01-03 00:00:00.0000000 +00:00 | 2008-10-17 00:00:00.0000000 +00:00 | 2009-05-03 00:00:00.0000000 +00:00 | 2009-06-25 00:00:00.0000000 +00:00 | 2009-12-10 00:00:00.0000000 +00:00 | 2008-01-03 00:00:00.0000000 +00:00 | 2008-10-29 00:00:00.0000000 +00:00 |  | 2009-10-30 00:00:00.0000000 +00:00 | 2010-04-16 00:00:00.0000000 +00:00 | 2009-05-15 00:00:00.0000000 +00:00 | 2010-04-16 00:00:00.0000000 +00:00
LBM08WBRF | Y | 2007-10-31 00:00:00.0000000 +00:00 | 2009-04-10 00:00:00.0000000 +00:00 | 2009-06-05 00:00:00.0000000 +00:00 | 2012-04-24 00:00:00.0000000 +00:00 | 2013-12-17 00:00:00.0000000 +00:00 | 2007-10-31 00:00:00.0000000 +00:00 | 2008-04-24 00:00:00.0000000 +00:00 | 2008-08-03 00:00:00.0000000 +00:00 | 2008-10-30 00:00:00.0000000 +00:00 | 2009-04-04 00:00:00.0000000 +00:00 | 2007-10-31 00:00:00.0000000 +00:00 | 2008-08-29 00:00:00.0000000 +00:00 | 2008-12-08 00:00:00.0000000 +00:00 | 2010-04-16 00:00:00.0000000 +00:00 | 2010-12-20 00:00:00.0000000 +00:00 | 2007-10-31 00:00:00.0000000 +00:00 | 2009-04-10 00:00:00.0000000 +00:00 |  | 2012-04-24 00:00:00.0000000 +00:00 | 2013-12-17 00:00:00.0000000 +00:00 | 2009-06-05 00:00:00.0000000 +00:00 | 2012-12-28 00:00:00.0000000 +00:00
LBM13ARFS | Y | 2013-07-15 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2019-03-01 00:00:00.0000000 +00:00 | 2019-11-29 17:00:00.0000000 +00:00 | 2020-11-29 17:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-08-24 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2016-07-30 00:00:00.0000000 +00:00 | 2017-09-07 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-07-15 00:00:00.0000000 +00:00 | 2017-04-08 00:00:00.0000000 +00:00 | 2019-03-04 00:00:00.0000000 +00:00 | 2020-10-26 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 |  |  |  | 2017-03-24 00:00:00.0000000 +00:00 |  | 2013-07-15 00:00:00.0000000 +00:00 |  | 2015-06-30 00:00:00.0000000 +00:00 |  |  |  | 2016-08-29 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 |  |  | 2017-01-01 00:00:00.0000000 +00:00 |  | 2017-01-01 00:00:00.0000000 +00:00 |  | 2019-03-01 00:00:00.0000000 +00:00 |  | 2019-11-29 17:00:00.0000000 +00:00 |  | 2020-11-29 17:00:00.0000000 +00:00 |  | 2019-09-07 00:00:00.0000000 +00:00 | 2021-05-01 00:00:00.0000000 +00:00 |  | 2021-05-01 00:00:00.0000000 +00:00 |  |  | 2017-10-30 12:12:32.4716101 -04:00
LBM13ARHC | Y | 2013-07-15 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2019-03-01 00:00:00.0000000 +00:00 | 2019-11-29 17:00:00.0000000 +00:00 | 2020-11-29 17:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2015-05-08 00:00:00.0000000 +00:00 | 2016-01-24 00:00:00.0000000 +00:00 | 2017-03-03 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-06-18 00:00:00.0000000 +00:00 | 2017-03-12 00:00:00.0000000 +00:00 | 2019-08-14 00:00:00.0000000 +00:00 | 2020-05-06 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 |  |  |  | 2017-03-24 00:00:00.0000000 +00:00 |  | 2013-07-15 00:00:00.0000000 +00:00 |  | 2015-06-30 00:00:00.0000000 +00:00 |  |  |  | 2016-03-30 00:00:00.0000000 +00:00 | 2016-03-30 00:00:00.0000000 +00:00 |  |  | 2017-03-01 00:00:00.0000000 +00:00 |  | 2017-03-01 00:00:00.0000000 +00:00 |  | 2019-03-01 00:00:00.0000000 +00:00 |  | 2019-11-29 17:00:00.0000000 +00:00 |  | 2020-11-29 17:00:00.0000000 +00:00 |  | 2019-03-03 00:00:00.0000000 +00:00 | 2021-05-29 00:00:00.0000000 +00:00 |  | 2021-05-29 00:00:00.0000000 +00:00
LBM13CGHC | Y | 2013-07-02 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2019-05-31 00:00:00.0000000 +00:00 | 2020-05-29 00:00:00.0000000 +00:00 | 2021-09-30 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2013-12-27 00:00:00.0000000 +00:00 | 2014-09-24 00:00:00.0000000 +00:00 | 2015-01-22 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2014-07-17 00:00:00.0000000 +00:00 | 2017-08-02 00:00:00.0000000 +00:00 | 2018-03-25 00:00:00.0000000 +00:00 | 2019-01-03 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2014-10-07 00:00:00.0000000 +00:00 |  |  |  | 2019-05-31 00:00:00.0000000 +00:00 |  | 2013-07-02 00:00:00.0000000 +00:00 |  | 2014-10-07 00:00:00.0000000 +00:00 |  | 2014-02-12 00:00:00.0000000 +00:00 |  | 2016-09-02 00:00:00.0000000 +00:00 | 2016-09-02 00:00:00.0000000 +00:00 |  | 2014-05-14 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 |  | 2018-07-30 00:00:00.0000000 +00:00 |  | 2019-05-31 00:00:00.0000000 +00:00 |  | 2020-05-29 00:00:00.0000000 +00:00 |  | 2021-09-30 00:00:00.0000000 +00:00 |  | 2017-11-01 00:00:00.0000000 +00:00 | 2022-09-30 00:00:00.0000000 +00:00 |  | 2022-09-30 00:00:00.0000000 +00:00 |  |  | 2017-11-30 08:37:47.0350901 -05:00
LBM13CHFS | Y | 2013-11-21 00:00:00.0000000 +00:00 | 2015-06-23 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2016-10-29 00:00:00.0000000 +00:00 | 2017-08-31 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2014-07-24 00:00:00.0000000 +00:00 | 2015-03-15 00:00:00.0000000 +00:00 | 2015-08-18 00:00:00.0000000 +00:00 | 2016-03-14 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2015-06-01 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2016-06-26 00:00:00.0000000 +00:00 | 2017-04-28 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2015-12-27 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 |  |  |  | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00
LBM13CYFS | Y | 2013-12-03 00:00:00.0000000 +00:00 | 2015-03-02 00:00:00.0000000 +00:00 | 2019-01-30 00:00:00.0000000 +00:00 | 2020-01-30 00:00:00.0000000 +00:00 | 2020-07-30 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2014-07-18 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2015-05-16 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2015-03-02 00:00:00.0000000 +00:00 | 2016-12-02 00:00:00.0000000 +00:00 | 2017-10-29 00:00:00.0000000 +00:00 | 2018-05-12 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-03 00:00:00.0000000 +00:00 |  | 2015-06-02 00:00:00.0000000 +00:00 |  | 2014-08-11 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 |  | 2014-10-10 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 |  | 2018-01-30 00:00:00.0000000 +00:00 |  | 2019-01-30 00:00:00.0000000 +00:00 |  | 2020-01-30 00:00:00.0000000 +00:00 |  | 2020-07-30 00:00:00.0000000 +00:00 |  | 2017-09-27 00:00:00.0000000 +00:00 | 2021-07-30 00:00:00.0000000 +00:00 |  | 2021-07-30 00:00:00.0000000 +00:00 |  |  | 2017-10-11 10:34:30.7683037 -04:00
LBM13DKBR | Y | 2013-06-25 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2019-01-11 00:00:00.0000000 +00:00 | 2019-08-23 00:00:00.0000000 +00:00 | 2021-04-12 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2014-05-01 00:00:00.0000000 +00:00 | 2015-10-03 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2018-06-27 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2018-02-16 00:00:00.0000000 +00:00 | 2020-02-28 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2014-09-24 00:00:00.0000000 +00:00 |  |  |  | 2019-03-15 00:00:00.0000000 +00:00 |  | 2013-06-25 00:00:00.0000000 +00:00 |  | 2014-09-24 00:00:00.0000000 +00:00 |  |  |  | 2016-02-19 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 |  |  | 2018-05-18 00:00:00.0000000 +00:00 |  | 2018-05-18 00:00:00.0000000 +00:00 |  | 2019-01-11 00:00:00.0000000 +00:00 |  | 2019-08-23 00:00:00.0000000 +00:00 |  | 2021-04-12 00:00:00.0000000 +00:00 |  | 2020-06-26 00:00:00.0000000 +00:00 | 2021-12-17 00:00:00.0000000 +00:00 |  | 2021-12-17 00:00:00.0000000 +00:00 |  |  | 2017-11-30 08:38:03.0835282 -05:00
LBM13DRFS | Y | 2013-07-29 00:00:00.0000000 +00:00 | 2015-06-09 00:00:00.0000000 +00:00 | 2016-01-14 00:00:00.0000000 +00:00 | 2016-12-15 00:00:00.0000000 +00:00 | 2017-09-13 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2014-08-21 00:00:00.0000000 +00:00 | 2015-01-22 00:00:00.0000000 +00:00 | 2015-09-05 00:00:00.0000000 +00:00 | 2016-01-22 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2016-04-24 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2017-10-11 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2015-06-10 00:00:00.0000000 +00:00 | 2016-01-14 00:00:00.0000000 +00:00 | 2016-11-30 17:00:00.0000000 +00:00 | 2017-09-13 00:00:00.0000000 +00:00 | 2016-01-06 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2015-06-10 00:00:00.0000000 +00:00 | 2015-06-10 00:00:00.0000000 +00:00 | 2014-10-21 00:00:00.0000000 +00:00 | 2015-08-09 00:00:00.0000000 +00:00 | 2015-08-09 00:00:00.0000000 +00:00 | 2015-08-09 00:00:00.0000000 +00:00 |  | 2014-12-12 00:00:00.0000000 +00:00 | 2015-10-09 00:00:00.0000000 +00:00 | 2015-10-09 00:00:00.0000000 +00:00 | 2015-10-09 00:00:00.0000000 +00:00 |  | 2016-01-14 00:00:00.0000000 +00:00 | 2016-01-14 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2016-11-30 00:00:00.0000000 +00:00 | 2017-09-13 00:00:00.0000000 +00:00 | 2017-09-13 00:00:00.0000000 +00:00 | 2018-01-21 00:00:00.0000000 +00:00 | 2018-09-13 00:00:00.0000000 +00:00 |  | 2018-09-13 00:00:00.0000000 +00:00 | 2018-09-13 00:00:00.0000000 +00:00 |  | 2017-12-15 10:33:35.3421721 -05:00
LBM13FLHC | Y | 2013-07-15 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 | 2019-06-28 00:00:00.0000000 +00:00 | 2020-06-19 00:00:00.0000000 +00:00 | 2021-10-22 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 | 2015-08-27 00:00:00.0000000 +00:00 | 2016-05-07 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 | 2017-02-26 00:00:00.0000000 +00:00 | 2017-11-14 00:00:00.0000000 +00:00 | 2018-07-26 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 |  |  |  | 2019-06-28 00:00:00.0000000 +00:00 |  | 2013-07-15 00:00:00.0000000 +00:00 |  | 2014-12-22 00:00:00.0000000 +00:00 |  | 2014-07-28 00:00:00.0000000 +00:00 | 2015-03-25 00:00:00.0000000 +00:00 | 2015-03-25 00:00:00.0000000 +00:00 | 2015-03-25 00:00:00.0000000 +00:00 |  | 2014-09-30 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 |  | 2018-06-29 00:00:00.0000000 +00:00 |  | 2019-06-28 00:00:00.0000000 +00:00 |  | 2020-06-19 00:00:00.0000000 +00:00 |  | 2021-10-22 00:00:00.0000000 +00:00 |  | 2018-05-07 00:00:00.0000000 +00:00 | 2022-10-21 00:00:00.0000000 +00:00 |  | 2022-10-21 00:00:00.0000000 +00:00 |  |  | 2017-11-30 08:51:55.0994797 -05:00
LBM13LDHC | Y | 2013-07-02 00:00:00.0000000 +00:00 | 2015-02-28 00:00:00.0000000 +00:00 | 2019-05-28 00:00:00.0000000 +00:00 | 2020-02-01 00:00:00.0000000 +00:00 | 2021-02-01 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2014-01-07 00:00:00.0000000 +00:00 | 2014-10-05 00:00:00.0000000 +00:00 | 2015-02-03 00:00:00.0000000 +00:00 | 2015-08-30 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2015-03-04 00:00:00.0000000 +00:00 | 2017-04-07 00:00:00.0000000 +00:00 | 2017-12-08 00:00:00.0000000 +00:00 | 2018-10-22 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 |  |  |  | 2017-09-17 00:00:00.0000000 +00:00 | 2021-02-01 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 |  | 2015-03-17 00:00:00.0000000 +00:00 |  |  | 2015-06-18 00:00:00.0000000 +00:00 | 2015-06-18 00:00:00.0000000 +00:00 | 2015-06-18 00:00:00.0000000 +00:00 |  |  | 2015-06-18 00:00:00.0000000 +00:00 | 2015-06-18 00:00:00.0000000 +00:00 | 2015-06-18 00:00:00.0000000 +00:00 |  | 2019-05-28 00:00:00.0000000 +00:00 |  | 2020-02-01 00:00:00.0000000 +00:00 |  | 2021-02-01 00:00:00.0000000 +00:00 |  | 2017-08-29 00:00:00.0000000 +00:00 | 2021-08-01 00:00:00.0000000 +00:00 |  | 2021-08-01 00:00:00.0000000 +00:00 |  |  | 2017-11-16 08:09:29.2229751 -05:00
LBM13RDFS | Y | 2013-10-20 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2016-11-21 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2003-10-20 00:00:00.0000000 +00:00 | 2004-07-03 00:00:00.0000000 +00:00 | 2005-04-23 00:00:00.0000000 +00:00 | 2005-10-15 00:00:00.0000000 +00:00 | 2006-06-12 00:00:00.0000000 +00:00 | 2003-10-20 00:00:00.0000000 +00:00 | 2005-08-04 00:00:00.0000000 +00:00 | 2007-08-28 00:00:00.0000000 +00:00 | 2008-02-19 00:00:00.0000000 +00:00 | 2010-02-27 00:00:00.0000000 +00:00 | 2013-10-20 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2016-11-21 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 |  |  | 2018-02-28 00:00:00.0000000 +00:00 | 2013-10-20 00:00:00.0000000 +00:00 | 2013-10-20 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2004-10-12 00:00:00.0000000 +00:00 | 2015-07-30 00:00:00.0000000 +00:00 | 2015-07-30 00:00:00.0000000 +00:00 | 2015-07-30 00:00:00.0000000 +00:00 | 2015-07-30 00:00:00.0000000 +00:00 | 2004-12-20 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2016-11-21 00:00:00.0000000 +00:00 | 2016-11-21 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2017-08-30 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2008-06-11 00:00:00.0000000 +00:00 | 2019-02-27 00:00:00.0000000 +00:00 |  | 2019-02-27 00:00:00.0000000 +00:00 | 2019-02-27 00:00:00.0000000 +00:00 |  | 2017-09-05 10:48:36.5680815 -04:00
LBM13SAFS | Y | 2013-12-06 00:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2016-01-17 00:00:00.0000000 +00:00 | 2016-08-08 00:00:00.0000000 +00:00 | 2018-03-22 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2014-08-24 00:00:00.0000000 +00:00 | 2015-06-14 00:00:00.0000000 +00:00 | 2015-12-13 00:00:00.0000000 +00:00 | 2016-08-24 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2015-03-18 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2016-04-20 00:00:00.0000000 +00:00 | 2017-05-10 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2016-01-17 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 |  | 2015-10-10 00:00:00.0000000 +00:00 | 2018-01-18 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2014-11-20 00:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2015-02-20 00:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2015-10-25 00:00:00.0000000 +00:00 | 2015-10-25 00:00:00.0000000 +00:00 | 2015-10-25 00:00:00.0000000 +00:00 | 2016-01-17 00:00:00.0000000 +00:00 | 2016-01-17 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-03-22 00:00:00.0000000 +00:00 | 2018-08-24 00:00:00.0000000 +00:00 | 2019-03-22 00:00:00.0000000 +00:00 |  | 2020-01-17 00:00:00.0000000 +00:00 | 2019-03-22 00:00:00.0000000 +00:00 |  | 2017-09-08 08:33:55.2792503 -04:00
LBM13UPFS | Y | 2013-12-06 00:00:00.0000000 +00:00 | 2015-06-10 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-06-10 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2014-08-21 00:00:00.0000000 +00:00 | 2015-06-11 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2016-07-12 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2015-10-06 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2017-03-26 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2015-06-10 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-01-04 00:00:00.0000000 +00:00 | 2015-11-03 00:00:00.0000000 +00:00 | 2017-06-09 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 |  |  |  | 2015-09-30 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00
LBM14BWRF | Y | 2014-02-14 00:00:00.0000000 +00:00 | 2015-08-19 00:00:00.0000000 +00:00 | 2018-05-31 00:00:00.0000000 +00:00 | 2019-05-31 00:00:00.0000000 +00:00 | 2020-09-30 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2015-03-01 00:00:00.0000000 +00:00 | 2016-02-28 00:00:00.0000000 +00:00 | 2016-05-02 00:00:00.0000000 +00:00 | 2017-07-12 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 | 2018-03-10 00:00:00.0000000 +00:00 | 2019-05-20 00:00:00.0000000 +00:00 | 2014-02-14 00:00:00.0000000 +00:00 | 2015-10-05 00:00:00.0000000 +00:00 | [5 empty] | 2014-02-14 00:00:00.0000000 +00:00 |  | 2015-10-05 00:00:00.0000000 +00:00 |  | 2015-07-03 00:00:00.0000000 +00:00 | 2016-04-18 00:00:00.0000000 +00:00 | 2016-04-18 00:00:00.0000000 +00:00 | 2016-04-18 00:00:00.0000000 +00:00 |  | 2015-12-25 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2018-05-31 00:00:00.0000000 +00:00 |  | 2019-05-31 00:00:00.0000000 +00:00 |  | 2020-09-30 00:00:00.0000000 +00:00 |  | 2019-07-12 00:00:00.0000000 +00:00 | 2021-09-30 00:00:00.0000000 +00:00 |  | 2021-09-30 00:00:00.0000000 +00:00 |  |  | 2017-09-05 10:46:53.7544388 -04:00
LBM14CDRF | Y | 2014-04-15 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2015-11-16 00:00:00.0000000 +00:00 | 2017-03-19 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2014-08-17 00:00:00.0000000 +00:00 | 2015-08-30 00:00:00.0000000 +00:00 | 2016-05-11 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2017-03-18 00:00:00.0000000 +00:00 | 2018-03-22 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 |  | 2016-09-23 18:00:00.0000000 +00:00 | 2017-06-26 17:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 | [17 empty] | 2016-09-23 00:00:00.0000000 +00:00 |  | 2017-06-26 00:00:00.0000000 +00:00 | 2018-11-15 00:00:00.0000000 +00:00 | 2019-06-20 00:00:00.0000000 +00:00 |  |  | 2018-06-26 00:00:00.0000000 +00:00
LBM14MRHC | Y | 2013-11-18 00:00:00.0000000 +00:00 | 2014-10-08 00:00:00.0000000 +00:00 | 2015-11-28 00:00:00.0000000 +00:00 | 2016-05-08 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2013-11-18 00:00:00.0000000 +00:00 | 2014-08-24 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2015-08-11 00:00:00.0000000 +00:00 | 2016-04-21 00:00:00.0000000 +00:00 | 2013-11-18 00:00:00.0000000 +00:00 | 2014-10-08 00:00:00.0000000 +00:00 | 2015-11-28 00:00:00.0000000 +00:00 | 2016-05-08 00:00:00.0000000 +00:00 | 2017-10-18 00:00:00.0000000 +00:00 | 2013-11-18 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-09-07 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2017-09-07 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-23 00:00:00.0000000 +00:00 | 2015-04-23 00:00:00.0000000 +00:00 |  |  |  | 2015-04-23 00:00:00.0000000 +00:00 | 2015-04-23 00:00:00.0000000 +00:00 | [9 empty] | 2018-09-07 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-13 08:59:31.9096230 -04:00
LBM14WTRF | Y | 2014-03-14 00:00:00.0000000 +00:00 | 2014-06-09 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2016-09-05 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2014-06-09 00:00:00.0000000 +00:00 | 2015-05-18 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2016-01-30 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2014-06-09 00:00:00.0000000 +00:00 | 2015-05-18 00:00:00.0000000 +00:00 | 2015-11-13 00:00:00.0000000 +00:00 | 2016-11-12 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2014-06-09 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2016-08-05 00:00:00.0000000 +00:00 | 2017-06-30 17:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2017-12-06 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 |  |  |  | 2015-01-28 00:00:00.0000000 +00:00 | 2015-01-28 00:00:00.0000000 +00:00 | [8 empty] | 2018-01-29 00:00:00.0000000 +00:00 | 2019-09-05 00:00:00.0000000 +00:00
LBM14WWRF | Y | 2014-03-15 00:00:00.0000000 +00:00 | 2015-09-16 00:00:00.0000000 +00:00 | 2017-06-23 00:00:00.0000000 +00:00 | 2018-05-17 00:00:00.0000000 +00:00 | 2019-01-20 00:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2016-03-17 00:00:00.0000000 +00:00 | 2016-11-20 00:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | 2015-03-07 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-02-12 00:00:00.0000000 +00:00 | 2017-10-18 00:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | 2015-09-16 00:00:00.0000000 +00:00 | 2017-06-23 00:00:00.0000000 +00:00 |  |  | 2017-10-31 00:00:00.0000000 +00:00 |  | 2014-03-15 00:00:00.0000000 +00:00 |  | 2015-09-16 00:00:00.0000000 +00:00 |  |  | 2016-03-31 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 |  |  | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 |  | 2017-06-23 00:00:00.0000000 +00:00 |  |  | 2018-08-17 00:00:00.0000000 +00:00 |  | 2019-01-17 00:00:00.0000000 +00:00 | 2018-11-20 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 |  |  | 2020-12-15 00:00:00.0000000 +00:00 |  | 2017-10-23 09:14:18.7635522 -04:00
LBM15GBRF | Y | 2014-12-03 00:00:00.0000000 +00:00 | 2016-03-01 00:00:00.0000000 +00:00 | 2019-01-05 00:00:00.0000000 +00:00 | 2019-08-22 00:00:00.0000000 +00:00 | 2020-08-02 00:00:00.0000000 +00:00 | 2014-12-03 00:00:00.0000000 +00:00 | 2015-05-02 00:00:00.0000000 +00:00 | 2015-08-28 00:00:00.0000000 +00:00 | 2015-12-28 00:00:00.0000000 +00:00 | 2016-07-25 00:00:00.0000000 +00:00 | 2014-12-03 00:00:00.0000000 +00:00 | 2016-03-01 00:00:00.0000000 +00:00 | 2017-08-25 00:00:00.0000000 +00:00 | 2019-12-20 00:00:00.0000000 +00:00 | 2021-01-17 00:00:00.0000000 +00:00 | 2014-12-03 00:00:00.0000000 +00:00 | 2016-03-01 00:00:00.0000000 +00:00 |  |  |  | 2019-01-05 00:00:00.0000000 +00:00 | 2020-08-02 00:00:00.0000000 +00:00 | 2014-12-03 00:00:00.0000000 +00:00 |  | 2016-03-01 00:00:00.0000000 +00:00 |  |  |  | 2016-05-19 00:00:00.0000000 +00:00 | 2016-05-19 00:00:00.0000000 +00:00 |  |  |  | 2016-06-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 |  | 2019-01-05 00:00:00.0000000 +00:00 |  | 2019-08-22 00:00:00.0000000 +00:00 |  | 2020-08-02 00:00:00.0000000 +00:00 |  | 2018-07-25 00:00:00.0000000 +00:00 | 2021-02-02 00:00:00.0000000 +00:00 |  | 2021-02-02 00:00:00.0000000 +00:00 |  |  | 2017-10-30 12:40:54.3701840 -04:00
LBM15MPRF | Y | 2014-11-14 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2019-05-17 00:00:00.0000000 +00:00 | 2020-12-18 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2015-08-08 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2016-06-20 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2015-08-08 00:00:00.0000000 +00:00 | 2017-02-26 00:00:00.0000000 +00:00 | 2019-09-05 00:00:00.0000000 +00:00 | 2020-09-15 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 |  |  |  | 2018-11-21 00:00:00.0000000 +00:00 | 2021-03-09 00:00:00.0000000 +00:00 | 2014-11-14 00:00:00.0000000 +00:00 |  | 2015-06-24 00:00:00.0000000 +00:00 |  |  |  | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 |  |  | 2018-03-16 00:00:00.0000000 +00:00 |  | 2018-03-16 00:00:00.0000000 +00:00 |  | 2018-09-21 00:00:00.0000000 +00:00 |  | 2019-05-17 00:00:00.0000000 +00:00 |  | 2020-12-18 00:00:00.0000000 +00:00 |  | 2019-07-01 00:00:00.0000000 +00:00 | 2021-05-14 00:00:00.0000000 +00:00 |  | 2021-05-14 00:00:00.0000000 +00:00
LBM15RDHC | Y | 2014-12-04 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2018-08-31 00:00:00.0000000 +00:00 | 2019-05-31 00:00:00.0000000 +00:00 | 2020-09-30 00:00:00.0000000 +00:00 | 2014-12-04 00:00:00.0000000 +00:00 | 2015-07-22 00:00:00.0000000 +00:00 | 2016-03-21 00:00:00.0000000 +00:00 | 2016-06-04 00:00:00.0000000 +00:00 | 2017-05-14 00:00:00.0000000 +00:00 | 2014-12-04 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2017-04-22 00:00:00.0000000 +00:00 | 2017-10-05 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2014-12-04 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-04 00:00:00.0000000 +00:00 |  | 2015-11-24 00:00:00.0000000 +00:00 |  | 2015-08-28 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2015-11-27 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 |  | 2018-04-30 00:00:00.0000000 +00:00 |  | 2018-08-31 00:00:00.0000000 +00:00 |  | 2019-05-31 00:00:00.0000000 +00:00 |  | 2020-09-30 00:00:00.0000000 +00:00 |  |  | 2021-09-30 00:00:00.0000000 +00:00 |  | 2021-09-30 00:00:00.0000000 +00:00 |  |  | 2017-09-05 10:47:41.3905776 -04:00
LBM15RDRF | Y | 2014-10-16 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2020-02-14 00:00:00.0000000 +00:00 | 2021-06-14 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2016-03-29 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2017-05-30 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2015-11-02 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2018-09-27 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 |  |  |  | 2019-02-15 00:00:00.0000000 +00:00 |  | 2014-10-16 00:00:00.0000000 +00:00 |  | 2015-11-24 00:00:00.0000000 +00:00 |  | 2015-10-12 00:00:00.0000000 +00:00 | 2016-12-16 00:00:00.0000000 +00:00 | 2016-12-16 00:00:00.0000000 +00:00 | 2016-12-16 00:00:00.0000000 +00:00 |  | 2015-12-14 00:00:00.0000000 +00:00 | 2018-02-16 00:00:00.0000000 +00:00 |  | 2018-02-16 00:00:00.0000000 +00:00 |  | 2019-02-15 00:00:00.0000000 +00:00 |  | 2020-02-14 00:00:00.0000000 +00:00 |  | 2021-06-14 00:00:00.0000000 +00:00 |  | 2019-05-30 00:00:00.0000000 +00:00 | 2022-06-13 00:00:00.0000000 +00:00 |  | 2022-06-13 00:00:00.0000000 +00:00
LBM15WTFS | Y | 2015-05-05 00:00:00.0000000 +00:00 | 2015-12-23 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2018-05-17 00:00:00.0000000 +00:00 | 2015-05-05 00:00:00.0000000 +00:00 | 2015-12-23 00:00:00.0000000 +00:00 | 2016-08-02 00:00:00.0000000 +00:00 | 2017-03-01 00:00:00.0000000 +00:00 | 2018-01-01 00:00:00.0000000 +00:00 | 2015-05-05 00:00:00.0000000 +00:00 | 2015-12-23 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2017-06-14 00:00:00.0000000 +00:00 | 2018-04-16 00:00:00.0000000 +00:00 | 2015-05-05 00:00:00.0000000 +00:00 | 2015-12-23 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2017-02-28 13:00:00.0000000 +00:00 |  | 2016-05-14 00:00:00.0000000 +00:00 | 2018-05-17 00:00:00.0000000 +00:00 | [5 empty] | 2016-03-31 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 |  |  |  | 2016-03-31 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | [8 empty] | 2020-01-01 00:00:00.0000000 +00:00 | 2020-05-15 00:00:00.0000000 +00:00
LBM16GEEC | Y | [47 empty] | 2017-09-15 11:07:53.7600000 +00:00 | 2017-11-08 15:15:44.2911185 -05:00
LBM16GSFC | Y | 2015-11-24 00:00:00.0000000 +00:00 | 2016-12-01 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 | 2020-07-03 00:00:00.0000000 +00:00 | 2021-07-02 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2016-07-13 00:00:00.0000000 +00:00 | 2017-05-30 00:00:00.0000000 +00:00 | 2018-03-10 00:00:00.0000000 +00:00 | 2018-11-17 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2016-12-01 00:00:00.0000000 +00:00 | 2017-11-19 00:00:00.0000000 +00:00 | 2018-06-04 00:00:00.0000000 +00:00 | 2019-08-23 00:00:00.0000000 +00:00 | 2015-11-24 00:00:00.0000000 +00:00 | 2016-09-30 18:00:00.0000000 +00:00 |  |  |  | 2017-11-19 00:00:00.0000000 +00:00 | [6 empty] | 2018-04-26 00:00:00.0000000 +00:00 |  |  |  |  | 2018-12-28 00:00:00.0000000 +00:00 | [9 empty] | 2021-08-22 00:00:00.0000000 +00:00 | 2024-04-06 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-23 09:28:58.3127791 -04:00
LNBXA08LS4 | Y | 2008-01-24 00:00:00.0000000 +00:00 | 2009-03-30 00:00:00.0000000 +00:00 | 2010-11-10 00:00:00.0000000 +00:00 | 2012-03-02 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2008-01-24 00:00:00.0000000 +00:00 | 2009-03-30 00:00:00.0000000 +00:00 | 2010-11-10 00:00:00.0000000 +00:00 | 2012-03-02 00:00:00.0000000 +00:00 | 2013-10-26 00:00:00.0000000 +00:00 | 2008-01-24 00:00:00.0000000 +00:00 | 2009-03-30 00:00:00.0000000 +00:00 | 2010-11-10 00:00:00.0000000 +00:00 | 2012-03-02 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2008-01-24 00:00:00.0000000 +00:00 | 2009-03-30 00:00:00.0000000 +00:00 | 2010-11-10 00:00:00.0000000 +00:00 | 2012-03-02 00:00:00.0000000 +00:00 |  | 2010-11-10 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2008-01-24 00:00:00.0000000 +00:00 | 2008-01-24 00:00:00.0000000 +00:00 | 2009-03-30 00:00:00.0000000 +00:00 | 2009-03-30 00:00:00.0000000 +00:00 | 2009-04-30 00:00:00.0000000 +00:00 | 2009-06-30 00:00:00.0000000 +00:00 | 2009-06-30 00:00:00.0000000 +00:00 | 2009-06-30 00:00:00.0000000 +00:00 | 2009-06-30 00:00:00.0000000 +00:00 | 2009-05-30 00:00:00.0000000 +00:00 | 2009-08-31 00:00:00.0000000 +00:00 | 2009-08-31 00:00:00.0000000 +00:00 | 2009-08-31 00:00:00.0000000 +00:00 | 2009-08-31 00:00:00.0000000 +00:00 | 2010-11-10 00:00:00.0000000 +00:00 | 2010-11-10 00:00:00.0000000 +00:00 | 2012-03-02 00:00:00.0000000 +00:00 | 2012-03-02 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2020-07-16 00:00:00.0000000 +00:00 |  | 2020-07-16 00:00:00.0000000 +00:00 | 2020-07-16 00:00:00.0000000 +00:00 |  | 2017-08-31 14:47:15.7315100 -04:00
LNBXA08LS8 | Y | 2008-01-24 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 | 2014-10-29 00:00:00.0000000 +00:00 | 2016-07-28 00:00:00.0000000 +00:00 | 2017-02-04 00:00:00.0000000 +00:00 | 2008-01-24 00:00:00.0000000 +00:00 | 2008-07-31 00:00:00.0000000 +00:00 | 2014-11-30 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2015-03-08 00:00:00.0000000 +00:00 | 2008-01-24 00:00:00.0000000 +00:00 | 2008-07-31 00:00:00.0000000 +00:00 | 2014-11-30 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2016-02-22 00:00:00.0000000 +00:00 | 2008-01-24 00:00:00.0000000 +00:00 | 2014-10-13 00:00:00.0000000 +00:00 |  | 2016-07-28 00:00:00.0000000 +00:00 | 2017-01-25 00:00:00.0000000 +00:00 |  | 2017-01-29 00:00:00.0000000 +00:00 | [26 empty] | 2017-08-31 14:53:42.4064144 -04:00
LNC002ROS | Y | 2016-10-22 00:00:00.0000000 +00:00 | 2017-12-01 00:00:00.0000000 +00:00 | 2018-11-01 00:00:00.0000000 +00:00 | 2019-05-02 00:00:00.0000000 +00:00 | 2020-12-01 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2014-04-06 00:00:00.0000000 +00:00 | 2016-05-26 00:00:00.0000000 +00:00 | 2017-01-03 00:00:00.0000000 +00:00 | 2019-02-22 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2014-09-04 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2018-04-02 00:00:00.0000000 +00:00 | 2020-01-23 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2014-08-11 00:00:00.0000000 +00:00 |  |  |  | 2018-09-14 00:00:00.0000000 +00:00 | [21 empty] | 2021-02-21 00:00:00.0000000 +00:00 | 2022-12-01 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 14:38:42.4359822 -04:00
LNC005CC3 | Y | 2006-07-21 00:00:00.0000000 +00:00 | 2007-10-04 00:00:00.0000000 +00:00 | 2008-11-13 00:00:00.0000000 +00:00 | 2011-08-16 00:00:00.0000000 +00:00 | 2012-06-26 00:00:00.0000000 +00:00 | 2006-07-21 00:00:00.0000000 +00:00 | 2007-07-18 00:00:00.0000000 +00:00 | 2008-02-14 00:00:00.0000000 +00:00 | 2008-05-07 00:00:00.0000000 +00:00 | 2009-02-02 00:00:00.0000000 +00:00 | 2006-07-21 00:00:00.0000000 +00:00 | 2007-07-18 00:00:00.0000000 +00:00 | 2008-09-01 00:00:00.0000000 +00:00 | 2011-03-28 00:00:00.0000000 +00:00 | 2012-11-29 00:00:00.0000000 +00:00 | 2006-07-21 00:00:00.0000000 +00:00 | 2007-10-04 00:00:00.0000000 +00:00 | 2008-11-13 00:00:00.0000000 +00:00 | 2011-08-16 00:00:00.0000000 +00:00 | 2012-06-26 00:00:00.0000000 +00:00 | 2008-11-13 00:00:00.0000000 +00:00 | 2012-06-26 00:00:00.0000000 +00:00 | 2006-07-21 00:00:00.0000000 +00:00 | 2006-07-21 00:00:00.0000000 +00:00 | 2007-10-04 00:00:00.0000000 +00:00 | 2007-10-04 00:00:00.0000000 +00:00 | 2007-08-18 00:00:00.0000000 +00:00 | 2007-12-31 00:00:00.0000000 +00:00 | 2007-12-31 00:00:00.0000000 +00:00 | 2007-12-31 00:00:00.0000000 +00:00 | 2007-12-31 00:00:00.0000000 +00:00 | 2007-09-18 00:00:00.0000000 +00:00 | 2008-02-05 00:00:00.0000000 +00:00 | 2008-02-05 00:00:00.0000000 +00:00 | 2008-02-05 00:00:00.0000000 +00:00 | 2008-02-05 00:00:00.0000000 +00:00 | 2008-11-13 00:00:00.0000000 +00:00 | 2008-11-13 00:00:00.0000000 +00:00 | 2011-08-16 00:00:00.0000000 +00:00 | 2011-08-16 00:00:00.0000000 +00:00 | 2012-06-26 00:00:00.0000000 +00:00 | 2012-06-26 00:00:00.0000000 +00:00 | 2011-02-02 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 |  | 2014-06-26 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 |  | 2017-12-05 16:54:35.3171788 -05:00
LNC115REN2 | Y | 2003-02-07 00:00:00.0000000 +00:00 | 2003-02-08 00:00:00.0000000 +00:00 | 2003-03-25 00:00:00.0000000 +00:00 | 2003-12-03 00:00:00.0000000 +00:00 | 2006-05-16 00:00:00.0000000 +00:00 | 2003-02-07 00:00:00.0000000 +00:00 | 2003-02-08 00:00:00.0000000 +00:00 | 2003-03-25 00:00:00.0000000 +00:00 | 2003-12-03 00:00:00.0000000 +00:00 | 2006-06-30 00:00:00.0000000 +00:00 | 2003-02-07 00:00:00.0000000 +00:00 | 2003-02-08 00:00:00.0000000 +00:00 | 2003-03-25 00:00:00.0000000 +00:00 | 2003-12-03 00:00:00.0000000 +00:00 | 2006-05-16 00:00:00.0000000 +00:00 | 2003-02-07 00:00:00.0000000 +00:00 | 2003-02-08 00:00:00.0000000 +00:00 | 2003-03-25 00:00:00.0000000 +00:00 | 2003-12-03 00:00:00.0000000 +00:00 | 2006-05-16 00:00:00.0000000 +00:00 | 2003-03-25 00:00:00.0000000 +00:00 | 2006-05-16 00:00:00.0000000 +00:00
LNC2STAPL2 | Y | 2012-09-18 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-10-23 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2012-09-18 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-10-23 00:00:00.0000000 +00:00 | 2015-05-03 00:00:00.0000000 +00:00 | 2015-08-12 00:00:00.0000000 +00:00 | 2012-09-18 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-10-23 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2016-04-17 00:00:00.0000000 +00:00 | 2012-09-18 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2013-10-23 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2016-05-27 00:00:00.0000000 +00:00 | 2013-10-23 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2012-09-18 00:00:00.0000000 +00:00 | 2012-09-18 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | [10 empty] | 2013-10-23 00:00:00.0000000 +00:00 | 2013-10-23 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2016-05-27 00:00:00.0000000 +00:00 | 2016-05-27 00:00:00.0000000 +00:00 | 2016-08-12 00:00:00.0000000 +00:00 | 2019-05-27 00:00:00.0000000 +00:00 | 2019-05-27 00:00:00.0000000 +00:00 | 2019-05-27 00:00:00.0000000 +00:00 | 2019-05-27 00:00:00.0000000 +00:00 |  | 2017-11-27 12:29:44.0608285 -05:00
LNC4WLEX | Y | 2012-05-23 00:00:00.0000000 +00:00 | 2013-07-07 00:00:00.0000000 +00:00 | 2018-07-10 00:00:00.0000000 +00:00 | 2019-05-15 00:00:00.0000000 +00:00 | 2021-05-15 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2013-05-18 00:00:00.0000000 +00:00 | 2014-03-27 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 | 2018-01-10 00:00:00.0000000 +00:00 | 2018-11-03 00:00:00.0000000 +00:00 | 2020-05-01 00:00:00.0000000 +00:00 | 2012-05-23 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 |  |  |  | 2022-01-07 00:00:00.0000000 +00:00 |  | 2012-05-23 00:00:00.0000000 +00:00 |  | 2013-06-29 00:00:00.0000000 +00:00 |  |  | 2016-04-21 00:00:00.0000000 +00:00 | 2016-04-21 00:00:00.0000000 +00:00 | 2016-04-21 00:00:00.0000000 +00:00 |  |  | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-01-18 00:00:00.0000000 +00:00 |  | 2018-07-10 00:00:00.0000000 +00:00 |  | 2019-05-15 00:00:00.0000000 +00:00 |  | 2021-05-15 00:00:00.0000000 +00:00 |  | 2018-10-19 00:00:00.0000000 +00:00 | 2023-05-15 00:00:00.0000000 +00:00 |  | 2023-05-15 00:00:00.0000000 +00:00 |  |  | 2017-08-31 10:07:26.2372221 -04:00
LNCA08BEL | Y | 2007-10-19 00:00:00.0000000 +00:00 | 2010-05-26 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2007-10-19 00:00:00.0000000 +00:00 | 2008-08-20 00:00:00.0000000 +00:00 | 2009-01-13 00:00:00.0000000 +00:00 | 2009-03-25 00:00:00.0000000 +00:00 | 2009-09-10 00:00:00.0000000 +00:00 | 2007-10-19 00:00:00.0000000 +00:00 | 2009-11-02 00:00:00.0000000 +00:00 | 2011-05-03 00:00:00.0000000 +00:00 | 2012-12-04 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2007-10-19 00:00:00.0000000 +00:00 | 2010-05-26 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2011-05-15 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | [26 empty] | 2017-08-31 15:12:03.0325950 -04:00
LNCA08BEL1 | Y | 2007-10-19 00:00:00.0000000 +00:00 | 2010-05-26 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2014-07-29 00:00:00.0000000 +00:00 | 2007-10-19 00:00:00.0000000 +00:00 | 2010-05-26 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2012-09-01 00:00:00.0000000 +00:00 | 2013-02-17 00:00:00.0000000 +00:00 | 2007-10-19 00:00:00.0000000 +00:00 | 2010-05-26 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2013-08-24 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2007-10-19 00:00:00.0000000 +00:00 | 2010-05-26 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2014-07-29 00:00:00.0000000 +00:00 | 2011-10-03 00:00:00.0000000 +00:00 | 2014-06-24 00:00:00.0000000 +00:00 | [26 empty] | 2017-08-31 15:13:11.9684027 -04:00
LNCA0996S | Y | 2009-03-24 00:00:00.0000000 +00:00 | 2012-11-05 00:00:00.0000000 +00:00 | 2016-07-14 00:00:00.0000000 +00:00 | 2018-03-27 00:00:00.0000000 +00:00 | 2018-03-27 00:00:00.0000000 +00:00 | 2009-03-24 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 | 2012-01-28 00:00:00.0000000 +00:00 | 2012-07-26 00:00:00.0000000 +00:00 | 2013-07-21 00:00:00.0000000 +00:00 | 2009-03-24 00:00:00.0000000 +00:00 | 2012-04-27 00:00:00.0000000 +00:00 | 2014-12-06 00:00:00.0000000 +00:00 | 2015-11-07 00:00:00.0000000 +00:00 | 2015-05-28 00:00:00.0000000 +00:00 | 2009-03-24 00:00:00.0000000 +00:00 | 2012-06-09 00:00:00.0000000 +00:00 | 2016-04-22 00:00:00.0000000 +00:00 | 2017-05-31 17:00:00.0000000 +00:00 |  |  | 2018-03-27 00:00:00.0000000 +00:00 | [20 empty] | 2014-02-20 00:00:00.0000000 +00:00 | 2020-01-03 00:00:00.0000000 +00:00
LNCA09BEL | Y | 2009-02-27 00:00:00.0000000 +00:00 | 2010-05-21 00:00:00.0000000 +00:00 | 2010-11-01 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-12-01 00:00:00.0000000 +00:00 | 2009-02-27 00:00:00.0000000 +00:00 | 2009-11-15 00:00:00.0000000 +00:00 | 2010-04-19 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-11-05 00:00:00.0000000 +00:00 | 2009-02-27 00:00:00.0000000 +00:00 | 2010-01-02 00:00:00.0000000 +00:00 | 2010-06-06 00:00:00.0000000 +00:00 | 2010-09-12 00:00:00.0000000 +00:00 | 2011-03-08 00:00:00.0000000 +00:00 | 2009-02-27 00:00:00.0000000 +00:00 | 2010-05-21 00:00:00.0000000 +00:00 | 2010-11-01 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-12-01 00:00:00.0000000 +00:00 | 2010-10-30 00:00:00.0000000 +00:00 | 2012-02-07 00:00:00.0000000 +00:00 | 2009-02-27 00:00:00.0000000 +00:00 | 2009-02-27 00:00:00.0000000 +00:00 | 2010-05-21 00:00:00.0000000 +00:00 | 2010-05-21 00:00:00.0000000 +00:00 | 2009-12-15 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2010-01-15 00:00:00.0000000 +00:00 | 2010-08-02 00:00:00.0000000 +00:00 | 2010-08-02 00:00:00.0000000 +00:00 | 2010-08-02 00:00:00.0000000 +00:00 | 2010-08-02 00:00:00.0000000 +00:00 | 2010-11-01 00:00:00.0000000 +00:00 | 2010-11-01 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-12-01 00:00:00.0000000 +00:00 | 2011-12-01 00:00:00.0000000 +00:00 | 2012-11-05 00:00:00.0000000 +00:00 | 2013-12-01 00:00:00.0000000 +00:00 |  | 2013-12-01 00:00:00.0000000 +00:00 | 2013-12-01 00:00:00.0000000 +00:00 |  | 2017-12-05 16:53:17.9373136 -05:00
LNCA09TRE | Y | 2009-04-23 00:00:00.0000000 +00:00 | 2010-09-01 00:00:00.0000000 +00:00 | 2011-02-28 00:00:00.0000000 +00:00 | 2013-01-10 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2009-04-23 00:00:00.0000000 +00:00 | 2010-01-08 00:00:00.0000000 +00:00 | 2010-06-21 00:00:00.0000000 +00:00 | 2010-08-21 00:00:00.0000000 +00:00 | 2010-12-29 00:00:00.0000000 +00:00 | 2009-04-23 00:00:00.0000000 +00:00 | 2010-02-21 00:00:00.0000000 +00:00 | 2010-08-04 00:00:00.0000000 +00:00 | 2011-03-14 00:00:00.0000000 +00:00 | 2012-08-27 00:00:00.0000000 +00:00 | 2009-04-23 00:00:00.0000000 +00:00 | 2010-09-01 00:00:00.0000000 +00:00 | 2011-02-28 00:00:00.0000000 +00:00 | 2013-01-10 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2011-03-30 00:00:00.0000000 +00:00 | 2015-06-06 00:00:00.0000000 +00:00
LNCA10115A | Y | 2011-06-30 00:00:00.0000000 +00:00 | 2014-11-06 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2018-08-30 00:00:00.0000000 +00:00 | 2019-08-30 00:00:00.0000000 +00:00 | 2011-06-30 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 | 2013-01-27 00:00:00.0000000 +00:00 | 2013-08-06 00:00:00.0000000 +00:00 | 2014-03-08 00:00:00.0000000 +00:00 | 2011-06-30 00:00:00.0000000 +00:00 | 2013-08-22 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2006-03-19 00:00:00.0000000 +00:00 | 2006-01-21 00:00:00.0000000 +00:00 | 2011-06-30 00:00:00.0000000 +00:00 | 2013-08-22 00:00:00.0000000 +00:00 |  |  |  | 2018-02-28 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | [20 empty] | 2016-03-07 00:00:00.0000000 +00:00 | 2021-01-13 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-28 13:38:00.1035408 -04:00
LNCA10AGL | Y | 2009-11-03 00:00:00.0000000 +00:00 | 2013-03-20 00:00:00.0000000 +00:00 | 2017-12-24 00:00:00.0000000 +00:00 | 2018-09-20 00:00:00.0000000 +00:00 | 2019-08-15 00:00:00.0000000 +00:00 | 2009-11-03 00:00:00.0000000 +00:00 | 2010-08-13 00:00:00.0000000 +00:00 | 2011-05-25 00:00:00.0000000 +00:00 | 2011-09-23 00:00:00.0000000 +00:00 | 2012-08-09 00:00:00.0000000 +00:00 | 2009-11-03 00:00:00.0000000 +00:00 | 2012-03-16 00:00:00.0000000 +00:00 | 2016-12-11 00:00:00.0000000 +00:00 | 2017-04-29 00:00:00.0000000 +00:00 | 2018-01-04 00:00:00.0000000 +00:00 | 2009-11-03 00:00:00.0000000 +00:00 | 2011-12-01 00:00:00.0000000 +00:00 |  |  |  | 2018-04-18 00:00:00.0000000 +00:00 | 2019-07-02 00:00:00.0000000 +00:00 | [20 empty] | 2014-08-09 00:00:00.0000000 +00:00 | 2020-05-25 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-02 10:02:27.9280525 -04:00
LNCA10EPH | Y | 2010-05-01 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2012-01-24 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2010-05-01 00:00:00.0000000 +00:00 | 2011-06-07 00:00:00.0000000 +00:00 | 2011-11-20 00:00:00.0000000 +00:00 | 2012-07-03 00:00:00.0000000 +00:00 | 2013-03-08 00:00:00.0000000 +00:00 | 2010-05-01 00:00:00.0000000 +00:00 | 2011-06-07 00:00:00.0000000 +00:00 | 2012-01-24 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2010-05-01 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2012-01-24 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2015-07-23 00:00:00.0000000 +00:00 | 2012-01-18 00:00:00.0000000 +00:00 | 2015-07-22 00:00:00.0000000 +00:00
LNCA10GRC | Y | 2010-04-01 00:00:00.0000000 +00:00 | 2010-12-08 00:00:00.0000000 +00:00 | 2011-12-21 00:00:00.0000000 +00:00 | 2012-08-07 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2010-04-01 00:00:00.0000000 +00:00 | 2010-12-08 00:00:00.0000000 +00:00 | 2011-07-12 00:00:00.0000000 +00:00 | 2011-09-27 00:00:00.0000000 +00:00 | 2012-06-10 00:00:00.0000000 +00:00 | 2010-04-01 00:00:00.0000000 +00:00 | 2010-12-08 00:00:00.0000000 +00:00 | 2011-12-11 00:00:00.0000000 +00:00 | 2012-05-30 00:00:00.0000000 +00:00 | 2013-03-20 00:00:00.0000000 +00:00 | 2010-04-01 00:00:00.0000000 +00:00 | 2010-12-08 00:00:00.0000000 +00:00 | 2011-12-21 00:00:00.0000000 +00:00 | 2012-08-07 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2011-12-10 00:00:00.0000000 +00:00 | 2013-06-01 00:00:00.0000000 +00:00
LNCA10JMB | Y | 2009-11-03 00:00:00.0000000 +00:00 | 2010-02-28 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | 2020-10-07 00:00:00.0000000 +00:00 | 2009-11-03 00:00:00.0000000 +00:00 | 2010-08-13 00:00:00.0000000 +00:00 | 2011-06-09 00:00:00.0000000 +00:00 | 2011-10-15 00:00:00.0000000 +00:00 | 2012-11-14 00:00:00.0000000 +00:00 | 2009-11-03 00:00:00.0000000 +00:00 | 2010-05-22 00:00:00.0000000 +00:00 | 2015-11-23 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2018-03-22 00:00:00.0000000 +00:00 | 2009-11-03 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2017-12-05 00:00:00.0000000 +00:00 |  |  | 2017-08-30 00:00:00.0000000 +00:00 | 2020-03-06 00:00:00.0000000 +00:00 | 2009-11-03 00:00:00.0000000 +00:00 |  | 2010-07-01 00:00:00.0000000 +00:00 |  |  | 2011-06-09 00:00:00.0000000 +00:00 | 2011-06-09 00:00:00.0000000 +00:00 | 2011-06-09 00:00:00.0000000 +00:00 |  |  | 2015-07-02 00:00:00.0000000 +00:00 |  | 2015-07-02 00:00:00.0000000 +00:00 |  | 2017-10-27 00:00:00.0000000 +00:00 |  | 2018-07-14 00:00:00.0000000 +00:00 |  | 2020-01-11 00:00:00.0000000 +00:00 |  | 2014-11-14 00:00:00.0000000 +00:00 | 2021-07-07 00:00:00.0000000 +00:00 |  | 2020-10-21 00:00:00.0000000 +00:00 |  |  | 2017-12-05 16:08:48.6420280 -05:00
LNCA10RIS | Y | 2013-07-15 00:00:00.0000000 +00:00 | 2016-04-21 00:00:00.0000000 +00:00 | 2017-10-10 00:00:00.0000000 +00:00 | 2018-08-02 00:00:00.0000000 +00:00 | 2019-12-01 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-04-13 00:00:00.0000000 +00:00 | 2016-06-02 00:00:00.0000000 +00:00 | 2016-12-31 00:00:00.0000000 +00:00 | 2019-02-03 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | 2016-11-18 00:00:00.0000000 +00:00 | 2018-03-25 00:00:00.0000000 +00:00 | 2018-08-26 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-12-19 17:00:00.0000000 +00:00 | 2017-10-18 00:00:00.0000000 +00:00 |  |  | 2017-09-30 00:00:00.0000000 +00:00 | 2019-10-20 00:00:00.0000000 +00:00 | [20 empty] | 2021-02-02 00:00:00.0000000 +00:00 | 2020-11-20 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-06 13:19:17.6455056 -05:00
LNCA10TH1 | Y | 2011-11-23 00:00:00.0000000 +00:00 | 2013-04-11 00:00:00.0000000 +00:00 | 2013-10-23 00:00:00.0000000 +00:00 | 2014-08-05 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2011-11-23 00:00:00.0000000 +00:00 | 2012-12-30 00:00:00.0000000 +00:00 | 2013-06-01 00:00:00.0000000 +00:00 | 2013-09-01 00:00:00.0000000 +00:00 | 2014-04-01 00:00:00.0000000 +00:00 | 2011-11-23 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2013-11-16 00:00:00.0000000 +00:00 | 2014-08-05 00:00:00.0000000 +00:00 | 2015-07-28 00:00:00.0000000 +00:00 | 2011-11-23 00:00:00.0000000 +00:00 | 2013-04-11 00:00:00.0000000 +00:00 | 2013-10-23 00:00:00.0000000 +00:00 | 2014-08-05 00:00:00.0000000 +00:00 | 2015-10-08 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2015-10-07 00:00:00.0000000 +00:00 | [21 empty] | 2017-12-31 00:00:00.0000000 +00:00 |  |  |  |  | 2017-12-12 10:08:41.9900076 -05:00
LNCA10YRK | Y | 2009-10-21 00:00:00.0000000 +00:00 | 2010-11-24 00:00:00.0000000 +00:00 | 2011-06-29 00:00:00.0000000 +00:00 | 2012-08-08 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2010-06-17 00:00:00.0000000 +00:00 | 2010-06-22 00:00:00.0000000 +00:00 | 2010-06-26 00:00:00.0000000 +00:00 | 2010-07-02 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2010-11-18 00:00:00.0000000 +00:00 | 2010-12-29 00:00:00.0000000 +00:00 | 2011-10-04 00:00:00.0000000 +00:00 | 2012-02-19 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2010-11-24 00:00:00.0000000 +00:00 | 2011-06-29 00:00:00.0000000 +00:00 | 2012-08-08 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2011-06-29 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2010-11-24 00:00:00.0000000 +00:00 | 2010-11-24 00:00:00.0000000 +00:00 | 2010-06-18 00:00:00.0000000 +00:00 | 2010-12-31 00:00:00.0000000 +00:00 | 2010-12-31 00:00:00.0000000 +00:00 | 2010-12-31 00:00:00.0000000 +00:00 | 2010-12-31 00:00:00.0000000 +00:00 | 2010-06-21 00:00:00.0000000 +00:00 | 2011-03-24 00:00:00.0000000 +00:00 | 2011-03-24 00:00:00.0000000 +00:00 | 2011-03-24 00:00:00.0000000 +00:00 | 2011-03-24 00:00:00.0000000 +00:00 | 2011-06-29 00:00:00.0000000 +00:00 | 2011-06-29 00:00:00.0000000 +00:00 | 2012-08-08 00:00:00.0000000 +00:00 | 2012-08-08 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2018-08-24 00:00:00.0000000 +00:00 |  | 2015-12-09 00:00:00.0000000 +00:00 | 2018-08-20 00:00:00.0000000 +00:00 |  | 2017-12-05 17:17:22.5334958 -05:00
LNCA1167S | Y | 2011-02-10 00:00:00.0000000 +00:00 | 2014-11-04 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2018-07-01 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2011-02-10 00:00:00.0000000 +00:00 | 2011-10-01 00:00:00.0000000 +00:00 | 2012-04-01 00:00:00.0000000 +00:00 | 2012-08-01 00:00:00.0000000 +00:00 | 2013-06-09 00:00:00.0000000 +00:00 | 2011-02-10 00:00:00.0000000 +00:00 | 2012-05-14 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 | 2015-07-26 00:00:00.0000000 +00:00 | 2016-06-02 00:00:00.0000000 +00:00 | 2011-02-10 00:00:00.0000000 +00:00 | 2013-04-18 00:00:00.0000000 +00:00 | 2017-10-19 00:00:00.0000000 +00:00 |  |  | 2016-04-04 00:00:00.0000000 +00:00 |  | 2011-02-10 00:00:00.0000000 +00:00 |  | 2013-04-18 00:00:00.0000000 +00:00 |  | 2011-12-01 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 |  | 2012-02-01 00:00:00.0000000 +00:00 | 2015-04-18 00:00:00.0000000 +00:00 | 2015-04-18 00:00:00.0000000 +00:00 | 2015-04-18 00:00:00.0000000 +00:00 |  | 2017-10-30 00:00:00.0000000 +00:00 |  | 2018-07-01 00:00:00.0000000 +00:00 |  | 2019-07-01 00:00:00.0000000 +00:00 |  | 2015-06-09 00:00:00.0000000 +00:00 | 2020-03-26 00:00:00.0000000 +00:00 |  | 2021-07-01 00:00:00.0000000 +00:00 |  |  | 2017-10-23 13:22:15.9652878 -04:00
LNCA11BEL | Y | 2011-10-21 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2016-10-07 00:00:00.0000000 +00:00 | 2018-10-10 00:00:00.0000000 +00:00 | 2011-10-20 00:00:00.0000000 +00:00 | 2012-03-30 00:00:00.0000000 +00:00 | 2012-07-09 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-08-06 00:00:00.0000000 +00:00 | 2011-10-20 00:00:00.0000000 +00:00 | 2013-03-03 00:00:00.0000000 +00:00 | 2014-01-21 00:00:00.0000000 +00:00 | 2015-02-17 00:00:00.0000000 +00:00 | 2015-04-14 00:00:00.0000000 +00:00 | 2011-10-21 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 |  | 2014-02-22 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00
LNCA11BLD | Y | 2012-03-12 00:00:00.0000000 +00:00 | 2013-09-05 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2012-03-12 00:00:00.0000000 +00:00 | 2012-12-01 00:00:00.0000000 +00:00 | 2013-10-26 00:00:00.0000000 +00:00 | 2014-05-24 00:00:00.0000000 +00:00 | 2015-02-19 00:00:00.0000000 +00:00 | 2012-03-12 00:00:00.0000000 +00:00 | 2013-04-19 00:00:00.0000000 +00:00 | 2017-02-06 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2018-07-17 00:00:00.0000000 +00:00 | 2012-03-12 00:00:00.0000000 +00:00 | 2013-04-19 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 |  |  | 2019-06-30 00:00:00.0000000 +00:00 |  | 2012-03-12 00:00:00.0000000 +00:00 |  | 2013-04-19 00:00:00.0000000 +00:00 |  | 2013-02-01 00:00:00.0000000 +00:00 | 2014-01-12 00:00:00.0000000 +00:00 | 2014-01-12 00:00:00.0000000 +00:00 | 2014-01-12 00:00:00.0000000 +00:00 |  | 2013-04-01 00:00:00.0000000 +00:00 | 2014-04-13 00:00:00.0000000 +00:00 | 2014-04-13 00:00:00.0000000 +00:00 | 2014-04-13 00:00:00.0000000 +00:00 |  | 2016-12-28 00:00:00.0000000 +00:00 |  | 2018-05-01 00:00:00.0000000 +00:00 |  | 2019-05-01 00:00:00.0000000 +00:00 |  | 2017-02-19 00:00:00.0000000 +00:00 | 2021-05-01 00:00:00.0000000 +00:00 |  | 2021-05-01 00:00:00.0000000 +00:00 |  |  | 2017-11-21 13:29:11.0186353 -05:00
LNCA11CCL | Y | 2014-08-25 00:00:00.0000000 +00:00 | 2014-12-18 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2017-06-23 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2015-05-08 00:00:00.0000000 +00:00 | 2015-09-12 00:00:00.0000000 +00:00 | 2016-03-26 00:00:00.0000000 +00:00 | 2017-01-02 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2015-05-08 00:00:00.0000000 +00:00 | 2015-12-08 00:00:00.0000000 +00:00 | 2017-10-22 00:00:00.0000000 +00:00 | 2018-06-07 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2014-12-18 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2017-06-23 17:00:00.0000000 +00:00 |  | 2015-08-08 00:00:00.0000000 +00:00 | 2018-01-01 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2014-12-18 00:00:00.0000000 +00:00 | 2014-12-18 00:00:00.0000000 +00:00 | 2015-06-08 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2017-06-23 00:00:00.0000000 +00:00 | 2017-06-23 17:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 |  | 2019-12-31 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00
LNCA11SNV | Y | 2010-12-21 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2014-09-17 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2010-12-21 00:00:00.0000000 +00:00 | 2011-06-25 00:00:00.0000000 +00:00 | 2012-01-24 00:00:00.0000000 +00:00 | 2012-05-09 00:00:00.0000000 +00:00 | 2012-12-16 00:00:00.0000000 +00:00 | 2010-12-21 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-10-05 00:00:00.0000000 +00:00 | 2014-06-17 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | 2010-12-21 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2014-09-17 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2015-05-21 00:00:00.0000000 +00:00
LNCA12EPH | Y | 2012-01-09 00:00:00.0000000 +00:00 | 2018-09-30 00:00:00.0000000 +00:00 | 2018-07-01 00:00:00.0000000 +00:00 | 2019-01-29 00:00:00.0000000 +00:00 | 2020-09-01 00:00:00.0000000 +00:00 | 2012-01-09 00:00:00.0000000 +00:00 | 2012-09-29 00:00:00.0000000 +00:00 | 2013-05-01 00:00:00.0000000 +00:00 | 2013-12-04 00:00:00.0000000 +00:00 | 2014-06-14 00:00:00.0000000 +00:00 | 2012-01-09 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2017-01-19 00:00:00.0000000 +00:00 | 2017-08-27 00:00:00.0000000 +00:00 | 2019-09-27 00:00:00.0000000 +00:00 | 2012-01-09 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 |  |  |  | 2014-06-29 00:00:00.0000000 +00:00 | [7 empty] | 2017-11-28 00:00:00.0000000 +00:00 | [13 empty] | 2016-06-13 00:00:00.0000000 +00:00 | 2022-09-01 00:00:00.0000000 +00:00
LNCA12RSD | Y | 2012-01-05 00:00:00.0000000 +00:00 | 2012-07-01 00:00:00.0000000 +00:00 | 2013-05-17 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 | 2012-01-05 00:00:00.0000000 +00:00 | 2012-09-01 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 | 2013-09-04 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 | 2012-01-05 00:00:00.0000000 +00:00 | 2012-09-01 00:00:00.0000000 +00:00 | 2013-07-29 00:00:00.0000000 +00:00 | 2014-03-28 00:00:00.0000000 +00:00 | 2014-10-22 00:00:00.0000000 +00:00 | 2012-01-05 00:00:00.0000000 +00:00 | 2012-07-01 00:00:00.0000000 +00:00 | 2013-05-17 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 | 2013-05-28 00:00:00.0000000 +00:00 | 2015-07-26 00:00:00.0000000 +00:00
LNCA12SWP | Y | 2012-02-17 00:00:00.0000000 +00:00 | 2013-10-16 00:00:00.0000000 +00:00 | 2014-10-31 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2016-12-17 00:00:00.0000000 +00:00 | 2012-02-17 00:00:00.0000000 +00:00 | 2013-02-01 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2015-03-22 00:00:00.0000000 +00:00 | 2012-02-17 00:00:00.0000000 +00:00 | 2013-10-16 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2016-12-22 00:00:00.0000000 +00:00 | 2012-02-17 00:00:00.0000000 +00:00 | 2013-10-16 00:00:00.0000000 +00:00 | 2014-10-31 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 |  | 2014-11-10 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00
LNCA13CCL | Y | 2013-04-01 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2014-01-24 00:00:00.0000000 +00:00 | 2014-10-21 00:00:00.0000000 +00:00 | 2015-03-22 00:00:00.0000000 +00:00 | 2015-11-14 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2016-03-24 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2017-05-11 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2014-12-23 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2017-06-13 17:00:00.0000000 +00:00 |  | 2017-01-13 00:00:00.0000000 +00:00 | 2017-11-11 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 |  | 2014-01-24 00:00:00.0000000 +00:00 |  | 2014-03-31 00:00:00.0000000 +00:00 | 2015-04-28 00:00:00.0000000 +00:00 | 2015-04-28 00:00:00.0000000 +00:00 | 2015-04-28 00:00:00.0000000 +00:00 |  | 2014-08-28 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 |  | 2017-01-13 00:00:00.0000000 +00:00 |  | 2017-06-13 00:00:00.0000000 +00:00 | 2017-06-13 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2020-05-04 00:00:00.0000000 +00:00 | 2019-02-14 00:00:00.0000000 +00:00 |  | 2020-05-04 00:00:00.0000000 +00:00 | 2020-05-04 00:00:00.0000000 +00:00 |  | 2017-10-31 16:44:11.2010599 -04:00
LNCA13ECH | Y | 2013-05-30 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2019-05-01 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 | 2015-12-13 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 | 2016-06-02 00:00:00.0000000 +00:00 | 2017-04-20 00:00:00.0000000 +00:00 | 2018-01-20 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 |  |  |  | 2017-03-27 00:00:00.0000000 +00:00 |  | 2013-05-30 00:00:00.0000000 +00:00 |  | 2015-08-17 00:00:00.0000000 +00:00 |  | 2014-05-31 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 |  |  | 2015-10-13 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 |  |  |  | 2018-07-16 00:00:00.0000000 +00:00 |  | 2019-05-01 00:00:00.0000000 +00:00 |  | 2019-01-20 00:00:00.0000000 +00:00 | 2021-04-29 00:00:00.0000000 +00:00 |  | 2021-04-29 00:00:00.0000000 +00:00 |  |  | 2017-11-08 10:52:01.4003948 -05:00
LNCA13GBR | Y | 2013-05-20 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2018-04-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2020-03-02 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2013-12-26 00:00:00.0000000 +00:00 | 2014-12-25 00:00:00.0000000 +00:00 | 2015-07-30 00:00:00.0000000 +00:00 | 2016-08-24 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2012-04-17 00:00:00.0000000 +00:00 | 2017-04-02 00:00:00.0000000 +00:00 | 2018-04-28 00:00:00.0000000 +00:00 | 2013-03-18 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 |  |  |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2013-03-18 00:00:00.0000000 +00:00 |  | 2014-06-16 00:00:00.0000000 +00:00 |  | 2014-03-31 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 |  | 2014-09-30 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 |  | 2018-04-15 00:00:00.0000000 +00:00 |  | 2019-01-15 00:00:00.0000000 +00:00 |  | 2020-03-02 00:00:00.0000000 +00:00 |  | 2018-08-24 00:00:00.0000000 +00:00 | 2021-09-02 00:00:00.0000000 +00:00 |  | 2021-09-02 00:00:00.0000000 +00:00
LNCA13HAM | Y | 2013-05-26 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2018-09-30 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2020-12-30 00:00:00.0000000 +00:00 | 2013-01-08 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2015-02-17 00:00:00.0000000 +00:00 | 2015-09-24 00:00:00.0000000 +00:00 | 2017-02-16 00:00:00.0000000 +00:00 | 2013-01-08 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2018-03-08 00:00:00.0000000 +00:00 | 2019-08-01 00:00:00.0000000 +00:00 | 2013-03-18 00:00:00.0000000 +00:00 | 2013-11-19 00:00:00.0000000 +00:00 |  |  |  | 2020-01-11 00:00:00.0000000 +00:00 | [21 empty] | 2019-02-16 00:00:00.0000000 +00:00 | 2022-12-30 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 10:44:34.8384527 -04:00
LNCA13HUD | Y | 2013-04-02 00:00:00.0000000 +00:00 | 2015-10-18 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2020-04-12 00:00:00.0000000 +00:00 | 2021-10-14 00:00:00.0000000 +00:00 | 2013-04-02 00:00:00.0000000 +00:00 | 2013-11-27 00:00:00.0000000 +00:00 | 2014-12-06 00:00:00.0000000 +00:00 | 2015-01-21 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2013-04-02 00:00:00.0000000 +00:00 | 2014-11-07 00:00:00.0000000 +00:00 | 2016-11-12 00:00:00.0000000 +00:00 | 2018-12-14 00:00:00.0000000 +00:00 | 2020-07-05 00:00:00.0000000 +00:00 | 2013-04-02 00:00:00.0000000 +00:00 | 2014-11-07 00:00:00.0000000 +00:00 |  |  |  | 2016-09-30 00:00:00.0000000 +00:00 | [21 empty] | 2017-12-20 00:00:00.0000000 +00:00 | 2023-10-14 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 14:40:03.9193523 -04:00
LNCA13MLB | Y | 2013-02-07 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2013-02-07 00:00:00.0000000 +00:00 | 2014-01-10 00:00:00.0000000 +00:00 | 2014-08-25 00:00:00.0000000 +00:00 | 2015-01-23 00:00:00.0000000 +00:00 | 2015-09-03 00:00:00.0000000 +00:00 | 2013-02-07 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 | 2015-09-27 00:00:00.0000000 +00:00 | 2016-02-05 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2013-02-07 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 |  |  |  | 2018-02-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2013-02-07 00:00:00.0000000 +00:00 |  | 2014-12-09 00:00:00.0000000 +00:00 |  | 2014-03-10 00:00:00.0000000 +00:00 | 2015-03-15 00:00:00.0000000 +00:00 | 2015-03-15 00:00:00.0000000 +00:00 | 2015-03-15 00:00:00.0000000 +00:00 |  | 2014-05-10 00:00:00.0000000 +00:00 | 2015-06-16 00:00:00.0000000 +00:00 | 2015-06-16 00:00:00.0000000 +00:00 | 2015-06-16 00:00:00.0000000 +00:00 |  | 2018-02-15 00:00:00.0000000 +00:00 |  | 2018-09-15 00:00:00.0000000 +00:00 |  | 2019-09-15 00:00:00.0000000 +00:00 |  | 2017-09-03 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 |  | 2021-09-15 00:00:00.0000000 +00:00 |  |  | 2017-09-11 10:46:12.8854608 -04:00
LNCA13MOR | Y | 2013-02-27 00:00:00.0000000 +00:00 | 2014-10-06 00:00:00.0000000 +00:00 | 2018-01-01 00:00:00.0000000 +00:00 | 2018-10-01 00:00:00.0000000 +00:00 | 2019-10-01 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2014-03-16 00:00:00.0000000 +00:00 | 2015-06-26 00:00:00.0000000 +00:00 | 2015-12-29 00:00:00.0000000 +00:00 | 2017-03-30 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2014-11-06 00:00:00.0000000 +00:00 | 2016-05-13 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 |  |  |  | 2017-10-16 00:00:00.0000000 +00:00 | [5 empty] | 2014-11-24 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 | 2014-12-26 00:00:00.0000000 +00:00 |  |  | 2015-02-27 00:00:00.0000000 +00:00 | 2016-12-26 00:00:00.0000000 +00:00 | 2016-12-26 00:00:00.0000000 +00:00 | [8 empty] | 2021-05-05 00:00:00.0000000 +00:00 | 2020-10-08 00:00:00.0000000 +00:00 |  |  |  |  | 2017-12-12 15:53:40.2256774 -05:00
LNCA13MOT | Y | 2013-02-27 00:00:00.0000000 +00:00 | 2015-03-04 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2018-10-02 00:00:00.0000000 +00:00 | 2019-09-26 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2014-01-08 00:00:00.0000000 +00:00 | 2014-10-03 00:00:00.0000000 +00:00 | 2015-04-29 00:00:00.0000000 +00:00 | 2016-02-24 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2015-12-12 00:00:00.0000000 +00:00 | 2016-07-24 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2014-01-23 00:00:00.0000000 +00:00 |  |  |  | 2017-12-17 00:00:00.0000000 +00:00 | 2019-07-17 00:00:00.0000000 +00:00 | [20 empty] | 2021-04-01 00:00:00.0000000 +00:00 | 2020-08-20 00:00:00.0000000 +00:00
LNCA13NAM | Y | 2013-01-07 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2018-01-01 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2019-08-15 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2014-04-07 00:00:00.0000000 +00:00 | 2015-01-12 00:00:00.0000000 +00:00 | 2015-09-05 00:00:00.0000000 +00:00 | 2016-07-25 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2017-08-17 00:00:00.0000000 +00:00 | 2018-03-12 00:00:00.0000000 +00:00 | 2019-01-30 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 |  |  |  | 2017-10-31 00:00:00.0000000 +00:00 |  | 2013-01-07 00:00:00.0000000 +00:00 |  | 2015-03-17 00:00:00.0000000 +00:00 |  | 2014-06-07 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 |  | 2014-08-07 00:00:00.0000000 +00:00 | 2016-06-07 00:00:00.0000000 +00:00 | 2016-06-07 00:00:00.0000000 +00:00 | 2016-06-07 00:00:00.0000000 +00:00 |  | 2017-10-31 00:00:00.0000000 +00:00 |  | 2018-07-01 00:00:00.0000000 +00:00 |  | 2019-07-01 00:00:00.0000000 +00:00 |  | 2018-07-25 00:00:00.0000000 +00:00 | 2021-07-01 00:00:00.0000000 +00:00 |  | 2021-07-01 00:00:00.0000000 +00:00 |  |  | 2017-12-04 17:19:16.1073448 -05:00
LNCA13THL | Y | 2014-03-25 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2015-06-08 00:00:00.0000000 +00:00 | 2016-05-19 00:00:00.0000000 +00:00 | 2017-04-08 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2016-08-28 00:00:00.0000000 +00:00 | 2017-06-25 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2016-08-02 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | 2015-06-08 00:00:00.0000000 +00:00 | 2016-05-19 00:00:00.0000000 +00:00 | 2016-12-01 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2017-04-08 00:00:00.0000000 +00:00 | [21 empty] | 2017-12-31 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-27 11:58:13.9649516 -05:00
LNCA13TRE | Y | 2013-05-06 00:00:00.0000000 +00:00 | 2014-12-02 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2016-09-12 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2013-05-06 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2015-03-06 00:00:00.0000000 +00:00 | 2015-11-22 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2013-05-06 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-10-16 00:00:00.0000000 +00:00 | 2017-06-22 00:00:00.0000000 +00:00 | 2013-05-06 00:00:00.0000000 +00:00 | 2014-12-02 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2016-09-22 00:00:00.0000000 +00:00 | 2017-09-20 00:00:00.0000000 +00:00 | 2016-04-25 00:00:00.0000000 +00:00 | 2017-05-29 00:00:00.0000000 +00:00 | 2013-05-06 00:00:00.0000000 +00:00 | 2013-05-06 00:00:00.0000000 +00:00 | 2014-12-02 00:00:00.0000000 +00:00 | 2014-12-02 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2014-09-26 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2016-09-12 00:00:00.0000000 +00:00 | 2016-09-12 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2018-12-30 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 |  | 2019-09-30 00:00:00.0000000 +00:00 | 2019-09-30 00:00:00.0000000 +00:00 |  | 2017-09-26 10:20:55.4491257 -04:00
LNCA1458S | Y | 2014-09-01 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2014-11-13 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2017-07-31 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2015-05-30 00:00:00.0000000 +00:00 | 2015-06-06 00:00:00.0000000 +00:00 | 2015-12-27 00:00:00.0000000 +00:00 | 2016-07-31 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2014-09-25 00:00:00.0000000 +00:00 | 2015-09-02 00:00:00.0000000 +00:00 | 2017-02-10 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2015-04-29 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2017-07-08 00:00:00.0000000 +00:00 | 2014-11-18 00:00:00.0000000 +00:00 | 2018-02-14 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-26 10:22:50.3639550 -04:00
LNCA14MBG | Y | 2014-09-08 00:00:00.0000000 +00:00 | 2016-02-07 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2015-03-28 00:00:00.0000000 +00:00 | 2015-09-01 00:00:00.0000000 +00:00 | 2016-02-14 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2015-03-28 00:00:00.0000000 +00:00 | 2016-07-12 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2018-09-21 00:00:00.0000000 +00:00 | 2014-09-08 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 |  |  |  | 2018-03-17 00:00:00.0000000 +00:00 |  | 2014-09-08 00:00:00.0000000 +00:00 |  | 2015-08-24 00:00:00.0000000 +00:00 |  | 2015-04-28 00:00:00.0000000 +00:00 | 2016-02-26 00:00:00.0000000 +00:00 | 2016-02-26 00:00:00.0000000 +00:00 | 2016-02-26 00:00:00.0000000 +00:00 |  | 2015-05-28 00:00:00.0000000 +00:00 | 2017-08-28 00:00:00.0000000 +00:00 | 2017-08-28 00:00:00.0000000 +00:00 | 2017-08-28 00:00:00.0000000 +00:00 |  | 2018-02-15 00:00:00.0000000 +00:00 |  | 2018-09-15 00:00:00.0000000 +00:00 |  | 2019-09-15 00:00:00.0000000 +00:00 |  | 2018-11-22 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 |  | 2021-09-15 00:00:00.0000000 +00:00 |  |  | 2017-09-11 10:45:10.0162511 -04:00
LNCA14SPD | Y | 2014-09-01 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2017-06-27 00:00:00.0000000 +00:00 | 2018-04-27 00:00:00.0000000 +00:00 | 2018-08-28 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 | 2015-09-04 00:00:00.0000000 +00:00 | 2016-03-26 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2018-04-23 00:00:00.0000000 +00:00 | 2004-11-25 00:00:00.0000000 +00:00 | 2018-07-26 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2017-06-27 00:00:00.0000000 +00:00 |  |  | 2019-06-27 00:00:00.0000000 +00:00 |  | 2014-09-01 00:00:00.0000000 +00:00 |  | 2016-06-01 00:00:00.0000000 +00:00 |  | 2015-03-08 00:00:00.0000000 +00:00 | 2016-09-22 00:00:00.0000000 +00:00 | 2016-09-22 00:00:00.0000000 +00:00 | 2016-09-22 00:00:00.0000000 +00:00 |  | 2015-06-08 00:00:00.0000000 +00:00 | 2016-10-26 00:00:00.0000000 +00:00 | 2016-10-26 00:00:00.0000000 +00:00 | 2016-10-26 00:00:00.0000000 +00:00 |  | 2017-06-27 00:00:00.0000000 +00:00 |  | 2018-02-28 00:00:00.0000000 +00:00 |  | 2018-08-28 00:00:00.0000000 +00:00 |  | 2018-08-30 00:00:00.0000000 +00:00 | 2020-08-28 00:00:00.0000000 +00:00 |  | 2020-08-28 00:00:00.0000000 +00:00
LNCA15BLD | Y | 2014-12-22 00:00:00.0000000 +00:00 | 2015-04-09 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2017-03-17 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2015-03-31 00:00:00.0000000 +00:00 | 2015-12-29 00:00:00.0000000 +00:00 | 2016-03-28 00:00:00.0000000 +00:00 | 2016-08-13 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2015-04-09 00:00:00.0000000 +00:00 | 2016-05-24 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2015-04-09 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2017-01-06 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2017-03-17 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 10:36:52.2458275 -05:00
LNCA15EDW | Y | 2014-11-24 00:00:00.0000000 +00:00 | 2016-07-06 00:00:00.0000000 +00:00 | 2018-01-03 00:00:00.0000000 +00:00 | 2018-10-05 00:00:00.0000000 +00:00 | 2019-10-04 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2016-02-24 00:00:00.0000000 +00:00 | 2016-07-24 00:00:00.0000000 +00:00 | 2017-05-26 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2016-01-06 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2017-10-21 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 |  |  |  | 2018-02-28 00:00:00.0000000 +00:00 | [21 empty] | 2019-05-26 00:00:00.0000000 +00:00 | 2021-01-02 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 10:55:57.8927646 -04:00
LNCA15MOT | Y | 2014-11-24 00:00:00.0000000 +00:00 | 2015-12-10 00:00:00.0000000 +00:00 | 2018-04-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2017-02-24 00:00:00.0000000 +00:00 | 2017-07-24 00:00:00.0000000 +00:00 | 2018-05-26 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2015-12-09 00:00:00.0000000 +00:00 | 2016-09-03 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 | 2014-11-24 00:00:00.0000000 +00:00 | 2015-12-10 00:00:00.0000000 +00:00 |  |  |  | 2016-12-31 00:00:00.0000000 +00:00 |  | 2014-11-24 00:00:00.0000000 +00:00 |  | 2015-12-10 00:00:00.0000000 +00:00 |  | 2015-12-14 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 |  | 2016-03-08 00:00:00.0000000 +00:00 | 2016-10-20 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 |  | 2018-05-15 00:00:00.0000000 +00:00 |  | 2019-01-15 00:00:00.0000000 +00:00 |  | 2020-01-15 00:00:00.0000000 +00:00 |  | 2019-05-12 00:00:00.0000000 +00:00 | 2022-03-21 00:00:00.0000000 +00:00 |  | 2022-03-21 00:00:00.0000000 +00:00 |  |  | 2017-10-11 10:32:02.4478799 -04:00
LNCA15RSD | Y | 2014-12-15 00:00:00.0000000 +00:00 | 2017-01-10 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2018-09-28 00:00:00.0000000 +00:00 | 2019-07-30 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-04-29 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2015-12-04 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2015-09-01 00:00:00.0000000 +00:00 | 2017-06-08 00:00:00.0000000 +00:00 | 2018-01-02 00:00:00.0000000 +00:00 | 2018-04-26 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 |  |  |  | 2020-02-27 00:00:00.0000000 +00:00 |  | 2014-12-15 00:00:00.0000000 +00:00 |  | 2016-04-04 00:00:00.0000000 +00:00 |  |  | 2017-08-24 00:00:00.0000000 +00:00 | 2017-08-24 00:00:00.0000000 +00:00 | 2017-08-24 00:00:00.0000000 +00:00 |  |  | 2017-08-25 00:00:00.0000000 +00:00 | 2017-08-25 00:00:00.0000000 +00:00 | 2017-08-25 00:00:00.0000000 +00:00 |  | 2018-02-28 00:00:00.0000000 +00:00 |  | 2018-09-28 00:00:00.0000000 +00:00 |  | 2019-07-30 00:00:00.0000000 +00:00 |  | 2018-07-01 00:00:00.0000000 +00:00 | 2021-07-30 00:00:00.0000000 +00:00 |  | 2021-07-30 00:00:00.0000000 +00:00 |  |  | 2017-08-31 10:58:46.3453170 -04:00
LNCA15SPK | Y | 2014-11-17 00:00:00.0000000 +00:00 | 2015-08-29 00:00:00.0000000 +00:00 | 2016-04-30 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2015-08-29 00:00:00.0000000 +00:00 | 2016-04-30 00:00:00.0000000 +00:00 | 2016-10-13 00:00:00.0000000 +00:00 | 2017-03-13 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2015-08-29 00:00:00.0000000 +00:00 | 2016-04-30 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2017-06-27 00:00:00.0000000 +00:00 | 2014-11-17 00:00:00.0000000 +00:00 | 2015-02-12 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2016-05-25 00:00:00.0000000 +00:00 |  | 2015-06-05 00:00:00.0000000 +00:00 | 2017-10-03 00:00:00.0000000 +00:00 | [26 empty] | 2017-10-31 16:51:03.3866561 -04:00
LNCAL15CC | Y | 2014-12-18 00:00:00.0000000 +00:00 | 2016-10-31 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2019-02-09 00:00:00.0000000 +00:00 | 2020-08-09 00:00:00.0000000 +00:00 | 2014-12-18 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2015-11-17 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2017-11-22 00:00:00.0000000 +00:00 | 2014-12-18 00:00:00.0000000 +00:00 | 2016-03-25 00:00:00.0000000 +00:00 | 2017-04-13 00:00:00.0000000 +00:00 | 2017-10-11 00:00:00.0000000 +00:00 | 2019-04-19 00:00:00.0000000 +00:00 | 2014-12-18 00:00:00.0000000 +00:00 | 2016-10-31 17:00:00.0000000 +00:00 |  |  |  | 2018-11-14 00:00:00.0000000 +00:00 |  | 2014-12-18 00:00:00.0000000 +00:00 |  | 2016-10-31 17:00:00.0000000 +00:00 |  | 2015-07-05 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 |  | 2017-12-29 00:00:00.0000000 +00:00 |  | 2015-08-05 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 |  | 2018-02-15 00:00:00.0000000 +00:00 |  | 2018-07-15 00:00:00.0000000 +00:00 |  | 2019-02-09 00:00:00.0000000 +00:00 |  | 2020-08-09 00:00:00.0000000 +00:00 |  | 2019-11-22 00:00:00.0000000 +00:00 | 2022-08-09 00:00:00.0000000 +00:00 |  | 2022-08-09 00:00:00.0000000 +00:00
LNCAL15CP | Y | 2014-12-31 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2017-12-20 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2016-08-31 00:00:00.0000000 +00:00 | 2017-05-20 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2016-02-07 00:00:00.0000000 +00:00 | 2018-03-11 00:00:00.0000000 +00:00 | 2018-10-25 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2017-06-08 17:00:00.0000000 +00:00 |  | 2015-02-14 00:00:00.0000000 +00:00 | 2017-11-29 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 |  | 2015-06-05 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 |  | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2015-08-04 00:00:00.0000000 +00:00 | 2017-06-08 00:00:00.0000000 +00:00 | 2017-06-08 00:00:00.0000000 +00:00 |  |  | 2019-05-20 00:00:00.0000000 +00:00 | 2019-12-14 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-31 16:36:53.4876588 -04:00
LNCAL15TV | Y | 2014-12-12 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-09-01 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2014-11-26 00:00:00.0000000 +00:00 | 2015-08-02 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2016-06-20 00:00:00.0000000 +00:00 | 2017-03-29 00:00:00.0000000 +00:00 | 2014-11-26 00:00:00.0000000 +00:00 | 2015-08-02 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2016-09-22 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | 2014-12-04 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 |  |  |  | 2018-01-15 00:00:00.0000000 +00:00 |  | 2014-12-04 00:00:00.0000000 +00:00 |  | 2015-06-24 00:00:00.0000000 +00:00 |  | 2015-09-02 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 |  | 2015-10-02 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2018-08-01 00:00:00.0000000 +00:00 |  | 2019-07-01 00:00:00.0000000 +00:00 |  | 2019-03-29 00:00:00.0000000 +00:00 | 2021-07-01 00:00:00.0000000 +00:00 |  | 2021-07-01 00:00:00.0000000 +00:00 |  |  | 2017-12-04 11:04:14.6033287 -05:00
LNCEA08GC | Y | 2008-01-25 00:00:00.0000000 +00:00 | 2009-12-29 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2017-02-16 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2008-01-25 00:00:00.0000000 +00:00 | 2008-12-06 00:00:00.0000000 +00:00 | 2009-06-10 00:00:00.0000000 +00:00 | 2009-09-11 00:00:00.0000000 +00:00 | 2010-06-10 00:00:00.0000000 +00:00 | 2008-01-25 00:00:00.0000000 +00:00 | 2010-01-21 00:00:00.0000000 +00:00 | 2011-08-16 00:00:00.0000000 +00:00 | 2015-12-29 00:00:00.0000000 +00:00 | 2017-09-14 00:00:00.0000000 +00:00 | 2008-01-25 00:00:00.0000000 +00:00 | 2009-12-29 00:00:00.0000000 +00:00 |  |  |  | 2011-08-16 00:00:00.0000000 +00:00 | 2016-08-16 00:00:00.0000000 +00:00 | [26 empty] | 2017-08-31 15:46:50.4289445 -04:00
LNCEA08GC1 | Y | 2008-01-25 00:00:00.0000000 +00:00 | 2009-12-29 00:00:00.0000000 +00:00 | 2010-12-12 00:00:00.0000000 +00:00 | 2013-06-18 00:00:00.0000000 +00:00 | 2015-02-09 00:00:00.0000000 +00:00 | 2008-01-25 00:00:00.0000000 +00:00 | 2009-12-29 00:00:00.0000000 +00:00 | 2010-07-26 00:00:00.0000000 +00:00 | 2010-10-27 00:00:00.0000000 +00:00 | 2011-10-26 00:00:00.0000000 +00:00 | 2008-01-25 00:00:00.0000000 +00:00 | 2009-12-29 00:00:00.0000000 +00:00 | 2010-12-14 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2008-01-25 00:00:00.0000000 +00:00 | 2009-12-29 00:00:00.0000000 +00:00 | 2010-12-12 00:00:00.0000000 +00:00 | 2013-06-18 00:00:00.0000000 +00:00 | 2015-02-09 00:00:00.0000000 +00:00 | 2010-12-14 00:00:00.0000000 +00:00 | 2015-01-24 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-05 17:15:08.0098040 -05:00
LNCL15CAS | Y | 2014-12-04 00:00:00.0000000 +00:00 | 2016-04-22 00:00:00.0000000 +00:00 | 2018-09-01 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2020-07-01 00:00:00.0000000 +00:00 | 2014-12-04 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 | 2015-12-05 00:00:00.0000000 +00:00 | 2016-03-22 00:00:00.0000000 +00:00 | 2017-12-03 00:00:00.0000000 +00:00 | 2014-12-04 00:00:00.0000000 +00:00 | 2015-03-27 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | 2018-06-18 00:00:00.0000000 +00:00 | 2019-04-04 00:00:00.0000000 +00:00 | 2014-12-04 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 |  |  |  | 2018-08-01 00:00:00.0000000 +00:00 |  | 2014-12-04 00:00:00.0000000 +00:00 |  | 2015-05-04 00:00:00.0000000 +00:00 |  | 2015-06-27 00:00:00.0000000 +00:00 | 2017-02-03 00:00:00.0000000 +00:00 | 2017-02-03 00:00:00.0000000 +00:00 | 2017-02-03 00:00:00.0000000 +00:00 |  | 2015-09-28 00:00:00.0000000 +00:00 | [10 empty] | 2019-12-03 00:00:00.0000000 +00:00 | 2022-07-01 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 11:08:13.6394053 -04:00
LNCM10DCH | Y | 2010-09-02 00:00:00.0000000 +00:00 | 2011-03-01 00:00:00.0000000 +00:00 | 2011-05-27 00:00:00.0000000 +00:00 | 2012-05-10 00:00:00.0000000 +00:00 | 2015-05-11 00:00:00.0000000 +00:00 | 2010-09-02 00:00:00.0000000 +00:00 | 2011-03-01 00:00:00.0000000 +00:00 | 2011-05-27 00:00:00.0000000 +00:00 | 2011-11-08 00:00:00.0000000 +00:00 | 2014-11-08 00:00:00.0000000 +00:00 | 2010-09-02 00:00:00.0000000 +00:00 | 2011-05-27 00:00:00.0000000 +00:00 | 2011-03-01 00:00:00.0000000 +00:00 | 2012-05-10 00:00:00.0000000 +00:00 | 2015-05-11 00:00:00.0000000 +00:00 | 2010-09-02 00:00:00.0000000 +00:00 | 2011-03-01 00:00:00.0000000 +00:00 | 2011-05-27 00:00:00.0000000 +00:00 | 2012-05-10 00:00:00.0000000 +00:00 | 2015-05-11 00:00:00.0000000 +00:00 | 2011-05-27 00:00:00.0000000 +00:00 | 2015-05-11 00:00:00.0000000 +00:00
LNCM10WCH | Y | 2011-12-02 00:00:00.0000000 +00:00 | 2013-05-11 00:00:00.0000000 +00:00 | 2018-02-09 00:00:00.0000000 +00:00 | 2018-10-19 00:00:00.0000000 +00:00 | 2021-06-07 00:00:00.0000000 +00:00 | 2011-12-02 00:00:00.0000000 +00:00 | 2013-05-15 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 | 2015-06-11 00:00:00.0000000 +00:00 | 2017-05-31 00:00:00.0000000 +00:00 | 2011-12-02 00:00:00.0000000 +00:00 | 2013-05-15 00:00:00.0000000 +00:00 | 2017-07-07 00:00:00.0000000 +00:00 | 2018-06-23 00:00:00.0000000 +00:00 | 2020-06-12 00:00:00.0000000 +00:00 | 2011-12-02 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 |  |  |  | 2018-02-09 00:00:00.0000000 +00:00 |  | 2011-12-02 00:00:00.0000000 +00:00 |  | 2013-05-13 00:00:00.0000000 +00:00 |  |  |  | 2014-06-13 00:00:00.0000000 +00:00 | 2014-06-13 00:00:00.0000000 +00:00 |  |  |  | 2016-11-25 00:00:00.0000000 +00:00 | 2016-11-25 00:00:00.0000000 +00:00 |  | 2018-02-09 00:00:00.0000000 +00:00 |  | 2019-01-18 00:00:00.0000000 +00:00 |  | 2021-06-07 00:00:00.0000000 +00:00 |  | 2019-05-31 00:00:00.0000000 +00:00 | 2022-02-11 00:00:00.0000000 +00:00 |  | 2022-02-11 00:00:00.0000000 +00:00 |  |  | 2017-12-05 12:05:01.7644088 -05:00
LNCM10WCH1 | Y | 2013-10-01 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 |  |  |  | 2013-10-01 00:00:00.0000000 +00:00 | 2014-04-06 00:00:00.0000000 +00:00 | 2016-03-26 00:00:00.0000000 +00:00 | 2016-03-26 00:00:00.0000000 +00:00 | 2016-05-25 00:00:00.0000000 +00:00 | 2013-10-01 00:00:00.0000000 +00:00 | 2014-05-20 00:00:00.0000000 +00:00 | 2017-12-13 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2017-11-05 00:00:00.0000000 +00:00 | 2013-10-01 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2016-06-21 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2016-10-11 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 | 2016-11-16 00:00:00.0000000 +00:00 | 2013-10-01 00:00:00.0000000 +00:00 |  | 2014-05-19 00:00:00.0000000 +00:00 |  |  |  | 2015-05-08 00:00:00.0000000 +00:00 | 2015-05-08 00:00:00.0000000 +00:00 |  |  |  | 2015-12-11 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 |  | 2016-05-08 00:00:00.0000000 +00:00 |  | 2016-07-22 00:00:00.0000000 +00:00 |  | 2016-12-12 00:00:00.0000000 +00:00 |  |  |  | 2016-12-12 00:00:00.0000000 +00:00 | 2016-12-12 00:00:00.0000000 +00:00 |  |  | 2017-11-29 15:04:02.2357704 -05:00
LNCM12CPT | Y | 2014-07-07 00:00:00.0000000 +00:00 | 2015-12-26 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-06-18 00:00:00.0000000 +00:00 | 2019-04-18 00:00:00.0000000 +00:00 | 2014-07-07 00:00:00.0000000 +00:00 | 2015-04-22 00:00:00.0000000 +00:00 | 2016-12-28 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 | 2017-12-18 00:00:00.0000000 +00:00 | 2014-07-07 00:00:00.0000000 +00:00 | 2015-04-22 00:00:00.0000000 +00:00 | 2016-01-19 00:00:00.0000000 +00:00 | 2016-05-19 00:00:00.0000000 +00:00 | 2017-01-29 00:00:00.0000000 +00:00 | 2014-07-07 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 |  |  | 2017-05-24 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-30 00:00:00.0000000 +00:00 | 2016-06-16 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 |  |  | 2016-03-25 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2017-01-27 00:00:00.0000000 +00:00 | [8 empty] | 2018-12-17 00:00:00.0000000 +00:00 | 2021-02-18 00:00:00.0000000 +00:00
LNCM12NDP | Y | 2014-06-19 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2016-10-12 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2017-11-20 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2016-05-05 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2015-05-23 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2016-12-27 00:00:00.0000000 +00:00 | 2017-04-18 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2016-10-12 00:00:00.0000000 +00:00 | 2017-06-05 17:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 |  |  | 2014-06-19 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2015-01-16 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-02-03 00:00:00.0000000 +00:00 | 2016-10-12 00:00:00.0000000 +00:00 | 2016-10-12 00:00:00.0000000 +00:00 | 2017-06-05 00:00:00.0000000 +00:00 | 2017-06-05 17:00:00.0000000 +00:00 | 2017-11-20 00:00:00.0000000 +00:00 | 2017-11-20 00:00:00.0000000 +00:00 | 2018-05-05 00:00:00.0000000 +00:00 | 2019-11-20 00:00:00.0000000 +00:00 |  | 2019-11-20 00:00:00.0000000 +00:00 | 2019-11-20 00:00:00.0000000 +00:00 |  | 2017-11-27 11:59:30.0854446 -05:00
LNDSVRENO | Y | 2005-11-03 00:00:00.0000000 +00:00 | 2007-09-06 00:00:00.0000000 +00:00 | 2008-06-27 00:00:00.0000000 +00:00 | 2012-07-10 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | 2005-11-03 00:00:00.0000000 +00:00 | 2006-08-03 00:00:00.0000000 +00:00 | 2007-06-03 00:00:00.0000000 +00:00 | 2007-11-03 00:00:00.0000000 +00:00 | 2008-08-03 00:00:00.0000000 +00:00 | 2005-11-03 00:00:00.0000000 +00:00 | 2007-09-06 00:00:00.0000000 +00:00 | 2008-06-27 00:00:00.0000000 +00:00 | 2010-03-04 00:00:00.0000000 +00:00 | 2013-03-03 00:00:00.0000000 +00:00 | 2005-11-03 00:00:00.0000000 +00:00 | 2007-09-06 00:00:00.0000000 +00:00 |  | 2012-07-10 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2008-06-27 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-05 17:10:52.9593883 -05:00
LNEA08MHV1 | Y | 2009-10-20 00:00:00.0000000 +00:00 | 2009-10-22 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2012-05-29 00:00:00.0000000 +00:00 | 2013-08-23 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2012-05-29 00:00:00.0000000 +00:00 | 2013-07-16 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2012-05-29 00:00:00.0000000 +00:00 | 2013-08-23 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2009-10-22 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2012-05-29 00:00:00.0000000 +00:00 | 2013-09-09 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2013-08-23 00:00:00.0000000 +00:00
LNEA08MHV2 | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2013-07-24 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2013-07-24 00:00:00.0000000 +00:00 | 2013-10-28 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2013-07-24 00:00:00.0000000 +00:00 | 2014-07-11 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2013-07-24 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-06 09:25:24.9594184 -05:00
LNEA08MHV3 | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2018-10-30 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2014-01-18 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-01-29 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2017-08-29 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 |  |  |  | 2015-06-27 00:00:00.0000000 +00:00 | [5 empty] | 2009-10-20 00:00:00.0000000 +00:00 | 2010-03-15 00:00:00.0000000 +00:00 | 2010-03-15 00:00:00.0000000 +00:00 |  |  | 2010-03-16 00:00:00.0000000 +00:00 | 2010-08-19 00:00:00.0000000 +00:00 | 2010-08-19 00:00:00.0000000 +00:00 | [8 empty] | 2016-01-18 00:00:00.0000000 +00:00 | 2020-10-30 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 11:19:28.4706128 -04:00
LNEA13HGR | Y | 2013-05-20 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2019-04-15 00:00:00.0000000 +00:00 | 2020-04-15 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2013-12-13 00:00:00.0000000 +00:00 | 2014-12-12 00:00:00.0000000 +00:00 | 2015-07-17 00:00:00.0000000 +00:00 | 2016-08-11 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2014-06-15 00:00:00.0000000 +00:00 | 2017-07-13 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2019-03-13 00:00:00.0000000 +00:00 | 2013-03-18 00:00:00.0000000 +00:00 | 2014-05-12 00:00:00.0000000 +00:00 |  |  |  | 2019-07-09 00:00:00.0000000 +00:00 |  | 2013-03-18 00:00:00.0000000 +00:00 |  | 2014-05-12 00:00:00.0000000 +00:00 |  |  | 2014-09-22 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 |  |  | 2018-01-29 00:00:00.0000000 +00:00 |  | 2018-01-29 00:00:00.0000000 +00:00 |  | 2018-07-15 00:00:00.0000000 +00:00 |  | 2019-04-15 00:00:00.0000000 +00:00 |  | 2020-04-15 00:00:00.0000000 +00:00 |  | 2018-08-11 00:00:00.0000000 +00:00 | 2022-05-18 00:00:00.0000000 +00:00 |  | 2022-05-18 00:00:00.0000000 +00:00 |  |  | 2017-08-31 11:21:14.7743460 -04:00
LNEA13MAC | Y | 2013-05-30 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2016-07-04 00:00:00.0000000 +00:00 | 2017-08-12 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2015-03-21 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2017-01-14 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2016-12-31 00:00:00.0000000 +00:00 | 2018-02-08 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 |  |  | 2015-03-11 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-07 16:45:24.2729218 -04:00
LNEA13MHU | Y | 2013-02-11 00:00:00.0000000 +00:00 | 2016-05-29 00:00:00.0000000 +00:00 | 2018-01-19 00:00:00.0000000 +00:00 | 2018-09-17 00:00:00.0000000 +00:00 | 2019-08-19 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2013-05-13 00:00:00.0000000 +00:00 | 2013-07-23 00:00:00.0000000 +00:00 | 2013-12-21 00:00:00.0000000 +00:00 | 2014-07-10 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2016-05-13 00:00:00.0000000 +00:00 | 2016-10-22 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2014-11-20 00:00:00.0000000 +00:00 |  |  |  | 2016-09-03 00:00:00.0000000 +00:00 | [21 empty] | 2016-07-09 00:00:00.0000000 +00:00 | 2021-08-18 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-02 10:34:23.4530509 -04:00
LNEA13STG | Y | 2013-02-04 00:00:00.0000000 +00:00 | 2016-01-06 00:00:00.0000000 +00:00 | 2018-01-12 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2020-01-30 00:00:00.0000000 +00:00 | 2013-02-04 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 | 2014-09-13 00:00:00.0000000 +00:00 | 2015-01-27 00:00:00.0000000 +00:00 | 2016-07-07 00:00:00.0000000 +00:00 | 2013-02-04 00:00:00.0000000 +00:00 | 2015-05-21 00:00:00.0000000 +00:00 | 2016-10-30 00:00:00.0000000 +00:00 | 2017-10-29 00:00:00.0000000 +00:00 | 2019-09-25 00:00:00.0000000 +00:00 | 2013-02-04 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 |  |  |  | 2018-08-28 00:00:00.0000000 +00:00 |  | 2013-02-24 00:00:00.0000000 +00:00 |  | 2016-01-28 00:00:00.0000000 +00:00 |  |  | 2016-11-01 00:00:00.0000000 +00:00 | 2016-11-01 00:00:00.0000000 +00:00 | 2016-11-01 00:00:00.0000000 +00:00 |  |  | 2017-06-07 00:00:00.0000000 +00:00 | 2017-06-07 00:00:00.0000000 +00:00 | 2017-06-07 00:00:00.0000000 +00:00 |  | 2018-01-12 00:00:00.0000000 +00:00 |  | 2018-07-30 00:00:00.0000000 +00:00 |  | 2020-01-30 00:00:00.0000000 +00:00 |  | 2021-06-06 00:00:00.0000000 +00:00 | 2021-05-11 00:00:00.0000000 +00:00 |  | 2021-05-11 00:00:00.0000000 +00:00 |  |  | 2017-12-04 16:43:29.9661541 -05:00
LNEA13TNK | Y | 2013-02-04 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 | 2018-01-19 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 | 2019-04-15 00:00:00.0000000 +00:00 | 2013-02-04 00:00:00.0000000 +00:00 | 2014-01-03 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-04-14 00:00:00.0000000 +00:00 | 2016-02-06 00:00:00.0000000 +00:00 | 2013-02-04 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2016-12-08 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2019-03-29 00:00:00.0000000 +00:00 | 2013-02-04 00:00:00.0000000 +00:00 | 2015-09-21 00:00:00.0000000 +00:00 |  |  |  | 2017-12-28 00:00:00.0000000 +00:00 |  | 2013-02-04 00:00:00.0000000 +00:00 |  | 2015-09-21 00:00:00.0000000 +00:00 |  |  | 2016-01-11 00:00:00.0000000 +00:00 | 2016-01-11 00:00:00.0000000 +00:00 | 2016-01-11 00:00:00.0000000 +00:00 |  |  | 2016-05-05 00:00:00.0000000 +00:00 | 2016-05-05 00:00:00.0000000 +00:00 | 2016-05-05 00:00:00.0000000 +00:00 |  | 2018-01-19 00:00:00.0000000 +00:00 |  | 2018-07-30 00:00:00.0000000 +00:00 |  | 2019-04-15 00:00:00.0000000 +00:00 |  | 2018-02-05 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 |  | 2020-01-15 00:00:00.0000000 +00:00 |  |  | 2017-08-31 11:26:26.6414159 -04:00
LNEA14ECH | Y | 2014-07-22 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2014-11-27 00:00:00.0000000 +00:00 | 2016-02-10 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2014-11-27 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2015-12-30 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-04-15 00:00:00.0000000 +00:00 | 2016-08-18 00:00:00.0000000 +00:00 | 2017-08-08 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2014-11-27 00:00:00.0000000 +00:00 | 2016-02-10 00:00:00.0000000 +00:00 | 2016-10-08 00:00:00.0000000 +00:00 | [28 empty] | 2017-11-30 10:52:45.3689639 -05:00
LNEA14RTW | Y | 2014-09-22 00:00:00.0000000 +00:00 | 2015-01-16 00:00:00.0000000 +00:00 | 2015-03-16 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2016-12-01 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-01-08 00:00:00.0000000 +00:00 | 2015-03-22 00:00:00.0000000 +00:00 | 2015-10-04 00:00:00.0000000 +00:00 | 2016-07-06 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-01-08 00:00:00.0000000 +00:00 | 2015-03-22 00:00:00.0000000 +00:00 | 2015-11-03 00:00:00.0000000 +00:00 | 2016-08-05 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-01-16 00:00:00.0000000 +00:00 | 2015-03-16 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2016-11-17 00:00:00.0000000 +00:00 | 2015-03-22 00:00:00.0000000 +00:00 | 2016-12-01 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-01-16 00:00:00.0000000 +00:00 | 2015-01-16 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-02-05 00:00:00.0000000 +00:00 | 2015-03-16 00:00:00.0000000 +00:00 | 2015-03-16 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2016-12-01 00:00:00.0000000 +00:00 | 2016-11-17 00:00:00.0000000 +00:00 | 2018-07-06 00:00:00.0000000 +00:00 | 2018-12-01 00:00:00.0000000 +00:00 |  | 2018-12-01 00:00:00.0000000 +00:00 | 2018-12-01 00:00:00.0000000 +00:00 |  | 2017-11-27 12:27:35.4762756 -05:00
LNEA14VNT | Y | 2014-09-22 00:00:00.0000000 +00:00 | 2015-11-15 00:00:00.0000000 +00:00 | 2018-07-15 00:00:00.0000000 +00:00 | 2019-03-15 00:00:00.0000000 +00:00 | 2020-03-15 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-06-10 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-04-28 00:00:00.0000000 +00:00 | 2017-02-04 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-06-10 00:00:00.0000000 +00:00 | 2016-09-22 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2018-02-07 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-08-28 00:00:00.0000000 +00:00 |  |  |  | 2019-06-19 00:00:00.0000000 +00:00 | [21 empty] | 2019-02-04 00:00:00.0000000 +00:00 | 2021-03-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 11:27:49.2018100 -04:00
LNEAL15RT | Y | 2014-12-09 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-09-01 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2014-11-26 00:00:00.0000000 +00:00 | 2015-08-01 00:00:00.0000000 +00:00 | 2015-12-06 00:00:00.0000000 +00:00 | 2016-06-19 00:00:00.0000000 +00:00 | 2017-03-28 00:00:00.0000000 +00:00 | 2014-11-26 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2017-07-12 00:00:00.0000000 +00:00 | 2018-01-02 00:00:00.0000000 +00:00 | 2018-10-11 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 |  |  |  | 2018-01-15 00:00:00.0000000 +00:00 |  | 2014-12-09 00:00:00.0000000 +00:00 |  | 2015-06-24 00:00:00.0000000 +00:00 |  | 2015-09-01 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 |  | 2015-10-01 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 |  | 2017-12-01 00:00:00.0000000 +00:00 |  | 2018-07-01 00:00:00.0000000 +00:00 |  | 2019-07-01 00:00:00.0000000 +00:00 |  | 2019-03-28 00:00:00.0000000 +00:00 | 2021-07-01 00:00:00.0000000 +00:00 |  | 2021-07-01 00:00:00.0000000 +00:00 |  |  | 2017-09-19 10:55:53.7124396 -04:00
LNEM08AGL | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-28 00:00:00.0000000 +00:00 | 2012-03-16 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-03-19 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-28 00:00:00.0000000 +00:00 | 2012-03-16 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2012-03-16 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00
LNEM08CLB | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-03-19 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00
LNEM08EPH | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-11-26 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-11-26 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-11-26 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2013-11-26 00:00:00.0000000 +00:00
LNEM08HUD | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-03-19 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2014-06-29 00:00:00.0000000 +00:00
LNEM12MLB | Y | 2012-02-01 00:00:00.0000000 +00:00 | 2013-07-13 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2012-02-01 00:00:00.0000000 +00:00 | 2013-02-01 00:00:00.0000000 +00:00 | 2013-11-01 00:00:00.0000000 +00:00 | 2014-06-15 00:00:00.0000000 +00:00 | 2015-03-15 00:00:00.0000000 +00:00 | 2012-02-01 00:00:00.0000000 +00:00 | 2013-04-23 00:00:00.0000000 +00:00 | 2015-01-10 00:00:00.0000000 +00:00 | 2017-06-25 00:00:00.0000000 +00:00 | 2018-06-22 00:00:00.0000000 +00:00 | 2012-02-01 00:00:00.0000000 +00:00 | 2013-04-23 00:00:00.0000000 +00:00 | 2015-04-21 00:00:00.0000000 +00:00 |  |  | 2015-03-29 00:00:00.0000000 +00:00 |  | 2012-02-01 00:00:00.0000000 +00:00 |  | 2013-04-23 00:00:00.0000000 +00:00 |  | 2013-04-01 00:00:00.0000000 +00:00 | 2014-12-06 00:00:00.0000000 +00:00 | 2014-12-06 00:00:00.0000000 +00:00 | 2014-12-06 00:00:00.0000000 +00:00 |  | 2013-06-01 00:00:00.0000000 +00:00 | 2014-12-06 00:00:00.0000000 +00:00 | 2014-12-06 00:00:00.0000000 +00:00 | 2014-12-06 00:00:00.0000000 +00:00 |  | 2015-04-21 00:00:00.0000000 +00:00 |  | 2018-09-15 00:00:00.0000000 +00:00 |  | 2019-09-15 00:00:00.0000000 +00:00 |  | 2017-03-15 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 |  | 2021-09-15 00:00:00.0000000 +00:00
LNEM13ALL | Y | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-03-24 00:00:00.0000000 +00:00 | 2015-03-20 00:00:00.0000000 +00:00 | 2015-12-06 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 |  | 2015-11-20 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-29 09:38:23.2715539 -05:00
LNEM13EDW | Y | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-07-30 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2015-03-21 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2017-01-14 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-05-24 00:00:00.0000000 +00:00 | 2017-01-03 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2015-11-20 00:00:00.0000000 +00:00 | 2017-02-07 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-05 16:55:54.1201986 -05:00
LNEM13JMK | Y | 2013-05-30 00:00:00.0000000 +00:00 | 2015-09-20 00:00:00.0000000 +00:00 | 2016-10-07 00:00:00.0000000 +00:00 | 2017-11-06 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2015-03-21 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2017-01-14 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2015-12-29 00:00:00.0000000 +00:00 | 2016-12-27 00:00:00.0000000 +00:00 | 2018-03-23 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2015-12-29 00:00:00.0000000 +00:00 |  |  | 2016-01-09 00:00:00.0000000 +00:00 | 2018-07-26 00:00:00.0000000 +00:00 | [20 empty] | 2019-01-14 00:00:00.0000000 +00:00 | 2019-03-26 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-31 16:39:00.0037199 -04:00
LNEM13MSH | Y | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-05-25 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2015-03-21 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2017-01-14 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-04-18 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-05-25 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2017-02-07 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-29 12:28:50.5450832 -05:00
LNEM13SPV | Y | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-27 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-07-12 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2015-03-21 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2017-01-14 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-27 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-04-24 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2015-12-27 00:00:00.0000000 +00:00 | 2017-02-13 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-29 12:33:24.8475034 -05:00
LNEM13VNE | Y | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2015-03-21 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2017-01-14 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2016-09-06 00:00:00.0000000 +00:00 | 2017-07-18 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2015-12-19 00:00:00.0000000 +00:00 | 2017-05-09 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-05 17:14:26.5532927 -05:00
LNEM14HUG | Y | 2014-09-01 00:00:00.0000000 +00:00 | 2014-10-23 00:00:00.0000000 +00:00 | 2014-12-11 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2017-02-06 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-11-08 00:00:00.0000000 +00:00 | 2015-08-05 00:00:00.0000000 +00:00 | 2016-02-25 00:00:00.0000000 +00:00 | 2016-07-31 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-11-08 00:00:00.0000000 +00:00 | 2015-08-05 00:00:00.0000000 +00:00 | 2016-05-12 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-10-23 00:00:00.0000000 +00:00 | 2014-12-11 00:00:00.0000000 +00:00 | 2016-01-07 00:00:00.0000000 +00:00 | 2016-10-27 00:00:00.0000000 +00:00 | 2015-07-20 00:00:00.0000000 +00:00 | 2016-10-09 00:00:00.0000000 +00:00
LNEM14JPK | Y | 2014-09-01 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2015-01-20 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 | 2015-06-06 00:00:00.0000000 +00:00 | 2015-12-27 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 | 2015-06-06 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2016-07-20 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2015-01-20 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2016-11-16 00:00:00.0000000 +00:00 | 2015-06-06 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00
LNEM14NDP | Y | 2014-09-15 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2017-06-12 00:00:00.0000000 +00:00 | 2017-12-19 00:00:00.0000000 +00:00 | 2018-07-13 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-12-24 00:00:00.0000000 +00:00 | 2016-07-30 00:00:00.0000000 +00:00 | 2017-07-31 00:00:00.0000000 +00:00 | 2014-09-15 00:00:00.0000000 +00:00 | 2015-06-03 00:00:00.0000000 +00:00 | 2017-08-27 00:00:00.0000000 +00:00 | 2018-06-19 00:00:00.0000000 +00:00 | 2018-04-22 00:00:00.0000000 +00:00 | 2014-09-15 12:00:00.0000000 +00:00 | 2015-06-25 12:00:00.0000000 +00:00 | 2017-06-12 00:00:00.0000000 +00:00 |  |  | 2022-05-16 00:00:00.0000000 +00:00 |  | 2014-09-15 12:00:00.0000000 +00:00 |  | 2015-06-25 12:00:00.0000000 +00:00 |  | 2014-12-30 00:00:00.0000000 +00:00 | 2015-09-02 00:00:00.0000000 +00:00 | 2015-09-02 00:00:00.0000000 +00:00 | 2015-09-02 00:00:00.0000000 +00:00 |  | 2015-06-25 00:00:00.0000000 +00:00 | 2016-10-26 00:00:00.0000000 +00:00 | 2016-10-26 00:00:00.0000000 +00:00 | 2016-10-26 00:00:00.0000000 +00:00 |  | 2017-06-12 00:00:00.0000000 +00:00 |  | 2017-12-09 00:00:00.0000000 +00:00 |  | 2018-07-13 00:00:00.0000000 +00:00 |  | 2019-07-31 00:00:00.0000000 +00:00 | 2020-07-13 00:00:00.0000000 +00:00 |  | 2020-07-13 00:00:00.0000000 +00:00 |  |  | 2017-08-31 11:43:20.9615038 -04:00
LNEM14WKF | Y | 2014-06-03 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2015-08-11 00:00:00.0000000 +00:00 | 2016-05-05 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2014-06-03 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2015-11-27 00:00:00.0000000 +00:00 | 2016-04-25 00:00:00.0000000 +00:00 | 2016-09-23 00:00:00.0000000 +00:00 | 2014-06-03 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2016-06-25 00:00:00.0000000 +00:00 | 2017-10-20 00:00:00.0000000 +00:00 | 2014-06-03 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2015-12-10 00:00:00.0000000 +00:00 | 2016-06-11 00:00:00.0000000 +00:00 |  | 2015-08-12 00:00:00.0000000 +00:00 | 2017-10-14 00:00:00.0000000 +00:00 | 2014-06-03 00:00:00.0000000 +00:00 | 2014-06-03 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | 2015-05-04 00:00:00.0000000 +00:00 | [10 empty] | 2015-12-10 00:00:00.0000000 +00:00 | 2015-12-10 00:00:00.0000000 +00:00 | 2016-06-11 00:00:00.0000000 +00:00 | 2016-06-11 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-12-29 00:00:00.0000000 +00:00 |  | 2018-12-29 00:00:00.0000000 +00:00 | 2018-12-29 00:00:00.0000000 +00:00
LNEM15PCH | Y | 2014-11-19 00:00:00.0000000 +00:00 | 2015-04-16 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2017-03-30 00:00:00.0000000 +00:00 | 2014-11-19 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2016-03-20 00:00:00.0000000 +00:00 | 2016-10-16 00:00:00.0000000 +00:00 | 2014-11-19 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2016-09-07 00:00:00.0000000 +00:00 | 2017-06-26 00:00:00.0000000 +00:00 | 2014-11-19 00:00:00.0000000 +00:00 | 2015-04-16 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2017-02-10 00:00:00.0000000 +00:00 | 2015-09-26 00:00:00.0000000 +00:00 | 2017-02-02 00:00:00.0000000 +00:00
LNEM15RVD | Y | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2017-05-07 00:00:00.0000000 +00:00 | 2018-03-07 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2015-11-01 00:00:00.0000000 +00:00 | 2017-03-01 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2017-01-02 17:00:00.0000000 +00:00 | 2017-05-26 17:00:00.0000000 +00:00 | 2015-08-21 00:00:00.0000000 +00:00 | 2017-03-24 00:00:00.0000000 +00:00 | [20 empty] | 2019-03-01 00:00:00.0000000 +00:00 | 2020-03-06 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-29 12:31:52.7165481 -05:00
LNEMA08WS | Y | 2009-02-25 00:00:00.0000000 +00:00 | 2009-09-23 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2014-06-09 00:00:00.0000000 +00:00 | 2017-02-02 00:00:00.0000000 +00:00 | 2009-02-25 00:00:00.0000000 +00:00 | 2009-09-11 00:00:00.0000000 +00:00 | 2010-07-18 00:00:00.0000000 +00:00 | 2011-01-30 00:00:00.0000000 +00:00 | 2012-05-30 00:00:00.0000000 +00:00 | 2009-02-25 00:00:00.0000000 +00:00 | 2009-09-11 00:00:00.0000000 +00:00 | 2012-09-07 00:00:00.0000000 +00:00 | 2013-11-20 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2009-02-25 00:00:00.0000000 +00:00 | 2009-09-23 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2014-06-09 00:00:00.0000000 +00:00 | 2017-03-17 00:00:00.0000000 +00:00 | 2012-11-01 00:00:00.0000000 +00:00 | 2013-02-23 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-05 17:16:50.2531260 -05:00
LNMA12TOT | Y | 2012-01-26 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2016-04-17 00:00:00.0000000 +00:00 | 2016-10-16 00:00:00.0000000 +00:00 | 2017-03-19 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2013-02-09 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2014-05-06 00:00:00.0000000 +00:00 | 2014-09-25 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2016-04-17 00:00:00.0000000 +00:00 | 2016-10-16 00:00:00.0000000 +00:00 | 2017-03-19 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2015-04-17 00:00:00.0000000 +00:00 | 2016-04-27 00:00:00.0000000 +00:00 | 2016-12-20 00:00:00.0000000 +00:00 | 2016-04-17 00:00:00.0000000 +00:00 | 2016-12-20 00:00:00.0000000 +00:00 | [21 empty] | 2017-12-31 00:00:00.0000000 +00:00 |  |  |  |  | 2017-12-12 10:09:43.6693995 -05:00
LNMA12WAS | Y | 2013-02-13 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2013-02-13 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-08-20 00:00:00.0000000 +00:00 | 2016-07-19 00:00:00.0000000 +00:00 | 2013-02-13 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2013-02-13 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2013-02-26 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 |  | 2016-11-07 00:00:00.0000000 +00:00
LNMNA08LS | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2008-12-15 00:00:00.0000000 +00:00 | 2009-07-04 00:00:00.0000000 +00:00 | 2009-11-08 00:00:00.0000000 +00:00 | 2011-04-25 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-05-04 00:00:00.0000000 +00:00 | 2016-12-19 00:00:00.0000000 +00:00 | 2016-12-21 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2014-08-15 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2015-05-30 00:00:00.0000000 +00:00 | [26 empty] | 2017-08-31 16:32:35.7424402 -04:00
LNMNA08LS1 | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-01-08 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-01-08 00:00:00.0000000 +00:00 | 2015-08-08 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2013-01-08 00:00:00.0000000 +00:00 | 2015-05-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00
LNMNA08LS5 | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2014-07-19 00:00:00.0000000 +00:00 | 2017-04-25 00:00:00.0000000 +00:00 | 2018-01-06 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-06-01 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2016-03-25 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2014-07-19 00:00:00.0000000 +00:00 | 2017-04-06 17:00:00.0000000 +00:00 |  | 2014-08-18 00:00:00.0000000 +00:00 | 2018-01-06 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2010-06-25 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2014-07-19 00:00:00.0000000 +00:00 | 2014-07-19 00:00:00.0000000 +00:00 | 2017-04-06 00:00:00.0000000 +00:00 | 2017-04-06 00:00:00.0000000 +00:00 | 2018-01-06 00:00:00.0000000 +00:00 | 2018-01-06 00:00:00.0000000 +00:00 | 2015-11-22 00:00:00.0000000 +00:00 | 2019-01-06 00:00:00.0000000 +00:00 |  | 2019-01-06 00:00:00.0000000 +00:00 | 2019-01-06 00:00:00.0000000 +00:00 |  | 2017-10-27 13:21:13.4527104 -04:00
LNMNA08LS6 | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2016-07-08 00:00:00.0000000 +00:00 | 2017-02-08 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-12 00:00:00.0000000 +00:00 | 2013-06-07 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2014-09-27 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2015-08-18 00:00:00.0000000 +00:00 | 2017-02-08 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-05 17:14:41.6845745 -05:00
LNMNA08LS7 | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-01-03 00:00:00.0000000 +00:00 | 2017-06-07 00:00:00.0000000 +00:00 | 2018-03-07 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2017-01-04 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-01-03 00:00:00.0000000 +00:00 | 2017-06-07 17:00:00.0000000 +00:00 |  | 2013-01-15 00:00:00.0000000 +00:00 | 2018-03-07 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2010-05-21 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2011-05-23 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2013-01-03 00:00:00.0000000 +00:00 | 2013-01-03 00:00:00.0000000 +00:00 | 2017-06-07 00:00:00.0000000 +00:00 | 2017-06-07 00:00:00.0000000 +00:00 | 2018-03-07 00:00:00.0000000 +00:00 | 2018-03-07 00:00:00.0000000 +00:00 | 2015-11-22 00:00:00.0000000 +00:00 | 2019-03-07 00:00:00.0000000 +00:00 |  | 2019-03-07 00:00:00.0000000 +00:00 | 2019-03-07 00:00:00.0000000 +00:00 |  | 2017-08-31 11:50:34.7903997 -04:00
LNMNA08LS8 | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-12-28 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2018-05-22 00:00:00.0000000 +00:00 | 2020-05-17 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 |  |  | 2013-01-15 00:00:00.0000000 +00:00 |  | 2008-01-07 00:00:00.0000000 +00:00 |  | 2009-10-27 00:00:00.0000000 +00:00 |  | 2010-05-24 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 |  | 2011-05-23 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 | 2011-06-24 00:00:00.0000000 +00:00 |  | 2014-12-16 00:00:00.0000000 +00:00 |  | 2018-09-15 00:00:00.0000000 +00:00 |  | 2019-09-15 00:00:00.0000000 +00:00 |  | 2015-11-22 00:00:00.0000000 +00:00 | 2021-09-15 00:00:00.0000000 +00:00 |  | 2021-09-15 00:00:00.0000000 +00:00 |  |  | 2017-08-31 11:52:31.2248497 -04:00
LNMNA08LS9 | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-05-17 00:00:00.0000000 +00:00 | 2016-06-19 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2012-06-07 00:00:00.0000000 +00:00 | 2013-11-22 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2015-05-10 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-27 00:00:00.0000000 +00:00 | 2013-05-17 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2014-04-13 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-29 15:56:25.2723050 -05:00
LNMWHTREA | Y | 2006-09-14 00:00:00.0000000 +00:00 | 2006-09-15 00:00:00.0000000 +00:00 | 2009-02-01 00:00:00.0000000 +00:00 | 2009-12-21 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00 | 2006-09-14 00:00:00.0000000 +00:00 | 2006-09-15 00:00:00.0000000 +00:00 | 2009-02-01 00:00:00.0000000 +00:00 | 2009-09-12 00:00:00.0000000 +00:00 | 2010-09-13 00:00:00.0000000 +00:00 | 2006-09-14 00:00:00.0000000 +00:00 | 2006-09-15 00:00:00.0000000 +00:00 | 2009-02-01 00:00:00.0000000 +00:00 | 2009-12-21 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00 | 2006-09-14 00:00:00.0000000 +00:00 | 2006-09-15 00:00:00.0000000 +00:00 | 2009-02-01 00:00:00.0000000 +00:00 | 2009-12-21 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00 | 2009-04-03 00:00:00.0000000 +00:00 | 2011-12-30 00:00:00.0000000 +00:00
LNRA10STG | Y | 2009-09-25 00:00:00.0000000 +00:00 | 2012-01-20 00:00:00.0000000 +00:00 | 2012-11-09 00:00:00.0000000 +00:00 | 2014-08-08 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2009-09-25 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2011-01-03 00:00:00.0000000 +00:00 | 2011-04-01 00:00:00.0000000 +00:00 | 2011-12-01 00:00:00.0000000 +00:00 | 2009-09-25 00:00:00.0000000 +00:00 | 2012-01-02 00:00:00.0000000 +00:00 | 2012-12-28 00:00:00.0000000 +00:00 | 2014-08-04 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2009-09-25 00:00:00.0000000 +00:00 | 2012-01-20 00:00:00.0000000 +00:00 | 2012-11-09 00:00:00.0000000 +00:00 | 2014-08-08 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-05 17:11:52.6716787 -05:00
LNSIM12LS | Y | 2012-01-26 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2015-04-17 00:00:00.0000000 +00:00 | 2016-03-12 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2013-02-16 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2014-05-13 00:00:00.0000000 +00:00 | 2014-10-02 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2015-04-17 00:00:00.0000000 +00:00 | 2016-03-12 00:00:00.0000000 +00:00 | 2017-07-19 00:00:00.0000000 +00:00 | 2012-01-26 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2015-04-17 00:00:00.0000000 +00:00 | 2016-04-27 00:00:00.0000000 +00:00 | 2017-06-08 00:00:00.0000000 +00:00 | 2015-04-17 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-05 17:15:32.5735748 -05:00
LNXA11WFM | Y | 2011-01-31 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 | 2018-09-13 00:00:00.0000000 +00:00 | 2019-06-04 00:00:00.0000000 +00:00 | 2011-01-31 00:00:00.0000000 +00:00 | 2011-11-14 00:00:00.0000000 +00:00 | 2012-07-08 00:00:00.0000000 +00:00 | 2013-03-12 00:00:00.0000000 +00:00 | 2013-10-11 00:00:00.0000000 +00:00 | 2011-01-31 00:00:00.0000000 +00:00 | 2012-08-03 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2017-06-11 00:00:00.0000000 +00:00 | 2011-01-31 00:00:00.0000000 +00:00 | 2012-07-23 00:00:00.0000000 +00:00 |  |  |  |  | 2019-04-29 00:00:00.0000000 +00:00 | [20 empty] | 2015-10-11 00:00:00.0000000 +00:00 | 2020-02-19 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-28 10:06:50.5950309 -05:00
LNXA12GRC | Y | 2012-01-05 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2020-01-14 00:00:00.0000000 +00:00 | 2012-01-05 00:00:00.0000000 +00:00 | 2012-09-26 00:00:00.0000000 +00:00 | 2013-07-08 00:00:00.0000000 +00:00 | 2014-02-04 00:00:00.0000000 +00:00 | 2015-02-27 00:00:00.0000000 +00:00 | 2012-01-05 00:00:00.0000000 +00:00 | 2013-04-23 00:00:00.0000000 +00:00 | 2015-08-26 00:00:00.0000000 +00:00 | 2016-04-10 00:00:00.0000000 +00:00 | 2017-05-03 00:00:00.0000000 +00:00 | 2012-01-05 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2017-08-11 00:00:00.0000000 +00:00 |  |  | 2016-05-30 00:00:00.0000000 +00:00 |  | 2012-01-05 00:00:00.0000000 +00:00 |  | 2013-04-24 00:00:00.0000000 +00:00 |  |  | 2013-07-30 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 | 2013-07-30 00:00:00.0000000 +00:00 |  |  | 2014-12-09 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 | 2014-12-09 00:00:00.0000000 +00:00 |  | 2017-08-11 00:00:00.0000000 +00:00 |  | 2018-06-15 00:00:00.0000000 +00:00 |  | 2020-01-14 00:00:00.0000000 +00:00 |  | 2017-02-26 00:00:00.0000000 +00:00 | 2020-12-08 00:00:00.0000000 +00:00 |  | 2020-12-08 00:00:00.0000000 +00:00 |  |  | 2017-10-02 10:32:42.5148062 -04:00
LNXA13SPV | Y | 2013-06-10 00:00:00.0000000 +00:00 | 2013-08-22 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2015-04-20 00:00:00.0000000 +00:00 | 2013-06-10 00:00:00.0000000 +00:00 | 2013-09-27 00:00:00.0000000 +00:00 | 2013-10-24 00:00:00.0000000 +00:00 | 2014-05-15 00:00:00.0000000 +00:00 | 2014-10-27 00:00:00.0000000 +00:00 | 2013-06-10 00:00:00.0000000 +00:00 | 2013-09-27 00:00:00.0000000 +00:00 | 2014-08-20 00:00:00.0000000 +00:00 | 2015-09-13 00:00:00.0000000 +00:00 | 2015-11-16 00:00:00.0000000 +00:00 | 2013-06-10 00:00:00.0000000 +00:00 | 2013-08-22 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2015-04-20 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2015-04-20 00:00:00.0000000 +00:00
LNXA13WKF | Y | [10 empty] | 2013-02-20 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2017-02-01 00:00:00.0000000 +00:00 | 2017-08-24 00:00:00.0000000 +00:00 | 2019-02-16 00:00:00.0000000 +00:00
LNXEA08BA | Y | 2015-11-05 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2017-01-19 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2019-03-29 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2016-06-25 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-05 17:00:00.0000000 +00:00 | 2011-11-05 17:00:00.0000000 +00:00 | 2017-07-10 00:00:00.0000000 +00:00 |  |  | 2015-12-05 00:00:00.0000000 +00:00 | 2018-06-28 00:00:00.0000000 +00:00 |  |  |  |  | 2015-11-05 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 |  |  |  | 2016-01-16 00:00:00.0000000 +00:00 | 2016-06-24 00:00:00.0000000 +00:00 | [9 empty] | 2020-03-30 00:00:00.0000000 +00:00 | 2020-10-01 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 11:59:31.1082659 -04:00
LNXEA08BX | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-01-11 00:00:00.0000000 +00:00 | 2009-12-19 00:00:00.0000000 +00:00 | 2010-04-25 00:00:00.0000000 +00:00 | 2011-04-24 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-06-23 00:00:00.0000000 +00:00 | 2010-11-28 00:00:00.0000000 +00:00 | 2015-09-16 00:00:00.0000000 +00:00 | 2017-03-13 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 |  |  | 2011-11-23 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | [26 empty] | 2017-12-12 09:43:33.2243745 -05:00
LNXEA08BX1 | Y | 2008-01-07 00:00:00.0000000 +00:00 |  | 2017-01-19 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 | 2012-04-14 00:00:00.0000000 +00:00 | 2012-06-12 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2016-10-03 00:00:00.0000000 +00:00 | 2020-11-11 00:00:00.0000000 +00:00 | 2020-12-06 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2011-11-05 00:00:00.0000000 +00:00 |  |  |  | 2021-09-19 00:00:00.0000000 +00:00 | [21 empty] | 2014-06-12 00:00:00.0000000 +00:00 | [5 empty] | 2017-11-08 09:16:28.3276213 -05:00
LNXEA08CP | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2017-07-10 00:00:00.0000000 +00:00 | 2018-05-30 00:00:00.0000000 +00:00 | 2019-05-30 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2014-08-13 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 | 2018-02-18 00:00:00.0000000 +00:00 | 2019-07-24 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2017-07-10 00:00:00.0000000 +00:00 |  |  | 2016-03-15 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 |  |  |  |  | 2009-10-20 00:00:00.0000000 +00:00 | 2010-04-20 00:00:00.0000000 +00:00 |  |  |  | 2010-04-21 00:00:00.0000000 +00:00 | 2010-12-21 00:00:00.0000000 +00:00 | [9 empty] | 2016-08-12 00:00:00.0000000 +00:00 | 2020-04-29 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 12:04:44.9576046 -04:00
LNXEA08FN | Y | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2017-07-10 00:00:00.0000000 +00:00 | 2018-04-10 00:00:00.0000000 +00:00 | 2019-04-10 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2014-08-13 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 | 2016-10-05 00:00:00.0000000 +00:00 | 2018-12-25 00:00:00.0000000 +00:00 | 2008-01-07 00:00:00.0000000 +00:00 | 2009-10-20 00:00:00.0000000 +00:00 | 2017-07-10 00:00:00.0000000 +00:00 |  |  | 2016-01-10 00:00:00.0000000 +00:00 | 2017-02-02 00:00:00.0000000 +00:00 |  |  |  |  | 2009-10-20 00:00:00.0000000 +00:00 | 2010-04-20 00:00:00.0000000 +00:00 |  |  |  | 2010-04-20 00:00:00.0000000 +00:00 | 2011-10-17 00:00:00.0000000 +00:00 | [9 empty] | 2016-08-12 00:00:00.0000000 +00:00 | 2021-09-01 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 14:36:12.3145195 -04:00
LQ122-BC2 | Y | 2013-07-18 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2016-04-11 00:00:00.0000000 +00:00 | 2017-02-06 00:00:00.0000000 +00:00 | 2013-07-18 00:00:00.0000000 +00:00 | 2013-09-19 00:00:00.0000000 +00:00 | 2014-04-01 00:00:00.0000000 +00:00 | 2014-09-29 00:00:00.0000000 +00:00 | 2015-07-27 00:00:00.0000000 +00:00 | 2013-07-18 00:00:00.0000000 +00:00 | 2013-11-18 00:00:00.0000000 +00:00 | 2015-05-01 00:00:00.0000000 +00:00 | 2016-02-10 00:00:00.0000000 +00:00 | 2016-12-07 00:00:00.0000000 +00:00 | 2013-07-18 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 |  |  | 2015-02-27 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | [26 empty] | 2017-10-18 10:37:04.0764744 -04:00
LQ122-CEL | Y | 2008-10-23 00:00:00.0000000 +00:00 |  |  | 2009-05-26 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2008-10-23 00:00:00.0000000 +00:00 | 2008-10-25 00:00:00.0000000 +00:00 | 2008-12-13 00:00:00.0000000 +00:00 | 2009-04-16 00:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2008-10-23 00:00:00.0000000 +00:00 | 2008-10-25 00:00:00.0000000 +00:00 | 2008-12-13 00:00:00.0000000 +00:00 | 2009-06-16 00:00:00.0000000 +00:00 | 2013-12-13 00:00:00.0000000 +00:00 | 2008-10-23 00:00:00.0000000 +00:00 |  |  | 2009-05-26 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2008-12-13 00:00:00.0000000 +00:00 | 2013-04-17 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 10:57:34.6083746 -05:00
LQ122-FHR | Y | 2014-03-25 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2015-03-09 00:00:00.0000000 +00:00 | 2017-10-21 00:00:00.0000000 +00:00 | 2018-07-23 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2014-07-22 00:00:00.0000000 +00:00 | 2015-02-01 00:00:00.0000000 +00:00 | 2015-03-17 00:00:00.0000000 +00:00 | 2015-12-27 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2014-02-20 00:00:00.0000000 +00:00 | 2015-04-10 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2018-01-22 00:00:00.0000000 +00:00 | 2014-03-25 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2015-03-09 00:00:00.0000000 +00:00 | 2016-06-22 18:00:00.0000000 +00:00 | 2017-06-12 17:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2017-06-12 00:00:00.0000000 +00:00 | [21 empty] | 2018-07-24 00:00:00.0000000 +00:00
LQ122-LH | Y | 2012-05-01 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-01-16 00:00:00.0000000 +00:00 | 2014-07-30 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 | 2012-05-09 00:00:00.0000000 +00:00 | 2012-06-30 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2013-10-09 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2013-05-23 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-01-16 00:00:00.0000000 +00:00 | 2014-07-30 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2013-07-06 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00
LQ122-W | Y | 2012-04-30 00:00:00.0000000 +00:00 | 2013-03-20 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | 2012-04-30 00:00:00.0000000 +00:00 | 2012-05-06 00:00:00.0000000 +00:00 | 2012-06-27 00:00:00.0000000 +00:00 | 2013-01-08 00:00:00.0000000 +00:00 | 2013-10-06 00:00:00.0000000 +00:00 | 2012-04-30 00:00:00.0000000 +00:00 | 2013-03-20 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2016-09-19 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2012-04-30 00:00:00.0000000 +00:00 | 2013-03-20 00:00:00.0000000 +00:00 | 2015-04-06 00:00:00.0000000 +00:00 | 2016-11-10 17:00:00.0000000 +00:00 |  | 2017-04-09 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | [21 empty] | 2019-07-02 00:00:00.0000000 +00:00
LQARVEXPN | Y | 2015-09-30 00:00:00.0000000 +00:00 | 2018-05-17 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2020-08-16 00:00:00.0000000 +00:00 | 2023-08-23 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2018-04-14 00:00:00.0000000 +00:00 | 2019-04-18 00:00:00.0000000 +00:00 | 2021-04-12 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2017-07-02 00:00:00.0000000 +00:00 | 2020-01-15 00:00:00.0000000 +00:00 | 2020-07-12 00:00:00.0000000 +00:00 | 2022-07-13 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 |  |  |  |  | 2020-01-15 00:00:00.0000000 +00:00 | 2023-08-23 00:00:00.0000000 +00:00
LQASADA | Y | 2015-10-21 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2020-01-09 00:00:00.0000000 +00:00 | 2020-07-10 00:00:00.0000000 +00:00 | 2022-08-21 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2018-07-09 00:00:00.0000000 +00:00 | 2019-02-11 00:00:00.0000000 +00:00 | 2020-02-22 00:00:00.0000000 +00:00 | 2003-10-20 00:00:00.0000000 +00:00 | 2004-03-24 00:00:00.0000000 +00:00 | 2004-06-02 00:00:00.0000000 +00:00 | 2018-06-23 00:00:00.0000000 +00:00 | 2018-07-04 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 |  |  |  | 2020-01-09 00:00:00.0000000 +00:00 | 2022-08-21 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-11 14:48:36.7770498 -04:00
LQC122-GK | Y | 2003-10-20 00:00:00.0000000 +00:00 | 2005-05-19 00:00:00.0000000 +00:00 | 2008-01-23 00:00:00.0000000 +00:00 | 2008-09-09 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2003-10-20 00:00:00.0000000 +00:00 | 2005-05-19 00:00:00.0000000 +00:00 | 2007-07-15 00:00:00.0000000 +00:00 | 2008-01-15 00:00:00.0000000 +00:00 | 2009-12-03 00:00:00.0000000 +00:00 | 2003-10-20 00:00:00.0000000 +00:00 | 2005-05-19 00:00:00.0000000 +00:00 | 2007-09-12 00:00:00.0000000 +00:00 | 2008-09-14 00:00:00.0000000 +00:00 | 2011-05-14 00:00:00.0000000 +00:00 | 2003-10-20 00:00:00.0000000 +00:00 | 2005-05-19 00:00:00.0000000 +00:00 | 2008-01-23 00:00:00.0000000 +00:00 | 2008-09-09 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2008-01-23 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 11:05:57.2961205 -05:00
LQD122-AU | Y | 2012-05-04 00:00:00.0000000 +00:00 | 2012-06-11 00:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 | 2013-08-08 00:00:00.0000000 +00:00 | 2012-05-04 00:00:00.0000000 +00:00 | 2012-06-11 00:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2014-02-24 00:00:00.0000000 +00:00 | 2012-05-04 00:00:00.0000000 +00:00 | 2012-06-11 00:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2014-02-24 00:00:00.0000000 +00:00 | 2012-05-04 00:00:00.0000000 +00:00 | 2012-06-11 00:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2013-04-09 00:00:00.0000000 +00:00 | 2013-08-08 00:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | [21 empty] | 2016-10-31 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 |  |  |  | 2017-09-12 15:42:07.7620829 -04:00
LQD122BCE | Y | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2023-06-28 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | [5 empty] | 2013-07-18 17:00:00.0000000 +00:00 | 2013-09-16 17:00:00.0000000 +00:00 |  |  |  | 2015-09-28 00:00:00.0000000 +00:00 | [27 empty] | 2017-11-30 13:04:09.3283045 -05:00
LQD122BR2 | Y | 2014-02-13 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2018-06-27 00:00:00.0000000 +00:00 | 2019-04-26 00:00:00.0000000 +00:00 | 2020-09-13 00:00:00.0000000 +00:00 | 2014-02-13 00:00:00.0000000 +00:00 | 2015-01-01 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2017-10-22 00:00:00.0000000 +00:00 | 2014-02-13 00:00:00.0000000 +00:00 | 2015-06-20 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2017-08-25 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2014-02-13 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 |  |  |  | 2018-06-27 00:00:00.0000000 +00:00 | [11 empty] | 2017-11-16 00:00:00.0000000 +00:00 | [15 empty] | 2017-10-25 13:34:55.6941669 -04:00
LQD122BT1 | Y | 2012-03-07 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2016-12-29 00:00:00.0000000 +00:00 | 2018-09-12 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2013-02-03 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 | 2014-04-30 00:00:00.0000000 +00:00 | 2015-02-16 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2017-02-26 00:00:00.0000000 +00:00 | 2017-08-26 00:00:00.0000000 +00:00 | 2018-06-14 00:00:00.0000000 +00:00 | 2012-03-07 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 |  |  |  | 2016-07-01 00:00:00.0000000 +00:00 | 2016-10-29 00:00:00.0000000 +00:00
LQD122-BW | Y | 2012-07-02 00:00:00.0000000 +00:00 | 2014-05-06 00:00:00.0000000 +00:00 | 2014-11-18 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2017-05-21 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2012-12-15 00:00:00.0000000 +00:00 | 2013-03-01 00:00:00.0000000 +00:00 | 2013-06-20 00:00:00.0000000 +00:00 | 2013-11-13 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-08-30 00:00:00.0000000 +00:00 | 2015-02-17 00:00:00.0000000 +00:00 | 2016-04-27 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2014-05-06 00:00:00.0000000 +00:00 | 2014-11-18 00:00:00.0000000 +00:00 | 2016-06-21 18:00:00.0000000 +00:00 | 2017-04-18 17:00:00.0000000 +00:00 | 2015-08-25 00:00:00.0000000 +00:00 | 2017-10-26 00:00:00.0000000 +00:00 | [21 empty] | 2018-04-18 00:00:00.0000000 +00:00
LQD122-F2 | Y | 2011-11-01 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2016-11-25 00:00:00.0000000 +00:00 | 2018-04-07 00:00:00.0000000 +00:00 | 2019-04-08 00:00:00.0000000 +00:00 | 2011-11-01 00:00:00.0000000 +00:00 | 2012-07-13 00:00:00.0000000 +00:00 | 2013-01-10 00:00:00.0000000 +00:00 | 2013-05-26 00:00:00.0000000 +00:00 | 2013-11-30 00:00:00.0000000 +00:00 | 2011-11-01 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2016-01-25 00:00:00.0000000 +00:00 | 2017-07-25 00:00:00.0000000 +00:00 | 2018-07-26 00:00:00.0000000 +00:00 | 2011-11-01 00:00:00.0000000 +00:00 | 2013-06-25 00:00:00.0000000 +00:00 | 2016-11-25 00:00:00.0000000 +00:00 |  |  | 2016-11-25 00:00:00.0000000 +00:00
LQD122GL2 | Y | 2010-03-24 00:00:00.0000000 +00:00 | 2011-12-06 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2019-08-15 00:00:00.0000000 +00:00 | 2010-03-24 00:00:00.0000000 +00:00 | 2010-10-30 00:00:00.0000000 +00:00 | 2011-08-19 00:00:00.0000000 +00:00 | 2012-04-03 00:00:00.0000000 +00:00 | 2013-04-08 00:00:00.0000000 +00:00 | 2010-03-24 00:00:00.0000000 +00:00 | 2011-08-07 00:00:00.0000000 +00:00 | 2015-05-30 00:00:00.0000000 +00:00 | 2016-03-23 00:00:00.0000000 +00:00 | 2017-04-19 00:00:00.0000000 +00:00 | 2010-03-24 00:00:00.0000000 +00:00 | 2011-12-06 00:00:00.0000000 +00:00 | 2017-03-10 00:00:00.0000000 +00:00 |  |  | 2017-03-10 00:00:00.0000000 +00:00 | 2019-08-15 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-11 14:49:41.9997752 -04:00
LQD122-HO | Y | 2012-03-20 00:00:00.0000000 +00:00 | 2012-07-14 00:00:00.0000000 +00:00 | 2012-11-26 00:00:00.0000000 +00:00 | 2014-07-28 00:00:00.0000000 +00:00 | 2014-11-05 00:00:00.0000000 +00:00 | 2012-03-20 00:00:00.0000000 +00:00 | 2012-07-14 00:00:00.0000000 +00:00 | 2012-11-11 00:00:00.0000000 +00:00 | 2013-03-27 00:00:00.0000000 +00:00 | 2013-07-04 00:00:00.0000000 +00:00 | 2012-03-20 00:00:00.0000000 +00:00 | 2012-07-14 00:00:00.0000000 +00:00 | 2012-11-11 00:00:00.0000000 +00:00 | 2013-07-01 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2012-03-20 00:00:00.0000000 +00:00 | 2012-07-14 00:00:00.0000000 +00:00 | 2012-11-26 00:00:00.0000000 +00:00 | 2014-07-28 00:00:00.0000000 +00:00 | 2014-11-05 00:00:00.0000000 +00:00 | 2012-11-11 00:00:00.0000000 +00:00 | 2014-12-21 00:00:00.0000000 +00:00
LQD122HO1 | Y | 2014-02-12 00:00:00.0000000 +00:00 | 2015-04-15 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2019-07-15 00:00:00.0000000 +00:00 | 2021-03-19 00:00:00.0000000 +00:00 | 2014-02-12 00:00:00.0000000 +00:00 | 2014-10-26 00:00:00.0000000 +00:00 | 2015-11-03 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2017-11-22 00:00:00.0000000 +00:00 | 2014-02-12 00:00:00.0000000 +00:00 | 2015-02-10 00:00:00.0000000 +00:00 | 2016-06-13 00:00:00.0000000 +00:00 | 2017-05-25 00:00:00.0000000 +00:00 | 1930-07-11 00:00:00.0000000 +00:00 | 2014-02-12 00:00:00.0000000 +00:00 | 2015-04-14 00:00:00.0000000 +00:00 |  |  |  | 2019-01-15 00:00:00.0000000 +00:00 | [11 empty] | 2018-05-15 00:00:00.0000000 +00:00 | [10 empty] | 2022-08-25 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-31 14:31:02.1363758 -04:00
LQD122HV3B | Y | 2009-08-24 00:00:00.0000000 +00:00 | 2010-11-05 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-04-15 00:00:00.0000000 +00:00 | 2011-02-09 00:00:00.0000000 +00:00 | 2011-08-10 00:00:00.0000000 +00:00 | 2012-08-12 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-11-22 00:00:00.0000000 +00:00 | 2012-04-25 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2016-10-05 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-11-05 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 |  | 2011-12-28 00:00:00.0000000 +00:00 | 2015-11-10 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-12 15:45:23.9452943 -04:00
LQD122HV3O | Y | 2009-08-24 00:00:00.0000000 +00:00 | 2010-11-05 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2013-04-11 00:00:00.0000000 +00:00 | 2013-12-10 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-05-23 00:00:00.0000000 +00:00 | 2010-11-20 00:00:00.0000000 +00:00 | 2011-04-05 00:00:00.0000000 +00:00 | 2011-10-10 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-11-22 00:00:00.0000000 +00:00 | 2011-12-31 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2013-07-16 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-11-05 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2013-04-11 00:00:00.0000000 +00:00 | 2013-12-10 00:00:00.0000000 +00:00 | 2011-12-31 00:00:00.0000000 +00:00 | 2013-08-28 00:00:00.0000000 +00:00
LQD122HV3R | Y | 2009-08-24 00:00:00.0000000 +00:00 | 2010-11-05 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2014-10-03 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-05-23 00:00:00.0000000 +00:00 | 2010-11-20 00:00:00.0000000 +00:00 | 2011-05-05 00:00:00.0000000 +00:00 | 2011-11-09 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-11-22 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2013-06-09 00:00:00.0000000 +00:00 | 2014-11-23 00:00:00.0000000 +00:00 | 2009-08-24 00:00:00.0000000 +00:00 | 2010-11-05 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2014-10-03 00:00:00.0000000 +00:00 | 2011-12-28 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 12:34:22.7854761 -05:00
LQD122LIC | Y | 2009-09-15 00:00:00.0000000 +00:00 | 2011-10-21 00:00:00.0000000 +00:00 | 2013-01-22 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2016-04-29 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2010-04-03 00:00:00.0000000 +00:00 | 2010-09-27 00:00:00.0000000 +00:00 | 2011-02-10 00:00:00.0000000 +00:00 | 2011-09-12 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2011-10-21 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2015-01-21 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 | 2009-09-15 00:00:00.0000000 +00:00 | 2011-10-21 00:00:00.0000000 +00:00 | 2013-01-22 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 |  | 2013-01-22 00:00:00.0000000 +00:00 | 2016-02-22 00:00:00.0000000 +00:00
LQD122-MG | Y | 2012-03-30 00:00:00.0000000 +00:00 | 2013-02-01 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2016-04-30 00:00:00.0000000 +00:00 | 2017-05-15 00:00:00.0000000 +00:00 | 2012-03-30 00:00:00.0000000 +00:00 | 2012-12-04 00:00:00.0000000 +00:00 | 2013-07-01 00:00:00.0000000 +00:00 | 2014-01-12 00:00:00.0000000 +00:00 | 2014-10-10 00:00:00.0000000 +00:00 | 2012-03-30 00:00:00.0000000 +00:00 | 2013-02-01 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2015-03-19 00:00:00.0000000 +00:00 | 2015-12-15 00:00:00.0000000 +00:00 | 2012-03-30 00:00:00.0000000 +00:00 | 2013-01-24 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2016-05-31 00:00:00.0000000 +00:00 | 2017-06-07 00:00:00.0000000 +00:00 | 2013-08-21 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | [21 empty] | 2018-06-07 00:00:00.0000000 +00:00
LQD122NF4 | Y | 2011-12-02 00:00:00.0000000 +00:00 | 2013-08-02 00:00:00.0000000 +00:00 | 2018-08-09 00:00:00.0000000 +00:00 | 2019-01-17 00:00:00.0000000 +00:00 | 2020-07-29 00:00:00.0000000 +00:00 | 2011-12-02 00:00:00.0000000 +00:00 | 2012-08-19 00:00:00.0000000 +00:00 | 2014-01-25 00:00:00.0000000 +00:00 | 2014-04-29 00:00:00.0000000 +00:00 | 2015-11-06 00:00:00.0000000 +00:00 | 2011-12-02 00:00:00.0000000 +00:00 | 2013-01-30 00:00:00.0000000 +00:00 | 2016-05-03 00:00:00.0000000 +00:00 | 2018-01-14 00:00:00.0000000 +00:00 | 2019-07-24 00:00:00.0000000 +00:00 | 2011-12-02 00:00:00.0000000 +00:00 | 2013-01-30 00:00:00.0000000 +00:00 |  |  |  | 2018-08-09 00:00:00.0000000 +00:00 | [11 empty] | 2017-12-20 00:00:00.0000000 +00:00 | [15 empty] | 2017-10-27 15:45:00.6181343 -04:00
LQD122QH1 | Y | 2012-08-16 00:00:00.0000000 +00:00 | 2013-05-29 00:00:00.0000000 +00:00 | 2015-05-13 00:00:00.0000000 +00:00 | 2016-08-10 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2012-08-16 00:00:00.0000000 +00:00 | 2013-05-29 00:00:00.0000000 +00:00 | 2013-10-19 00:00:00.0000000 +00:00 | 2014-04-24 00:00:00.0000000 +00:00 | 2014-11-20 00:00:00.0000000 +00:00 | 2012-08-16 00:00:00.0000000 +00:00 | 2013-05-29 00:00:00.0000000 +00:00 | 2015-05-13 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2016-10-29 00:00:00.0000000 +00:00 | 2012-08-16 00:00:00.0000000 +00:00 | 2013-05-29 00:00:00.0000000 +00:00 | 2015-05-13 00:00:00.0000000 +00:00 | 2016-06-22 18:00:00.0000000 +00:00 | 2017-06-30 17:00:00.0000000 +00:00 | 2015-05-13 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | [21 empty] | 2018-06-30 00:00:00.0000000 +00:00
LQD122-QW | Y | 2010-02-01 00:00:00.0000000 +00:00 | 2010-07-06 00:00:00.0000000 +00:00 | 2013-03-30 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2010-02-01 00:00:00.0000000 +00:00 | 2011-03-31 00:00:00.0000000 +00:00 | 2012-06-13 00:00:00.0000000 +00:00 | 2012-08-22 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2010-02-01 00:00:00.0000000 +00:00 | 2010-07-06 00:00:00.0000000 +00:00 | 2013-06-26 00:00:00.0000000 +00:00 | 2014-05-03 00:00:00.0000000 +00:00 | 2016-05-27 00:00:00.0000000 +00:00 | 2010-02-01 00:00:00.0000000 +00:00 | 2010-07-06 00:00:00.0000000 +00:00 | 2013-03-30 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 |  | 2014-01-05 00:00:00.0000000 +00:00 | 2018-05-17 00:00:00.0000000 +00:00 | 2010-02-01 00:00:00.0000000 +00:00 | 2010-02-01 00:00:00.0000000 +00:00 | 2011-03-31 00:00:00.0000000 +00:00 | 2010-07-06 00:00:00.0000000 +00:00 | 2011-06-13 00:00:00.0000000 +00:00 | 2011-06-13 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2011-06-13 00:00:00.0000000 +00:00 | 2012-03-15 00:00:00.0000000 +00:00 | 2011-07-22 00:00:00.0000000 +00:00 | 2011-07-22 00:00:00.0000000 +00:00 | 2012-10-26 00:00:00.0000000 +00:00 | 2011-07-22 00:00:00.0000000 +00:00 | 2012-10-26 00:00:00.0000000 +00:00 | 2012-06-13 00:00:00.0000000 +00:00 | 2013-03-30 00:00:00.0000000 +00:00 | 2012-08-22 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 |  | 2018-08-14 00:00:00.0000000 +00:00 |  |  | 2017-08-14 00:00:00.0000000 +00:00 |  | 2017-08-29 12:21:49.0191542 -04:00
LQD122-QW-1 | Y | 2010-02-01 00:00:00.0000000 +00:00 | 2010-07-06 00:00:00.0000000 +00:00 | 2013-03-30 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2010-02-01 00:00:00.0000000 +00:00 | 2010-07-06 00:00:00.0000000 +00:00 | 2013-03-30 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2010-02-01 00:00:00.0000000 +00:00 | 2010-07-06 00:00:00.0000000 +00:00 | 2013-03-30 00:00:00.0000000 +00:00 | 2015-02-26 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2010-02-01 00:00:00.0000000 +00:00 | 2010-07-06 00:00:00.0000000 +00:00 |  | 2015-02-26 00:00:00.0000000 +00:00 |  |  | 2017-02-14 00:00:00.0000000 +00:00
LQD122RF3A | Y | 2009-08-06 00:00:00.0000000 +00:00 | 2010-05-10 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-05-20 00:00:00.0000000 +00:00 | 2014-10-07 00:00:00.0000000 +00:00 | 2009-08-06 00:00:00.0000000 +00:00 | 2010-05-10 00:00:00.0000000 +00:00 | 2010-09-15 00:00:00.0000000 +00:00 | 2011-04-04 00:00:00.0000000 +00:00 | 2011-10-12 00:00:00.0000000 +00:00 | 2009-08-06 00:00:00.0000000 +00:00 | 2010-05-10 00:00:00.0000000 +00:00 | 2013-01-09 00:00:00.0000000 +00:00 | 2015-11-08 00:00:00.0000000 +00:00 | 2017-01-13 00:00:00.0000000 +00:00 | 2009-08-06 00:00:00.0000000 +00:00 | 2010-05-10 00:00:00.0000000 +00:00 |  | 2014-05-20 00:00:00.0000000 +00:00 | 2014-10-07 00:00:00.0000000 +00:00 | 2013-01-09 00:00:00.0000000 +00:00 | 2014-10-30 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 10:25:34.6294325 -05:00
LQD122RF3C | Y | 2010-10-05 00:00:00.0000000 +00:00 | 2012-10-24 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2017-07-03 00:00:00.0000000 +00:00 | 2018-06-21 00:00:00.0000000 +00:00 | 2010-10-05 00:00:00.0000000 +00:00 | 2012-10-24 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2013-12-06 00:00:00.0000000 +00:00 | 2014-05-21 00:00:00.0000000 +00:00 | 2010-10-05 00:00:00.0000000 +00:00 | 2012-10-24 00:00:00.0000000 +00:00 | 2015-01-06 00:00:00.0000000 +00:00 | 2015-12-01 00:00:00.0000000 +00:00 | 2016-06-14 00:00:00.0000000 +00:00 | 2010-10-05 00:00:00.0000000 +00:00 | 2012-10-24 00:00:00.0000000 +00:00 | 2015-07-07 00:00:00.0000000 +00:00 | 2017-02-07 17:00:00.0000000 +00:00 |  | 2015-01-06 00:00:00.0000000 +00:00 | 2018-08-05 00:00:00.0000000 +00:00
LQD122-RO | Y | 2006-08-23 00:00:00.0000000 +00:00 | 2007-09-12 00:00:00.0000000 +00:00 | 2010-10-30 00:00:00.0000000 +00:00 | 2012-04-05 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2006-08-23 00:00:00.0000000 +00:00 | 2007-04-15 00:00:00.0000000 +00:00 | 2007-11-12 00:00:00.0000000 +00:00 | 2008-01-12 00:00:00.0000000 +00:00 | 2008-07-21 00:00:00.0000000 +00:00 | 2006-08-23 00:00:00.0000000 +00:00 | 2007-09-13 00:00:00.0000000 +00:00 | 2010-07-24 00:00:00.0000000 +00:00 | 2012-01-10 00:00:00.0000000 +00:00 | 2013-07-27 00:00:00.0000000 +00:00 | 2006-08-23 00:00:00.0000000 +00:00 | 2007-09-12 00:00:00.0000000 +00:00 |  | 2012-04-05 00:00:00.0000000 +00:00 | 2015-09-25 00:00:00.0000000 +00:00 | 2010-12-10 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 11:12:52.4186947 -05:00
LQD122RO2 | Y | 2011-01-31 00:00:00.0000000 +00:00 | 2014-05-20 00:00:00.0000000 +00:00 | 2018-07-09 00:00:00.0000000 +00:00 | 2019-01-08 00:00:00.0000000 +00:00 | 2020-06-27 00:00:00.0000000 +00:00 | 2011-01-31 00:00:00.0000000 +00:00 | 2011-10-18 00:00:00.0000000 +00:00 | 2012-04-07 00:00:00.0000000 +00:00 | 2012-10-05 00:00:00.0000000 +00:00 | 2013-04-25 00:00:00.0000000 +00:00 | 2011-01-31 00:00:00.0000000 +00:00 | 2014-05-20 00:00:00.0000000 +00:00 | 2018-01-07 00:00:00.0000000 +00:00 | 2019-01-06 00:00:00.0000000 +00:00 | 2019-07-27 00:00:00.0000000 +00:00 | 2011-01-31 00:00:00.0000000 +00:00 | 2014-05-20 00:00:00.0000000 +00:00 |  |  |  | 2018-07-03 00:00:00.0000000 +00:00 | [27 empty] | 2017-11-28 14:55:03.4642691 -05:00
LQD122-RO3 | Y | 2012-03-29 00:00:00.0000000 +00:00 | 2012-09-01 00:00:00.0000000 +00:00 | 2013-10-22 00:00:00.0000000 +00:00 | 2014-07-31 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2012-03-29 00:00:00.0000000 +00:00 | 2012-09-01 00:00:00.0000000 +00:00 | 2013-01-24 00:00:00.0000000 +00:00 | 2013-09-01 00:00:00.0000000 +00:00 | 2014-04-30 00:00:00.0000000 +00:00 | 2012-03-29 00:00:00.0000000 +00:00 | 2012-09-01 00:00:00.0000000 +00:00 | 2013-01-24 00:00:00.0000000 +00:00 | 2013-10-28 00:00:00.0000000 +00:00 | 2014-12-08 00:00:00.0000000 +00:00 | 2012-03-29 00:00:00.0000000 +00:00 | 2012-09-01 00:00:00.0000000 +00:00 |  | 2014-07-31 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2013-10-22 00:00:00.0000000 +00:00 | 2015-04-30 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 11:08:54.0500975 -05:00
LQD122-S2 | Y | 2012-03-14 00:00:00.0000000 +00:00 | 2013-04-22 00:00:00.0000000 +00:00 | 2017-08-09 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2020-07-01 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2014-01-08 00:00:00.0000000 +00:00 | 2015-05-03 00:00:00.0000000 +00:00 | 2015-12-01 00:00:00.0000000 +00:00 | 2016-12-23 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2013-04-22 00:00:00.0000000 +00:00 | 2016-10-16 00:00:00.0000000 +00:00 | 2017-11-12 00:00:00.0000000 +00:00 | 2019-04-17 00:00:00.0000000 +00:00 | 2012-03-14 00:00:00.0000000 +00:00 | 2013-04-19 00:00:00.0000000 +00:00 | 2017-08-09 00:00:00.0000000 +00:00 |  |  | 2017-09-28 00:00:00.0000000 +00:00 | 2020-07-01 00:00:00.0000000 +00:00 | [26 empty] | 2017-10-27 15:35:50.4530991 -04:00
LQD122SA1 | Y | 2012-03-01 00:00:00.0000000 +00:00 | 2015-01-20 00:00:00.0000000 +00:00 | 2016-07-19 00:00:00.0000000 +00:00 | 2017-02-02 00:00:00.0000000 +00:00 | 2017-07-05 00:00:00.0000000 +00:00 | 2012-03-01 00:00:00.0000000 +00:00 | 2013-03-15 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 | 2012-03-01 00:00:00.0000000 +00:00 | 2014-11-21 00:00:00.0000000 +00:00 | 2016-02-19 00:00:00.0000000 +00:00 | 2016-09-04 00:00:00.0000000 +00:00 | 2017-02-04 00:00:00.0000000 +00:00 | 2012-03-01 00:00:00.0000000 +00:00 | 2015-01-20 00:00:00.0000000 +00:00 |  |  |  | 2016-04-19 00:00:00.0000000 +00:00 | 2017-04-05 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 17:18:02.0984157 -05:00
LQD122-WN | Y | 2014-02-12 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2019-02-01 00:00:00.0000000 +00:00 | 2019-07-12 00:00:00.0000000 +00:00 | 2020-08-01 00:00:00.0000000 +00:00 | 2014-02-12 00:00:00.0000000 +00:00 | 2014-10-26 00:00:00.0000000 +00:00 | 2015-11-03 00:00:00.0000000 +00:00 | 2016-05-16 00:00:00.0000000 +00:00 | 2017-11-22 00:00:00.0000000 +00:00 | 2014-02-12 00:00:00.0000000 +00:00 | 2015-06-22 00:00:00.0000000 +00:00 | 2017-06-24 00:00:00.0000000 +00:00 | 2018-01-05 00:00:00.0000000 +00:00 | 2018-02-20 00:00:00.0000000 +00:00 | 2014-02-12 17:00:00.0000000 +00:00 | 2015-06-22 17:00:00.0000000 +00:00 |  |  |  | 2019-02-01 00:00:00.0000000 +00:00 | [6 empty] | 2017-04-05 00:00:00.0000000 +00:00 | 2017-04-05 00:00:00.0000000 +00:00 |  |  |  | 2017-12-22 00:00:00.0000000 +00:00 | [10 empty] | 2022-08-01 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-28 11:24:00.7891558 -05:00
LQD122WS3 | Y | 2014-03-17 00:00:00.0000000 +00:00 |  |  | 2015-06-22 00:00:00.0000000 +00:00 | 2016-01-13 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-07-05 00:00:00.0000000 +00:00 | 2015-06-19 00:00:00.0000000 +00:00 | 2015-02-08 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-07-05 00:00:00.0000000 +00:00 | 2015-06-19 00:00:00.0000000 +00:00 | 2015-02-08 00:00:00.0000000 +00:00 | 2016-02-18 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-07-05 00:00:00.0000000 +00:00 |  | 2015-06-22 00:00:00.0000000 +00:00 | 2016-01-13 00:00:00.0000000 +00:00 | 2015-06-19 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 12:34:42.3909897 -05:00
LQDLHVAC | Y | 2015-12-03 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 | 2018-09-18 00:00:00.0000000 +00:00 | 2019-08-21 00:00:00.0000000 +00:00 | 2020-09-07 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2016-10-27 00:00:00.0000000 +00:00 | 2018-09-28 00:00:00.0000000 +00:00 | 2019-08-21 00:00:00.0000000 +00:00 | 2020-09-07 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00 | 2016-06-27 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-08-27 00:00:00.0000000 +00:00 | 2015-12-03 00:00:00.0000000 +00:00
LQDOUGMTG | Y | 2016-03-07 00:00:00.0000000 +00:00 | 2017-05-05 00:00:00.0000000 +00:00 | 2018-09-28 00:00:00.0000000 +00:00 | 2019-04-04 00:00:00.0000000 +00:00 | 2020-04-03 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2016-09-07 00:00:00.0000000 +00:00 | 2017-01-14 00:00:00.0000000 +00:00 | 2017-01-19 00:00:00.0000000 +00:00 | 2017-01-30 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2017-01-05 00:00:00.0000000 +00:00 | 2018-01-04 00:00:00.0000000 +00:00 | 2018-01-09 00:00:00.0000000 +00:00 | 2018-04-08 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2017-05-15 17:00:00.0000000 +00:00 |  |  |  | 2018-09-28 00:00:00.0000000 +00:00
LQFLELV | Y | 2015-10-22 00:00:00.0000000 +00:00 | 2016-06-10 00:00:00.0000000 +00:00 | 2018-06-27 00:00:00.0000000 +00:00 | 2018-12-24 00:00:00.0000000 +00:00 | 2020-07-11 00:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2019-01-03 00:00:00.0000000 +00:00 | 2020-07-21 00:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2016-07-16 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-10-15 00:00:00.0000000 +00:00 | 2020-05-02 00:00:00.0000000 +00:00 | 2015-10-22 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 |  |  |  | 2018-06-27 00:00:00.0000000 +00:00
LQHIHVAC | Y | 2015-11-25 00:00:00.0000000 +00:00 | 2017-05-08 00:00:00.0000000 +00:00 | 2018-09-05 00:00:00.0000000 +00:00 | 2019-03-23 00:00:00.0000000 +00:00 | 2020-01-27 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 | 2016-08-23 00:00:00.0000000 +00:00 | 2017-10-18 00:00:00.0000000 +00:00 | 2018-11-03 00:00:00.0000000 +00:00 | 2019-09-09 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2018-01-16 00:00:00.0000000 +00:00 | 2018-11-03 00:00:00.0000000 +00:00 | 2019-09-09 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 | 2017-05-05 17:00:00.0000000 +00:00 |  |  |  | 2018-09-05 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-20 00:00:00.0000000 +00:00
LQHIROOF | Y | 2015-10-20 00:00:00.0000000 +00:00 | 2017-03-30 00:00:00.0000000 +00:00 | 2018-08-15 00:00:00.0000000 +00:00 | 2019-02-12 00:00:00.0000000 +00:00 | 2019-09-26 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2016-07-01 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2017-03-05 00:00:00.0000000 +00:00 | 2017-10-17 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2016-10-10 00:00:00.0000000 +00:00 | 2018-02-07 00:00:00.0000000 +00:00 | 2018-06-18 00:00:00.0000000 +00:00 | 2019-01-30 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2017-03-27 17:00:00.0000000 +00:00 |  |  |  | 2018-08-15 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-20 00:00:00.0000000 +00:00 | [15 empty] | 2021-08-29 00:00:00.0000000 +00:00
LQJHHVAC | Y | 2015-11-09 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2020-02-21 00:00:00.0000000 +00:00 | 2015-11-09 00:00:00.0000000 +00:00 | 2016-08-05 00:00:00.0000000 +00:00 | 2017-11-09 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2017-11-21 00:00:00.0000000 +00:00 | 2015-11-09 00:00:00.0000000 +00:00 | 2016-06-07 00:00:00.0000000 +00:00 | 2017-12-09 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2017-12-21 00:00:00.0000000 +00:00 | 2015-11-09 00:00:00.0000000 +00:00 | 2017-03-06 17:00:00.0000000 +00:00 |  |  |  | 2018-07-20 00:00:00.0000000 +00:00 | [22 empty] | 2022-02-19 00:00:00.0000000 +00:00
LQLAROOF | Y | 2015-10-20 00:00:00.0000000 +00:00 | 2016-09-26 00:00:00.0000000 +00:00 | 2018-07-09 00:00:00.0000000 +00:00 | 2019-01-04 00:00:00.0000000 +00:00 | 2020-01-09 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2018-06-28 00:00:00.0000000 +00:00 | 2019-07-03 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-06-28 00:00:00.0000000 +00:00 | 2018-06-28 00:00:00.0000000 +00:00 | 2019-07-03 00:00:00.0000000 +00:00 | 2015-10-20 00:00:00.0000000 +00:00 | 2016-09-26 18:00:00.0000000 +00:00 |  |  |  | 2018-08-11 00:00:00.0000000 +00:00
LQMA-BLR | Y | 2017-02-14 00:00:00.0000000 +00:00 | 2017-03-01 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2017-07-27 00:00:00.0000000 +00:00 | 2017-11-18 00:00:00.0000000 +00:00 | 2017-02-14 00:00:00.0000000 +00:00 | 2017-03-01 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2017-07-27 00:00:00.0000000 +00:00 | 2017-10-12 00:00:00.0000000 +00:00 | [5 empty] | 2017-02-14 00:00:00.0000000 +00:00 | 2017-03-01 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2017-07-27 00:00:00.0000000 +00:00 | 2017-11-03 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | 2017-11-03 00:00:00.0000000 +00:00 | [20 empty] | 2018-10-12 00:00:00.0000000 +00:00 | [5 empty] | 2017-11-09 15:56:22.6180055 -05:00
LQMVHVAC | Y | 2016-01-28 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2019-01-15 00:00:00.0000000 +00:00 | 2021-01-23 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2016-12-01 00:00:00.0000000 +00:00 | 2016-12-22 00:00:00.0000000 +00:00 | 2017-01-10 00:00:00.0000000 +00:00 | 2018-01-10 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2016-12-11 00:00:00.0000000 +00:00 | 2018-02-13 00:00:00.0000000 +00:00 | 2018-03-04 00:00:00.0000000 +00:00 | 2018-03-16 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2017-03-07 17:00:00.0000000 +00:00 |  |  |  | 2018-07-16 00:00:00.0000000 +00:00 | [27 empty] | 2017-11-27 16:04:22.1541408 -05:00
LQOZROOF | Y | 2016-07-22 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2019-01-13 00:00:00.0000000 +00:00 | 2020-01-13 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2018-11-15 00:00:00.0000000 +00:00 | 2019-11-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-22 17:00:00.0000000 +00:00 | 2017-02-15 17:00:00.0000000 +00:00 |  |  |  | 2018-07-16 00:00:00.0000000 +00:00 | [11 empty] | 2018-01-17 00:00:00.0000000 +00:00 | [10 empty] | 2022-01-12 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-28 14:53:14.8332886 -05:00
LQQ122-1E2 | Y | 2005-05-06 00:00:00.0000000 +00:00 | 2005-08-10 00:00:00.0000000 +00:00 | 2009-03-26 00:00:00.0000000 +00:00 | 2011-12-12 00:00:00.0000000 +00:00 | 2016-04-25 00:00:00.0000000 +00:00 | 2005-05-06 00:00:00.0000000 +00:00 | 2005-08-10 00:00:00.0000000 +00:00 | 2007-11-09 00:00:00.0000000 +00:00 | 2008-07-22 00:00:00.0000000 +00:00 | 2010-03-28 00:00:00.0000000 +00:00 | 2005-05-06 00:00:00.0000000 +00:00 | 2005-08-10 00:00:00.0000000 +00:00 | 2008-09-18 00:00:00.0000000 +00:00 | 2010-02-02 00:00:00.0000000 +00:00 | 2012-01-02 00:00:00.0000000 +00:00 | 2005-05-06 00:00:00.0000000 +00:00 | 2005-08-10 00:00:00.0000000 +00:00 | 2009-03-26 00:00:00.0000000 +00:00 | 2011-12-12 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | 2009-02-02 00:00:00.0000000 +00:00 | 2016-04-14 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 11:07:06.1387752 -05:00
LQQ122-BL | Y | 2012-10-22 00:00:00.0000000 +00:00 | 2015-04-29 00:00:00.0000000 +00:00 | 2016-06-22 00:00:00.0000000 +00:00 | 2017-10-24 00:00:00.0000000 +00:00 | 2018-11-01 00:00:00.0000000 +00:00 | 2012-10-22 00:00:00.0000000 +00:00 | 2013-11-27 00:00:00.0000000 +00:00 | 2014-05-18 00:00:00.0000000 +00:00 | 2014-11-15 00:00:00.0000000 +00:00 | 2015-05-30 00:00:00.0000000 +00:00 | 2012-10-22 00:00:00.0000000 +00:00 | 2015-02-23 00:00:00.0000000 +00:00 | 2016-12-06 00:00:00.0000000 +00:00 | 2017-12-23 00:00:00.0000000 +00:00 | 2018-07-07 00:00:00.0000000 +00:00 | 2012-10-22 00:00:00.0000000 +00:00 | 2015-04-28 00:00:00.0000000 +00:00 | 2016-06-22 00:00:00.0000000 +00:00 | 2017-10-24 00:00:00.0000000 +00:00 |  | 2018-06-04 00:00:00.0000000 +00:00 | [27 empty] | 2017-10-24 12:43:20.5076142 -04:00
LQQ122CLD1 | Y | 2004-04-29 00:00:00.0000000 +00:00 | 2006-07-13 00:00:00.0000000 +00:00 | 2008-03-14 00:00:00.0000000 +00:00 | 2008-09-17 00:00:00.0000000 +00:00 | 2011-04-25 00:00:00.0000000 +00:00 | 2004-04-29 00:00:00.0000000 +00:00 | 2005-07-07 00:00:00.0000000 +00:00 | 2006-12-17 00:00:00.0000000 +00:00 | 2009-02-24 00:00:00.0000000 +00:00 | 2010-09-23 00:00:00.0000000 +00:00 | 2004-04-29 00:00:00.0000000 +00:00 | 2006-07-13 00:00:00.0000000 +00:00 | 2008-03-18 00:00:00.0000000 +00:00 | 2010-07-25 00:00:00.0000000 +00:00 | 2013-07-05 00:00:00.0000000 +00:00 | 2004-04-29 00:00:00.0000000 +00:00 | 2006-07-13 00:00:00.0000000 +00:00 |  | 2008-09-17 00:00:00.0000000 +00:00 | 2011-04-25 00:00:00.0000000 +00:00 | 2008-03-29 00:00:00.0000000 +00:00 | 2011-04-25 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 10:26:09.1449472 -05:00
LQQ122CLD4 | Y | 2004-04-29 00:00:00.0000000 +00:00 | 2006-07-13 00:00:00.0000000 +00:00 | 2008-03-14 00:00:00.0000000 +00:00 | 2008-09-17 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2004-04-29 00:00:00.0000000 +00:00 | 2006-07-13 00:00:00.0000000 +00:00 | 2008-03-14 00:00:00.0000000 +00:00 | 2008-09-17 00:00:00.0000000 +00:00 | 2012-07-30 00:00:00.0000000 +00:00 | 2004-04-29 00:00:00.0000000 +00:00 | 2006-07-13 00:00:00.0000000 +00:00 | 2008-03-14 00:00:00.0000000 +00:00 | 2008-09-17 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2004-04-29 00:00:00.0000000 +00:00 | 2006-07-13 00:00:00.0000000 +00:00 |  | 2008-09-17 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2008-03-14 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 11:07:53.5089041 -05:00
LQQ122-DL1 | Y | 2011-08-05 00:00:00.0000000 +00:00 | 2012-03-26 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | 2011-08-05 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2013-05-22 00:00:00.0000000 +00:00 | 2014-02-18 00:00:00.0000000 +00:00 | 2011-08-05 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2014-04-23 00:00:00.0000000 +00:00 | 2011-08-05 00:00:00.0000000 +00:00 | 2012-03-26 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2014-03-08 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 11:04:34.4241235 -05:00
LQQ122-DL2 | Y | 2011-08-05 00:00:00.0000000 +00:00 | 2012-03-26 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | 2011-08-05 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2013-05-22 00:00:00.0000000 +00:00 | 2014-02-18 00:00:00.0000000 +00:00 | 2011-08-05 00:00:00.0000000 +00:00 | 2012-03-25 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2014-03-26 00:00:00.0000000 +00:00 | 2011-08-05 00:00:00.0000000 +00:00 | 2012-03-26 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2013-06-19 00:00:00.0000000 +00:00 | 2014-04-25 00:00:00.0000000 +00:00 | 2012-05-16 00:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 11:07:26.8593018 -05:00
LQQ122-DL3 | Y | 2012-06-05 00:00:00.0000000 +00:00 | 2014-01-31 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2017-07-10 00:00:00.0000000 +00:00 | 2018-07-27 00:00:00.0000000 +00:00 | 2012-06-05 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-03-15 00:00:00.0000000 +00:00 | 2014-09-27 00:00:00.0000000 +00:00 | 2015-04-26 00:00:00.0000000 +00:00 | 2012-06-05 00:00:00.0000000 +00:00 | 2014-01-31 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2018-02-10 00:00:00.0000000 +00:00 | 2019-12-02 00:00:00.0000000 +00:00 | 2012-06-05 00:00:00.0000000 +00:00 | 2014-01-31 00:00:00.0000000 +00:00 |  | 2017-07-14 00:00:00.0000000 +00:00 |  | 2016-12-12 00:00:00.0000000 +00:00 | 2018-08-14 00:00:00.0000000 +00:00 | [21 empty] | 2020-07-27 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-28 11:19:37.4617965 -04:00
LQQ122EE2 | Y | 2010-01-07 00:00:00.0000000 +00:00 | 2010-10-20 00:00:00.0000000 +00:00 | 2015-07-08 00:00:00.0000000 +00:00 | 2016-08-03 00:00:00.0000000 +00:00 | 2018-08-03 00:00:00.0000000 +00:00 | 2010-01-07 00:00:00.0000000 +00:00 | 2010-09-05 00:00:00.0000000 +00:00 | 2011-09-08 00:00:00.0000000 +00:00 | 2012-01-22 00:00:00.0000000 +00:00 | 2013-06-14 00:00:00.0000000 +00:00 | 2010-01-07 00:00:00.0000000 +00:00 | 2010-10-05 00:00:00.0000000 +00:00 | 2015-02-19 00:00:00.0000000 +00:00 | 2016-04-21 00:00:00.0000000 +00:00 | 2017-09-12 00:00:00.0000000 +00:00 | 2010-01-07 00:00:00.0000000 +00:00 | 2010-10-20 00:00:00.0000000 +00:00 |  | 2016-08-03 18:00:00.0000000 +00:00 |  | 2015-07-08 00:00:00.0000000 +00:00 | 2018-08-03 00:00:00.0000000 +00:00 | [21 empty] | 2020-08-03 00:00:00.0000000 +00:00
LQQ122-FA1 | Y | 2011-09-30 00:00:00.0000000 +00:00 | 2012-01-14 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 | 2018-06-24 00:00:00.0000000 +00:00 | 2021-06-24 00:00:00.0000000 +00:00 | 2011-09-30 00:00:00.0000000 +00:00 | 2011-12-13 00:00:00.0000000 +00:00 | 2013-09-28 00:00:00.0000000 +00:00 | 2018-04-24 00:00:00.0000000 +00:00 | 2021-05-18 00:00:00.0000000 +00:00 | 2011-09-30 00:00:00.0000000 +00:00 | 2012-01-14 00:00:00.0000000 +00:00 | 2016-03-25 00:00:00.0000000 +00:00 | 2016-08-28 00:00:00.0000000 +00:00 | 2018-12-17 00:00:00.0000000 +00:00 | 2011-09-30 00:00:00.0000000 +00:00 | 2012-01-10 00:00:00.0000000 +00:00 | 2017-08-18 00:00:00.0000000 +00:00 |  |  | 2017-08-21 00:00:00.0000000 +00:00 | [27 empty] | 2017-10-24 10:30:10.9821886 -04:00
LQQ122-FA2 | Y | 2015-04-04 00:00:00.0000000 +00:00 | 2016-04-03 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2015-07-28 00:00:00.0000000 +00:00 | 2016-04-03 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2018-01-12 00:00:00.0000000 +00:00 | 2018-04-09 00:00:00.0000000 +00:00 | 2019-10-29 00:00:00.0000000 +00:00 | 2020-06-29 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2015-07-09 00:00:00.0000000 +00:00 | 2015-10-10 00:00:00.0000000 +00:00 |  |  | 2015-10-10 00:00:00.0000000 +00:00
LQQ122-KE | Y | 2007-11-26 00:00:00.0000000 +00:00 | 2008-08-07 00:00:00.0000000 +00:00 | 2010-12-31 00:00:00.0000000 +00:00 | 2012-10-12 00:00:00.0000000 +00:00 | 2017-04-28 00:00:00.0000000 +00:00 | 2007-11-26 00:00:00.0000000 +00:00 | 2008-08-17 00:00:00.0000000 +00:00 | 2009-05-24 00:00:00.0000000 +00:00 | 2009-11-06 00:00:00.0000000 +00:00 | 2011-03-30 00:00:00.0000000 +00:00 | 2007-11-26 00:00:00.0000000 +00:00 | 2008-08-17 00:00:00.0000000 +00:00 | 2011-01-10 00:00:00.0000000 +00:00 | 2012-10-09 00:00:00.0000000 +00:00 | 2016-10-25 00:00:00.0000000 +00:00 | 2007-11-26 00:00:00.0000000 +00:00 | 2008-08-07 00:00:00.0000000 +00:00 |  | 2012-01-10 00:00:00.0000000 +00:00 | 2017-04-28 00:00:00.0000000 +00:00 | 2011-01-10 00:00:00.0000000 +00:00 | 2017-04-28 00:00:00.0000000 +00:00
LQQ122-KE1 | Y | 2012-05-01 00:00:00.0000000 +00:00 |  |  | 2012-07-02 00:00:00.0000000 +00:00 | 2017-06-02 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 |  |  | 2012-07-02 00:00:00.0000000 +00:00 | 2013-01-22 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 |  |  | 2012-07-02 00:00:00.0000000 +00:00 | 2013-01-22 00:00:00.0000000 +00:00 | 2012-05-01 00:00:00.0000000 +00:00 |  |  | 2012-07-02 00:00:00.0000000 +00:00 | 2013-01-22 00:00:00.0000000 +00:00 |  | 2013-01-22 00:00:00.0000000 +00:00
LQQ122LRC | Y | 2012-12-13 00:00:00.0000000 +00:00 | 2013-02-28 00:00:00.0000000 +00:00 | 2013-04-08 00:00:00.0000000 +00:00 | 2014-05-26 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2012-12-31 00:00:00.0000000 +00:00 | 2013-02-28 00:00:00.0000000 +00:00 | 2013-05-25 00:00:00.0000000 +00:00 | 2013-10-18 00:00:00.0000000 +00:00 | 2014-04-02 00:00:00.0000000 +00:00 | 2012-12-31 00:00:00.0000000 +00:00 | 2013-02-28 00:00:00.0000000 +00:00 | 2013-05-25 00:00:00.0000000 +00:00 | 2014-03-19 00:00:00.0000000 +00:00 | 2016-01-02 00:00:00.0000000 +00:00 | 2012-12-13 00:00:00.0000000 +00:00 | 2013-02-28 00:00:00.0000000 +00:00 |  | 2014-05-26 00:00:00.0000000 +00:00 | 2014-09-10 00:00:00.0000000 +00:00 | 2013-05-25 00:00:00.0000000 +00:00 | 2015-11-25 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 12:33:59.8909939 -05:00
LQQBHHVAC | Y | 2016-02-05 00:00:00.0000000 +00:00 | 2017-01-17 00:00:00.0000000 +00:00 | 2019-07-05 00:00:00.0000000 +00:00 | 2020-02-02 00:00:00.0000000 +00:00 | 2021-05-04 00:00:00.0000000 +00:00 | 2016-02-05 00:00:00.0000000 +00:00 | 2017-04-12 00:00:00.0000000 +00:00 | 2017-05-03 00:00:00.0000000 +00:00 | 2017-05-22 00:00:00.0000000 +00:00 | 2017-06-03 00:00:00.0000000 +00:00 | 2016-02-05 00:00:00.0000000 +00:00 | 2017-04-12 00:00:00.0000000 +00:00 | 2018-07-03 00:00:00.0000000 +00:00 | 2019-07-20 00:00:00.0000000 +00:00 | 2020-10-19 00:00:00.0000000 +00:00 | 2016-02-05 00:00:00.0000000 +00:00 | 2017-01-17 17:00:00.0000000 +00:00 |  |  |  | 2019-07-05 00:00:00.0000000 +00:00 | [27 empty] | 2017-11-28 14:54:05.7231728 -05:00
LQQVHVAC | Y | 2015-10-19 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | 2019-02-03 00:00:00.0000000 +00:00 | 2020-02-04 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2016-08-18 00:00:00.0000000 +00:00 | 2017-07-21 00:00:00.0000000 +00:00 | 2018-07-24 00:00:00.0000000 +00:00 | 2019-07-25 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2017-01-05 00:00:00.0000000 +00:00 | 2018-01-17 00:00:00.0000000 +00:00 | 2018-08-08 00:00:00.0000000 +00:00 | 2019-08-09 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2017-03-06 17:00:00.0000000 +00:00 |  |  |  | 2018-08-17 00:00:00.0000000 +00:00 | [22 empty] | 2022-01-27 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-27 16:13:23.6667991 -05:00
LQQVROOF | Y | 2015-10-19 00:00:00.0000000 +00:00 | 2017-05-25 00:00:00.0000000 +00:00 | 2018-09-22 00:00:00.0000000 +00:00 | 2019-03-22 00:00:00.0000000 +00:00 | 2020-03-22 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2016-08-18 00:00:00.0000000 +00:00 | 2017-07-21 00:00:00.0000000 +00:00 | 2018-07-24 00:00:00.0000000 +00:00 | 2019-07-25 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2016-08-18 00:00:00.0000000 +00:00 | 2017-07-21 00:00:00.0000000 +00:00 | 2018-04-24 00:00:00.0000000 +00:00 | 2019-04-25 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2017-05-05 17:00:00.0000000 +00:00 |  |  |  | 2018-09-22 00:00:00.0000000 +00:00 | [27 empty] | 2017-11-22 15:07:18.0515089 -05:00
LQRAVUPK | Y | 2014-03-17 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2015-07-29 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2015-07-29 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2015-07-29 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2015-05-19 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2015-07-29 00:00:00.0000000 +00:00 |  | 2015-07-29 00:00:00.0000000 +00:00 | [26 empty] | 2017-11-30 11:08:43.0664984 -05:00
LQRDMASON | Y | 2015-11-16 00:00:00.0000000 +00:00 | 2016-11-18 00:00:00.0000000 +00:00 | 2018-10-05 00:00:00.0000000 +00:00 | 2019-05-06 00:00:00.0000000 +00:00 | 2020-05-06 00:00:00.0000000 +00:00 | 2015-11-16 00:00:00.0000000 +00:00 | 2016-04-26 00:00:00.0000000 +00:00 | 2017-02-06 00:00:00.0000000 +00:00 | 2017-07-24 00:00:00.0000000 +00:00 | 2018-01-31 00:00:00.0000000 +00:00 | 2015-11-16 00:00:00.0000000 +00:00 | 2016-04-26 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | 2031-08-29 00:00:00.0000000 +00:00 | 2032-03-07 00:00:00.0000000 +00:00 | 2015-11-16 00:00:00.0000000 +00:00 | 2016-11-18 17:00:00.0000000 +00:00 |  |  |  | 2018-10-05 00:00:00.0000000 +00:00 | [22 empty] | 2022-01-13 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-28 14:25:35.5613292 -05:00
LQSARENOV | Y | 2015-12-23 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-06-05 00:00:00.0000000 +00:00 | 2019-11-18 00:00:00.0000000 +00:00 | 2021-11-16 00:00:00.0000000 +00:00 | 2015-12-23 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2018-03-24 00:00:00.0000000 +00:00 | 2019-03-26 00:00:00.0000000 +00:00 | 2021-03-24 00:00:00.0000000 +00:00 | 2015-12-23 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2018-03-24 00:00:00.0000000 +00:00 | 2018-12-26 00:00:00.0000000 +00:00 | 2020-12-24 00:00:00.0000000 +00:00 | 2015-12-23 00:00:00.0000000 +00:00 | [32 empty] | 2017-09-12 11:51:07.8034636 -04:00
LQSAROOF | Y | 2015-01-21 00:00:00.0000000 +00:00 | 2015-10-21 00:00:00.0000000 +00:00 | 2017-06-02 00:00:00.0000000 +00:00 | 2018-02-16 00:00:00.0000000 +00:00 | 2019-02-28 00:00:00.0000000 +00:00 | 2015-01-21 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2016-06-04 00:00:00.0000000 +00:00 | 2016-10-27 00:00:00.0000000 +00:00 | 2017-07-12 00:00:00.0000000 +00:00 | 2015-01-21 00:00:00.0000000 +00:00 | 2015-10-16 00:00:00.0000000 +00:00 | 2017-06-29 00:00:00.0000000 +00:00 | 2017-11-21 00:00:00.0000000 +00:00 | 2019-04-21 00:00:00.0000000 +00:00 | 2015-01-21 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2017-06-02 00:00:00.0000000 +00:00 |  |  | 2017-06-02 00:00:00.0000000 +00:00
LQSEHVAC | Y | 2015-11-19 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2019-01-12 00:00:00.0000000 +00:00 | 2019-12-15 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-08-03 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-05-17 00:00:00.0000000 +00:00 | 2018-10-16 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-08-03 00:00:00.0000000 +00:00 | 2018-01-15 00:00:00.0000000 +00:00 | 2018-05-17 00:00:00.0000000 +00:00 | 2018-10-16 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-11-15 17:00:00.0000000 +00:00 |  |  |  | 2020-07-16 00:00:00.0000000 +00:00 | [21 empty] | 2020-10-15 00:00:00.0000000 +00:00 | 2021-12-14 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-29 12:22:29.5359807 -05:00
LQSUADA | Y | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 | 2016-08-19 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2019-07-22 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-12-23 00:00:00.0000000 +00:00 | 2017-10-24 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-07-03 00:00:00.0000000 +00:00 | 2018-05-04 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 |  |  |  | 2016-07-29 00:00:00.0000000 +00:00 | [27 empty] | 2017-08-31 15:38:14.2242223 -04:00
LQWSADA | Y | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 | 2016-08-19 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2019-07-23 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2016-12-23 00:00:00.0000000 +00:00 | 2017-10-24 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-07-03 00:00:00.0000000 +00:00 | 2018-05-04 00:00:00.0000000 +00:00 | 2015-10-26 00:00:00.0000000 +00:00 | 2015-12-11 00:00:00.0000000 +00:00 |  |  |  | 2016-07-29 00:00:00.0000000 +00:00 | [27 empty] | 2017-12-05 15:25:45.7395565 -05:00
LRCA08SCH | Y | 2008-01-27 00:00:00.0000000 +00:00 | 2010-05-07 00:00:00.0000000 +00:00 | 2013-08-01 00:00:00.0000000 +00:00 | 2014-08-04 00:00:00.0000000 +00:00 | 2016-01-28 00:00:00.0000000 +00:00 | 2008-01-27 00:00:00.0000000 +00:00 | 2009-09-13 00:00:00.0000000 +00:00 | 2010-10-08 00:00:00.0000000 +00:00 | 2011-05-22 00:00:00.0000000 +00:00 | 2012-10-24 00:00:00.0000000 +00:00 | 2008-01-27 00:00:00.0000000 +00:00 | 2010-05-01 00:00:00.0000000 +00:00 | 2013-07-26 00:00:00.0000000 +00:00 | 2014-09-24 00:00:00.0000000 +00:00 | 2016-02-27 00:00:00.0000000 +00:00 | 2008-01-27 00:00:00.0000000 +00:00 | 2010-05-07 00:00:00.0000000 +00:00 | 2013-08-01 00:00:00.0000000 +00:00 |  |  | 2013-08-01 00:00:00.0000000 +00:00 | 2013-06-17 00:00:00.0000000 +00:00 | [26 empty] | 2017-08-31 16:51:59.8501211 -04:00
LRCA11LPA | Y | 2012-01-27 00:00:00.0000000 +00:00 | 2012-02-01 00:00:00.0000000 +00:00 | 2012-02-14 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2015-07-21 00:00:00.0000000 +00:00 | 2012-01-27 00:00:00.0000000 +00:00 | 2012-02-01 00:00:00.0000000 +00:00 | 2012-02-14 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2015-07-21 00:00:00.0000000 +00:00 | 2012-01-27 00:00:00.0000000 +00:00 | 2012-02-01 00:00:00.0000000 +00:00 | 2012-02-14 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2015-07-21 00:00:00.0000000 +00:00 | 2012-01-27 00:00:00.0000000 +00:00 | 2012-02-01 00:00:00.0000000 +00:00 | 2012-02-14 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2015-07-21 00:00:00.0000000 +00:00 |  | 2015-07-21 00:00:00.0000000 +00:00
LRCA13LPA | Y | 2013-07-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-11-21 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2014-02-05 00:00:00.0000000 +00:00 | 2015-03-31 00:00:00.0000000 +00:00 | 2015-10-14 00:00:00.0000000 +00:00 | 2016-08-09 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-01-12 00:00:00.0000000 +00:00 | 2016-05-03 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2017-06-29 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-02-03 00:00:00.0000000 +00:00 | 2016-10-20 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2017-09-27 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 |  | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-02-03 00:00:00.0000000 +00:00 | 2015-02-03 00:00:00.0000000 +00:00 |  |  | 2015-06-18 00:00:00.0000000 +00:00 | 2015-06-18 00:00:00.0000000 +00:00 | 2015-06-18 00:00:00.0000000 +00:00 |  |  | 2016-02-26 00:00:00.0000000 +00:00 | 2016-02-26 00:00:00.0000000 +00:00 | 2016-02-26 00:00:00.0000000 +00:00 | 2016-10-20 00:00:00.0000000 +00:00 | 2016-10-20 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2018-08-09 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 |  | 2018-06-17 00:00:00.0000000 +00:00 | 2018-06-17 00:00:00.0000000 +00:00 |  | 2017-09-27 13:38:51.3824033 -04:00
LRCA17SCH | Y | 2017-08-01 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2017-11-14 00:00:00.0000000 +00:00 | 2018-05-14 00:00:00.0000000 +00:00 | 2021-05-14 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2017-11-14 00:00:00.0000000 +00:00 | 2018-05-14 00:00:00.0000000 +00:00 | 2021-05-14 00:00:00.0000000 +00:00 | [5 empty] | 2017-08-01 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | [30 empty] | 2017-09-09 15:33:19.3900000 +00:00
MED594 | Y | 2007-02-23 00:00:00.0000000 +00:00 | 2012-08-22 00:00:00.0000000 +00:00 | 2018-05-14 00:00:00.0000000 +00:00 | 2019-01-08 00:00:00.0000000 +00:00 | 2022-01-07 00:00:00.0000000 +00:00 | 2007-02-23 00:00:00.0000000 +00:00 | 2009-10-15 00:00:00.0000000 +00:00 | 2010-04-15 00:00:00.0000000 +00:00 | 2010-10-15 00:00:00.0000000 +00:00 | 2011-10-14 00:00:00.0000000 +00:00 | 2007-02-23 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-11-29 00:00:00.0000000 +00:00 | 2015-11-28 00:00:00.0000000 +00:00 | 2007-02-23 00:00:00.0000000 +00:00 | 2012-08-22 00:00:00.0000000 +00:00 |  |  |  | 2017-10-17 00:00:00.0000000 +00:00 |  | 2007-02-23 00:00:00.0000000 +00:00 |  | 2012-08-22 00:00:00.0000000 +00:00 |  | 2010-01-08 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | 2014-07-25 00:00:00.0000000 +00:00 | [6 empty] | 2017-10-16 00:00:00.0000000 +00:00 |  | 2018-05-27 00:00:00.0000000 +00:00 |  | 2021-05-25 00:00:00.0000000 +00:00 |  | 2014-10-13 00:00:00.0000000 +00:00 | 2025-01-06 00:00:00.0000000 +00:00 |  | 2024-05-24 00:00:00.0000000 +00:00
MED597 | Y | 2007-02-16 00:00:00.0000000 +00:00 | 2020-04-14 00:00:00.0000000 +00:00 | 2022-01-15 00:00:00.0000000 +00:00 | 2022-07-15 00:00:00.0000000 +00:00 | 2024-07-14 00:00:00.0000000 +00:00 | 2007-02-16 00:00:00.0000000 +00:00 | 2009-04-01 00:00:00.0000000 +00:00 | 2010-04-01 00:00:00.0000000 +00:00 | 2010-10-01 00:00:00.0000000 +00:00 | 2011-10-01 00:00:00.0000000 +00:00 | 2007-02-16 00:00:00.0000000 +00:00 | 2019-05-15 00:00:00.0000000 +00:00 | 2020-05-25 00:00:00.0000000 +00:00 | 2020-11-24 00:00:00.0000000 +00:00 | 2021-11-24 00:00:00.0000000 +00:00 | 2007-02-16 00:00:00.0000000 +00:00 | [10 empty] | 2010-01-01 00:00:00.0000000 +00:00 | 2021-06-15 00:00:00.0000000 +00:00 | [14 empty] | 2014-09-30 00:00:00.0000000 +00:00 | 2027-07-14 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-31 13:49:43.1029742 -04:00
MED598 | Y | 2007-02-15 00:00:00.0000000 +00:00 | 2008-07-01 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2018-04-16 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2008-04-01 00:00:00.0000000 +00:00 | 2009-04-01 00:00:00.0000000 +00:00 | 2009-10-01 00:00:00.0000000 +00:00 | 2010-10-01 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2008-07-01 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2016-08-27 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2008-07-01 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 |  | 2012-04-18 00:00:00.0000000 +00:00 | 2016-10-29 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2007-02-15 00:00:00.0000000 +00:00 | 2008-07-01 00:00:00.0000000 +00:00 | 2008-07-01 00:00:00.0000000 +00:00 |  | 2011-05-09 00:00:00.0000000 +00:00 | 2011-05-09 00:00:00.0000000 +00:00 | 2011-05-09 00:00:00.0000000 +00:00 | 2011-05-09 00:00:00.0000000 +00:00 | [5 empty] | 2012-04-18 00:00:00.0000000 +00:00 | 2012-04-18 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2012-12-17 00:00:00.0000000 +00:00 | 2018-04-16 00:00:00.0000000 +00:00 | 2018-04-16 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2021-04-15 00:00:00.0000000 +00:00 |  | 2021-04-15 00:00:00.0000000 +00:00 | 2021-04-15 00:00:00.0000000 +00:00
MED598B | Y | 2011-06-03 00:00:00.0000000 +00:00 | 2012-06-28 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2011-06-03 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2017-01-15 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2019-07-14 00:00:00.0000000 +00:00 | 2011-06-03 00:00:00.0000000 +00:00 | 2012-06-28 00:00:00.0000000 +00:00 | 2015-03-01 00:00:00.0000000 +00:00 | 2015-08-29 00:00:00.0000000 +00:00 | 2017-08-27 00:00:00.0000000 +00:00 | 2011-06-03 00:00:00.0000000 +00:00 | 2012-06-28 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 |  | 2014-02-19 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2011-06-03 00:00:00.0000000 +00:00 | 2011-06-03 00:00:00.0000000 +00:00 | 2012-06-28 00:00:00.0000000 +00:00 | 2012-06-28 00:00:00.0000000 +00:00 |  | 2013-06-24 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | [5 empty] | 2014-06-19 00:00:00.0000000 +00:00 | 2014-06-19 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2021-01-02 00:00:00.0000000 +00:00 | 2022-01-02 00:00:00.0000000 +00:00 |  | 2022-01-02 00:00:00.0000000 +00:00 | 2022-01-02 00:00:00.0000000 +00:00 |  | 2017-11-29 14:54:44.3916088 -05:00
MED600B | Y | 2010-04-22 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2016-07-13 00:00:00.0000000 +00:00 | 2010-04-22 00:00:00.0000000 +00:00 | 2011-03-12 00:00:00.0000000 +00:00 | 2012-01-15 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2010-04-22 00:00:00.0000000 +00:00 | 2012-08-19 00:00:00.0000000 +00:00 | 2012-07-12 00:00:00.0000000 +00:00 | 2013-01-10 00:00:00.0000000 +00:00 | 2015-01-11 00:00:00.0000000 +00:00 | 2010-04-22 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2016-07-31 00:00:00.0000000 +00:00 | 2010-04-22 00:00:00.0000000 +00:00 | 2010-04-22 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 | 2011-08-15 00:00:00.0000000 +00:00 |  | 2011-10-27 00:00:00.0000000 +00:00 | 2011-10-27 00:00:00.0000000 +00:00 | 2011-10-27 00:00:00.0000000 +00:00 | 2011-10-27 00:00:00.0000000 +00:00 | [5 empty] | 2012-08-21 00:00:00.0000000 +00:00 | 2012-08-21 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2016-07-13 00:00:00.0000000 +00:00 | 2016-07-13 00:00:00.0000000 +00:00 | 2017-07-15 00:00:00.0000000 +00:00 | 2019-10-14 00:00:00.0000000 +00:00 |  | 2019-07-13 00:00:00.0000000 +00:00 | 2019-07-13 00:00:00.0000000 +00:00 |  | 2017-09-01 16:32:22.0736396 -04:00
MED607 | Y | 2008-05-01 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2015-08-27 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2019-09-22 00:00:00.0000000 +00:00 | 2008-05-01 00:00:00.0000000 +00:00 | 2009-07-15 00:00:00.0000000 +00:00 | 2011-01-15 00:00:00.0000000 +00:00 | 2011-08-01 00:00:00.0000000 +00:00 | 2013-07-31 00:00:00.0000000 +00:00 | 2008-05-01 00:00:00.0000000 +00:00 | 2013-03-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2015-04-16 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2008-05-01 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2015-08-27 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 |  | 2021-03-13 00:00:00.0000000 +00:00 | 2019-09-22 00:00:00.0000000 +00:00 | 2008-05-01 00:00:00.0000000 +00:00 | 2008-05-01 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 | 2013-09-30 00:00:00.0000000 +00:00 |  | 2015-02-20 00:00:00.0000000 +00:00 | 2015-02-20 00:00:00.0000000 +00:00 | 2015-02-20 00:00:00.0000000 +00:00 | 2015-02-20 00:00:00.0000000 +00:00 | [5 empty] | 2015-08-27 00:00:00.0000000 +00:00 | 2015-08-27 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2017-03-27 00:00:00.0000000 +00:00 | 2019-09-22 00:00:00.0000000 +00:00 | 2019-09-22 00:00:00.0000000 +00:00 | 2016-07-30 00:00:00.0000000 +00:00 | 2022-09-21 00:00:00.0000000 +00:00 |  | 2022-09-21 00:00:00.0000000 +00:00 | 2022-09-21 00:00:00.0000000 +00:00 |  | 2017-09-01 15:36:58.2952009 -04:00
MED608 | Y | 2009-03-06 00:00:00.0000000 +00:00 | 2013-01-29 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-09-08 00:00:00.0000000 +00:00 | 2018-06-23 00:00:00.0000000 +00:00 | 2009-03-06 00:00:00.0000000 +00:00 | 2013-01-29 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-09-08 00:00:00.0000000 +00:00 | 2018-06-23 00:00:00.0000000 +00:00 | 2009-03-06 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-04-13 00:00:00.0000000 +00:00 | 2017-02-21 00:00:00.0000000 +00:00 | 2018-09-05 00:00:00.0000000 +00:00 | 2009-03-06 00:00:00.0000000 +00:00 | 2013-01-29 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-09-08 00:00:00.0000000 +00:00 |  | 2014-08-27 00:00:00.0000000 +00:00 | 2018-06-23 00:00:00.0000000 +00:00 | 2009-03-06 00:00:00.0000000 +00:00 | 2009-03-06 00:00:00.0000000 +00:00 | 2013-01-29 00:00:00.0000000 +00:00 | 2013-01-29 00:00:00.0000000 +00:00 | 2013-05-12 00:00:00.0000000 +00:00 | 2013-05-12 00:00:00.0000000 +00:00 | 2013-05-12 00:00:00.0000000 +00:00 | 2013-05-12 00:00:00.0000000 +00:00 | 2013-05-12 00:00:00.0000000 +00:00 | [5 empty] | 2014-08-27 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-09-08 00:00:00.0000000 +00:00 | 2015-09-08 00:00:00.0000000 +00:00 | 2018-06-23 00:00:00.0000000 +00:00 | 2018-06-23 00:00:00.0000000 +00:00 | 2020-06-23 00:00:00.0000000 +00:00 | 2020-06-23 00:00:00.0000000 +00:00 |  | 2020-06-23 00:00:00.0000000 +00:00 | 2020-06-23 00:00:00.0000000 +00:00 |  | 2017-09-19 12:05:08.5536184 -04:00
MED609 | Y | 2008-06-06 00:00:00.0000000 +00:00 | 2010-03-01 00:00:00.0000000 +00:00 | 2011-07-22 00:00:00.0000000 +00:00 | 2012-04-23 00:00:00.0000000 +00:00 | 2021-01-23 00:00:00.0000000 +00:00 | 2008-06-06 00:00:00.0000000 +00:00 | 2009-07-15 00:00:00.0000000 +00:00 | 2011-01-15 00:00:00.0000000 +00:00 | 2011-08-01 00:00:00.0000000 +00:00 | 2013-07-31 00:00:00.0000000 +00:00 | 2008-06-06 00:00:00.0000000 +00:00 | 2009-08-20 00:00:00.0000000 +00:00 | 2011-04-12 00:00:00.0000000 +00:00 | 2012-01-13 00:00:00.0000000 +00:00 | 2014-01-12 00:00:00.0000000 +00:00 | 2008-06-06 18:00:00.0000000 +00:00 | 2010-03-01 17:00:00.0000000 +00:00 | 2011-07-22 00:00:00.0000000 +00:00 | 2012-04-23 18:00:00.0000000 +00:00 |  | 2011-04-23 00:00:00.0000000 +00:00 | 2020-01-24 00:00:00.0000000 +00:00 | 2008-06-06 00:00:00.0000000 +00:00 | 2008-06-06 00:00:00.0000000 +00:00 | 2010-03-01 00:00:00.0000000 +00:00 | 2010-03-01 00:00:00.0000000 +00:00 | 2010-04-09 00:00:00.0000000 +00:00 | 2010-11-10 00:00:00.0000000 +00:00 | 2010-11-17 00:00:00.0000000 +00:00 | 2010-11-17 00:00:00.0000000 +00:00 | 2010-11-17 00:00:00.0000000 +00:00 | [5 empty] | 2011-07-22 00:00:00.0000000 +00:00 | 2011-07-22 00:00:00.0000000 +00:00 | 2012-04-23 00:00:00.0000000 +00:00 | 2012-04-23 00:00:00.0000000 +00:00 | 2017-10-18 00:00:00.0000000 +00:00 | 2017-10-18 00:00:00.0000000 +00:00 | 2016-07-31 00:00:00.0000000 +00:00 | 2024-01-23 00:00:00.0000000 +00:00 |  | 2020-10-18 00:00:00.0000000 +00:00 | 2020-10-18 00:00:00.0000000 +00:00 |  | 2017-10-17 17:05:24.1827760 -04:00
MED611 | Y | 2015-03-13 00:00:00.0000000 +00:00 | 2022-01-15 00:00:00.0000000 +00:00 | 2022-12-31 00:00:00.0000000 +00:00 | 2023-06-30 00:00:00.0000000 +00:00 | 2024-06-28 00:00:00.0000000 +00:00 | 2015-03-13 00:00:00.0000000 +00:00 | 2022-01-15 00:00:00.0000000 +00:00 | 2022-12-31 00:00:00.0000000 +00:00 | 2023-06-30 00:00:00.0000000 +00:00 | 2024-06-28 00:00:00.0000000 +00:00 | [5 empty] | 2015-03-13 00:00:00.0000000 +00:00 |  |  |  |  | 2022-12-31 00:00:00.0000000 +00:00 | 2024-06-28 00:00:00.0000000 +00:00 |  |  |  |  | 2022-06-30 00:00:00.0000000 +00:00 | 2022-06-30 00:00:00.0000000 +00:00 | [14 empty] | 2026-06-29 00:00:00.0000000 +00:00 | 2026-06-29 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-01 17:36:13.0576595 -04:00
MED616 | Y | 2014-05-19 00:00:00.0000000 +00:00 | 2016-05-26 00:00:00.0000000 +00:00 | 2017-11-10 00:00:00.0000000 +00:00 | 2018-05-09 00:00:00.0000000 +00:00 | 2020-05-10 00:00:00.0000000 +00:00 | 2014-05-19 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-05-19 17:00:00.0000000 +00:00 | 2016-05-26 18:00:00.0000000 +00:00 |  |  |  | 2017-11-10 00:00:00.0000000 +00:00 |  | 2014-05-19 17:00:00.0000000 +00:00 |  | 2016-05-26 18:00:00.0000000 +00:00 |  | 2017-11-05 00:00:00.0000000 +00:00 | 2017-11-05 00:00:00.0000000 +00:00 |  | 2017-11-05 00:00:00.0000000 +00:00 | [6 empty] | 2017-11-10 00:00:00.0000000 +00:00 |  | 2018-05-09 00:00:00.0000000 +00:00 |  | 2020-05-10 00:00:00.0000000 +00:00 |  | 2023-06-30 00:00:00.0000000 +00:00 | 2023-05-10 00:00:00.0000000 +00:00 |  | 2023-05-10 00:00:00.0000000 +00:00 |  |  | 2017-08-31 15:12:18.0756616 -04:00
MED617 | Y | 2010-05-12 00:00:00.0000000 +00:00 | 2011-08-08 00:00:00.0000000 +00:00 | 2012-02-08 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2010-07-01 00:00:00.0000000 +00:00 | 2011-01-03 00:00:00.0000000 +00:00 | 2011-07-01 00:00:00.0000000 +00:00 | 2012-07-01 00:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2011-04-09 00:00:00.0000000 +00:00 | 2012-04-08 00:00:00.0000000 +00:00 | 2012-10-04 00:00:00.0000000 +00:00 | 2013-10-05 00:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2011-08-08 00:00:00.0000000 +00:00 | 2012-02-08 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2012-08-07 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2010-05-12 00:00:00.0000000 +00:00 | 2011-08-08 00:00:00.0000000 +00:00 | 2011-08-08 00:00:00.0000000 +00:00 |  | 2011-10-11 00:00:00.0000000 +00:00 | 2011-10-11 00:00:00.0000000 +00:00 | 2011-10-11 00:00:00.0000000 +00:00 | 2011-10-11 00:00:00.0000000 +00:00 | [5 empty] | 2012-02-08 00:00:00.0000000 +00:00 | 2012-02-08 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2015-06-05 00:00:00.0000000 +00:00 | 2015-07-01 00:00:00.0000000 +00:00 | 2018-06-04 00:00:00.0000000 +00:00 |  | 2018-06-04 00:00:00.0000000 +00:00 | 2018-06-04 00:00:00.0000000 +00:00 |  | 2017-09-01 16:35:58.2297176 -04:00
MED619 | Y | 2013-10-15 00:00:00.0000000 +00:00 | 2016-05-24 00:00:00.0000000 +00:00 | 2018-05-10 00:00:00.0000000 +00:00 | 2019-01-04 00:00:00.0000000 +00:00 | 2021-01-04 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | 2017-10-14 00:00:00.0000000 +00:00 | 2019-10-15 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-10-16 00:00:00.0000000 +00:00 | 2017-04-14 00:00:00.0000000 +00:00 | 2017-10-14 00:00:00.0000000 +00:00 | 2019-10-15 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2016-05-24 00:00:00.0000000 +00:00 |  |  |  | 2017-11-10 00:00:00.0000000 +00:00 |  | 2013-10-15 00:00:00.0000000 +00:00 |  | 2016-05-24 00:00:00.0000000 +00:00 |  | 2016-09-15 00:00:00.0000000 +00:00 | 2018-02-12 00:00:00.0000000 +00:00 |  | 2018-02-12 00:00:00.0000000 +00:00 | [6 empty] | 2018-05-10 00:00:00.0000000 +00:00 |  | 2018-05-12 00:00:00.0000000 +00:00 |  | 2020-05-12 00:00:00.0000000 +00:00 |  | 2022-10-14 00:00:00.0000000 +00:00 | 2023-11-06 00:00:00.0000000 +00:00 |  | 2023-05-12 00:00:00.0000000 +00:00
MED625 | Y | 2011-08-01 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2013-11-25 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | 2011-08-01 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2011-08-01 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2015-01-15 00:00:00.0000000 +00:00 | 2011-08-01 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2013-11-25 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 |  | 2013-11-25 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | 2011-08-01 00:00:00.0000000 +00:00 | 2011-08-01 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2012-12-14 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | [5 empty] | 2013-11-25 00:00:00.0000000 +00:00 | 2013-11-25 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 | 2015-01-19 00:00:00.0000000 +00:00 | 2017-06-16 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | 2018-01-14 00:00:00.0000000 +00:00 | 2021-07-19 00:00:00.0000000 +00:00 |  | 2020-06-15 00:00:00.0000000 +00:00 | 2021-07-19 00:00:00.0000000 +00:00
MED630 | Y | 2013-05-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2016-09-21 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 | 2021-06-20 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-05-31 00:00:00.0000000 +00:00 | 2016-01-16 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2018-07-14 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2014-05-31 00:00:00.0000000 +00:00 | 2016-01-16 00:00:00.0000000 +00:00 | 2016-07-15 00:00:00.0000000 +00:00 | 2018-07-14 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2016-09-21 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 |  |  | 2021-06-20 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2015-09-03 00:00:00.0000000 +00:00 | 2015-09-03 00:00:00.0000000 +00:00 | 2015-09-03 00:00:00.0000000 +00:00 | 2015-09-03 00:00:00.0000000 +00:00 | [5 empty] | 2016-09-21 00:00:00.0000000 +00:00 | 2016-09-21 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 | 2017-09-25 00:00:00.0000000 +00:00 | 2019-03-22 00:00:00.0000000 +00:00 | 2021-06-20 00:00:00.0000000 +00:00 | 2021-07-13 00:00:00.0000000 +00:00 | 2024-06-20 00:00:00.0000000 +00:00 |  | 2022-03-20 00:00:00.0000000 +00:00 | 2024-06-20 00:00:00.0000000 +00:00 |  | 2017-10-18 14:11:39.5979789 -04:00
MED642 | Y | 2015-01-30 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-12-31 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | [5 empty] | 2015-01-30 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 |  | 2016-07-26 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2015-01-30 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 | 2016-01-15 00:00:00.0000000 +00:00 |  | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-26 00:00:00.0000000 +00:00 | 2016-07-26 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2017-10-02 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2019-03-30 00:00:00.0000000 +00:00 | 2021-06-28 00:00:00.0000000 +00:00 | 2022-03-29 00:00:00.0000000 +00:00 |  | 2022-03-29 00:00:00.0000000 +00:00 | 2022-03-29 00:00:00.0000000 +00:00 |  | 2017-11-17 11:24:12.1831220 -05:00
MED-645 | Y | 2017-08-16 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-08-30 00:00:00.0000000 +00:00 | 2020-02-28 00:00:00.0000000 +00:00 | 2017-08-16 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-08-30 00:00:00.0000000 +00:00 | 2020-02-28 00:00:00.0000000 +00:00 | [5 empty] | 2017-08-16 00:00:00.0000000 +00:00 | 2017-09-05 00:00:00.0000000 +00:00 |  |  |  | 2017-12-30 00:00:00.0000000 +00:00 |  | 2017-08-16 00:00:00.0000000 +00:00 |  | 2017-09-05 00:00:00.0000000 +00:00 |  | 2017-11-13 00:00:00.0000000 +00:00 | 2017-11-13 00:00:00.0000000 +00:00 | 2017-11-13 00:00:00.0000000 +00:00 | 2017-11-13 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-30 00:00:00.0000000 +00:00 |  | 2018-08-30 00:00:00.0000000 +00:00 |  | 2020-02-28 00:00:00.0000000 +00:00 |  | 2023-02-26 00:00:00.0000000 +00:00 | 2023-02-26 00:00:00.0000000 +00:00 |  | 2023-02-26 00:00:00.0000000 +00:00 |  | 2017-09-09 15:33:15.6470000 +00:00 | 2017-11-28 09:21:32.5341208 -05:00
MEDA001 | Y | 2014-09-16 00:00:00.0000000 +00:00 | 2014-11-03 00:00:00.0000000 +00:00 | 2014-12-24 00:00:00.0000000 +00:00 | 2015-12-01 00:00:00.0000000 +00:00 | 2017-09-04 00:00:00.0000000 +00:00 | 2014-09-16 00:00:00.0000000 +00:00 | 2014-11-03 00:00:00.0000000 +00:00 | 2014-12-24 00:00:00.0000000 +00:00 | 2015-09-18 00:00:00.0000000 +00:00 | 2017-09-16 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-16 17:00:00.0000000 +00:00 | 2014-11-03 17:00:00.0000000 +00:00 | 2014-12-24 00:00:00.0000000 +00:00 | 2015-12-01 17:00:00.0000000 +00:00 | 2017-09-04 00:00:00.0000000 +00:00 | 2014-12-24 00:00:00.0000000 +00:00 | 2017-09-04 00:00:00.0000000 +00:00 | 2014-09-16 17:00:00.0000000 +00:00 | 2014-09-16 17:00:00.0000000 +00:00 | 2014-11-03 17:00:00.0000000 +00:00 | 2014-11-03 17:00:00.0000000 +00:00 |  | 2014-11-28 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | 2014-11-28 00:00:00.0000000 +00:00 | [5 empty] | 2014-12-24 00:00:00.0000000 +00:00 | 2014-12-24 00:00:00.0000000 +00:00 | 2015-12-01 17:00:00.0000000 +00:00 | 2015-12-01 17:00:00.0000000 +00:00 | 2017-09-04 00:00:00.0000000 +00:00 | 2017-09-04 00:00:00.0000000 +00:00 | 2020-09-15 00:00:00.0000000 +00:00 | 2020-09-03 00:00:00.0000000 +00:00 |  | 2020-09-03 00:00:00.0000000 +00:00 | 2020-09-03 00:00:00.0000000 +00:00 |  | 2017-11-17 11:24:39.1270451 -05:00
MEDA002 | Y | 2015-05-05 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 | 2019-03-09 00:00:00.0000000 +00:00 | 2015-05-05 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2017-07-01 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-05 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 |  | 2015-07-04 00:00:00.0000000 +00:00 | 2019-03-09 00:00:00.0000000 +00:00 | 2015-05-05 00:00:00.0000000 +00:00 | 2015-05-05 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-09-07 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-30 00:00:00.0000000 +00:00 | 2015-10-30 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 | 2017-09-11 00:00:00.0000000 +00:00 | 2019-03-09 00:00:00.0000000 +00:00 | 2019-03-09 00:00:00.0000000 +00:00 | 2018-06-26 00:00:00.0000000 +00:00 | 2022-03-08 00:00:00.0000000 +00:00 |  | 2022-03-08 00:00:00.0000000 +00:00 | 2022-03-08 00:00:00.0000000 +00:00 |  | 2017-11-17 11:25:07.7898701 -05:00
MEDA003 | Y | 2015-05-05 00:00:00.0000000 +00:00 | 2016-10-16 00:00:00.0000000 +00:00 | 2016-12-14 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2019-08-13 00:00:00.0000000 +00:00 | 2015-05-05 00:00:00.0000000 +00:00 | 2016-01-01 00:00:00.0000000 +00:00 | 2016-12-31 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2018-07-01 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-05 00:00:00.0000000 +00:00 | 2016-10-16 00:00:00.0000000 +00:00 | 2016-12-14 00:00:00.0000000 +00:00 |  |  | 2016-12-14 00:00:00.0000000 +00:00 | 2019-02-10 00:00:00.0000000 +00:00 | 2015-05-05 00:00:00.0000000 +00:00 |  | 2016-10-16 00:00:00.0000000 +00:00 |  | 2016-05-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | 2016-11-15 00:00:00.0000000 +00:00 | [6 empty] | 2016-12-14 00:00:00.0000000 +00:00 |  | 2018-04-15 00:00:00.0000000 +00:00 |  | 2019-02-09 00:00:00.0000000 +00:00 |  | 2019-06-26 00:00:00.0000000 +00:00 | 2021-08-14 00:00:00.0000000 +00:00 |  | 2020-04-10 00:00:00.0000000 +00:00
MIBBNC001 | Y | 2012-12-18 00:00:00.0000000 +00:00 | 2013-04-18 00:00:00.0000000 +00:00 | 2014-04-04 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2012-12-18 00:00:00.0000000 +00:00 | 2013-04-18 00:00:00.0000000 +00:00 | 2014-04-04 00:00:00.0000000 +00:00 | 2015-09-14 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 | 2012-12-18 00:00:00.0000000 +00:00 | 2013-04-17 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | 2014-08-16 00:00:00.0000000 +00:00 | 2015-08-15 00:00:00.0000000 +00:00 | 2012-12-18 08:00:00.0000000 +00:00 | 2013-04-18 08:00:00.0000000 +00:00 | 2014-04-04 00:00:00.0000000 +00:00 | 2015-09-14 17:00:00.0000000 +00:00 |  | 2014-04-04 00:00:00.0000000 +00:00 | 2017-12-11 00:00:00.0000000 +00:00 |  |  |  |  | 2013-11-21 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | 2013-11-21 00:00:00.0000000 +00:00 | [13 empty] | 2018-12-06 00:00:00.0000000 +00:00 | 2018-12-06 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-13 09:58:22.5771936 -04:00
MIBBNC002 | Y | 2013-12-09 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2016-10-28 00:00:00.0000000 +00:00 | 2018-04-16 00:00:00.0000000 +00:00 | 2019-11-06 00:00:00.0000000 +00:00 | 2013-12-09 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2016-10-28 00:00:00.0000000 +00:00 | 2018-04-16 00:00:00.0000000 +00:00 | 2019-11-06 00:00:00.0000000 +00:00 | [5 empty] | 2013-12-09 17:00:00.0000000 +00:00 | 2015-06-15 17:00:00.0000000 +00:00 | 2016-10-28 00:00:00.0000000 +00:00 |  |  | 2016-10-28 00:00:00.0000000 +00:00 | 2019-11-06 00:00:00.0000000 +00:00 | 2013-12-09 17:00:00.0000000 +00:00 |  | 2015-06-15 17:00:00.0000000 +00:00 |  | 2016-05-04 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 | 2016-05-04 00:00:00.0000000 +00:00 | [6 empty] | 2016-10-28 00:00:00.0000000 +00:00 |  | 2018-04-16 00:00:00.0000000 +00:00 | 2018-04-16 00:00:00.0000000 +00:00 | 2019-11-06 00:00:00.0000000 +00:00 | 2019-11-06 00:00:00.0000000 +00:00 | 2020-10-31 00:00:00.0000000 +00:00 | 2020-10-31 00:00:00.0000000 +00:00 |  | 2020-10-31 00:00:00.0000000 +00:00 |  |  | 2017-09-15 11:37:33.1327437 -04:00
MIBBNC003 | Y | 2014-10-28 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-12-30 00:00:00.0000000 +00:00 | 2020-12-28 00:00:00.0000000 +00:00 | 2014-10-28 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2017-12-30 00:00:00.0000000 +00:00 | 2018-12-30 00:00:00.0000000 +00:00 | 2020-12-28 00:00:00.0000000 +00:00 | [5 empty] | 2014-10-28 00:00:00.0000000 +00:00 | 2016-08-29 17:00:00.0000000 +00:00 |  |  |  | 2017-12-30 00:00:00.0000000 +00:00 |  | 2014-10-28 00:00:00.0000000 +00:00 |  | 2016-08-29 17:00:00.0000000 +00:00 |  | 2017-09-19 00:00:00.0000000 +00:00 | 2017-09-19 00:00:00.0000000 +00:00 | 2017-09-19 00:00:00.0000000 +00:00 | 2017-09-19 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-30 00:00:00.0000000 +00:00 |  | 2018-12-30 00:00:00.0000000 +00:00 |  | 2020-12-28 00:00:00.0000000 +00:00 |  | 2021-12-23 00:00:00.0000000 +00:00 | 2021-12-23 00:00:00.0000000 +00:00 |  | 2021-12-23 00:00:00.0000000 +00:00 |  |  | 2017-09-29 07:56:14.2605331 -04:00
MIBBNC005 | Y | 2015-09-17 00:00:00.0000000 +00:00 | 2018-01-08 00:00:00.0000000 +00:00 | 2019-10-31 00:00:00.0000000 +00:00 | 2020-08-03 00:00:00.0000000 +00:00 | 2022-08-02 00:00:00.0000000 +00:00 | 2015-09-17 00:00:00.0000000 +00:00 | 2018-01-08 00:00:00.0000000 +00:00 | 2019-10-31 00:00:00.0000000 +00:00 | 2020-08-03 00:00:00.0000000 +00:00 | 2022-08-02 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-17 09:00:00.0000000 +00:00 | [10 empty] | 2019-04-23 00:00:00.0000000 +00:00 | 2019-04-28 00:00:00.0000000 +00:00 | [14 empty] | 2023-08-28 00:00:00.0000000 +00:00 | 2023-08-28 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-29 07:56:42.3017513 -04:00
MIBBNC04A | Y | 2015-05-15 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2018-11-29 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2021-11-27 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 | 2018-11-29 00:00:00.0000000 +00:00 | 2019-11-29 00:00:00.0000000 +00:00 | 2021-11-27 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-15 00:00:00.0000000 +00:00 | 2017-08-14 00:00:00.0000000 +00:00 |  |  |  | 2018-11-29 00:00:00.0000000 +00:00 |  | 2015-05-15 00:00:00.0000000 +00:00 |  | 2017-08-14 00:00:00.0000000 +00:00 |  | 2018-04-17 00:00:00.0000000 +00:00 | 2018-04-17 00:00:00.0000000 +00:00 |  | 2018-04-17 00:00:00.0000000 +00:00 | [6 empty] | 2018-11-29 00:00:00.0000000 +00:00 |  | 2019-11-29 00:00:00.0000000 +00:00 |  | 2021-11-27 00:00:00.0000000 +00:00 |  | 2022-11-22 00:00:00.0000000 +00:00 | 2022-11-22 00:00:00.0000000 +00:00 |  | 2022-11-22 00:00:00.0000000 +00:00 |  |  | 2017-09-29 08:06:15.1879690 -04:00
MODULAR01 | Y
MODULAR02 | Y | [48 empty] | 2017-08-30 14:51:38.8235897 -04:00
MODULAR03 | Y
MODULAR04 | Y
MODULAR05 | Y
MODULAR07 | Y
MODULAR08 | Y
MODULAR09 | Y
MODULAR10 | Y
MODULAR11 | Y
MODULAR12 | Y
NC-61 | Y | 2011-04-14 00:00:00.0000000 +00:00 | 2012-09-07 00:00:00.0000000 +00:00 | 2017-06-02 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2020-06-17 00:00:00.0000000 +00:00 | 2011-04-14 00:00:00.0000000 +00:00 | 2012-09-07 00:00:00.0000000 +00:00 | 2013-04-27 00:00:00.0000000 +00:00 | 2015-07-02 00:00:00.0000000 +00:00 | 2016-12-29 00:00:00.0000000 +00:00 | 2011-04-14 00:00:00.0000000 +00:00 | 2012-09-07 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2019-08-10 00:00:00.0000000 +00:00 | 2022-01-24 00:00:00.0000000 +00:00 | 2011-04-14 00:00:00.0000000 +00:00 | 2012-09-07 00:00:00.0000000 +00:00 | 2017-06-02 00:00:00.0000000 +00:00 |  |  | 2017-07-31 00:00:00.0000000 +00:00 |  | 2011-04-14 00:00:00.0000000 +00:00 |  | 2012-09-07 00:00:00.0000000 +00:00 |  | 2012-12-07 00:00:00.0000000 +00:00 | 2013-03-11 00:00:00.0000000 +00:00 | 2013-03-11 00:00:00.0000000 +00:00 | 2013-03-11 00:00:00.0000000 +00:00 |  | 2013-02-07 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 |  | 2017-06-02 00:00:00.0000000 +00:00 |  | 2018-06-29 00:00:00.0000000 +00:00 |  | 2020-06-17 00:00:00.0000000 +00:00 |  | 2017-12-29 00:00:00.0000000 +00:00 | 2021-06-17 00:00:00.0000000 +00:00 |  | 2021-06-17 00:00:00.0000000 +00:00 |  |  | 2017-09-05 14:16:52.9075972 -04:00
NC-61A | Y | 2011-04-14 00:00:00.0000000 +00:00 | 2012-09-07 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2018-08-31 00:00:00.0000000 +00:00 | 2020-08-20 00:00:00.0000000 +00:00 | 2011-04-14 00:00:00.0000000 +00:00 | 2012-09-07 00:00:00.0000000 +00:00 | 2013-04-27 00:00:00.0000000 +00:00 | 2015-07-02 00:00:00.0000000 +00:00 | 2016-12-29 00:00:00.0000000 +00:00 | 2011-04-14 00:00:00.0000000 +00:00 | 2012-09-07 00:00:00.0000000 +00:00 | 2013-06-27 00:00:00.0000000 +00:00 | 2016-04-05 00:00:00.0000000 +00:00 | 2015-03-29 00:00:00.0000000 +00:00 | 2011-04-14 00:00:00.0000000 +00:00 | 2012-09-07 00:00:00.0000000 +00:00 |  |  |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2011-04-14 00:00:00.0000000 +00:00 |  | 2012-09-07 00:00:00.0000000 +00:00 |  | 2012-12-07 00:00:00.0000000 +00:00 | 2013-03-11 00:00:00.0000000 +00:00 | 2013-03-11 00:00:00.0000000 +00:00 | 2013-03-11 00:00:00.0000000 +00:00 |  | 2013-02-07 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 |  | 2017-12-22 00:00:00.0000000 +00:00 |  | 2018-08-31 00:00:00.0000000 +00:00 |  | 2020-08-20 00:00:00.0000000 +00:00 |  | 2018-12-29 00:00:00.0000000 +00:00 | 2021-08-20 00:00:00.0000000 +00:00 |  | 2021-08-20 00:00:00.0000000 +00:00
NDFIBZ | Y | 2017-02-15 00:00:00.0000000 +00:00 | 2017-12-25 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | 2020-07-06 00:00:00.0000000 +00:00 | 2022-07-05 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2017-12-25 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | 2020-07-06 00:00:00.0000000 +00:00 | 2022-07-05 00:00:00.0000000 +00:00 | [5 empty] | 2017-02-15 00:00:00.0000000 +00:00 |  |  |  |  | 2019-10-30 00:00:00.0000000 +00:00 | 2022-07-05 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2017-02-15 00:00:00.0000000 +00:00 | 2017-12-25 00:00:00.0000000 +00:00 | 2017-12-25 00:00:00.0000000 +00:00 | 2019-01-01 00:00:00.0000000 +00:00 | 2019-01-01 00:00:00.0000000 +00:00 |  | 2019-01-01 00:00:00.0000000 +00:00 | 2019-01-01 00:00:00.0000000 +00:00 | [5 empty] | 2019-10-30 00:00:00.0000000 +00:00 | 2019-10-30 00:00:00.0000000 +00:00 | 2020-07-06 00:00:00.0000000 +00:00 | 2020-07-06 00:00:00.0000000 +00:00 | 2022-07-05 00:00:00.0000000 +00:00 | 2022-07-05 00:00:00.0000000 +00:00 | 2025-07-04 00:00:00.0000000 +00:00 | 2025-07-04 00:00:00.0000000 +00:00 |  | 2025-07-04 00:00:00.0000000 +00:00 | 2025-07-04 00:00:00.0000000 +00:00 |  | 2017-08-30 14:43:24.1462451 -04:00
P-102DELV | Y | 2016-01-04 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-02-11 00:00:00.0000000 +00:00 | 2021-02-08 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-02-11 00:00:00.0000000 +00:00 | 2021-02-08 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-04 00:00:00.0000000 +00:00 | 2016-10-19 00:00:00.0000000 +00:00 |  |  |  | 2018-03-15 00:00:00.0000000 +00:00 | [5 empty] | 2017-08-09 00:00:00.0000000 +00:00 | 2018-01-16 00:00:00.0000000 +00:00 | [14 empty] | 2024-02-06 00:00:00.0000000 +00:00 | 2024-02-06 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-18 14:18:16.3082531 -04:00
P-109STAR | Y | 2012-02-09 00:00:00.0000000 +00:00 | 2013-03-27 00:00:00.0000000 +00:00 | 2016-02-28 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2018-02-24 00:00:00.0000000 +00:00 | 2012-02-09 00:00:00.0000000 +00:00 | 2012-11-30 00:00:00.0000000 +00:00 | 2013-11-29 00:00:00.0000000 +00:00 | 2014-05-30 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2012-02-09 00:00:00.0000000 +00:00 | 2013-03-27 00:00:00.0000000 +00:00 | 2016-02-28 00:00:00.0000000 +00:00 | 2016-11-14 00:00:00.0000000 +00:00 | 2018-02-24 00:00:00.0000000 +00:00 | 2012-02-09 00:00:00.0000000 +00:00 | 2013-03-27 00:00:00.0000000 +00:00 |  |  |  | 2018-02-01 00:00:00.0000000 +00:00 | 2018-04-05 00:00:00.0000000 +00:00
P109STARA | Y | 2012-02-09 00:00:00.0000000 +00:00 | 2012-02-09 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2018-08-31 00:00:00.0000000 +00:00 | 2019-08-31 00:00:00.0000000 +00:00 | 2012-02-09 00:00:00.0000000 +00:00 | 2012-02-09 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2018-08-31 00:00:00.0000000 +00:00 | 2019-08-31 00:00:00.0000000 +00:00 | [5 empty] | 2012-02-09 17:00:00.0000000 +00:00 | 2013-03-27 00:00:00.0000000 +00:00 | 2017-06-20 00:00:00.0000000 +00:00 |  |  |  |  | 2012-02-09 17:00:00.0000000 +00:00 |  | 2013-03-27 00:00:00.0000000 +00:00 |  | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 |  | 2014-08-14 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 |  | 2017-06-30 00:00:00.0000000 +00:00 |  | 2018-08-31 00:00:00.0000000 +00:00 |  | 2019-08-31 00:00:00.0000000 +00:00 |  | 2022-08-31 00:00:00.0000000 +00:00 | 2022-08-03 00:00:00.0000000 +00:00 |  | 2022-08-03 00:00:00.0000000 +00:00 |  |  | 2017-11-20 10:42:25.4104209 -05:00
P-1CROT16 | Y | 2011-01-19 00:00:00.0000000 +00:00 | 2011-11-16 00:00:00.0000000 +00:00 | 2013-01-04 00:00:00.0000000 +00:00 | 2014-03-20 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2011-01-19 00:00:00.0000000 +00:00 | 2011-11-16 00:00:00.0000000 +00:00 | 2013-01-04 00:00:00.0000000 +00:00 | 2013-10-14 00:00:00.0000000 +00:00 | 2014-12-24 00:00:00.0000000 +00:00 | 2011-01-19 00:00:00.0000000 +00:00 | 2011-11-16 00:00:00.0000000 +00:00 | 2013-01-04 00:00:00.0000000 +00:00 | 2014-03-20 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2011-01-19 00:00:00.0000000 +00:00 | 2011-11-16 00:00:00.0000000 +00:00 | 2013-01-04 00:00:00.0000000 +00:00 | 2014-03-20 00:00:00.0000000 +00:00 |  | 2013-01-04 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2011-01-01 00:00:00.0000000 +00:00 | 2011-01-19 00:00:00.0000000 +00:00 | 2011-11-16 00:00:00.0000000 +00:00 | 2011-11-16 00:00:00.0000000 +00:00 | 2011-11-17 00:00:00.0000000 +00:00 | 2011-11-17 00:00:00.0000000 +00:00 | 2011-11-17 00:00:00.0000000 +00:00 | 2011-11-17 00:00:00.0000000 +00:00 | 2011-11-17 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 | 2011-11-18 00:00:00.0000000 +00:00 | 2013-01-04 00:00:00.0000000 +00:00 | 2013-01-04 00:00:00.0000000 +00:00 | 2014-03-20 00:00:00.0000000 +00:00 | 2014-03-20 00:00:00.0000000 +00:00 | 2018-01-31 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2021-01-29 00:00:00.0000000 +00:00 | 2021-01-29 00:00:00.0000000 +00:00 |  | 2021-01-29 00:00:00.0000000 +00:00 | 2021-01-29 00:00:00.0000000 +00:00
P-1FERY6A | Y | 2011-07-01 00:00:00.0000000 +00:00 |  |  | 2012-03-13 00:00:00.0000000 +00:00 | 2013-03-25 00:00:00.0000000 +00:00 | 2011-07-01 00:00:00.0000000 +00:00 |  |  | 2012-03-13 00:00:00.0000000 +00:00 | 2013-03-10 00:00:00.0000000 +00:00 | 2011-07-01 00:00:00.0000000 +00:00 |  |  | 2012-03-13 00:00:00.0000000 +00:00 | 2013-06-30 00:00:00.0000000 +00:00 | 2011-07-01 00:00:00.0000000 +00:00 |  |  | 2012-03-13 00:00:00.0000000 +00:00 | 2013-03-25 00:00:00.0000000 +00:00 |  | 2013-06-30 00:00:00.0000000 +00:00 | [21 empty] | 2019-12-15 00:00:00.0000000 +00:00
P-1FERY6B | Y | 2015-10-27 00:00:00.0000000 +00:00 |  |  | 2016-01-22 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | 2015-10-27 00:00:00.0000000 +00:00 |  |  | 2016-01-22 00:00:00.0000000 +00:00 | 2016-04-22 00:00:00.0000000 +00:00 | 2015-10-27 00:00:00.0000000 +00:00 |  |  | 2016-01-22 00:00:00.0000000 +00:00 | 2016-04-22 00:00:00.0000000 +00:00 | 2015-10-27 00:00:00.0000000 +00:00 |  |  | 2016-01-22 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 |  | 2016-04-22 00:00:00.0000000 +00:00 | [21 empty] | 2019-12-15 00:00:00.0000000 +00:00
P-1SAND01 | Y | 2014-08-26 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2016-02-24 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2019-06-26 00:00:00.0000000 +00:00 | 2014-08-26 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2016-02-24 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2017-03-07 00:00:00.0000000 +00:00 | [5 empty] | 2014-08-27 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2016-02-24 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 |  | 2016-02-24 00:00:00.0000000 +00:00 | 2019-06-26 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | 2015-09-29 00:00:00.0000000 +00:00 | [5 empty] | 2016-02-24 00:00:00.0000000 +00:00 | 2016-02-24 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2019-06-26 00:00:00.0000000 +00:00 | 2019-06-26 00:00:00.0000000 +00:00 | 2020-03-06 00:00:00.0000000 +00:00 | 2022-06-25 00:00:00.0000000 +00:00 |  | 2022-06-25 00:00:00.0000000 +00:00 | 2022-06-25 00:00:00.0000000 +00:00
P-1STARLP | Y | 2014-08-26 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | 2018-07-03 00:00:00.0000000 +00:00 | 2020-12-29 00:00:00.0000000 +00:00 | 2014-08-26 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 | 2017-08-16 00:00:00.0000000 +00:00 | 2018-04-17 00:00:00.0000000 +00:00 | 2020-10-14 00:00:00.0000000 +00:00 | [5 empty] | 2014-08-26 00:00:00.0000000 +00:00 | 2015-06-24 00:00:00.0000000 +00:00 |  |  |  | 2017-12-29 00:00:00.0000000 +00:00 |  | 2014-08-26 00:00:00.0000000 +00:00 |  | 2015-06-24 00:00:00.0000000 +00:00 |  | 2016-10-04 00:00:00.0000000 +00:00 | 2016-10-04 00:00:00.0000000 +00:00 | 2016-10-04 00:00:00.0000000 +00:00 | 2016-10-04 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  | 2018-07-03 00:00:00.0000000 +00:00 |  | 2020-12-29 00:00:00.0000000 +00:00 |  | 2023-10-13 00:00:00.0000000 +00:00 | 2023-12-29 00:00:00.0000000 +00:00 |  | 2023-12-29 00:00:00.0000000 +00:00
P-1VCPDBR | Y | 2015-08-05 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2018-07-22 00:00:00.0000000 +00:00 | 2019-03-19 00:00:00.0000000 +00:00 | 2021-03-18 00:00:00.0000000 +00:00 | 2015-08-05 00:00:00.0000000 +00:00 | 2016-02-12 00:00:00.0000000 +00:00 | 2018-02-11 00:00:00.0000000 +00:00 | 2018-07-27 00:00:00.0000000 +00:00 | 2020-07-25 00:00:00.0000000 +00:00 | [5 empty] | 2015-08-05 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 |  |  |  | 2018-07-22 00:00:00.0000000 +00:00 |  | 2015-08-05 00:00:00.0000000 +00:00 |  | 2016-07-22 00:00:00.0000000 +00:00 |  | 2017-12-04 00:00:00.0000000 +00:00 | 2017-12-04 00:00:00.0000000 +00:00 |  | 2017-12-04 00:00:00.0000000 +00:00 | [6 empty] | 2018-07-22 00:00:00.0000000 +00:00 |  | 2019-03-19 00:00:00.0000000 +00:00 |  | 2021-03-18 00:00:00.0000000 +00:00 |  | 2023-07-25 00:00:00.0000000 +00:00 | 2024-03-17 00:00:00.0000000 +00:00 |  | 2024-03-17 00:00:00.0000000 +00:00
P1YANK15A | Y | 2012-07-16 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 | 2012-07-16 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2014-12-03 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | 2017-03-30 00:00:00.0000000 +00:00 | 2012-07-16 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2015-12-09 00:00:00.0000000 +00:00 | 2016-08-12 00:00:00.0000000 +00:00 | 2018-04-05 00:00:00.0000000 +00:00 | 2012-07-16 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-06-15 17:00:00.0000000 +00:00 |  | 2016-03-16 00:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 | 2012-07-16 00:00:00.0000000 +00:00 | 2012-07-16 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2014-02-03 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2014-07-03 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2015-06-17 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2016-07-22 00:00:00.0000000 +00:00 | 2017-06-15 17:00:00.0000000 +00:00 | 2017-06-15 17:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 | 2019-06-15 00:00:00.0000000 +00:00 | 2018-03-30 00:00:00.0000000 +00:00 | 2022-12-31 00:00:00.0000000 +00:00 |  | 2022-12-31 00:00:00.0000000 +00:00 | 2022-12-31 00:00:00.0000000 +00:00
P-30420SP | Y | 2015-12-16 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2017-10-11 00:00:00.0000000 +00:00 | 2018-02-21 00:00:00.0000000 +00:00 | 2015-12-16 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2017-10-11 00:00:00.0000000 +00:00 | 2018-01-21 00:00:00.0000000 +00:00 | [5 empty] | 2015-12-16 17:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-08-25 00:00:00.0000000 +00:00 | 2017-04-27 17:00:00.0000000 +00:00 |  | 2016-08-05 00:00:00.0000000 +00:00 | 2018-02-21 00:00:00.0000000 +00:00 | 2015-12-16 00:00:00.0000000 +00:00 | 2015-12-16 17:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-07-05 00:00:00.0000000 +00:00 | 2016-08-25 00:00:00.0000000 +00:00 | 2016-08-25 00:00:00.0000000 +00:00 | 2017-04-27 00:00:00.0000000 +00:00 | 2017-04-27 17:00:00.0000000 +00:00 | 2018-02-21 00:00:00.0000000 +00:00 | 2018-02-21 00:00:00.0000000 +00:00 | 2019-12-06 00:00:00.0000000 +00:00 | 2021-01-21 00:00:00.0000000 +00:00 |  | 2021-01-21 00:00:00.0000000 +00:00 | 2021-01-21 00:00:00.0000000 +00:00 |  | 2017-11-20 10:40:20.8387785 -05:00
P-3RANDAL | Y | 2015-11-09 00:00:00.0000000 +00:00 | 2016-11-10 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2020-07-01 00:00:00.0000000 +00:00 | 2015-11-09 00:00:00.0000000 +00:00 | 2016-11-10 00:00:00.0000000 +00:00 | 2018-05-03 00:00:00.0000000 +00:00 | 2019-01-02 00:00:00.0000000 +00:00 | 2020-07-01 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-09 00:00:00.0000000 +00:00 | 2016-11-10 00:00:00.0000000 +00:00 |  |  |  | 2018-05-03 00:00:00.0000000 +00:00 | 2020-07-01 00:00:00.0000000 +00:00 | 2015-11-09 00:00:00.0000000 +00:00 |  | 2016-11-10 00:00:00.0000000 +00:00 |  | 2018-01-02 00:00:00.0000000 +00:00 | 2018-04-02 00:00:00.0000000 +00:00 |  | 2018-04-02 00:00:00.0000000 +00:00 | [6 empty] | 2018-06-15 00:00:00.0000000 +00:00 |  | 2019-01-02 00:00:00.0000000 +00:00 |  | 2020-07-01 00:00:00.0000000 +00:00 |  | 2022-07-02 00:00:00.0000000 +00:00 | 2022-07-02 00:00:00.0000000 +00:00 |  | 2022-07-02 00:00:00.0000000 +00:00
P-407BHI3 | Y | 2015-04-01 00:00:00.0000000 +00:00 | 2017-01-25 00:00:00.0000000 +00:00 | 2019-03-25 00:00:00.0000000 +00:00 | 2020-01-25 00:00:00.0000000 +00:00 | 2021-06-25 00:00:00.0000000 +00:00 | 2015-04-01 00:00:00.0000000 +00:00 | 2017-01-25 00:00:00.0000000 +00:00 | 2019-03-25 00:00:00.0000000 +00:00 | 2020-01-25 00:00:00.0000000 +00:00 | 2021-06-25 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-01 00:00:00.0000000 +00:00 | 2017-01-25 00:00:00.0000000 +00:00 |  |  |  | 2019-03-25 00:00:00.0000000 +00:00 | [5 empty] | 2018-03-15 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 |  |  |  | 2018-09-14 00:00:00.0000000 +00:00 | 2018-09-14 00:00:00.0000000 +00:00 | [9 empty] | 2024-06-25 00:00:00.0000000 +00:00 | 2024-06-25 00:00:00.0000000 +00:00
P-407BHV4 | Y
P-407KIN2 | Y | 2016-03-09 00:00:00.0000000 +00:00 | 2016-09-20 00:00:00.0000000 +00:00 | 2018-01-22 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | 2016-03-09 00:00:00.0000000 +00:00 | 2016-09-20 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-09-15 00:00:00.0000000 +00:00 | 2019-09-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-03-09 00:00:00.0000000 +00:00 | 2016-09-20 00:00:00.0000000 +00:00 |  |  |  | 2018-01-22 00:00:00.0000000 +00:00 |  | 2016-03-09 00:00:00.0000000 +00:00 |  | 2016-09-20 00:00:00.0000000 +00:00 |  | 2016-12-30 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 |  | 2017-03-18 00:00:00.0000000 +00:00 | 2017-03-18 00:00:00.0000000 +00:00 | 2017-03-18 00:00:00.0000000 +00:00 | 2017-03-18 00:00:00.0000000 +00:00 |  | 2017-12-15 00:00:00.0000000 +00:00 |  | 2018-09-15 00:00:00.0000000 +00:00 |  | 2019-09-15 00:00:00.0000000 +00:00 |  | 2022-09-15 00:00:00.0000000 +00:00 | 2022-09-15 00:00:00.0000000 +00:00 |  | 2022-09-15 00:00:00.0000000 +00:00 |  |  | 2017-10-24 08:38:36.1118049 -04:00
P-413QCF1 | Y | 2016-01-04 00:00:00.0000000 +00:00 | 2016-07-11 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2018-09-19 00:00:00.0000000 +00:00 | 2020-03-25 00:00:00.0000000 +00:00 | 2016-01-04 00:00:00.0000000 +00:00 | 2016-07-11 00:00:00.0000000 +00:00 | 2017-07-11 00:00:00.0000000 +00:00 | 2018-02-21 00:00:00.0000000 +00:00 | 2019-07-09 00:00:00.0000000 +00:00 | [5 empty] | 2016-01-04 17:00:00.0000000 +00:00 | 2016-07-11 17:00:00.0000000 +00:00 |  |  |  | 2018-02-15 00:00:00.0000000 +00:00 | 2020-03-25 00:00:00.0000000 +00:00 | 2016-01-04 17:00:00.0000000 +00:00 |  | 2016-07-11 17:00:00.0000000 +00:00 |  | 2017-01-13 00:00:00.0000000 +00:00 | 2017-02-23 00:00:00.0000000 +00:00 | 2017-02-23 00:00:00.0000000 +00:00 | 2017-02-23 00:00:00.0000000 +00:00 |  | 2017-04-14 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 | 2017-08-15 00:00:00.0000000 +00:00 |  | 2018-02-15 00:00:00.0000000 +00:00 |  | 2018-09-19 00:00:00.0000000 +00:00 |  | 2020-03-25 00:00:00.0000000 +00:00 |  | 2021-07-08 00:00:00.0000000 +00:00 | 2023-03-24 00:00:00.0000000 +00:00 |  | 2023-03-24 00:00:00.0000000 +00:00 |  |  | 2017-10-12 11:01:32.8770022 -04:00
P-415PAS2 | Y | 2015-09-09 00:00:00.0000000 +00:00 | 2017-06-30 00:00:00.0000000 +00:00 | 2019-06-30 00:00:00.0000000 +00:00 | 2019-12-28 00:00:00.0000000 +00:00 | 2022-12-26 00:00:00.0000000 +00:00 | 2015-09-09 00:00:00.0000000 +00:00 | 2017-03-17 00:00:00.0000000 +00:00 | 2019-03-17 00:00:00.0000000 +00:00 | 2019-09-14 00:00:00.0000000 +00:00 | 2022-09-12 00:00:00.0000000 +00:00 | 2011-12-20 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2015-09-09 18:00:00.0000000 +00:00 | [26 empty] | 2023-09-07 00:00:00.0000000 +00:00 | 2023-12-21 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-27 12:03:39.7961500 -05:00
P-415PAS3 | Y | 2015-09-09 00:00:00.0000000 +00:00 | 2017-04-25 00:00:00.0000000 +00:00 | 2019-04-24 00:00:00.0000000 +00:00 | 2019-10-22 00:00:00.0000000 +00:00 | 2022-10-20 00:00:00.0000000 +00:00 | 2015-09-09 00:00:00.0000000 +00:00 | 2017-04-25 17:00:00.0000000 +00:00 | 2019-04-24 00:00:00.0000000 +00:00 | 2019-10-22 00:00:00.0000000 +00:00 | 2022-10-20 00:00:00.0000000 +00:00 | [5 empty] | 2015-09-09 00:00:00.0000000 +00:00 | 2017-04-25 00:00:00.0000000 +00:00 |  |  |  | 2019-04-24 00:00:00.0000000 +00:00 |  | 2015-09-09 00:00:00.0000000 +00:00 |  | 2017-04-25 00:00:00.0000000 +00:00 |  | 2018-06-20 00:00:00.0000000 +00:00 | 2018-06-20 00:00:00.0000000 +00:00 |  | 2018-06-20 00:00:00.0000000 +00:00 | [6 empty] | 2019-04-24 00:00:00.0000000 +00:00 |  | 2019-10-22 00:00:00.0000000 +00:00 |  | 2022-10-20 00:00:00.0000000 +00:00 |  | 2025-10-19 00:00:00.0000000 +00:00 | 2025-10-19 00:00:00.0000000 +00:00 |  | 2025-10-19 00:00:00.0000000 +00:00
P-502WIL2 | Y | 2012-07-24 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2014-08-28 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2012-07-24 00:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2013-10-18 00:00:00.0000000 +00:00 | 2014-04-14 00:00:00.0000000 +00:00 | 2015-04-13 00:00:00.0000000 +00:00 | [5 empty] | 2012-07-24 18:00:00.0000000 +00:00 | 2013-03-04 17:00:00.0000000 +00:00 | 2014-08-28 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2014-08-28 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2012-07-24 00:00:00.0000000 +00:00 | 2012-07-24 18:00:00.0000000 +00:00 | 2013-03-04 00:00:00.0000000 +00:00 | 2013-03-04 17:00:00.0000000 +00:00 |  | 2013-08-19 00:00:00.0000000 +00:00 | 2013-08-19 00:00:00.0000000 +00:00 | 2013-08-19 00:00:00.0000000 +00:00 | 2013-08-19 00:00:00.0000000 +00:00 | [5 empty] | 2014-08-28 00:00:00.0000000 +00:00 | 2014-08-28 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 | 2016-08-29 00:00:00.0000000 +00:00 |  | 2019-08-29 00:00:00.0000000 +00:00 |  |  | 2019-08-29 00:00:00.0000000 +00:00 |  | 2017-11-27 12:43:02.8854058 -05:00
P-5PNYC06 | Y | 2010-10-05 00:00:00.0000000 +00:00 |  |  | 2011-01-04 00:00:00.0000000 +00:00 | 2015-10-28 00:00:00.0000000 +00:00 | 2010-10-05 00:00:00.0000000 +00:00 |  |  | 2011-01-04 00:00:00.0000000 +00:00 | 2014-06-30 00:00:00.0000000 +00:00 | 2010-10-05 00:00:00.0000000 +00:00 |  |  | 2011-01-04 00:00:00.0000000 +00:00 | 2015-07-13 00:00:00.0000000 +00:00 | 2010-10-05 00:00:00.0000000 +00:00 |  |  | 2011-01-04 00:00:00.0000000 +00:00 | 2015-10-28 00:00:00.0000000 +00:00 |  | 2015-07-13 00:00:00.0000000 +00:00
P5SPKHORA | Y | 2012-01-01 00:00:00.0000000 +00:00 | 2012-03-23 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2014-05-22 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2012-01-12 00:00:00.0000000 +00:00 | 2012-04-14 00:00:00.0000000 +00:00 | 2012-10-31 00:00:00.0000000 +00:00 | 2014-03-17 00:00:00.0000000 +00:00 | 2013-12-13 00:00:00.0000000 +00:00 | 2012-01-12 00:00:00.0000000 +00:00 | 2012-04-14 00:00:00.0000000 +00:00 | 2012-10-31 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2014-09-25 00:00:00.0000000 +00:00 | 2012-01-01 00:00:00.0000000 +00:00 | 2012-03-23 00:00:00.0000000 +00:00 |  | 2014-05-22 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00
PDWTC2013 | Y | 2012-09-24 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2012-09-24 00:00:00.0000000 +00:00 | 2013-01-02 00:00:00.0000000 +00:00 | 2013-06-15 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-04-15 00:00:00.0000000 +00:00 | 2012-09-24 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2013-06-27 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2016-02-27 00:00:00.0000000 +00:00 | 2012-09-24 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 |  | 2013-06-28 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2012-09-24 00:00:00.0000000 +00:00 | 2012-09-24 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 | 2013-01-14 00:00:00.0000000 +00:00 |  | 2013-04-15 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | 2013-04-15 00:00:00.0000000 +00:00 | [5 empty] | 2013-07-15 00:00:00.0000000 +00:00 | 2013-07-15 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2015-05-10 00:00:00.0000000 +00:00 | 2017-12-22 00:00:00.0000000 +00:00 | 2017-04-15 00:00:00.0000000 +00:00 | 2020-12-21 00:00:00.0000000 +00:00 |  | 2018-05-09 00:00:00.0000000 +00:00 | 2020-12-21 00:00:00.0000000 +00:00
PO002-116 | Y | 2017-08-01 00:00:00.0000000 +00:00 | 2017-09-14 00:00:00.0000000 +00:00 | 2019-02-07 00:00:00.0000000 +00:00 | 2019-10-05 00:00:00.0000000 +00:00 | 2022-04-05 00:00:00.0000000 +00:00 | 2017-08-01 00:00:00.0000000 +00:00 | 2017-10-30 00:00:00.0000000 +00:00 | 2019-03-24 00:00:00.0000000 +00:00 | 2019-10-05 00:00:00.0000000 +00:00 | 2022-04-05 00:00:00.0000000 +00:00 | [5 empty] | 2017-08-01 00:00:00.0000000 +00:00 | 2017-09-14 00:00:00.0000000 +00:00 |  |  |  | 2019-02-07 00:00:00.0000000 +00:00 | [5 empty] | 2018-03-10 00:00:00.0000000 +00:00 | 2018-02-20 00:00:00.0000000 +00:00 |  |  |  | 2018-07-19 00:00:00.0000000 +00:00 | 2018-07-11 00:00:00.0000000 +00:00 | [9 empty] | 2023-01-15 00:00:00.0000000 +00:00 | 2023-01-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-20 15:05:17.5198153 -04:00
PO141-40P | Y | 2014-07-08 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2018-06-21 00:00:00.0000000 +00:00 | 2021-06-25 00:00:00.0000000 +00:00 | 2014-07-08 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2018-06-21 00:00:00.0000000 +00:00 | 2021-06-25 00:00:00.0000000 +00:00 | 2014-07-08 00:00:00.0000000 +00:00 | 2015-01-09 00:00:00.0000000 +00:00 | 2016-04-09 00:00:00.0000000 +00:00 | 2016-09-03 00:00:00.0000000 +00:00 | 2018-09-28 00:00:00.0000000 +00:00 | 2014-07-08 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 |  |  | 2017-01-26 00:00:00.0000000 +00:00 |  | 2014-07-08 00:00:00.0000000 +00:00 | 2014-07-08 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2015-08-02 00:00:00.0000000 +00:00 | 2015-08-02 00:00:00.0000000 +00:00 | 2015-08-02 00:00:00.0000000 +00:00 | 2015-08-02 00:00:00.0000000 +00:00 | 2015-08-02 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2018-06-21 00:00:00.0000000 +00:00 | 2018-06-21 00:00:00.0000000 +00:00 | 2021-06-25 00:00:00.0000000 +00:00 | 2021-06-25 00:00:00.0000000 +00:00 | 2023-06-25 00:00:00.0000000 +00:00 | 2023-06-25 00:00:00.0000000 +00:00 |  | 2023-06-23 00:00:00.0000000 +00:00 | 2023-06-25 00:00:00.0000000 +00:00 |  | 2017-09-21 17:01:02.3755856 -04:00
PO205-PA | Y | 2007-02-16 00:00:00.0000000 +00:00 | 2008-04-01 00:00:00.0000000 +00:00 | 2011-02-28 00:00:00.0000000 +00:00 | 2010-09-24 00:00:00.0000000 +00:00 | 2014-10-31 00:00:00.0000000 +00:00 | 2007-02-16 00:00:00.0000000 +00:00 | 2008-04-01 00:00:00.0000000 +00:00 | 2010-11-14 00:00:00.0000000 +00:00 | 2010-11-19 00:00:00.0000000 +00:00 | 2012-12-31 00:00:00.0000000 +00:00 | 2007-02-16 00:00:00.0000000 +00:00 | 2008-04-01 00:00:00.0000000 +00:00 | 2010-11-14 00:00:00.0000000 +00:00 | 2010-11-19 00:00:00.0000000 +00:00 | 2014-10-31 00:00:00.0000000 +00:00 | 2007-02-16 00:00:00.0000000 +00:00 | 2008-04-01 00:00:00.0000000 +00:00 |  | 2010-09-24 00:00:00.0000000 +00:00 | 2014-10-31 00:00:00.0000000 +00:00 | 2010-11-14 00:00:00.0000000 +00:00 | 2014-10-31 00:00:00.0000000 +00:00
PO223-001 | Y | 2006-05-23 00:00:00.0000000 +00:00 | 2006-06-06 00:00:00.0000000 +00:00 | 2009-03-05 00:00:00.0000000 +00:00 | 2010-01-04 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2006-02-22 00:00:00.0000000 +00:00 | 2006-03-15 00:00:00.0000000 +00:00 | 2007-07-29 00:00:00.0000000 +00:00 | 2008-02-20 00:00:00.0000000 +00:00 | 2010-09-22 00:00:00.0000000 +00:00 | 2006-05-23 00:00:00.0000000 +00:00 | 2006-06-06 00:00:00.0000000 +00:00 | 2009-01-18 00:00:00.0000000 +00:00 | 2010-07-11 00:00:00.0000000 +00:00 | 2013-07-27 00:00:00.0000000 +00:00 | 2006-05-23 00:00:00.0000000 +00:00 | 2006-06-06 00:00:00.0000000 +00:00 |  | 2010-01-04 00:00:00.0000000 +00:00 | 2013-05-24 00:00:00.0000000 +00:00 | 2009-04-24 00:00:00.0000000 +00:00 | 2012-07-25 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-15 14:29:38.4933923 -04:00
PO79120EX | Y | 2013-03-28 00:00:00.0000000 +00:00 | 2014-03-08 00:00:00.0000000 +00:00 | 2015-05-12 00:00:00.0000000 +00:00 | 2016-04-19 00:00:00.0000000 +00:00 | 2017-10-25 00:00:00.0000000 +00:00 | 2013-03-23 00:00:00.0000000 +00:00 | 2013-11-15 00:00:00.0000000 +00:00 | 2014-05-14 00:00:00.0000000 +00:00 | 2014-08-30 00:00:00.0000000 +00:00 | 2015-09-16 00:00:00.0000000 +00:00 | 2013-03-28 00:00:00.0000000 +00:00 | 2014-03-08 00:00:00.0000000 +00:00 | 2015-05-17 00:00:00.0000000 +00:00 | 2016-02-18 00:00:00.0000000 +00:00 | 2017-03-06 00:00:00.0000000 +00:00 | 2013-03-28 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2015-05-12 00:00:00.0000000 +00:00 | 2016-04-19 18:00:00.0000000 +00:00 |  | 2016-01-27 00:00:00.0000000 +00:00 | 2017-10-25 00:00:00.0000000 +00:00 | 2013-03-28 00:00:00.0000000 +00:00 | 2013-03-28 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 |  | 2014-08-06 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 |  | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2015-05-12 00:00:00.0000000 +00:00 | 2015-05-12 00:00:00.0000000 +00:00 | 2016-04-19 00:00:00.0000000 +00:00 | 2016-04-19 18:00:00.0000000 +00:00 | 2017-10-25 00:00:00.0000000 +00:00 | 2017-10-25 00:00:00.0000000 +00:00 | 2019-10-10 00:00:00.0000000 +00:00 | 2018-10-25 00:00:00.0000000 +00:00 |  | 2018-10-25 00:00:00.0000000 +00:00 | 2018-10-25 00:00:00.0000000 +00:00
PO79-77AX | Y | 2013-05-02 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2016-11-29 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-11-29 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 | 2015-10-19 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | 2017-05-23 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-11-29 00:00:00.0000000 +00:00 |  | 2015-11-19 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2013-05-02 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 |  | 2014-12-19 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2014-12-19 00:00:00.0000000 +00:00 | 2015-05-07 00:00:00.0000000 +00:00 | 2015-05-07 00:00:00.0000000 +00:00 | 2015-05-07 00:00:00.0000000 +00:00 | 2015-05-07 00:00:00.0000000 +00:00 | 2015-05-07 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2015-11-19 00:00:00.0000000 +00:00 | 2016-11-29 00:00:00.0000000 +00:00 | 2016-11-29 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2018-07-02 00:00:00.0000000 +00:00 | 2020-07-01 00:00:00.0000000 +00:00 | 2020-07-01 00:00:00.0000000 +00:00 |  | 2020-07-01 00:00:00.0000000 +00:00 | 2020-07-01 00:00:00.0000000 +00:00
PO79-77FA | Y | [5 empty] | 2017-06-02 00:00:00.0000000 +00:00 | 2018-01-22 00:00:00.0000000 +00:00 | 2019-02-05 00:00:00.0000000 +00:00 | 2019-08-20 00:00:00.0000000 +00:00 | 2022-06-24 00:00:00.0000000 +00:00 | [16 empty] | 2018-04-23 00:00:00.0000000 +00:00 |  |  |  |  | 2018-06-25 00:00:00.0000000 +00:00 | [10 empty] | 2023-04-04 00:00:00.0000000 +00:00
PO79BMADS | Y | 2007-02-09 00:00:00.0000000 +00:00 | 2010-08-25 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2013-05-01 00:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2007-02-09 00:00:00.0000000 +00:00 | 2007-10-05 00:00:00.0000000 +00:00 | 2008-10-15 00:00:00.0000000 +00:00 | 2009-04-14 00:00:00.0000000 +00:00 | 2010-08-08 00:00:00.0000000 +00:00 | 2007-02-09 00:00:00.0000000 +00:00 | 2010-09-03 00:00:00.0000000 +00:00 | 2011-12-05 00:00:00.0000000 +00:00 | 2013-01-07 00:00:00.0000000 +00:00 | 2014-06-16 00:00:00.0000000 +00:00 | 2007-02-09 00:00:00.0000000 +00:00 | 2010-08-25 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2013-05-01 00:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2012-04-16 00:00:00.0000000 +00:00 | 2014-09-01 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-15 14:29:52.7396495 -04:00
PO79BMAHE | Y | 2013-08-09 00:00:00.0000000 +00:00 | 2013-09-01 00:00:00.0000000 +00:00 | 2013-12-16 00:00:00.0000000 +00:00 |  | 2015-04-24 00:00:00.0000000 +00:00 | 2013-08-09 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2013-11-09 00:00:00.0000000 +00:00 | 2014-02-03 00:00:00.0000000 +00:00 | 2014-05-03 00:00:00.0000000 +00:00 | 2013-08-09 00:00:00.0000000 +00:00 | 2013-08-29 00:00:00.0000000 +00:00 | 2013-11-09 00:00:00.0000000 +00:00 | 2014-02-03 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 | 2013-08-09 00:00:00.0000000 +00:00 | 2013-09-01 00:00:00.0000000 +00:00 |  |  | 2015-04-24 00:00:00.0000000 +00:00 | 2013-11-09 00:00:00.0000000 +00:00 | 2015-04-24 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-15 14:21:12.3783610 -04:00
PO79BMAHJ | Y | 2013-11-12 00:00:00.0000000 +00:00 | 2014-05-23 00:00:00.0000000 +00:00 | 2018-08-01 00:00:00.0000000 +00:00 | 2019-05-27 00:00:00.0000000 +00:00 | 2022-11-24 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-03-12 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2016-12-26 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-05-23 00:00:00.0000000 +00:00 | 2016-07-07 00:00:00.0000000 +00:00 | 2016-11-07 00:00:00.0000000 +00:00 | 2018-03-07 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-05-23 00:00:00.0000000 +00:00 |  |  |  | 2018-07-25 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-14 00:00:00.0000000 +00:00 | 2015-04-14 00:00:00.0000000 +00:00 | 2015-04-14 00:00:00.0000000 +00:00 |  |  | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | 2015-09-15 00:00:00.0000000 +00:00 | [8 empty] | 2018-12-26 00:00:00.0000000 +00:00 | 2024-11-23 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-22 11:32:17.3720276 -04:00
PO79BMAHK | Y | 2013-09-23 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2018-07-01 00:00:00.0000000 +00:00 | 2018-11-29 00:00:00.0000000 +00:00 | 2021-11-06 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2015-03-30 00:00:00.0000000 +00:00 | 2016-03-01 00:00:00.0000000 +00:00 | 2016-07-30 00:00:00.0000000 +00:00 | 2018-01-30 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2016-10-30 00:00:00.0000000 +00:00 | 2018-05-02 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 |  |  |  | 2020-05-07 00:00:00.0000000 +00:00 | 2023-04-14 00:00:00.0000000 +00:00 | [20 empty] | 2020-01-30 00:00:00.0000000 +00:00 | [5 empty] | 2017-09-15 14:30:14.9483277 -04:00
PO79BMAHQ | Y | 2013-11-12 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2018-12-12 00:00:00.0000000 +00:00 | 2020-04-01 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2015-06-15 00:00:00.0000000 +00:00 | 2015-07-10 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2017-03-26 00:00:00.0000000 +00:00 | 2017-11-22 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2014-08-06 00:00:00.0000000 +00:00 |  |  |  | 2020-12-15 00:00:00.0000000 +00:00 | 2022-02-06 00:00:00.0000000 +00:00 |  |  |  |  | 2015-04-14 00:00:00.0000000 +00:00 | 2015-04-14 00:00:00.0000000 +00:00 | 2015-04-14 00:00:00.0000000 +00:00 |  |  | 2015-05-15 00:00:00.0000000 +00:00 | 2017-09-22 00:00:00.0000000 +00:00 | 2017-09-22 00:00:00.0000000 +00:00 | [8 empty] | 2018-03-07 00:00:00.0000000 +00:00 | 2020-10-01 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-15 14:30:37.3206763 -04:00
PO79BMAHW | Y | 2014-08-13 00:00:00.0000000 +00:00 | 2015-10-18 00:00:00.0000000 +00:00 | 2018-04-01 00:00:00.0000000 +00:00 | 2019-04-01 00:00:00.0000000 +00:00 | 2020-10-28 00:00:00.0000000 +00:00 | 2014-08-13 00:00:00.0000000 +00:00 | 2015-08-30 00:00:00.0000000 +00:00 | 2016-05-30 00:00:00.0000000 +00:00 | 2016-10-01 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2014-08-13 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2016-08-30 00:00:00.0000000 +00:00 | 2017-01-01 00:00:00.0000000 +00:00 | 2018-07-31 00:00:00.0000000 +00:00 | 2014-08-13 00:00:00.0000000 +00:00 | 2015-10-15 00:00:00.0000000 +00:00 |  |  |  | 2018-04-01 00:00:00.0000000 +00:00 |  | 2014-08-13 00:00:00.0000000 +00:00 |  | 2015-10-15 00:00:00.0000000 +00:00 |  |  | 2016-01-27 00:00:00.0000000 +00:00 | 2016-01-27 00:00:00.0000000 +00:00 | 2016-01-27 00:00:00.0000000 +00:00 |  |  | 2016-08-22 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 | 2016-08-22 00:00:00.0000000 +00:00 |  | 2018-04-01 00:00:00.0000000 +00:00 |  | 2019-04-01 00:00:00.0000000 +00:00 |  | 2020-10-28 00:00:00.0000000 +00:00 |  | 2020-04-29 00:00:00.0000000 +00:00 | 2022-10-28 00:00:00.0000000 +00:00 |  | 2022-10-28 00:00:00.0000000 +00:00 |  |  | 2017-09-15 14:24:38.2596613 -04:00
PO79BMAIU | Y | 2015-11-10 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2017-03-09 00:00:00.0000000 +00:00 | 2018-05-04 00:00:00.0000000 +00:00 | 2015-11-10 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2017-03-09 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-10 17:00:00.0000000 +00:00 | 2016-03-03 17:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2017-03-09 17:00:00.0000000 +00:00 |  | 2016-09-14 00:00:00.0000000 +00:00 | 2018-05-04 00:00:00.0000000 +00:00 | 2015-11-10 00:00:00.0000000 +00:00 | 2015-11-10 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | 2016-03-03 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-04-15 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-06-17 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2016-09-14 00:00:00.0000000 +00:00 | 2017-03-09 00:00:00.0000000 +00:00 | 2017-03-09 00:00:00.0000000 +00:00 | 2018-05-04 00:00:00.0000000 +00:00 | 2018-05-04 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2018-10-20 00:00:00.0000000 +00:00 |  | 2018-10-20 00:00:00.0000000 +00:00 | 2018-10-20 00:00:00.0000000 +00:00 |  | 2017-09-15 14:25:29.3257563 -04:00
PO79-CPPR | Y | 2004-09-14 00:00:00.0000000 +00:00 | 2004-09-14 00:00:00.0000000 +00:00 | 2006-11-16 00:00:00.0000000 +00:00 | 2007-10-15 00:00:00.0000000 +00:00 | 2011-06-30 00:00:00.0000000 +00:00 | 2004-09-14 00:00:00.0000000 +00:00 | 2004-09-14 00:00:00.0000000 +00:00 | 2006-11-22 00:00:00.0000000 +00:00 | 2007-03-23 00:00:00.0000000 +00:00 | 2009-03-25 00:00:00.0000000 +00:00 | 2004-09-14 00:00:00.0000000 +00:00 | 2004-09-14 00:00:00.0000000 +00:00 | 2006-11-16 00:00:00.0000000 +00:00 | 2007-10-19 00:00:00.0000000 +00:00 | 2011-02-02 00:00:00.0000000 +00:00 | 2004-09-14 00:00:00.0000000 +00:00 | 2004-09-14 00:00:00.0000000 +00:00 |  | 2007-10-15 00:00:00.0000000 +00:00 | 2011-06-30 00:00:00.0000000 +00:00 | 2006-11-10 00:00:00.0000000 +00:00 | 2011-01-28 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-15 14:28:57.3838671 -04:00
PO79FDBNX | Y | 2016-06-03 00:00:00.0000000 +00:00 | 2016-10-06 00:00:00.0000000 +00:00 | 2018-02-23 00:00:00.0000000 +00:00 | 2018-11-11 00:00:00.0000000 +00:00 | 2019-10-20 00:00:00.0000000 +00:00 | 2016-06-03 00:00:00.0000000 +00:00 | 2016-10-06 00:00:00.0000000 +00:00 | 2018-02-23 00:00:00.0000000 +00:00 | 2018-11-11 00:00:00.0000000 +00:00 | 2019-10-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-06-03 17:00:00.0000000 +00:00 | 2016-10-06 17:00:00.0000000 +00:00 | [5 empty] | 2016-06-03 17:00:00.0000000 +00:00 |  | 2016-10-06 17:00:00.0000000 +00:00 |  | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 |  | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 |  | 2018-02-23 00:00:00.0000000 +00:00 |  | 2018-11-11 00:00:00.0000000 +00:00 |  | 2019-10-20 00:00:00.0000000 +00:00 |  | 2020-10-19 00:00:00.0000000 +00:00 | 2020-10-19 00:00:00.0000000 +00:00 |  | 2020-10-19 00:00:00.0000000 +00:00 |  |  | 2017-09-15 14:27:12.1985388 -04:00
PO79FDESK | Y | 2011-02-07 00:00:00.0000000 +00:00 |  |  | 2013-01-31 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2011-02-07 00:00:00.0000000 +00:00 |  |  | 2012-11-26 00:00:00.0000000 +00:00 | 2013-11-27 00:00:00.0000000 +00:00 | 2011-02-07 00:00:00.0000000 +00:00 |  |  | 2013-02-01 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2011-02-07 00:00:00.0000000 +00:00 |  |  | 2013-02-01 00:00:00.0000000 +00:00 |  |  | 2015-02-13 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-15 14:28:12.5724831 -04:00
PO79FDQNS | Y | 2016-06-03 00:00:00.0000000 +00:00 | 2016-10-18 00:00:00.0000000 +00:00 | 2018-02-23 00:00:00.0000000 +00:00 | 2018-11-11 00:00:00.0000000 +00:00 | 2019-10-20 00:00:00.0000000 +00:00 | 2016-06-03 00:00:00.0000000 +00:00 | 2016-10-18 00:00:00.0000000 +00:00 | 2018-02-23 00:00:00.0000000 +00:00 | 2018-11-11 00:00:00.0000000 +00:00 | 2019-10-20 00:00:00.0000000 +00:00 | [5 empty] | 2016-06-03 17:00:00.0000000 +00:00 | 2016-10-18 17:00:00.0000000 +00:00 |  |  |  | 2017-11-14 00:00:00.0000000 +00:00 |  | 2016-06-03 17:00:00.0000000 +00:00 |  | 2016-10-18 17:00:00.0000000 +00:00 |  | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 | 2016-12-09 00:00:00.0000000 +00:00 |  | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 | 2017-01-20 00:00:00.0000000 +00:00 |  | 2018-02-23 00:00:00.0000000 +00:00 |  | 2018-11-11 00:00:00.0000000 +00:00 |  | 2019-10-20 00:00:00.0000000 +00:00 |  | 2020-10-19 00:00:00.0000000 +00:00 | 2020-10-19 00:00:00.0000000 +00:00 |  | 2020-10-19 00:00:00.0000000 +00:00 |  |  | 2017-09-21 17:51:46.1086973 -04:00
PO79-FSUP | Y | 2010-01-04 00:00:00.0000000 +00:00 | 2010-09-29 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2013-05-08 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2010-01-04 00:00:00.0000000 +00:00 | 2010-04-01 00:00:00.0000000 +00:00 | 2011-04-29 00:00:00.0000000 +00:00 | 2011-09-01 00:00:00.0000000 +00:00 | 2012-10-02 00:00:00.0000000 +00:00 | 2010-01-04 00:00:00.0000000 +00:00 | 2010-09-08 00:00:00.0000000 +00:00 | 2012-06-25 00:00:00.0000000 +00:00 | 2012-12-26 00:00:00.0000000 +00:00 | 2015-03-15 00:00:00.0000000 +00:00 | 2010-01-04 00:00:00.0000000 +00:00 | 2010-09-29 00:00:00.0000000 +00:00 | 2012-06-15 00:00:00.0000000 +00:00 | 2013-05-08 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2012-02-15 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00
PO79GENER | Y | 2014-12-10 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2017-06-06 00:00:00.0000000 +00:00 | 2018-07-20 00:00:00.0000000 +00:00 | 2020-01-31 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2015-08-25 00:00:00.0000000 +00:00 | 2016-04-09 00:00:00.0000000 +00:00 | 2016-08-25 00:00:00.0000000 +00:00 | 2017-07-06 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2015-08-25 00:00:00.0000000 +00:00 | 2016-07-25 00:00:00.0000000 +00:00 | 2017-01-26 00:00:00.0000000 +00:00 | 2017-12-07 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2017-06-06 00:00:00.0000000 +00:00 |  |  | 2016-07-01 00:00:00.0000000 +00:00 | 2018-02-27 00:00:00.0000000 +00:00 | 2014-12-10 00:00:00.0000000 +00:00 |  | 2015-06-30 00:00:00.0000000 +00:00 |  |  | 2016-02-22 00:00:00.0000000 +00:00 | 2016-02-22 00:00:00.0000000 +00:00 | 2016-02-22 00:00:00.0000000 +00:00 |  |  | 2016-05-12 00:00:00.0000000 +00:00 | 2016-05-12 00:00:00.0000000 +00:00 | 2016-05-12 00:00:00.0000000 +00:00 |  | 2017-06-06 00:00:00.0000000 +00:00 |  | 2018-07-20 00:00:00.0000000 +00:00 |  | 2020-01-31 00:00:00.0000000 +00:00 |  | 2019-07-06 00:00:00.0000000 +00:00 | 2021-01-31 00:00:00.0000000 +00:00 |  | 2021-01-31 00:00:00.0000000 +00:00 |  |  | 2017-09-15 14:32:36.3729851 -04:00
PO79-GLEN | Y | 2015-06-02 00:00:00.0000000 +00:00 | 2016-05-26 00:00:00.0000000 +00:00 | 2019-06-01 18:00:00.0000000 +00:00 | 2020-03-03 00:00:00.0000000 +00:00 | 2023-02-16 00:00:00.0000000 +00:00 | 2015-06-02 00:00:00.0000000 +00:00 | 2016-05-26 00:00:00.0000000 +00:00 | 2019-06-01 00:00:00.0000000 +00:00 | 2020-03-03 00:00:00.0000000 +00:00 | 2023-02-16 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-02 18:00:00.0000000 +00:00 | 2016-05-26 18:00:00.0000000 +00:00 |  |  |  |  | 2023-02-16 00:00:00.0000000 +00:00 | [20 empty] | 2024-02-16 00:00:00.0000000 +00:00 | 2024-02-16 00:00:00.0000000 +00:00
PO79MOU1 | Y | 2013-06-06 00:00:00.0000000 +00:00 |  |  | 2013-09-04 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2013-06-06 00:00:00.0000000 +00:00 |  |  | 2013-09-04 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2013-06-06 00:00:00.0000000 +00:00 |  |  | 2013-09-04 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 | 2013-06-06 00:00:00.0000000 +00:00 |  |  | 2013-09-04 00:00:00.0000000 +00:00 | 2013-12-15 00:00:00.0000000 +00:00 |  | 2013-12-15 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-15 14:33:33.3629281 -04:00
PO79P76R | Y | [48 empty] | 2017-09-15 14:29:24.2245616 -04:00
PO79ROD | Y | 2017-07-24 00:00:00.0000000 +00:00 | 2018-05-28 00:00:00.0000000 +00:00 | 2020-10-29 00:00:00.0000000 +00:00 | 2021-08-07 00:00:00.0000000 +00:00 | 2025-09-04 00:00:00.0000000 +00:00 | 2017-07-24 00:00:00.0000000 +00:00 | 2018-05-28 00:00:00.0000000 +00:00 | 2020-10-29 00:00:00.0000000 +00:00 | 2021-08-07 00:00:00.0000000 +00:00 | 2025-09-04 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-24 00:00:00.0000000 +00:00 | [10 empty] | 2018-10-18 00:00:00.0000000 +00:00 | 2018-10-18 00:00:00.0000000 +00:00 |  |  |  | 2019-06-27 00:00:00.0000000 +00:00 | 2019-06-27 00:00:00.0000000 +00:00 | [9 empty] | 2026-11-25 00:00:00.0000000 +00:00 | 2026-11-25 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-05 16:20:56.0072972 -04:00
PO79SHOP6 | Y | [48 empty] | 2017-09-15 14:36:07.0676304 -04:00
PO79SHOPR | Y | 2016-05-23 00:00:00.0000000 +00:00 | 2018-01-22 00:00:00.0000000 +00:00 | 2019-01-07 00:00:00.0000000 +00:00 | 2019-07-28 00:00:00.0000000 +00:00 | 2020-08-02 00:00:00.0000000 +00:00 | 2016-05-23 00:00:00.0000000 +00:00 | 2018-01-22 00:00:00.0000000 +00:00 | 2019-01-07 00:00:00.0000000 +00:00 | 2019-07-28 00:00:00.0000000 +00:00 | 2020-08-02 00:00:00.0000000 +00:00 | [5 empty] | 2016-05-23 00:00:00.0000000 +00:00 | [10 empty] | 2018-03-28 00:00:00.0000000 +00:00 | 2018-03-28 00:00:00.0000000 +00:00 |  |  |  | 2018-07-16 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | [9 empty] | 2021-08-02 00:00:00.0000000 +00:00 | 2021-08-02 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-15 14:35:30.6863676 -04:00
PO79SIDW2 | Y | 2014-01-01 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-06-28 00:00:00.0000000 +00:00 | 2016-06-07 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2014-01-01 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-06-28 00:00:00.0000000 +00:00 | 2016-06-07 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2014-12-01 00:00:00.0000000 +00:00 |  |  | 2016-06-30 00:00:00.0000000 +00:00 | 2016-12-30 00:00:00.0000000 +00:00 | 2014-01-01 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-06-28 00:00:00.0000000 +00:00 | 2016-06-07 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2014-06-28 00:00:00.0000000 +00:00 |  | 2014-01-01 00:00:00.0000000 +00:00 | 2014-01-01 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | 2014-03-03 00:00:00.0000000 +00:00 | [10 empty] | 2014-06-28 00:00:00.0000000 +00:00 | 2014-06-28 00:00:00.0000000 +00:00 | 2016-06-07 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2017-09-29 00:00:00.0000000 +00:00 | 2017-10-13 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-15 14:36:29.8635853 -04:00
PO79SIDWK | Y | 2010-12-08 00:00:00.0000000 +00:00 |  |  | 2011-07-18 00:00:00.0000000 +00:00 | 2013-01-31 00:00:00.0000000 +00:00 | 2010-12-08 00:00:00.0000000 +00:00 |  |  | 2011-07-18 00:00:00.0000000 +00:00 | 2012-08-18 00:00:00.0000000 +00:00 | 2010-12-08 00:00:00.0000000 +00:00 |  |  | 2011-07-18 00:00:00.0000000 +00:00 | 2012-12-01 00:00:00.0000000 +00:00 | 2010-12-08 00:00:00.0000000 +00:00 |  |  | 2011-07-18 00:00:00.0000000 +00:00 | 2013-01-31 00:00:00.0000000 +00:00 |  | 2012-12-01 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-15 14:37:38.8461342 -04:00
PO79WNDWS | Y | 2014-09-22 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2021-11-15 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2018-07-16 00:00:00.0000000 +00:00 | 2019-07-01 00:00:00.0000000 +00:00 | 2021-11-15 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | 2016-06-07 00:00:00.0000000 +00:00 | 2016-11-27 00:00:00.0000000 +00:00 | 2017-11-27 00:00:00.0000000 +00:00 | 2014-09-22 00:00:00.0000000 +00:00 | 2015-09-30 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-22 00:00:00.0000000 +00:00 |  | 2015-09-30 00:00:00.0000000 +00:00 |  | 2016-07-18 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 | 2016-07-18 00:00:00.0000000 +00:00 |  | 2017-06-12 00:00:00.0000000 +00:00 | 2017-06-12 00:00:00.0000000 +00:00 | 2017-06-12 00:00:00.0000000 +00:00 | 2017-06-12 00:00:00.0000000 +00:00 |  | 2018-07-16 00:00:00.0000000 +00:00 |  | 2019-07-01 00:00:00.0000000 +00:00 |  | 2021-11-15 00:00:00.0000000 +00:00 |  | 2022-08-30 00:00:00.0000000 +00:00 | 2022-08-30 00:00:00.0000000 +00:00 |  | 2022-08-30 00:00:00.0000000 +00:00 |  |  | 2017-09-15 14:38:01.7210946 -04:00
PS-312CW | Y | 2012-12-21 00:00:00.0000000 +00:00 | 2012-12-21 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2014-10-07 00:00:00.0000000 +00:00 | 2012-12-21 00:00:00.0000000 +00:00 | 2012-12-21 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2014-06-23 00:00:00.0000000 +00:00 | 2012-12-21 00:00:00.0000000 +00:00 | 2012-12-21 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2014-06-23 00:00:00.0000000 +00:00 | 2012-12-21 17:00:00.0000000 +00:00 | 2012-12-21 17:00:00.0000000 +00:00 | 2013-01-11 17:00:00.0000000 +00:00 | 2013-06-24 18:00:00.0000000 +00:00 | 2014-10-07 17:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2014-10-07 00:00:00.0000000 +00:00 | 2012-12-21 17:00:00.0000000 +00:00 | 2012-12-21 00:00:00.0000000 +00:00 | 2012-12-21 17:00:00.0000000 +00:00 | 2012-12-21 00:00:00.0000000 +00:00 |  | 2012-12-26 00:00:00.0000000 +00:00 | 2012-12-26 00:00:00.0000000 +00:00 | 2012-12-26 00:00:00.0000000 +00:00 | 2012-12-26 00:00:00.0000000 +00:00 | [5 empty] | 2013-01-11 17:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2013-06-24 18:00:00.0000000 +00:00 | 2013-06-24 00:00:00.0000000 +00:00 | 2014-10-07 17:00:00.0000000 +00:00 | 2014-10-07 00:00:00.0000000 +00:00 |  | 2018-04-16 00:00:00.0000000 +00:00 |  | 2018-04-16 00:00:00.0000000 +00:00
PS-312CW1 | Y | 2013-03-07 00:00:00.0000000 +00:00 | 2013-10-07 00:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2016-08-12 00:00:00.0000000 +00:00 | 2013-03-07 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2016-07-31 00:00:00.0000000 +00:00 | 2013-03-07 00:00:00.0000000 +00:00 | 2013-06-03 00:00:00.0000000 +00:00 | 2014-03-08 00:00:00.0000000 +00:00 | 2014-09-05 00:00:00.0000000 +00:00 | 2015-09-05 00:00:00.0000000 +00:00 | 2013-03-07 12:00:00.0000000 +00:00 | 2013-10-07 07:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2015-08-17 00:00:00.0000000 +00:00 | 2016-08-12 17:00:00.0000000 +00:00 | 2014-07-01 00:00:00.0000000 +00:00 | 2016-08-12 00:00:00.0000000 +00:00 |  | 2013-03-07 12:00:00.0000000 +00:00 |  | 2013-10-07 07:00:00.0000000 +00:00 | 2013-12-17 00:00:00.0000000 +00:00 | 2013-12-17 00:00:00.0000000 +00:00 | 2013-12-17 00:00:00.0000000 +00:00 |  | 2013-12-17 00:00:00.0000000 +00:00 | [6 empty] | 2014-07-01 00:00:00.0000000 +00:00 |  | 2015-08-17 00:00:00.0000000 +00:00 |  | 2016-08-12 17:00:00.0000000 +00:00 | 2017-10-20 00:00:00.0000000 +00:00 | 2017-10-20 00:00:00.0000000 +00:00 |  |  | 2017-10-20 00:00:00.0000000 +00:00 |  | 2017-09-13 14:25:18.5815333 -04:00
PS-312KR | Y | 2012-11-15 00:00:00.0000000 +00:00 | 2012-11-19 00:00:00.0000000 +00:00 | 2014-01-02 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2018-02-17 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2012-11-26 00:00:00.0000000 +00:00 | 2014-01-02 00:00:00.0000000 +00:00 | 2015-12-21 00:00:00.0000000 +00:00 | 2018-02-17 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2012-11-26 00:00:00.0000000 +00:00 | 2013-10-28 00:00:00.0000000 +00:00 | 2005-05-26 00:00:00.0000000 +00:00 | 2007-05-28 00:00:00.0000000 +00:00 | 2012-11-15 12:00:00.0000000 +00:00 | 2012-11-26 12:00:00.0000000 +00:00 | 2014-01-02 00:00:00.0000000 +00:00 | 2015-12-21 17:00:00.0000000 +00:00 |  | 2014-01-02 00:00:00.0000000 +00:00 | 2018-02-17 00:00:00.0000000 +00:00 |  | 2012-11-15 12:00:00.0000000 +00:00 |  | 2012-11-26 12:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 |  | 2013-06-12 00:00:00.0000000 +00:00 | [6 empty] | 2014-01-02 00:00:00.0000000 +00:00 |  | 2015-12-21 17:00:00.0000000 +00:00 |  | 2018-02-17 00:00:00.0000000 +00:00 | 2019-02-12 00:00:00.0000000 +00:00 | 2019-02-12 00:00:00.0000000 +00:00 |  |  | 2019-02-12 00:00:00.0000000 +00:00 |  | 2017-11-30 14:52:04.8794340 -05:00
PS-312MX | Y | 2012-11-15 00:00:00.0000000 +00:00 | 2012-12-10 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2019-06-29 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2012-12-16 00:00:00.0000000 +00:00 | 2013-02-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2015-08-16 00:00:00.0000000 +00:00 | 2012-11-15 00:00:00.0000000 +00:00 | 2012-12-16 00:00:00.0000000 +00:00 | 2013-10-03 00:00:00.0000000 +00:00 | 2014-03-07 00:00:00.0000000 +00:00 | 2016-03-07 00:00:00.0000000 +00:00 | 2012-11-15 12:00:00.0000000 +00:00 | 2012-12-10 00:00:00.0000000 +00:00 | 2017-10-31 00:00:00.0000000 +00:00 |  |  | 2014-09-04 00:00:00.0000000 +00:00 |  | 2012-11-15 12:00:00.0000000 +00:00 |  | 2012-12-10 00:00:00.0000000 +00:00 |  | 2013-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | [6 empty] | 2017-12-15 00:00:00.0000000 +00:00 |  | 2018-06-30 00:00:00.0000000 +00:00 |  | 2019-06-29 00:00:00.0000000 +00:00 |  | 2018-07-14 00:00:00.0000000 +00:00 | 2021-06-29 00:00:00.0000000 +00:00 |  | 2021-06-29 00:00:00.0000000 +00:00 |  |  | 2017-11-15 16:37:59.6606764 -05:00
PS-312Q | Y | 2012-11-29 00:00:00.0000000 +00:00 | 2012-12-18 00:00:00.0000000 +00:00 | 2014-03-13 00:00:00.0000000 +00:00 | 2015-10-12 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2012-11-29 00:00:00.0000000 +00:00 | 2012-12-18 00:00:00.0000000 +00:00 | 2013-02-16 00:00:00.0000000 +00:00 | 2013-07-02 00:00:00.0000000 +00:00 | 2015-07-01 00:00:00.0000000 +00:00 | 2012-11-29 00:00:00.0000000 +00:00 | 2012-12-18 00:00:00.0000000 +00:00 | 2013-12-03 00:00:00.0000000 +00:00 | 2014-05-02 00:00:00.0000000 +00:00 | 2016-04-30 00:00:00.0000000 +00:00 | 2012-11-29 12:00:00.0000000 +00:00 | 2012-12-18 17:00:00.0000000 +00:00 | 2014-03-13 00:00:00.0000000 +00:00 | 2015-10-12 17:00:00.0000000 +00:00 | 2017-09-30 00:00:00.0000000 +00:00 | 2014-03-13 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2012-11-29 00:00:00.0000000 +00:00 | 2012-11-29 12:00:00.0000000 +00:00 | 2012-12-18 00:00:00.0000000 +00:00 | 2012-12-18 17:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | 2013-01-15 00:00:00.0000000 +00:00 | [5 empty] | 2014-03-13 00:00:00.0000000 +00:00 | 2014-03-13 00:00:00.0000000 +00:00 | 2015-10-12 00:00:00.0000000 +00:00 | 2015-10-12 17:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2018-07-01 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 |  | 2021-06-30 00:00:00.0000000 +00:00 | 2021-06-30 00:00:00.0000000 +00:00 |  | 2017-11-30 11:21:38.9127539 -05:00
P-USTA1 | Y | 2013-02-18 00:00:00.0000000 +00:00 | 2013-02-18 00:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 | 2014-01-22 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2013-02-18 00:00:00.0000000 +00:00 | 2013-02-18 00:00:00.0000000 +00:00 | 2013-08-12 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2014-10-06 00:00:00.0000000 +00:00 | 2013-02-18 00:00:00.0000000 +00:00 | 2013-02-18 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2014-08-13 00:00:00.0000000 +00:00 | 2015-03-11 00:00:00.0000000 +00:00 | 2013-02-18 12:00:00.0000000 +00:00 | 2013-02-18 12:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 | 2014-01-22 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2013-02-18 12:00:00.0000000 +00:00 | 2013-02-18 12:00:00.0000000 +00:00 | 2013-02-18 12:00:00.0000000 +00:00 | 2013-02-18 12:00:00.0000000 +00:00 | 2013-04-19 00:00:00.0000000 +00:00 | 2013-04-10 00:00:00.0000000 +00:00 | 2013-04-10 00:00:00.0000000 +00:00 | 2013-04-10 00:00:00.0000000 +00:00 | 2013-04-10 00:00:00.0000000 +00:00 | [5 empty] | 2013-08-26 00:00:00.0000000 +00:00 | 2013-08-26 00:00:00.0000000 +00:00 | 2014-01-22 00:00:00.0000000 +00:00 | 2014-01-22 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2015-07-31 00:00:00.0000000 +00:00 | 2017-10-05 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00 |  | 2018-07-30 00:00:00.0000000 +00:00 | 2018-07-30 00:00:00.0000000 +00:00
PV001SELM | Y | 2015-09-11 00:00:00.0000000 +00:00 | 2017-09-20 00:00:00.0000000 +00:00 | 2018-12-17 00:00:00.0000000 +00:00 | 2019-09-16 00:00:00.0000000 +00:00 | 2021-01-18 00:00:00.0000000 +00:00 | 2015-09-11 00:00:00.0000000 +00:00 | 2016-12-05 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2018-11-27 00:00:00.0000000 +00:00 | 2020-03-20 00:00:00.0000000 +00:00 | 2015-09-11 00:00:00.0000000 +00:00 | 2016-12-05 00:00:00.0000000 +00:00 | 2018-02-28 00:00:00.0000000 +00:00 | 2018-11-27 00:00:00.0000000 +00:00 | 2020-03-20 00:00:00.0000000 +00:00 | 2015-09-11 00:00:00.0000000 +00:00 | 2017-09-20 00:00:00.0000000 +00:00 |  |  |  | 2018-12-17 00:00:00.0000000 +00:00 | 2021-01-18 00:00:00.0000000 +00:00 | 2015-09-11 00:00:00.0000000 +00:00 |  | 2017-09-20 00:00:00.0000000 +00:00 | [11 empty] | 2018-12-17 00:00:00.0000000 +00:00 |  | 2019-09-16 00:00:00.0000000 +00:00 |  | 2021-01-18 00:00:00.0000000 +00:00 |  | 2022-03-20 00:00:00.0000000 +00:00 | 2023-01-18 00:00:00.0000000 +00:00 |  | 2023-01-18 00:00:00.0000000 +00:00 |  |  | 2017-09-28 16:33:42.3547737 -04:00
PV002CULT | Y | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2018-12-16 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2013-12-19 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2013-12-19 00:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2013-09-23 00:00:00.0000000 +00:00 | 2013-11-12 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 |  |  | 2018-12-16 00:00:00.0000000 +00:00 | [26 empty] | 2017-09-13 12:03:36.5969853 -04:00
PV019-REN | Y | [5 empty] | 2017-04-05 00:00:00.0000000 +00:00 | 2017-04-05 00:00:00.0000000 +00:00 | 2017-05-01 00:00:00.0000000 +00:00 | [18 empty] | 2017-04-05 00:00:00.0000000 +00:00 |  |  |  |  | 2017-04-05 00:00:00.0000000 +00:00 | [15 empty] | 2017-09-09 15:33:04.4830000 +00:00
PV022-FAC | Y | 2004-01-26 00:00:00.0000000 +00:00 | 2004-01-28 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 | 2004-09-17 00:00:00.0000000 +00:00 | 2008-10-16 00:00:00.0000000 +00:00 | 2004-01-26 00:00:00.0000000 +00:00 | 2004-01-28 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 | 2004-09-17 00:00:00.0000000 +00:00 | 2007-09-17 00:00:00.0000000 +00:00 | 2004-01-26 00:00:00.0000000 +00:00 | 2004-01-28 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 | 2004-09-17 00:00:00.0000000 +00:00 | 2007-09-17 00:00:00.0000000 +00:00 | 2004-01-26 00:00:00.0000000 +00:00 | 2004-01-28 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 | 2004-09-17 00:00:00.0000000 +00:00 | 2008-10-15 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 | 2007-09-17 00:00:00.0000000 +00:00 |  |  |  |  | 2004-03-02 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 |  |  | 2004-03-02 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 | 2004-03-02 00:00:00.0000000 +00:00 | [14 empty] | 2017-11-08 15:14:25.7011618 -05:00
PV028-ISA | Y | 2014-03-07 00:00:00.0000000 +00:00 |  |  | 2015-02-09 00:00:00.0000000 +00:00 | 2015-07-09 00:00:00.0000000 +00:00 | 2014-03-07 00:00:00.0000000 +00:00 |  |  | 2015-02-09 00:00:00.0000000 +00:00 | 2015-07-09 00:00:00.0000000 +00:00 | 2014-03-07 00:00:00.0000000 +00:00 |  |  | 2015-02-09 00:00:00.0000000 +00:00 | 2015-07-09 00:00:00.0000000 +00:00 | 2014-03-07 00:00:00.0000000 +00:00 |  |  | 2015-02-09 00:00:00.0000000 +00:00 | 2015-07-09 00:00:00.0000000 +00:00 |  | 2015-07-09 00:00:00.0000000 +00:00
PV028-ISS | Y | 2012-04-09 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2017-04-30 00:00:00.0000000 +00:00 | 2018-11-21 00:00:00.0000000 +00:00 | 2020-05-20 00:00:00.0000000 +00:00 | 2012-04-09 00:00:00.0000000 +00:00 | 2012-10-31 00:00:00.0000000 +00:00 | 2013-12-26 00:00:00.0000000 +00:00 | 2014-07-20 00:00:00.0000000 +00:00 | 2015-10-14 00:00:00.0000000 +00:00 | 2012-04-09 00:00:00.0000000 +00:00 | 2012-12-14 00:00:00.0000000 +00:00 | 2016-02-08 00:00:00.0000000 +00:00 | 2017-01-18 00:00:00.0000000 +00:00 | 2018-04-14 00:00:00.0000000 +00:00 | 2012-04-09 00:00:00.0000000 +00:00 | 2013-01-11 00:00:00.0000000 +00:00 | 2017-04-13 00:00:00.0000000 +00:00 |  |  | 2018-09-20 00:00:00.0000000 +00:00 | 2018-12-12 00:00:00.0000000 +00:00 | 2012-04-09 00:00:00.0000000 +00:00 |  | 2013-01-11 00:00:00.0000000 +00:00 |  | 2013-02-28 00:00:00.0000000 +00:00 | 2013-05-18 00:00:00.0000000 +00:00 | 2013-05-18 00:00:00.0000000 +00:00 | 2013-05-18 00:00:00.0000000 +00:00 |  | 2013-09-18 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 | 2013-12-18 00:00:00.0000000 +00:00 |  | 2017-04-13 00:00:00.0000000 +00:00 |  | 2018-11-21 00:00:00.0000000 +00:00 |  | 2020-05-20 00:00:00.0000000 +00:00 |  | 2017-10-13 00:00:00.0000000 +00:00 | 2022-05-20 00:00:00.0000000 +00:00 |  | 2022-05-20 00:00:00.0000000 +00:00 |  |  | 2017-10-13 10:07:43.5392569 -04:00
PV031ARC3 | Y | 2012-02-16 00:00:00.0000000 +00:00 | 2012-09-27 00:00:00.0000000 +00:00 | 2014-06-18 00:00:00.0000000 +00:00 | 2017-04-04 00:00:00.0000000 +00:00 | 2017-12-15 00:00:00.0000000 +00:00 | 2012-02-16 00:00:00.0000000 +00:00 | 2012-08-29 00:00:00.0000000 +00:00 | 2013-04-26 00:00:00.0000000 +00:00 | 2013-09-24 00:00:00.0000000 +00:00 | 2014-06-22 00:00:00.0000000 +00:00 | 2012-02-16 00:00:00.0000000 +00:00 | 2012-09-27 00:00:00.0000000 +00:00 | 2014-06-18 00:00:00.0000000 +00:00 | 2016-10-23 00:00:00.0000000 +00:00 | 2017-07-21 00:00:00.0000000 +00:00 | 2012-02-16 00:00:00.0000000 +00:00 | 2012-09-27 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2016-06-08 18:00:00.0000000 +00:00 |  | 2015-07-12 00:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2012-02-16 00:00:00.0000000 +00:00 | 2012-02-16 00:00:00.0000000 +00:00 | 2012-09-27 00:00:00.0000000 +00:00 | 2012-09-27 00:00:00.0000000 +00:00 |  | 2012-12-31 00:00:00.0000000 +00:00 | 2012-12-31 00:00:00.0000000 +00:00 | 2012-12-31 00:00:00.0000000 +00:00 | 2012-12-31 00:00:00.0000000 +00:00 |  | 2013-11-06 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2013-11-06 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2014-06-26 00:00:00.0000000 +00:00 | 2016-06-08 00:00:00.0000000 +00:00 | 2016-06-08 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2017-11-30 00:00:00.0000000 +00:00 | 2016-06-21 00:00:00.0000000 +00:00 | 2019-03-15 00:00:00.0000000 +00:00 |  | 2018-11-30 00:00:00.0000000 +00:00 | 2018-11-30 00:00:00.0000000 +00:00 |  | 2017-12-13 13:18:24.4423749 -05:00
PV034ELTK | Y | 2011-03-17 00:00:00.0000000 +00:00 | 2011-03-17 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2011-07-08 00:00:00.0000000 +00:00 | 2014-07-09 00:00:00.0000000 +00:00 | 2011-03-17 00:00:00.0000000 +00:00 | 2011-03-17 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2011-07-08 00:00:00.0000000 +00:00 | 2014-07-09 00:00:00.0000000 +00:00 | 2011-03-17 00:00:00.0000000 +00:00 | 2011-03-17 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2011-07-08 00:00:00.0000000 +00:00 | 2014-07-09 00:00:00.0000000 +00:00 | 2011-03-17 00:00:00.0000000 +00:00 | 2011-03-17 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2011-07-08 00:00:00.0000000 +00:00 | 2014-07-09 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2014-07-09 00:00:00.0000000 +00:00 | [5 empty] | 2011-06-01 00:00:00.0000000 +00:00 |  |  |  |  | 2011-06-01 00:00:00.0000000 +00:00 | [15 empty] | 2017-11-20 15:05:58.1083265 -05:00
PV034RFCP | Y | 2012-01-24 00:00:00.0000000 +00:00 | 2012-01-25 00:00:00.0000000 +00:00 | 2012-04-25 00:00:00.0000000 +00:00 | 2012-07-11 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2012-01-24 00:00:00.0000000 +00:00 | 2012-01-25 00:00:00.0000000 +00:00 | 2012-04-25 00:00:00.0000000 +00:00 | 2012-06-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2012-01-24 00:00:00.0000000 +00:00 | 2012-01-25 00:00:00.0000000 +00:00 | 2012-04-25 00:00:00.0000000 +00:00 | 2012-06-29 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2012-01-24 00:00:00.0000000 +00:00 | 2012-01-25 00:00:00.0000000 +00:00 | 2012-04-25 00:00:00.0000000 +00:00 | 2012-07-11 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | 2012-04-25 00:00:00.0000000 +00:00 | 2015-01-13 00:00:00.0000000 +00:00 | [5 empty] | 2012-04-25 00:00:00.0000000 +00:00 |  |  |  |  | 2012-04-25 00:00:00.0000000 +00:00 | [15 empty] | 2017-11-20 15:06:35.3361643 -05:00
PV034ROSE | Y | 2014-12-31 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-12-31 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 |  | 2015-05-28 00:00:00.0000000 +00:00 |  | 2015-05-29 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-06 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 |  |  |  | 2015-05-06 00:00:00.0000000 +00:00 | [15 empty] | 2017-11-20 15:07:05.3682234 -05:00
PV040BATH | Y | [48 empty] | 2017-09-01 12:57:51.2473849 -04:00
PV040ELEV | Y
PV101-MJH | Y | [47 empty] | 2017-09-09 15:33:05.7700000 +00:00 | 2017-12-04 15:04:03.0459844 -05:00
PV120CT7E | Y | 2014-05-23 00:00:00.0000000 +00:00 | 2014-06-12 00:00:00.0000000 +00:00 | 2016-05-21 00:00:00.0000000 +00:00 | 2017-01-04 00:00:00.0000000 +00:00 | 2017-12-31 00:00:00.0000000 +00:00 | 2014-05-23 00:00:00.0000000 +00:00 | 2014-06-12 00:00:00.0000000 +00:00 | 2016-05-21 00:00:00.0000000 +00:00 | 2017-01-04 00:00:00.0000000 +00:00 | 2017-08-03 00:00:00.0000000 +00:00 | [5 empty] | 2014-05-21 18:00:00.0000000 +00:00 | 2015-12-02 20:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2017-01-10 20:00:00.0000000 +00:00 |  | 2016-05-22 00:00:00.0000000 +00:00 | 2017-08-03 00:00:00.0000000 +00:00 | [20 empty] | 2019-08-03 00:00:00.0000000 +00:00 | 2019-03-29 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-05 15:17:40.3339140 -04:00
PV122-DTH | Y | 2014-01-15 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2018-02-15 00:00:00.0000000 +00:00 | 2018-11-10 00:00:00.0000000 +00:00 | 2020-10-29 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2015-04-11 00:00:00.0000000 +00:00 | 2016-11-19 00:00:00.0000000 +00:00 | 2017-08-02 00:00:00.0000000 +00:00 | 2019-02-01 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2017-03-30 00:00:00.0000000 +00:00 | 2018-01-14 00:00:00.0000000 +00:00 | 2019-07-16 00:00:00.0000000 +00:00 | 2014-01-15 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 |  |  |  | 2018-02-15 00:00:00.0000000 +00:00 | 2020-10-29 00:00:00.0000000 +00:00 | [6 empty] | 2016-07-12 00:00:00.0000000 +00:00 |  |  |  |  | 2016-09-20 00:00:00.0000000 +00:00 | [8 empty] | 2021-01-31 00:00:00.0000000 +00:00 | 2022-04-20 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-16 15:52:31.9258283 -04:00
PV124-DW | Y | 2013-02-28 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2016-05-18 00:00:00.0000000 +00:00 | 2017-06-29 00:00:00.0000000 +00:00 | 2018-12-10 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2013-10-15 00:00:00.0000000 +00:00 | 2014-07-15 00:00:00.0000000 +00:00 | 2015-02-15 00:00:00.0000000 +00:00 | 2016-06-15 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2014-01-22 00:00:00.0000000 +00:00 | 2015-04-11 00:00:00.0000000 +00:00 | 2016-05-05 00:00:00.0000000 +00:00 | 2017-09-03 00:00:00.0000000 +00:00 | 2013-01-28 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2016-05-18 00:00:00.0000000 +00:00 | 2017-06-29 17:00:00.0000000 +00:00 |  | 2015-01-05 00:00:00.0000000 +00:00 | 2018-12-10 00:00:00.0000000 +00:00 |  | 2013-01-28 00:00:00.0000000 +00:00 |  | 2014-04-09 00:00:00.0000000 +00:00 | 2014-01-13 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 | 2014-07-16 00:00:00.0000000 +00:00 |  | 2014-07-16 00:00:00.0000000 +00:00 | 2014-04-17 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 | 2014-12-16 00:00:00.0000000 +00:00 |  | 2014-12-16 00:00:00.0000000 +00:00 |  | 2016-05-18 00:00:00.0000000 +00:00 |  | 2017-06-29 00:00:00.0000000 +00:00 |  | 2018-12-10 00:00:00.0000000 +00:00 | 2018-06-15 00:00:00.0000000 +00:00 | 2020-12-09 00:00:00.0000000 +00:00 |  |  | 2020-12-09 00:00:00.0000000 +00:00 |  | 2017-09-07 15:43:59.6681925 -04:00
PV132DCTV | Y | [47 empty] | 2017-09-09 15:33:18.1430000 +00:00
PV175AQUA | Y | 2010-08-19 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2010-08-19 00:00:00.0000000 +00:00 | 2011-08-11 00:00:00.0000000 +00:00 | 2012-08-09 00:00:00.0000000 +00:00 | 2013-03-14 00:00:00.0000000 +00:00 | 2014-12-11 00:00:00.0000000 +00:00 | 2010-08-19 00:00:00.0000000 +00:00 | 2011-08-11 00:00:00.0000000 +00:00 | 2015-08-24 00:00:00.0000000 +00:00 | 2016-10-13 00:00:00.0000000 +00:00 | 2018-07-12 00:00:00.0000000 +00:00 | 2010-08-19 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 |  | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2010-08-09 00:00:00.0000000 +00:00 | 2010-08-19 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 | 2011-06-15 00:00:00.0000000 +00:00 |  |  | 2011-08-09 00:00:00.0000000 +00:00 | 2011-08-09 00:00:00.0000000 +00:00 | 2011-08-09 00:00:00.0000000 +00:00 |  |  | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2013-12-30 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2015-05-14 00:00:00.0000000 +00:00 | 2016-06-08 00:00:00.0000000 +00:00 | 2016-06-28 00:00:00.0000000 +00:00 |  | 2018-06-29 00:00:00.0000000 +00:00 |  | 2020-06-29 00:00:00.0000000 +00:00 |  |  | 2020-06-29 00:00:00.0000000 +00:00 |  | 2017-09-13 10:53:38.7971198 -04:00
PV175CHLA | Y | 2008-02-11 00:00:00.0000000 +00:00 | 2008-09-30 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2012-08-02 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2008-02-11 00:00:00.0000000 +00:00 | 2008-09-30 00:00:00.0000000 +00:00 | 2011-03-31 00:00:00.0000000 +00:00 | 2011-10-27 00:00:00.0000000 +00:00 | 2012-10-27 00:00:00.0000000 +00:00 | 2008-02-11 00:00:00.0000000 +00:00 | 2008-09-30 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2012-06-23 00:00:00.0000000 +00:00 | 2014-02-21 00:00:00.0000000 +00:00 | 2008-02-11 00:00:00.0000000 +00:00 | 2008-09-30 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2012-08-02 00:00:00.0000000 +00:00 | 2014-03-10 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2014-03-31 00:00:00.0000000 +00:00 | [21 empty] | 2017-12-11 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-01 13:00:07.7692897 -04:00
PV175ROOF | Y | 2017-01-02 00:00:00.0000000 +00:00 | 2017-02-07 00:00:00.0000000 +00:00 | 2018-02-01 00:00:00.0000000 +00:00 | 2018-11-01 00:00:00.0000000 +00:00 | 2020-05-01 00:00:00.0000000 +00:00 | 2017-01-02 00:00:00.0000000 +00:00 | 2017-02-07 00:00:00.0000000 +00:00 | 2017-11-01 00:00:00.0000000 +00:00 | 2018-05-01 00:00:00.0000000 +00:00 | 2020-05-01 00:00:00.0000000 +00:00 | [5 empty] | 2017-01-02 00:00:00.0000000 +00:00 | 2017-02-07 00:00:00.0000000 +00:00 |  |  |  | 2018-02-01 00:00:00.0000000 +00:00 |  | 2017-01-02 00:00:00.0000000 +00:00 |  | 2017-02-07 00:00:00.0000000 +00:00 |  |  | 2017-05-02 00:00:00.0000000 +00:00 | 2017-04-25 00:00:00.0000000 +00:00 | 2017-04-25 00:00:00.0000000 +00:00 |  |  | 2017-09-26 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 | 2017-09-08 00:00:00.0000000 +00:00 |  | 2018-02-01 00:00:00.0000000 +00:00 |  | 2018-11-01 00:00:00.0000000 +00:00 |  | 2020-05-01 00:00:00.0000000 +00:00 |  |  | 2022-05-02 00:00:00.0000000 +00:00 |  | 2022-05-02 00:00:00.0000000 +00:00 |  |  | 2017-10-04 15:47:20.5506195 -04:00
PV176CESU | Y | 2013-10-09 00:00:00.0000000 +00:00 | 2015-02-18 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2019-03-28 00:00:00.0000000 +00:00 | 2021-03-16 00:00:00.0000000 +00:00 | 2014-02-14 00:00:00.0000000 +00:00 | 2014-10-15 00:00:00.0000000 +00:00 | 2015-10-10 00:00:00.0000000 +00:00 | 2016-05-01 00:00:00.0000000 +00:00 | 2017-05-12 00:00:00.0000000 +00:00 | 2014-02-14 00:00:00.0000000 +00:00 | 2015-01-29 00:00:00.0000000 +00:00 | 2016-01-24 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2017-08-26 00:00:00.0000000 +00:00 | 2013-10-09 18:00:00.0000000 +00:00 | 2015-02-18 00:00:00.0000000 +00:00 |  |  |  | 2017-12-16 00:00:00.0000000 +00:00 | [21 empty] | 2019-05-12 00:00:00.0000000 +00:00 | 2022-09-06 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-14 10:38:03.8164550 -04:00
PV176ITF1 | Y | 2012-10-01 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2016-09-12 00:00:00.0000000 +00:00 | 2018-05-11 00:00:00.0000000 +00:00 | 2012-10-01 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2014-02-28 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2016-03-09 00:00:00.0000000 +00:00 | 2012-10-01 00:00:00.0000000 +00:00 | 2012-10-15 00:00:00.0000000 +00:00 | 2014-04-30 00:00:00.0000000 +00:00 | 2014-11-12 00:00:00.0000000 +00:00 | 2016-05-09 00:00:00.0000000 +00:00 | 2012-10-01 12:00:00.0000000 +00:00 | 2012-10-15 12:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2016-09-12 17:00:00.0000000 +00:00 |  | 2014-09-12 00:00:00.0000000 +00:00 | 2018-05-11 00:00:00.0000000 +00:00 | 2012-10-01 12:00:00.0000000 +00:00 | 2012-10-01 12:00:00.0000000 +00:00 | 2012-10-15 12:00:00.0000000 +00:00 | 2012-10-15 12:00:00.0000000 +00:00 | 2013-09-16 00:00:00.0000000 +00:00 | 2013-10-10 00:00:00.0000000 +00:00 | 2013-10-10 00:00:00.0000000 +00:00 | 2013-10-10 00:00:00.0000000 +00:00 | 2013-10-10 00:00:00.0000000 +00:00 | [5 empty] | 2014-09-12 00:00:00.0000000 +00:00 | 2014-09-12 00:00:00.0000000 +00:00 | 2016-09-12 17:00:00.0000000 +00:00 | 2016-09-12 17:00:00.0000000 +00:00 | 2018-05-11 00:00:00.0000000 +00:00 | 2018-05-11 00:00:00.0000000 +00:00 | 2019-03-09 00:00:00.0000000 +00:00 | 2021-05-10 00:00:00.0000000 +00:00 |  | 2021-05-10 00:00:00.0000000 +00:00 | 2021-05-10 00:00:00.0000000 +00:00 |  | 2017-11-30 14:24:18.8948918 -05:00
PV181HSA2 | Y | 2011-05-30 00:00:00.0000000 +00:00 | 2011-11-04 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2018-04-23 00:00:00.0000000 +00:00 | 2011-05-30 00:00:00.0000000 +00:00 | 2011-11-04 00:00:00.0000000 +00:00 | 2012-08-30 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2014-02-23 00:00:00.0000000 +00:00 | 2011-05-30 00:00:00.0000000 +00:00 | 2011-11-04 00:00:00.0000000 +00:00 | 2014-05-11 00:00:00.0000000 +00:00 | 2016-02-15 00:00:00.0000000 +00:00 | 2017-02-10 00:00:00.0000000 +00:00 | 2011-05-30 00:00:00.0000000 +00:00 | 2011-05-30 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2016-08-15 09:00:00.0000000 +00:00 |  | 2015-08-14 00:00:00.0000000 +00:00 | 2018-04-23 00:00:00.0000000 +00:00 | 2011-05-30 00:00:00.0000000 +00:00 | 2011-05-30 00:00:00.0000000 +00:00 | 2011-05-30 00:00:00.0000000 +00:00 | 2011-05-30 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2012-05-18 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2015-08-14 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2016-08-15 00:00:00.0000000 +00:00 | 2018-04-23 00:00:00.0000000 +00:00 | 2018-04-23 00:00:00.0000000 +00:00 | 2016-02-23 00:00:00.0000000 +00:00 | 2020-04-23 00:00:00.0000000 +00:00 |  | 2020-04-23 00:00:00.0000000 +00:00 | 2020-04-23 00:00:00.0000000 +00:00 |  | 2017-12-01 13:57:38.4913993 -05:00
PV204-LOB | Y | 2016-11-28 00:00:00.0000000 +00:00 | 2016-11-28 00:00:00.0000000 +00:00 | 2016-12-22 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 |  | 2016-11-28 00:00:00.0000000 +00:00 | 2016-11-28 00:00:00.0000000 +00:00 | 2016-12-22 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 | [6 empty] | 2016-11-28 00:00:00.0000000 +00:00 | 2016-11-28 00:00:00.0000000 +00:00 | 2016-12-22 00:00:00.0000000 +00:00 | 2017-03-22 00:00:00.0000000 +00:00 | [7 empty] | 2016-12-22 00:00:00.0000000 +00:00 | 2016-12-22 00:00:00.0000000 +00:00 | 2016-12-22 00:00:00.0000000 +00:00 |  |  | 2016-12-22 00:00:00.0000000 +00:00 | 2016-12-22 00:00:00.0000000 +00:00 | 2016-12-22 00:00:00.0000000 +00:00 | [14 empty] | 2017-11-30 15:17:14.2681128 -05:00
PV205ACAD | Y | 2015-05-26 00:00:00.0000000 +00:00 | 2015-07-01 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2016-02-17 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2015-07-01 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2016-05-27 00:00:00.0000000 +00:00 | 2019-05-24 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2015-07-01 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 | 2016-05-27 00:00:00.0000000 +00:00 | 2019-02-15 00:00:00.0000000 +00:00 | 2015-05-26 00:00:00.0000000 +00:00 | 2015-07-01 00:00:00.0000000 +00:00 |  | 2016-02-17 00:00:00.0000000 +00:00 |  |  | 2019-02-15 00:00:00.0000000 +00:00 | [5 empty] | 2015-11-05 00:00:00.0000000 +00:00 | 2015-11-05 00:00:00.0000000 +00:00 |  |  |  | 2015-11-05 00:00:00.0000000 +00:00 | [15 empty] | 2017-11-20 15:09:18.9285783 -05:00
PV205GREN | Y | 2014-08-14 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-04-23 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-08-14 00:00:00.0000000 +00:00 | 2014-08-27 00:00:00.0000000 +00:00 |  | 2015-05-20 00:00:00.0000000 +00:00 |  | 2015-05-29 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-04-23 00:00:00.0000000 +00:00 | 2015-04-23 00:00:00.0000000 +00:00 |  |  |  | 2015-04-23 00:00:00.0000000 +00:00 | [15 empty] | 2017-11-20 15:09:51.9372783 -05:00
PV205LIB1 | Y | 2011-01-04 00:00:00.0000000 +00:00 | 2011-10-04 00:00:00.0000000 +00:00 | 2012-05-04 00:00:00.0000000 +00:00 | 2012-06-28 00:00:00.0000000 +00:00 | 2015-05-27 00:00:00.0000000 +00:00 | 2011-01-04 00:00:00.0000000 +00:00 | 2011-10-04 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2012-06-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2011-01-04 00:00:00.0000000 +00:00 | 2011-10-04 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2012-06-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2011-01-04 00:00:00.0000000 +00:00 | 2011-10-04 00:00:00.0000000 +00:00 | 2012-05-04 00:00:00.0000000 +00:00 | 2012-06-28 00:00:00.0000000 +00:00 | 2015-05-27 00:00:00.0000000 +00:00 | 2012-05-15 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2012-05-04 00:00:00.0000000 +00:00 |  |  |  |  | 2012-05-04 00:00:00.0000000 +00:00 | [15 empty] | 2017-11-20 15:10:21.9466702 -05:00
PV209-SEC | Y | [47 empty] | 2017-09-09 15:33:07.0430000 +00:00
PV234CSV1 | Y | 2015-02-02 00:00:00.0000000 +00:00 |  |  | 2018-01-15 00:00:00.0000000 +00:00 | 2019-07-08 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 |  |  | 2016-02-03 00:00:00.0000000 +00:00 | 2017-07-26 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 |  |  | 2016-09-15 00:00:00.0000000 +00:00 | 2018-03-08 00:00:00.0000000 +00:00 | 2015-02-02 00:00:00.0000000 +00:00 | [5 empty] | 2019-07-08 00:00:00.0000000 +00:00
PV235HA3B | Y | 2014-10-10 00:00:00.0000000 +00:00 | 2014-10-29 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-10-10 00:00:00.0000000 +00:00 | 2014-10-29 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-10-10 00:00:00.0000000 +00:00 | 2014-10-29 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | 2014-10-10 00:00:00.0000000 +00:00 | 2014-10-29 00:00:00.0000000 +00:00 | 2015-04-01 00:00:00.0000000 +00:00 | 2015-05-05 00:00:00.0000000 +00:00 |  | 2015-05-29 00:00:00.0000000 +00:00 | 2018-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2015-05-29 00:00:00.0000000 +00:00 |  |  |  |  | 2015-05-29 00:00:00.0000000 +00:00 | [15 empty] | 2017-11-20 15:10:44.3664047 -05:00
PV235HAL3 | Y | 2013-02-08 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2013-06-27 00:00:00.0000000 +00:00 | 2016-06-29 00:00:00.0000000 +00:00 | 2013-02-08 00:00:00.0000000 +00:00 | 2013-02-27 00:00:00.0000000 +00:00 |  | 2013-06-28 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | [5 empty] | 2013-05-30 00:00:00.0000000 +00:00 | 2013-05-30 00:00:00.0000000 +00:00 |  |  |  | 2013-05-30 00:00:00.0000000 +00:00
PV236SGD1 | Y | 2013-01-24 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2013-05-10 00:00:00.0000000 +00:00 | 2013-06-12 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2013-01-24 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2016-06-30 00:00:00.0000000 +00:00 | 2013-01-24 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2013-06-28 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2013-01-24 00:00:00.0000000 +00:00 | 2013-02-11 00:00:00.0000000 +00:00 |  | 2013-06-12 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | 2013-05-31 00:00:00.0000000 +00:00 | 2016-03-04 00:00:00.0000000 +00:00 | [5 empty] | 2013-05-10 00:00:00.0000000 +00:00 | 2013-05-10 00:00:00.0000000 +00:00 |  |  |  | 2013-05-10 00:00:00.0000000 +00:00
PV236SGD2 | Y | 2014-12-22 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-06-04 00:00:00.0000000 +00:00 | 2015-07-06 00:00:00.0000000 +00:00 | 2017-07-05 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-05-29 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2015-08-01 00:00:00.0000000 +00:00 | 2018-07-31 00:00:00.0000000 +00:00 | 2014-12-22 00:00:00.0000000 +00:00 | 2015-01-05 00:00:00.0000000 +00:00 |  | 2015-06-19 00:00:00.0000000 +00:00 | 2017-07-05 00:00:00.0000000 +00:00 | 2015-06-30 00:00:00.0000000 +00:00 | 2018-06-29 00:00:00.0000000 +00:00 | [5 empty] | 2015-06-04 00:00:00.0000000 +00:00 | 2015-06-04 00:00:00.0000000 +00:00 |  |  |  | 2015-06-04 00:00:00.0000000 +00:00 | [15 empty] | 2017-11-20 15:14:29.7585162 -05:00
PV236SGD3 | Y
PV241EXTR | Y | 2016-11-17 00:00:00.0000000 +00:00 | 2018-02-01 00:00:00.0000000 +00:00 | 2019-02-01 00:00:00.0000000 +00:00 | 2019-10-01 00:00:00.0000000 +00:00 | 2020-12-31 00:00:00.0000000 +00:00 | 2016-10-26 00:00:00.0000000 +00:00 | 2018-02-01 00:00:00.0000000 +00:00 | 2019-02-01 00:00:00.0000000 +00:00 | 2019-10-01 00:00:00.0000000 +00:00 | 2020-12-31 00:00:00.0000000 +00:00 | [5 empty] | 2016-11-17 00:00:00.0000000 +00:00 |  |  |  |  | 2019-02-01 00:00:00.0000000 +00:00 | 2020-12-31 00:00:00.0000000 +00:00 | 2016-11-17 00:00:00.0000000 +00:00 |  | 2018-02-01 00:00:00.0000000 +00:00 | [11 empty] | 2019-02-01 00:00:00.0000000 +00:00 |  | 2019-10-01 00:00:00.0000000 +00:00 |  | 2020-12-31 00:00:00.0000000 +00:00 |  | 2022-12-30 00:00:00.0000000 +00:00 | 2022-12-30 00:00:00.0000000 +00:00 |  | 2022-12-30 00:00:00.0000000 +00:00 |  |  | 2017-08-25 12:05:36.4959718 -04:00
PV241MOD3 | Y | 2012-07-12 00:00:00.0000000 +00:00 |  | 2012-10-05 00:00:00.0000000 +00:00 | 2013-06-04 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | 2012-07-12 00:00:00.0000000 +00:00 |  | 2012-10-05 00:00:00.0000000 +00:00 | 2013-05-04 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2012-07-12 00:00:00.0000000 +00:00 |  | 2012-10-05 00:00:00.0000000 +00:00 | 2013-05-04 00:00:00.0000000 +00:00 | 2016-02-29 00:00:00.0000000 +00:00 | 2012-07-12 00:00:00.0000000 +00:00 |  | 2012-10-05 00:00:00.0000000 +00:00 | 2013-06-04 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | 2012-10-05 00:00:00.0000000 +00:00 | 2016-03-31 00:00:00.0000000 +00:00 | [21 empty] | 2017-12-29 00:00:00.0000000 +00:00 |  |  |  |  | 2017-09-01 13:01:14.5814235 -04:00
PV256-FRI | Y | 2010-10-07 00:00:00.0000000 +00:00 | 2011-06-13 00:00:00.0000000 +00:00 | 2012-12-10 00:00:00.0000000 +00:00 | 2013-07-05 00:00:00.0000000 +00:00 | 2013-10-07 00:00:00.0000000 +00:00 | 2010-10-07 00:00:00.0000000 +00:00 | 2011-06-13 00:00:00.0000000 +00:00 | 2012-06-13 00:00:00.0000000 +00:00 | 2012-12-19 00:00:00.0000000 +00:00 | 2014-01-31 00:00:00.0000000 +00:00 | 2010-10-07 00:00:00.0000000 +00:00 | 2011-06-13 00:00:00.0000000 +00:00 | 2012-12-10 00:00:00.0000000 +00:00 | 2013-07-21 00:00:00.0000000 +00:00 | 2014-09-02 00:00:00.0000000 +00:00 | 2010-10-07 00:00:00.0000000 +00:00 | 2011-06-13 00:00:00.0000000 +00:00 | 2012-12-10 00:00:00.0000000 +00:00 | 2013-07-05 00:00:00.0000000 +00:00 | 2013-10-07 00:00:00.0000000 +00:00 | 2012-12-10 00:00:00.0000000 +00:00 | 2014-02-15 00:00:00.0000000 +00:00 | [21 empty] | 2014-12-15 00:00:00.0000000 +00:00 | 2014-12-15 00:00:00.0000000 +00:00 |  |  |  | 2017-09-01 13:01:53.3400935 -04:00
PV262-AUD | Y | 2013-08-19 00:00:00.0000000 +00:00 | 2015-01-14 00:00:00.0000000 +00:00 | 2017-11-15 00:00:00.0000000 +00:00 | 2018-08-17 00:00:00.0000000 +00:00 | 2020-02-14 00:00:00.0000000 +00:00 | 2013-08-19 00:00:00.0000000 +00:00 | 2014-04-17 00:00:00.0000000 +00:00 | 2015-07-12 00:00:00.0000000 +00:00 | 2016-02-08 00:00:00.0000000 +00:00 | 2017-08-02 00:00:00.0000000 +00:00 | 2013-08-19 00:00:00.0000000 +00:00 | 2014-07-19 00:00:00.0000000 +00:00 | 2015-10-13 00:00:00.0000000 +00:00 | 2016-08-14 00:00:00.0000000 +00:00 | 2018-02-06 00:00:00.0000000 +00:00 | 2013-08-19 00:00:00.0000000 +00:00 | 2015-01-14 00:00:00.0000000 +00:00 | 2017-11-17 00:00:00.0000000 +00:00 |  |  | 2017-11-17 00:00:00.0000000 +00:00 |  | 2013-08-19 00:00:00.0000000 +00:00 |  | 2015-01-14 00:00:00.0000000 +00:00 |  | 2014-08-15 00:00:00.0000000 +00:00 | 2015-05-15 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 | 2015-04-27 00:00:00.0000000 +00:00 |  | 2015-02-19 00:00:00.0000000 +00:00 | 2015-08-18 00:00:00.0000000 +00:00 | 2015-07-09 00:00:00.0000000 +00:00 | 2015-07-09 00:00:00.0000000 +00:00 |  | 2017-11-15 00:00:00.0000000 +00:00 |  | 2018-08-17 00:00:00.0000000 +00:00 |  | 2020-02-14 00:00:00.0000000 +00:00 |  | 2019-08-02 00:00:00.0000000 +00:00 | 2022-02-14 00:00:00.0000000 +00:00 |  | 2022-02-14 00:00:00.0000000 +00:00 |  |  | 2017-12-04 11:01:44.6986215 -05:00
PV262-RT | Y | 2009-04-07 00:00:00.0000000 +00:00 | 2009-12-15 00:00:00.0000000 +00:00 | 2012-05-10 00:00:00.0000000 +00:00 | 2013-02-25 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2009-04-07 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2011-05-12 00:00:00.0000000 +00:00 | 2011-12-10 00:00:00.0000000 +00:00 | 2013-03-05 00:00:00.0000000 +00:00 | 2009-04-07 00:00:00.0000000 +00:00 | 2009-12-17 00:00:00.0000000 +00:00 | 2012-07-15 00:00:00.0000000 +00:00 | 2013-05-20 00:00:00.0000000 +00:00 | 2015-09-22 00:00:00.0000000 +00:00 | 2009-04-07 00:00:00.0000000 +00:00 | 2009-12-15 00:00:00.0000000 +00:00 | 2012-05-10 00:00:00.0000000 +00:00 | 2013-02-25 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2012-05-10 00:00:00.0000000 +00:00 | 2015-12-31 00:00:00.0000000 +00:00 | 2009-04-07 00:00:00.0000000 +00:00 |  | 2009-12-15 00:00:00.0000000 +00:00 | [11 empty] | 2012-05-10 00:00:00.0000000 +00:00 |  | 2013-02-25 00:00:00.0000000 +00:00 |  | 2015-12-31 00:00:00.0000000 +00:00 |  | 2015-03-05 00:00:00.0000000 +00:00 | 2017-12-18 00:00:00.0000000 +00:00 |  | 2017-12-18 00:00:00.0000000 +00:00 |  |  | 2017-09-07 16:40:02.3497865 -04:00
PV262-RTW | Y | 2017-07-11 00:00:00.0000000 +00:00 | 2018-01-11 00:00:00.0000000 +00:00 | 2019-02-21 00:00:00.0000000 +00:00 | 2020-02-24 00:00:00.0000000 +00:00 | 2021-08-27 00:00:00.0000000 +00:00 | 2017-07-11 00:00:00.0000000 +00:00 | 2018-01-11 00:00:00.0000000 +00:00 | 2019-02-21 00:00:00.0000000 +00:00 | 2020-02-24 00:00:00.0000000 +00:00 | 2021-08-27 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-11 00:00:00.0000000 +00:00 | [6 empty] | 2017-07-11 00:00:00.0000000 +00:00 |  | 2018-01-11 00:00:00.0000000 +00:00 | [11 empty] | 2019-02-21 00:00:00.0000000 +00:00 |  | 2020-02-24 00:00:00.0000000 +00:00 |  | 2021-08-27 00:00:00.0000000 +00:00 |  | 2023-08-27 00:00:00.0000000 +00:00 | 2023-08-27 00:00:00.0000000 +00:00 |  | 2023-08-27 00:00:00.0000000 +00:00 |  |  | 2017-08-25 12:06:15.0373008 -04:00
PV263MOH4 | Y | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-09-03 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-09-03 00:00:00.0000000 +00:00 | 2018-10-02 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-09-03 00:00:00.0000000 +00:00 | 2018-10-02 00:00:00.0000000 +00:00 | 2015-02-06 12:00:00.0000000 +00:00 | 2015-02-13 12:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-09-03 12:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2015-05-06 00:00:00.0000000 +00:00 | 2015-02-06 00:00:00.0000000 +00:00 |  | 2015-02-13 00:00:00.0000000 +00:00 |  | 2015-08-31 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 |  | 2015-08-31 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 | 2015-08-31 00:00:00.0000000 +00:00 |  | 2015-08-31 00:00:00.0000000 +00:00 |  | 2015-09-03 00:00:00.0000000 +00:00 |  | 2016-11-22 00:00:00.0000000 +00:00 |  | 2020-10-01 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00 | 2016-11-22 00:00:00.0000000 +00:00
PV266-EXT | Y | 2015-03-03 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2019-01-14 00:00:00.0000000 +00:00 | 2021-05-11 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2016-12-07 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2018-12-03 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2015-12-07 00:00:00.0000000 +00:00 | 2016-12-07 00:00:00.0000000 +00:00 | 2017-06-01 00:00:00.0000000 +00:00 | 2018-12-03 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 | 2016-02-23 17:00:00.0000000 +00:00 |  |  |  | 2018-04-30 00:00:00.0000000 +00:00 | 2021-05-11 00:00:00.0000000 +00:00 | 2015-03-03 00:00:00.0000000 +00:00 |  | 2016-02-23 00:00:00.0000000 +00:00 |  | 2016-06-01 00:00:00.0000000 +00:00 | 2016-06-01 00:00:00.0000000 +00:00 | 2016-06-02 00:00:00.0000000 +00:00 | 2016-06-02 00:00:00.0000000 +00:00 |  | 2016-09-30 00:00:00.0000000 +00:00 | 2016-09-30 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 | 2016-10-14 00:00:00.0000000 +00:00 |  | 2018-01-12 00:00:00.0000000 +00:00 |  | 2019-01-14 00:00:00.0000000 +00:00 |  | 2021-05-11 00:00:00.0000000 +00:00 |  | 2020-12-03 00:00:00.0000000 +00:00 | 2023-05-11 00:00:00.0000000 +00:00 |  | 2023-05-11 00:00:00.0000000 +00:00
PV272BMS | Y | 2011-08-18 00:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2013-11-14 00:00:00.0000000 +00:00 | 2015-09-16 00:00:00.0000000 +00:00 | 2017-05-04 00:00:00.0000000 +00:00 | 2011-08-18 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2013-08-15 00:00:00.0000000 +00:00 | 2014-02-17 00:00:00.0000000 +00:00 | 2015-02-13 00:00:00.0000000 +00:00 | 2011-08-18 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2013-10-13 00:00:00.0000000 +00:00 | 2015-11-14 00:00:00.0000000 +00:00 | 2016-11-09 00:00:00.0000000 +00:00 | 2011-08-18 00:00:00.0000000 +00:00 | 2012-09-17 00:00:00.0000000 +00:00 | 2013-11-14 00:00:00.0000000 +00:00 | 2015-10-13 17:00:00.0000000 +00:00 | 2017-05-03 17:00:00.0000000 +00:00 | 2013-09-17 00:00:00.0000000 +00:00 | 2016-06-11 00:00:00.0000000 +00:00 | [20 empty] | 2017-02-12 00:00:00.0000000 +00:00 | 2018-11-19 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-25 11:39:57.8867644 -04:00
PV272PATH | Y | 2009-12-01 00:00:00.0000000 +00:00 | 2010-12-06 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2014-02-03 00:00:00.0000000 +00:00 | 2015-09-10 00:00:00.0000000 +00:00 | 2009-12-01 00:00:00.0000000 +00:00 | 2010-06-01 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2011-12-01 00:00:00.0000000 +00:00 | 2013-04-01 00:00:00.0000000 +00:00 | 2009-12-01 00:00:00.0000000 +00:00 | 2010-12-06 00:00:00.0000000 +00:00 | 2013-05-19 00:00:00.0000000 +00:00 | 2014-06-23 00:00:00.0000000 +00:00 | 2016-10-10 00:00:00.0000000 +00:00 | 2009-12-01 00:00:00.0000000 +00:00 | 2010-12-06 00:00:00.0000000 +00:00 | 2013-04-24 00:00:00.0000000 +00:00 | 2014-02-03 00:00:00.0000000 +00:00 | 2015-09-10 00:00:00.0000000 +00:00 | 2013-05-19 00:00:00.0000000 +00:00 | 2016-02-02 00:00:00.0000000 +00:00 | [21 empty] | 2017-10-23 00:00:00.0000000 +00:00 | 2017-10-23 00:00:00.0000000 +00:00 |  |  |  | 2017-10-30 13:34:29.4337478 -04:00
PV272SIDE | Y | 2012-01-04 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2016-04-04 00:00:00.0000000 +00:00 | 2016-09-04 00:00:00.0000000 +00:00 | 2012-01-04 00:00:00.0000000 +00:00 | 2012-06-22 00:00:00.0000000 +00:00 | 2013-02-28 00:00:00.0000000 +00:00 | 2013-07-24 00:00:00.0000000 +00:00 | 2014-03-21 00:00:00.0000000 +00:00 | 2012-01-04 00:00:00.0000000 +00:00 | 2012-08-30 00:00:00.0000000 +00:00 | 2014-09-30 00:00:00.0000000 +00:00 | 2016-03-19 00:00:00.0000000 +00:00 | 2017-02-08 00:00:00.0000000 +00:00 | 2012-01-04 00:00:00.0000000 +00:00 | 2012-08-15 00:00:00.0000000 +00:00 | 2014-03-14 00:00:00.0000000 +00:00 | 2015-05-20 00:00:00.0000000 +00:00 | 2015-09-17 00:00:00.0000000 +00:00 | 2015-12-08 00:00:00.0000000 +00:00 | 2016-11-29 00:00:00.0000000 +00:00 | [21 empty] | 2017-09-01 00:00:00.0000000 +00:00 | 2016-11-18 00:00:00.0000000 +00:00 |  |  |  | 2017-08-21 15:34:07.1100826 +00:00
PV272SITE | Y | 2016-02-24 00:00:00.0000000 +00:00 | 2016-03-15 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2018-10-15 00:00:00.0000000 +00:00 | 2016-02-24 00:00:00.0000000 +00:00 | 2016-03-15 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 | 2017-10-16 00:00:00.0000000 +00:00 | 2018-10-15 00:00:00.0000000 +00:00 | [5 empty] | 2016-02-24 00:00:00.0000000 +00:00 | 2016-03-15 00:00:00.0000000 +00:00 | 2016-09-15 00:00:00.0000000 +00:00 |  |  | 2016-09-15 00:00:00.0000000 +00:00 | 2018-10-15 00:00:00.0000000 +00:00 | [21 empty] | 2019-12-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-25 12:06:43.6797602 -04:00
PV274-AHU | Y | 2007-11-06 00:00:00.0000000 +00:00 | 2009-06-02 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2012-06-05 00:00:00.0000000 +00:00 | 2015-05-18 00:00:00.0000000 +00:00 | 2007-11-06 00:00:00.0000000 +00:00 | 2009-06-02 00:00:00.0000000 +00:00 | 2010-11-30 00:00:00.0000000 +00:00 | 2011-05-30 00:00:00.0000000 +00:00 | 2012-05-30 00:00:00.0000000 +00:00 | 2007-11-06 00:00:00.0000000 +00:00 | 2009-06-02 00:00:00.0000000 +00:00 | 2011-07-01 00:00:00.0000000 +00:00 | 2012-07-30 00:00:00.0000000 +00:00 | 2015-06-10 00:00:00.0000000 +00:00 | 2007-11-06 00:00:00.0000000 +00:00 | 2009-06-02 00:00:00.0000000 +00:00 | 2011-06-27 00:00:00.0000000 +00:00 | 2012-06-05 00:00:00.0000000 +00:00 | 2015-05-18 00:00:00.0000000 +00:00 | 2011-07-01 00:00:00.0000000 +00:00 | 2015-08-07 00:00:00.0000000 +00:00 | [21 empty] | 2017-12-31 00:00:00.0000000 +00:00
PV274CHLL | Y | 2017-04-20 00:00:00.0000000 +00:00 | 2018-02-13 00:00:00.0000000 +00:00 | 2019-05-03 00:00:00.0000000 +00:00 | 2019-12-27 00:00:00.0000000 +00:00 | 2021-06-28 00:00:00.0000000 +00:00 | 2017-04-20 00:00:00.0000000 +00:00 | 2017-11-13 00:00:00.0000000 +00:00 | 2019-01-31 00:00:00.0000000 +00:00 | 2019-11-26 00:00:00.0000000 +00:00 | 2021-05-26 00:00:00.0000000 +00:00 | [5 empty] | 2017-04-20 00:00:00.0000000 +00:00 | [26 empty] | 2022-09-26 00:00:00.0000000 +00:00 | 2022-09-30 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-03 12:05:01.3454794 -04:00
PV274EXLT | Y | 2008-06-30 00:00:00.0000000 +00:00 | 2010-04-06 00:00:00.0000000 +00:00 | 2015-05-21 00:00:00.0000000 +00:00 | 2018-04-30 00:00:00.0000000 +00:00 | 2019-07-31 00:00:00.0000000 +00:00 | 2008-06-30 00:00:00.0000000 +00:00 | 2009-04-06 00:00:00.0000000 +00:00 | 2010-12-20 00:00:00.0000000 +00:00 | 2011-07-02 00:00:00.0000000 +00:00 | 2012-07-02 00:00:00.0000000 +00:00 | 2008-06-30 00:00:00.0000000 +00:00 | 2010-04-06 00:00:00.0000000 +00:00 | 2015-08-20 00:00:00.0000000 +00:00 | 2016-07-29 00:00:00.0000000 +00:00 | 2017-07-30 00:00:00.0000000 +00:00 | 2008-06-30 00:00:00.0000000 +00:00 | 2010-04-06 00:00:00.0000000 +00:00 | 2015-05-21 00:00:00.0000000 +00:00 | [24 empty] | 2014-07-02 00:00:00.0000000 +00:00 | 2020-10-30 00:00:00.0000000 +00:00 |  |  |  |  | 2017-10-30 13:35:00.2741687 -04:00
PV274GHIN | Y | 2007-10-16 00:00:00.0000000 +00:00 | 2008-08-27 00:00:00.0000000 +00:00 | 2010-07-30 00:00:00.0000000 +00:00 | 2012-08-09 00:00:00.0000000 +00:00 | 2015-11-30 00:00:00.0000000 +00:00 | 2007-10-16 00:00:00.0000000 +00:00 | 2008-08-27 00:00:00.0000000 +00:00 | 2009-10-21 00:00:00.0000000 +00:00 | 2010-04-20 00:00:00.0000000 +00:00 | 2014-08-09 00:00:00.0000000 +00:00 | 2007-10-16 00:00:00.0000000 +00:00 | 2008-08-27 00:00:00.0000000 +00:00 | 2010-07-30 00:00:00.0000000 +00:00 | 2012-03-27 00:00:00.0000000 +00:00 | 2015-09-28 00:00:00.0000000 +00:00 | 2007-10-16 00:00:00.0000000 +00:00 | 2008-08-27 00:00:00.0000000 +00:00 | 2010-07-30 00:00:00.0000000 +00:00 | 2012-08-09 00:00:00.0000000 +00:00 | 2016-02-11 00:00:00.0000000 +00:00 | 2010-07-30 00:00:00.0000000 +00:00 | 2016-02-07 00:00:00.0000000 +00:00 | [21 empty] | 2018-12-31 00:00:00.0000000 +00:00
PV274KITR | Y | 2016-07-07 00:00:00.0000000 +00:00 | 2016-07-07 00:00:00.0000000 +00:00 | 2018-01-31 00:00:00.0000000 +00:00 | 2018-08-31 00:00:00.0000000 +00:00 | 2020-01-31 00:00:00.0000000 +00:00 | 2016-07-07 00:00:00.0000000 +00:00 | 2016-07-07 00:00:00.0000000 +00:00 | 2017-02-28 00:00:00.0000000 +00:00 | 2017-07-07 00:00:00.0000000 +00:00 | 2017-12-29 00:00:00.0000000 +00:00 | [5 empty] | 2016-07-07 20:00:00.0000000 +00:00 | 2016-07-07 20:00:00.0000000 +00:00 |  |  |  | 2017-11-01 00:00:00.0000000 +00:00 | 2019-10-16 00:00:00.0000000 +00:00 | [20 empty] | 2021-03-28 00:00:00.0000000 +00:00 | 2021-03-15 00:00:00.0000000 +00:00 |  |  |  |  | 2017-08-25 12:07:31.9875813 -04:00
PV289ADAC | Y | 2015-06-29 00:00:00.0000000 +00:00 | 2015-07-29 00:00:00.0000000 +00:00 | 2015-10-28 00:00:00.0000000 +00:00 | 2016-05-27 00:00:00.0000000 +00:00 | 2019-05-27 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2015-07-29 00:00:00.0000000 +00:00 | 2015-10-28 00:00:00.0000000 +00:00 | 2016-05-27 00:00:00.0000000 +00:00 | 2019-05-27 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2015-07-29 00:00:00.0000000 +00:00 | 2015-10-28 00:00:00.0000000 +00:00 | 2016-05-27 00:00:00.0000000 +00:00 | 2019-05-27 00:00:00.0000000 +00:00 | 2015-06-29 00:00:00.0000000 +00:00 | 2015-07-29 00:00:00.0000000 +00:00 |  | 2016-02-26 00:00:00.0000000 +00:00 |  |  | 2019-05-27 00:00:00.0000000 +00:00 | [5 empty] | 2015-10-28 00:00:00.0000000 +00:00 | 2015-10-28 00:00:00.0000000 +00:00 |  |  |  | 2015-10-28 00:00:00.0000000 +00:00
PV289-DSN | Y | 2006-09-01 00:00:00.0000000 +00:00 | 2007-04-27 00:00:00.0000000 +00:00 | 2009-10-30 00:00:00.0000000 +00:00 |  |  | 2006-09-01 00:00:00.0000000 +00:00 | 2007-04-27 00:00:00.0000000 +00:00 | 2008-10-01 00:00:00.0000000 +00:00 | 2008-07-31 00:00:00.0000000 +00:00 | 2010-01-23 00:00:00.0000000 +00:00 | 2006-09-01 00:00:00.0000000 +00:00 | 2007-04-27 00:00:00.0000000 +00:00 | 2009-10-30 00:00:00.0000000 +00:00 | 2010-08-29 00:00:00.0000000 +00:00 | 2012-02-21 00:00:00.0000000 +00:00 | 2006-09-01 00:00:00.0000000 +00:00 | 2007-04-27 00:00:00.0000000 +00:00 | 2009-10-30 00:00:00.0000000 +00:00 |  |  | 2009-10-30 00:00:00.0000000 +00:00 | 2010-01-23 00:00:00.0000000 +00:00 | [5 empty] | 2009-10-30 00:00:00.0000000 +00:00 |  |  |  |  | 2009-10-30 00:00:00.0000000 +00:00 | [15 empty] | 2017-12-07 13:53:36.8397188 -05:00
PV289ELEV | Y | [47 empty] | 2017-10-02 13:00:19.6670000 +00:00 | 2017-10-04 15:53:43.0912305 -04:00
PV291-QM2 | Y | [48 empty] | 2017-11-03 12:05:29.4633055 -04:00
PV291QMX2 | Y | 2005-02-17 00:00:00.0000000 +00:00 | 2005-07-20 00:00:00.0000000 +00:00 | 2007-11-30 00:00:00.0000000 +00:00 | 2009-07-27 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 | 2005-02-17 00:00:00.0000000 +00:00 | 2005-07-20 00:00:00.0000000 +00:00 | 2006-12-28 00:00:00.0000000 +00:00 | 2007-04-11 00:00:00.0000000 +00:00 | 2008-12-17 00:00:00.0000000 +00:00 | 2005-02-17 00:00:00.0000000 +00:00 | 2005-07-20 00:00:00.0000000 +00:00 | 2007-03-25 00:00:00.0000000 +00:00 | 2008-10-03 00:00:00.0000000 +00:00 | 2012-09-14 00:00:00.0000000 +00:00 | 2005-02-17 00:00:00.0000000 +00:00 | 2005-07-20 00:00:00.0000000 +00:00 | 2007-11-30 00:00:00.0000000 +00:00 | 2009-07-27 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 | 2007-11-30 00:00:00.0000000 +00:00 | 2013-10-31 00:00:00.0000000 +00:00 | [21 empty] | 2018-12-31 00:00:00.0000000 +00:00
PV302-AB | Y | 2005-04-29 00:00:00.0000000 +00:00 | 2006-01-09 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2005-04-29 00:00:00.0000000 +00:00 | 2006-01-09 00:00:00.0000000 +00:00 | 2007-07-13 00:00:00.0000000 +00:00 | 2007-11-02 00:00:00.0000000 +00:00 | 2009-09-24 00:00:00.0000000 +00:00 | 2005-04-29 00:00:00.0000000 +00:00 | 2006-01-09 00:00:00.0000000 +00:00 | 2010-06-29 00:00:00.0000000 +00:00 | 2010-10-19 00:00:00.0000000 +00:00 | 2014-04-09 00:00:00.0000000 +00:00 | 2005-04-29 00:00:00.0000000 +00:00 | 2006-01-09 00:00:00.0000000 +00:00 | 2010-06-24 00:00:00.0000000 +00:00 | 2011-06-01 00:00:00.0000000 +00:00 | 2015-06-25 00:00:00.0000000 +00:00 | 2010-06-26 00:00:00.0000000 +00:00 | 2015-06-18 00:00:00.0000000 +00:00 | [21 empty] | 2020-03-20 00:00:00.0000000 +00:00
PV302BPH1 | Y | 2017-07-18 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-03-15 00:00:00.0000000 +00:00 | 2019-12-01 00:00:00.0000000 +00:00 | 2021-10-03 00:00:00.0000000 +00:00 | 2017-07-18 00:00:00.0000000 +00:00 | 2018-03-15 00:00:00.0000000 +00:00 | 2019-03-15 00:00:00.0000000 +00:00 | 2019-12-01 00:00:00.0000000 +00:00 | 2021-10-03 00:00:00.0000000 +00:00 | [5 empty] | 2017-07-18 00:00:00.0000000 +00:00 | [26 empty] | 2023-04-03 00:00:00.0000000 +00:00 | 2023-04-03 00:00:00.0000000 +00:00 |  |  |  |  | 2017-11-03 12:05:47.7238991 -04:00

## Budget
MANAGING_AGCY_CD | SHORT_DESCR | ClntAgcyCode | AgcyName | project_id | OCCURRENCE_ID | pobject | phasetype | PlannedAmt | CommittedAmt | LiquidatedAmt | AvailableAmt | DataAsOF
850 | DSNY - LIGHTING DEBUNDLING PROJECTS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ACEDOS501 | 001 | CONS | CAP | 1323000 | 1164680 | 1141409 | 158320 | 12/15/2017
850 | DSNY - LIGHTING DEBUNDLING PROJECTS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ACEDOS501 | 100 | IFDS | IFA | 130000 | 129999 | 76258 | 1 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 003 | DSGN | CAP | 70000 | 70000 | 70000 | 0 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 036 | CONS | CAP | -361000 | 0 | 0 | -361000 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 063 | EQFN | CAP | 1925000 | 0 | 0 | 1925000 | 12/15/2017
850 | CONGREGATE CARE FACILITIES | 096 | HUMAN RESOURCES ADMINISTRATION | ACSCCF | 001 | DSGN | CAP | 55000 | 42666 | 42666 | 12334 | 12/15/2017
850 | CONGREGATE CARE FACILITIES | 096 | HUMAN RESOURCES ADMINISTRATION | ACSCCF | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BETANCES KITCHEN & ANSUL SUPP(VAR SITES) | 125 | DEPARTMENT FOR THE AGING | AG1BKE | 014 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 020 | CONS | CAP | 54000 | 0 | 0 | 54000 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 012 | CONS | CAP | 16000 | 0 | 0 | 16000 | 12/15/2017
850 | SIROVICH FIRE CODE COMPLIANCE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR2 | 005 | IFSP | IFA | 104000 | 104000 | 104000 | 0 | 12/15/2017
850 | SIROVICH-INT WATER DAMAGE REPAIR AND RENOVATIONS | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4 | 004 | CONS | CAP | 13000 | 44460 | 44460 | -31460 | 12/15/2017
850 | SIROVICH BUILDING SUPERINTENDENT'S APARTMENT | 125 | DEPARTMENT FOR THE AGING | AG1SIRRSU | 006 | CTGY | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SIROVICH ROOF TERRACE | 125 | DEPARTMENT FOR THE AGING | AG1SIRRTE | 005 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 109 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | HOPE GARDENS/ADA (FRONT DOOR) | 125 | DEPARTMENT FOR THE AGING | AGC001HGM | 003 | IFSP | IFA | 1000 | 565 | 565 | 435 | 12/15/2017
850 | KINGSBAY SENIOR CENTER, BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | AGC001KBC | 017 | DSGN | CAP | 5000 | 5072 | 5072 | -72 | 12/15/2017
850 | Equipment for Providence Rest | 125 | DEPARTMENT FOR THE AGING | AGDPROVI | 001 | EQVH | CAP | 50000 | 50000 | 50000 | 0 | 12/15/2017
850 | NYCHANGE PROJECT WITH DFTA | 125 | DEPARTMENT FOR THE AGING | AGNYCHANG | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | NYCHANGE PROJECT WITH DFTA | 125 | DEPARTMENT FOR THE AGING | AGNYCHANG | 200 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | TODT HILL SENIOR CENTER - A/C SYSTEMS | 125 | DEPARTMENT FOR THE AGING | AGR001TAC | 010 | CONS | CAP | 56000 | 0 | 0 | 56000 | 12/15/2017
850 | TODT HILL SENIOR CENTER - A/C SYSTEMS | 125 | DEPARTMENT FOR THE AGING | AGR001TAC | 013 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | TODT HILL SENIOR CENTER - A/C SYSTEMS | 125 | DEPARTMENT FOR THE AGING | AGR001TAC | 022 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | JASA BRONX GROUP SERVICES | 125 | DEPARTMENT FOR THE AGING | AGX001LC | 018 | CTGY | CAP | 17000 | 0 | 0 | 17000 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 010 | CONS | CAP | 12000000 | 11999999 | 11869268 | 1 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 013 | CONS | CAP | 34000 | 27250 | 27250 | 6750 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY08-09 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10UU | 007 | SVCS | CAP | 380000 | 380469 | 380469 | -469 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 021 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | Standard boring contract sewer and watermain | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-SE-WM1 | 001 | SVCS | CAP | 1000000 | 1000000 | 950000 | 0 | 12/15/2017
850 | REPLACE 6 IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-744 | 002 | IFSP | IFA | 296000 | 295776 | 295776 | 224 | 12/15/2017
850 | ABANDON HP SYSTEM | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-752 | 003 | CONS | CAP | 1467000 | 0 | 0 | 1467000 | 12/15/2017
850 | Betts Boilers Replacement | 827 | DEPARTMENT OF SANITATION | ACEDOS503 | 003 | IFDS | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 031 | DSGN | CAP | 459000 | 458985 | 458985 | 15 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 057 | EQFN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | Interior and rear courtyard renovations | 125 | DEPARTMENT FOR THE AGING | AG-1LEON | 007 | SVCS | CAP | 13000 | 102814 | 102814 | -89814 | 12/15/2017
850 | LIRA MOTT SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AG-1LIMOT | 008 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SCSC-SUNYSIDE COMMUNITY SENIOR CENTER | 125 | DEPARTMENT FOR THE AGING | AG-QSUNY | 005 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BETANCES KITCHEN & ANSUL SUPP(VAR SITES) | 125 | DEPARTMENT FOR THE AGING | AG1BKE | 007 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 004 | CONS | CAP | 2750000 | 2749999 | 2747335 | 1 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 003 | DSGN | CAP | 12000 | 0 | 0 | 12000 | 12/15/2017
850 | SIROVICH FIRE CODE COMPLIANCE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR2 | 011 | CTGY | CAP | 150000 | 0 | 0 | 150000 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 110 | EQFN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | NEW CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-QUEEN | 009 | DSGN | CAP | 1000 | 111640 | 111640 | -110640 | 12/15/2017
850 | KINGSBAY SENIOR CENTER, BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | AGC001KBC | 014 | DSGN | CAP | 5000 | 123578 | 123578 | -118578 | 12/15/2017
850 | VANDALIA SR CTR/HVAC | 125 | DEPARTMENT FOR THE AGING | AGC001VCR | 002 | DSGN | CAP | 10000 | 0 | 0 | 10000 | 12/15/2017
850 | VANDALIA SR CTR/HVAC | 125 | DEPARTMENT FOR THE AGING | AGC001VCR | 007 | CONS | CAP | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 004 | SVCS | CAP | 99000 | 983433 | 877673 | -884433 | 12/15/2017
850 | NYCHANGE PROJECT WITH DFTA | 125 | DEPARTMENT FOR THE AGING | AGNYCHANG | 011 | CONS | CAP | 1692000 | 0 | 0 | 1692000 | 12/15/2017
850 | TODT HILL SENIOR CENTER - A/C SYSTEMS | 125 | DEPARTMENT FOR THE AGING | AGR001TAC | 026 | IFSP | IFA | 20000 | 9627 | 9627 | 10373 | 12/15/2017
850 | JASA BRONX GROUP SERVICES | 125 | DEPARTMENT FOR THE AGING | AGX001LC | 016 | CONS | CAP | 18000 | 0 | 0 | 18000 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 017 | IFSP | IFA | 350000 | 168259 | 168259 | 181741 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY05-6 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10PP | 002 | CTGY | CAP | 3600000 | 457415 | 457415 | 3142585 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 005 | SVCS | CAP | 200000 | 197203 | 197203 | 2797 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 011 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 018 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10XX | 005 | SVCS | CAP | 600000 | 600000 | 570000 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10XX | 014 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACE 6-IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-745 | 002 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | OCEAN PKWY BRDG OVER LIRR | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-748 | 004 | CONS | CAP | 555000 | 0 | 0 | 555000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 009 | CONS | CAP | 669000 | 0 | 0 | 669000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 019 | CTGY | CAP | 500000 | 0 | 0 | 500000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 020 | CTGY | CAP | 2000000 | 0 | 0 | 2000000 | 12/15/2017
850 | DCLA MMA - Air Handler Replacements: WHVAC-2, 3, 4, & 5 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ACEDCA437 | 001 | CONS | CAP | 1164000 | 1164263 | 1106050 | -263 | 12/15/2017
850 | DSNY - LIGHTING DEBUNDLING PROJECTS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ACEDOS501 | 101 | IFSP | IFA | 625000 | 499270 | 499270 | 125730 | 12/15/2017
850 | Betts Boilers Replacement | 827 | DEPARTMENT OF SANITATION | ACEDOS503 | 005 | CONS | CAP | 499000 | 499000 | 0 | 0 | 12/15/2017
850 | SCSC-SUNYSIDE COMMUNITY SENIOR CENTER | 125 | DEPARTMENT FOR THE AGING | AG-QSUNY | 002 | CONS | CAP | 1770000 | 1769999 | 1711699 | 1 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 017 | IFSP | IFA | 119000 | 118783 | 118783 | 217 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 032 | IFSP | IFA | 17000 | 16986 | 16986 | 14 | 12/15/2017
850 | NEW CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-QUEEN | 001 | DSGN | CAP | 68000 | 67467 | 63251 | 533 | 12/15/2017
850 | NEW CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-QUEEN | 006 | DSGN | CAP | 1000 | 52600 | 50220 | -51600 | 12/15/2017
850 | NEW CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-QUEEN | 009 | CONS | CAP | 110000 | 0 | 0 | 110000 | 12/15/2017
850 | NEW DORP SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AGC001NDF | 014 | CONS | CAP | 19000 | 0 | 0 | 19000 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 005 | CONS | CAP | 417000 | 392118 | 285742 | 24882 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 004 | DSGN | CAP | 4000 | 1023813 | 1023813 | -1019813 | 12/15/2017
850 | SCSC-SUNYSIDE COMMUNITY SENIOR CENTER | 126 | DEPARTMENT OF CULTURAL AFFAIRS | AGQSUNY2 | 001 | EQFN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 005 | IFSP | IFA | 600000 | 600000 | 600000 | 0 | 12/15/2017
850 | SEWER CONSTRUCTION | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWC | 003 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACE SEWER | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWR | 003 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY08-09 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10UU | 004 | SVCS | CAP | 500000 | 500000 | 500000 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY08-09 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10UU | 005 | SVCS | CAP | 1000000 | 188379 | 188379 | 811621 | 12/15/2017
850 | REPLACE 6-IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-745 | 004 | CONS | CAP | 1700000 | 0 | 0 | 1700000 | 12/15/2017
850 | REPLACE 6-IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-745 | 005 | CONS | CAP | 10041000 | 0 | 0 | 10041000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 017 | CONS | CAP | 17862000 | 2724688 | 2724688 | 15137312 | 12/15/2017
850 | REPLACE WATER MAIN IN CRESCENT ST, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-762 | 003 | CNSP | CAP | 2187000 | 2186166 | 2047586 | 834 | 12/15/2017
850 | REPLACE WATER MAIN IN CROPSEY AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-763 | 602 | IFSP | IFA | 60000 | 10457 | 10457 | 49543 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768A | 005 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACEMENT OF 8" AND 12" AND 20" DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-771 | 007 | CONS | CAP | 210000 | 0 | 0 | 210000 | 12/15/2017
850 | REPLACEMENT OF 8" AND 12" AND 20" DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-771 | 011 | IFSP | IFA | 245000 | 244255 | 244255 | 745 | 12/15/2017
850 | REPLACEMENT OF 8" AND 12" AND 20" DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-771 | 014 | IFSP | IFA | 376000 | 375775 | 375775 | 225 | 12/15/2017
850 | REPLACEMENT OF DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-772 | 004 | CONS | CAP | 728000 | 399261 | 399261 | 328739 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 013 | CONS | CAP | 134000 | 133904 | 0 | 96 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 016 | CONS | CAP | 126000 | 125362 | 0 | 638 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 011 | CONS | CAP | 233000 | 232674 | 16493 | 326 | 12/15/2017
850 | Interior and rear courtyard renovations | 125 | DEPARTMENT FOR THE AGING | AG-1LEON | 009 | DSGN | CAP | 623000 | 622999 | 622999 | 1 | 12/15/2017
850 | BETANCES KITCHEN & ANSUL SUPP(VAR SITES) | 125 | DEPARTMENT FOR THE AGING | AG1BKE | 001 | DSGN | CAP | 8000 | 0 | 0 | 8000 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 012 | CONS | CAP | 229000 | 229000 | 229000 | 0 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 014 | EQFN | CAP | 7000 | 2534886 | 1954719 | -2527886 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 024 | SVCS | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 106 | CONS | CAP | 527000 | 527000 | 527000 | 0 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 117 | EQFN | CAP | 1000 | 28619 | 18127 | -27619 | 12/15/2017
850 | SIROVICH ROOF TERRACE | 125 | DEPARTMENT FOR THE AGING | AG1SIRRTE | 004 | IFSP | IFA | 12000 | 12000 | 12000 | 0 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 001 | CONS | CAP | 6000 | 0 | 0 | 6000 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 113 | IFSP | IFA | 60000 | 21300 | 21300 | 38700 | 12/15/2017
850 | KINGSBAY SENIOR CENTER, BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | AGC001KBC | 021 | IFSP | IFA | 60000 | 23156 | 23156 | 36844 | 12/15/2017
850 | NEW DORP SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AGC001NDF | 009 | CTGY | CAP | 11000 | 32662 | 32662 | -21662 | 12/15/2017
850 | NEW DORP SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AGC001NDF | 013 | CONS | CAP | 2000 | 0 | 0 | 2000 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 002 | IFSP | IFA | 90000 | 3837 | 3837 | 86163 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 003 | DSGN | CAP | 125000 | 125306 | 125306 | -306 | 12/15/2017
850 | JASA IT upgrade | 125 | DEPARTMENT FOR THE AGING | AGDJASAIT | 001 | EQFN | CAP | 500000 | 500000 | 500000 | 0 | 12/15/2017
850 | Tomche Shabbos Boro Park VH | 125 | DEPARTMENT FOR THE AGING | AGDTOMS | 001 | EQVH | CAP | 35000 | 35000 | 35000 | 0 | 12/15/2017
850 | JASA BRONX GROUP SERVICES | 125 | DEPARTMENT FOR THE AGING | AGX001LC | 007 | SVCS | CAP | 1000 | 0 | 0 | 1000 | 12/15/2017
850 | BORINGS, FY'99 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10JJ | 004 | SVCS | CAP | 240000 | 0 | 0 | 240000 | 12/15/2017
850 | BORING, FY01 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10MM | 004 | SVCS | CAP | 300000 | 300000 | 300000 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10XX | 021 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | OCEAN PKWY BRDG OVER LIRR | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-748 | 002 | CNSP | CAP | 34000 | 0 | 0 | 34000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 008 | IFSP | IFA | 663000 | 662262 | 662262 | 738 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 20B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-765 | 002 | IFDS | IFA | 186000 | 185448 | 185448 | 552 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768B | 005 | CONS | CAP | 1600000 | 0 | 0 | 1600000 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 006 | CONS | CAP | 7354000 | 7333334 | 6498111 | 20666 | 12/15/2017
850 | REPLACEMENT OF 8" AND 12" AND 20" DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-771 | 009 | IFSP | IFA | 690000 | 689865 | 689865 | 135 | 12/15/2017
850 | DISTRIBUTION WATER MAINS IN 4 AV - 80 ST AND 95 ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-774 | 008 | CONS | CAP | 134000 | 99726 | 99726 | 34274 | 12/15/2017
850 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-776 | 007 | DSGN | CAP | 35000 | 34446 | 0 | 554 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 001 | CONS | CAP | 20055000 | 20054443 | 224974 | 557 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 014 | CONS | CAP | 37000 | 36537 | 0 | 463 | 12/15/2017
850 | DCLA: MMA Air Handlier Replacement JHVAC-4 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ACEDCA436 | 002 | IFSP | IFA | 30000 | 30000 | 0 | 0 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 028 | DSGN | CAP | 25000 | 0 | 0 | 25000 | 12/15/2017
850 | SCSC-SUNYSIDE COMMUNITY SENIOR CENTER | 125 | DEPARTMENT FOR THE AGING | AG-QSUNY | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 004 | DSGN | CAP | 23000 | 0 | 0 | 23000 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 005 | DSGN | CAP | 12000 | 0 | 0 | 12000 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 010 | IFSP | IFA | 130000 | 130000 | 130000 | 0 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 027 | CONS | CAP | 30000 | 29786 | 29786 | 214 | 12/15/2017
850 | SIROVICH-INT WATER DAMAGE REPAIR AND RENOVATIONS | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4 | 008 | CONS | CAP | 1150000 | 1150000 | 1150000 | 0 | 12/15/2017
850 | SIROVICH-INT WATER DAMAGE REPAIR AND RENOVATIONS | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4 | 009 | CONS | CAP | 1304000 | 1304000 | 1304000 | 0 | 12/15/2017
850 | SIROVICH STRUCTURAL REINFORCEMENT OF 6TH FLOOR | 125 | DEPARTMENT FOR THE AGING | AG1SIRRST | 003 | SVCS | CAP | 18000 | 0 | 0 | 18000 | 12/15/2017
850 | SIROVICH STRUCTURAL REINFORCEMENT OF 6TH FLOOR | 125 | DEPARTMENT FOR THE AGING | AG1SIRRST | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 100 | CONS | CAP | 718000 | 715402 | 715402 | 2598 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 103 | CONS | CAP | 151000 | 150196 | 150196 | 804 | 12/15/2017
850 | HOPE GARDENS/ADA (FRONT DOOR) | 125 | DEPARTMENT FOR THE AGING | AGC001HGM | 005 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | NEW DORP SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AGC001NDF | 016 | IFSP | IFA | 79000 | 29208 | 29208 | 49792 | 12/15/2017
850 | VANDALIA SR CTR/HVAC | 125 | DEPARTMENT FOR THE AGING | AGC001VCR | 008 | CONS | CAP | 149000 | 0 | 0 | 149000 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 001 | SVCS | CAP | 24000 | 816706 | 741364 | -792706 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 004 | CONS | CAP | 905000 | 0 | 0 | 905000 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 011 | IFSP | IFA | 240000 | 239946 | 239946 | 54 | 12/15/2017
850 | DOROT, INC. | 125 | DEPARTMENT FOR THE AGING | AGDDORT | 101 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | JEWISH HOME AND HOSPITAL FOR THE AGED | 125 | DEPARTMENT FOR THE AGING | AGMHOME | 002 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | NYCHANGE PROJECT WITH DFTA | 125 | DEPARTMENT FOR THE AGING | AGNYCHANG | 013 | CONS | CAP | 600000 | 0 | 0 | 600000 | 12/15/2017
850 | TODT HILL SENIOR CENTER - A/C SYSTEMS | 125 | DEPARTMENT FOR THE AGING | AGR001TAC | 001 | DSGN | CAP | 26000 | 0 | 0 | 26000 | 12/15/2017
850 | TODT HILL SENIOR CENTER - A/C SYSTEMS | 125 | DEPARTMENT FOR THE AGING | AGR001TAC | 007 | SVCS | CAP | 9000 | 0 | 0 | 9000 | 12/15/2017
850 | TODT HILL SENIOR CENTER - A/C SYSTEMS | 125 | DEPARTMENT FOR THE AGING | AGR001TAC | 025 | IFSP | IFA | 27000 | 0 | 0 | 27000 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 001 | CONS | CAP | 5490000 | 5487546 | 5487546 | 2454 | 12/15/2017
850 | BORINGS, FY'99 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10II | 001 | SVCS | CAP | 669000 | 0 | 0 | 669000 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 017 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10XX | 012 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10XX | 015 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10YY | 003 | SVCS | CAP | 1000000 | 0 | 0 | 1000000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 012 | CONS | CAP | 8409000 | 0 | 0 | 8409000 | 12/15/2017
850 | REPLACE WATER MAIN IN CRESCENT ST, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-762 | 601 | IFDS | IFA | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | REPLACE WATER MAIN IN CROPSEY AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-763 | 011 | CONS | CAP | 3000 | 2128 | 2128 | 872 | 12/15/2017
850 | REPLACE WATER MAIN IN FLUSHING AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-764 | 602 | IFSP | IFA | 10000 | 1257 | 1257 | 8743 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 20B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-765 | 014 | CONS | CAP | 55000 | 54050 | 54050 | 950 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 22B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-767 | 004 | CONS | CAP | 645000 | 644807 | 644807 | 193 | 12/15/2017
850 | REPLACEMENT OF 8" AND 12" AND 20" DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-771 | 013 | IFSP | IFA | 94000 | 93943 | 93943 | 57 | 12/15/2017
850 | DISTRIBUTION WATER MAINS IN 4 AV - 80 ST AND 95 ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-774 | 001 | IFDS | IFA | 200000 | 199998 | 199998 | 2 | 12/15/2017
850 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-776 | 606 | IFSP | IFA | 50000 | 0 | 0 | 50000 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 602 | IFDS | IFA | 61000 | 0 | 0 | 61000 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 004 | IFDS | IFA | 660000 | 659999 | 616641 | 1 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 008 | CONS | CAP | 578000 | 577824 | 197091 | 176 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T Carlton & portland | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778A | 602 | IFDS | IFA | 550000 | 549999 | 285483 | 1 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 002 | CONS | CAP | 4940000 | 4938979 | 4418568 | 1021 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 003 | CONS | CAP | 2297000 | 2296484 | 1980822 | 516 | 12/15/2017
850 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-794 | 002 | CONS | CAP | 4075000 | 0 | 0 | 4075000 | 12/15/2017
850 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-794 | 601 | IFDS | IFA | 157000 | 0 | 0 | 157000 | 12/15/2017
850 | WM replacement in Oriental Blvd | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-819 | 601 | IFSP | IFA | 500000 | 0 | 0 | 500000 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 802 | CONS | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-001 | 007 | CONS | CAP | 766000 | 765658 | 525595 | 342 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 104 | IFDS | IFA | 816000 | 810000 | 810000 | 6000 | 12/15/2017
850 | BRONX ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT2 | 003 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 006 | CONS | CAP | 11518000 | 0 | 0 | 11518000 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 016 | CTGY | CAP | 20000000 | 0 | 0 | 20000000 | 12/15/2017
850 | WHITE STREET JAIL | 072 | DEPARTMENT OF CORRECTION | C-109-3 | 011 | CTGY | CAP | 9000000 | 0 | 0 | 9000000 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 012 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 020 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | EGRESS STAIRS AT B'KLYN HOUSE OF DETENTION | 072 | DEPARTMENT OF CORRECTION | C104EGRES | 009 | CNSP | CAP | 804000 | 804202 | 804202 | -202 | 12/15/2017
850 | CIFM STAFF LOCKERS | 072 | DEPARTMENT OF CORRECTION | C114DDMOD | 002 | DSGN | CAP | 291000 | 256138 | 254607 | 34862 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 008 | CONS | CAP | 16024000 | 206323 | 206323 | 15817677 | 12/15/2017
850 | SUBMARINE CABLING EASTSIDE POWER | 072 | DEPARTMENT OF CORRECTION | C114MBE3A | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 011 | CONS | CAP | 32204000 | 0 | 0 | 32204000 | 12/15/2017
850 | CONGREGATE CARE FACILITIES | 096 | HUMAN RESOURCES ADMINISTRATION | ACSCCF | 003 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LIRA MOTT SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AG-1LIMOT | 011 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SCSC-SUNYSIDE COMMUNITY SENIOR CENTER | 125 | DEPARTMENT FOR THE AGING | AG-QSUNY | 003 | CONS | CAP | 315000 | 315000 | 315000 | 0 | 12/15/2017
850 | BETANCES KITCHEN & ANSUL SUPP(VAR SITES) | 125 | DEPARTMENT FOR THE AGING | AG1BKE | 009 | CONS | CAP | 346000 | 0 | 0 | 346000 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 022 | CTGY | CAP | 11000 | 0 | 0 | 11000 | 12/15/2017
850 | SIROVICH FIRE CODE COMPLIANCE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR2 | 002 | DSGN | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | SIROVICH-INT WATER DAMAGE REPAIR AND RENOVATIONS | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4 | 007 | CTGY | CAP | 100000 | 14109 | 14109 | 85891 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 003 | IFSP | IFA | 37000 | 37000 | 37000 | 0 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 117 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 104 | CTGY | CAP | 21000 | 0 | 0 | 21000 | 12/15/2017
850 | VANDALIA SR CTR/HVAC | 125 | DEPARTMENT FOR THE AGING | AGC001VCR | 012 | IFSP | IFA | 23000 | 22693 | 22693 | 307 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 015 | IFSP | IFA | 60000 | 14996 | 14996 | 45004 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 019 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | NYCHANGE PROJECT WITH DFTA | 125 | DEPARTMENT FOR THE AGING | AGNYCHANG | 003 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | JASA BRONX GROUP SERVICES | 125 | DEPARTMENT FOR THE AGING | AGX001LC | 014 | CONS | CAP | 76000 | 0 | 0 | 76000 | 12/15/2017
850 | SEWER CONSTRUCTION | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWC | 007 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACE SEWER | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWR | 010 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACE SEWER | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWR | 013 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 178 CHRISTOPHER STREET | 806 | HOUSING PRESERVATION AND DEVELOPEMENT | BAILEY | 100 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | BORING, FY01 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10LL | 004 | CTGY | CAP | 1000000 | 0 | 0 | 1000000 | 12/15/2017
850 | BORING, FY01 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10MM | 003 | SVCS | CAP | 601000 | 581225 | 581225 | 19775 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY05-6 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10SS | 004 | SVCS | CAP | 300000 | 0 | 0 | 300000 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY08-9 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10TT | 001 | SVCS | CAP | 1500000 | 1277786 | 1277786 | 222214 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 013 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10XX | 019 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | DIST MAIN IMPROVEMENT DUE TO REMOVAL OF HP SYSTEM | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-753 | 010 | IFSP | IFA | 5000 | 4879 | 4879 | 121 | 12/15/2017
850 | REPLACE WATER MAIN IN CROPSEY AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-763 | 003 | CNSP | CAP | 1526000 | 1359310 | 1359310 | 166690 | 12/15/2017
850 | REPLACE WATER MAIN IN CROPSEY AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-763 | 601 | IFDS | IFA | 55000 | 11057 | 11057 | 43943 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 20B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-765 | 009 | CONS | CAP | 1000 | 621 | 621 | 379 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 20B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-765 | 017 | IFDS | IFA | 35000 | 1999 | 1999 | 33001 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 029 | IFSP | IFA | 131000 | 130326 | 130326 | 674 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 20B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-765 | 007 | CONS | CAP | 468000 | 457929 | 456593 | 10071 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 22B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-767 | 601 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768A | 010 | CTGY | CAP | 3000000 | 0 | 0 | 3000000 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768B | 003 | CNSP | CAP | 160000 | 0 | 0 | 160000 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 002 | IFDS | IFA | 170000 | 169536 | 169536 | 464 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 011 | CNSP | CAP | 202000 | 200392 | 200392 | 1608 | 12/15/2017
850 | TRUNK MAIN (72") IN FT HAMILTON PKWY - 86 ST AND SHORE RD | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-770 | 011 | CONS | CAP | 18000 | 18000 | 0 | 0 | 12/15/2017
850 | REPLACEMENT OF 8" AND 12" AND 20" DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-771 | 004 | CTGY | CAP | 1200000 | 0 | 0 | 1200000 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 011 | CONS | CAP | 36000 | 36000 | 0 | 0 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | DC9 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 010 | CONS | CAP | 276000 | 275309 | 70843 | 691 | 12/15/2017
850 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-780 | 004 | CNSP | CAP | 160000 | 0 | 0 | 160000 | 12/15/2017
850 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-780 | 604 | IFSP | IFA | 80000 | 0 | 0 | 80000 | 12/15/2017
850 | WM & Sewer work in Atlantic Ave (HWD10105, NDF-ATLAV) | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-785A | 801 | CONS | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 004 | CONS | CAP | 4838000 | 4838168 | 0 | -168 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 012 | CONS | CAP | 135000 | 134307 | 0 | 693 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 020 | CONS | CAP | 1210000 | 1209355 | 0 | 645 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 607 | IFSP | IFA | 809000 | 0 | 0 | 809000 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-001 | 014 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-003 | 600 | IFDS | IFA | 100000 | 94999 | 68267 | 5001 | 12/15/2017
850 | BROOKLYN ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BKDETCT2 | 005 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 001 | CONS | CAP | 279000 | 0 | 0 | 279000 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 047 | CNSP | CAP | 161000 | 0 | 0 | 161000 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 047 | DSGN | CAP | 33000 | 503551 | 503551 | -470551 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 049 | CONS | CAP | 106000 | 105627 | 105627 | 373 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 051 | CONS | CAP | 291000 | 290820 | 290820 | 180 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 008 | CONS | CAP | 126000 | 126500 | 126500 | -500 | 12/15/2017
850 | WHITE STREET JAIL | 072 | DEPARTMENT OF CORRECTION | C-109-3 | 004 | IFSP | IFA | 9000 | 8854 | 8854 | 146 | 12/15/2017
850 | WHITE STREET JAIL | 072 | DEPARTMENT OF CORRECTION | C-109-3 | 010 | OTHR | CAP | 385000 | 0 | 0 | 385000 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 004 | CONS | CAP | 27000 | 0 | 0 | 27000 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 004 | CNSP | CAP | 580000 | 579705 | 579705 | 295 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 011 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | RECON OF WM IN KINGSTON AVE BTW EASTERN PKWY & EMPIRE BLVD | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-787 | 001 | CONS | CAP | 951000 | 950395 | 950395 | 605 | 12/15/2017
850 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-794 | 004 | CONS | CAP | 5489000 | 0 | 0 | 5489000 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-001 | 605 | IFSP | IFA | 120000 | 38999 | 38260 | 81001 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-002 | 606 | IFSP | IFA | 112000 | 95948 | 35319 | 16052 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-003 | 007 | CNSP | CAP | 121000 | 120680 | 0 | 320 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-003 | 601 | IFDS | IFA | 100000 | 0 | 0 | 100000 | 12/15/2017
850 | BERGEN STREET OFFICE RENOVATION | 806 | HOUSING PRESERVATION AND DEVELOPEMENT | BERGEN | 002 | IFSP | IFA | 170000 | 159999 | 11323 | 10001 | 12/15/2017
850 | BERGEN STREET OFFICE RENOVATION | 806 | HOUSING PRESERVATION AND DEVELOPEMENT | BERGEN | 005 | IFDS | IFA | 142000 | 141999 | 122023 | 1 | 12/15/2017
850 | FA - Boro Park YM & YWHA Center Renovations | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BPKYWHA2 | 001 | CONS | CAP | 45000 | 45000 | 0 | 0 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 003 | DSGN | CAP | 530000 | 529363 | 529363 | 637 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 012 | CONS | CAP | 585000 | 585035 | 585035 | -35 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 003 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 023 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 030 | DSGN | CAP | 201000 | 200090 | 200090 | 910 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 035 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 001 | CONS | CAP | -34000 | 0 | 0 | -34000 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 018 | CONS | CAP | 28000 | 0 | 0 | 28000 | 12/15/2017
850 | CAPACITY REPLACEMENT PROGRAM- BKDC RECON. & REPLACEMENT | 072 | DEPARTMENT OF CORRECTION | C114NEWF2 | 002 | IFDS | IFA | 1250000 | 1148999 | 1137935 | 101001 | 12/15/2017
850 | CAPACITY REPLACEMENT PROGRAM- BKDC RECON. & REPLACEMENT | 072 | DEPARTMENT OF CORRECTION | C114NEWF2 | 011 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | VISIT HOUSE | 072 | DEPARTMENT OF CORRECTION | C114VHCIF | 014 | DSGN | CAP | 56000 | 55806 | 55806 | 194 | 12/15/2017
850 | VISIT HOUSE | 072 | DEPARTMENT OF CORRECTION | C114VHCIF | 017 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 500 BED - OBCC | 072 | DEPARTMENT OF CORRECTION | C124-500 | 001 | DSGN | CAP | 8000 | 0 | 0 | 8000 | 12/15/2017
850 | OBCC BATHRM & SHWR FLOORS | 072 | DEPARTMENT OF CORRECTION | C124-FLOR | 007 | CONS | CAP | 1000 | 0 | 0 | 1000 | 12/15/2017
850 | OBCC BATHRM & SHWR FLOORS | 072 | DEPARTMENT OF CORRECTION | C124-FLOR | 018 | DSGN | CAP | 35000 | 34417 | 34417 | 583 | 12/15/2017
850 | ALTERATIONS TO POWER PLANT AT RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C130-P1 | 005 | IFSP | IFA | 30000 | 29999 | 29999 | 1 | 12/15/2017
850 | POWERHOUSE WALL REHAB | 072 | DEPARTMENT OF CORRECTION | C130-PIPE | 003 | IFSP | IFA | 45000 | 44998 | 44998 | 2 | 12/15/2017
850 | POWERHOUSE WALL REHAB | 072 | DEPARTMENT OF CORRECTION | C130-PIPE | 010 | CONS | CAP | 184000 | 0 | 0 | 184000 | 12/15/2017
850 | NIC WINDOW REPLACEMENT | 072 | DEPARTMENT OF CORRECTION | C133WNDW | 005 | CTGY | CAP | 100000 | 0 | 0 | 100000 | 12/15/2017
850 | CEILING RECON JATC,RI (W/C75-TRRF) | 072 | DEPARTMENT OF CORRECTION | C135-ROOF | 009 | CONS | CAP | 8000 | 0 | 0 | 8000 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 018 | CNSP | CAP | 263000 | 262915 | 0 | 85 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 021 | CNSP | CAP | 32000 | 31557 | 0 | 443 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 604 | IFSP | IFA | 400000 | 399999 | 336027 | 1 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | DC6 | CNSP | CAP | 128000 | 128000 | 128000 | 0 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T Carlton & portland | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778A | 604 | IFSP | IFA | 50000 | 0 | 0 | 50000 | 12/15/2017
850 | wm & Comb swr replacment. Williamsbug bridge plaza, bklyn | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-797 | 602 | IFDS | IFA | 57000 | 56999 | 1229 | 1 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 008 | CNSP | CAP | 887000 | 886999 | 0 | 1 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 019 | CONS | CAP | 226000 | 226450 | 0 | -450 | 12/15/2017
850 | BROOKLYN ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BKDETCT2 | 015 | IFSP | IFA | 80000 | 79953 | 79953 | 47 | 12/15/2017
850 | BRONX ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT2 | 009 | CTGY | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 001 | DSGN | CAP | 52000 | 0 | 0 | 52000 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 025 | CONS | CAP | 373000 | 361897 | 361897 | 11103 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 037 | CONS | CAP | 5000 | 4128 | 4128 | 872 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 038 | CONS | CAP | 631000 | 630445 | 630445 | 555 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 056 | SVCS | CAP | 2000 | 208797 | 208797 | -206797 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 013 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 014 | DSGN | CAP | 37000 | 35850 | 35850 | 1150 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 009 | CONS | CAP | 114000 | 114000 | 114000 | 0 | 12/15/2017
850 | EGRESS STAIRS AT B'KLYN HOUSE OF DETENTION | 072 | DEPARTMENT OF CORRECTION | C104EGRES | 003 | DSGN | CAP | 36000 | 1180684 | 1180684 | -1144684 | 12/15/2017
850 | 200 DORMITORY BEDS AT ARDC | 072 | DEPARTMENT OF CORRECTION | C114ARDC | 001 | DSGN | CAP | 1142000 | 1141293 | 1141293 | 707 | 12/15/2017
850 | 200 DORMITORY BEDS AT ARDC | 072 | DEPARTMENT OF CORRECTION | C114ARDC | 007 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CIFM STAFF LOCKERS | 072 | DEPARTMENT OF CORRECTION | C114DDMOD | 008 | DSGN | CAP | 169000 | 168573 | 168573 | 427 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 019 | SVCS | CAP | 126000 | 2390353 | 2390353 | -2264353 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 016 | CONS | CAP | 99000 | 0 | 0 | 99000 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 025 | CONS | CAP | 2000 | 0 | 0 | 2000 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 032 | CONS | CAP | 53000 | 50142 | 50142 | 2858 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 014 | CONS | CAP | 9000 | 0 | 0 | 9000 | 12/15/2017
850 | CAPACITY REPLACEMENT PROGRAM- BKDC RECON. & REPLACEMENT | 072 | DEPARTMENT OF CORRECTION | C114NEWF2 | 013 | CONS | CAP | 216000 | 215095 | 171998 | 905 | 12/15/2017
850 | NEW RIKERS ISLAND FACILITY | 072 | DEPARTMENT OF CORRECTION | C114NEWRI | 002 | CNSP | CAP | 44013000 | 0 | 0 | 44013000 | 12/15/2017
850 | NEW RIKERS ISLAND FACILITY | 072 | DEPARTMENT OF CORRECTION | C114NEWRI | 002 | CONS | CAP | 13487000 | 57207846 | 14758133 | -43720846 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 003 | IFSP | IFA | 313000 | 312256 | 312256 | 744 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 015 | CTGY | CAP | 909000 | 0 | 0 | 909000 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 024 | AART | CAP | 200000 | 200000 | 200000 | 0 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 033 | SVCS | CAP | 100000 | 0 | 0 | 100000 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 054 | IFSP | IFA | 348000 | 302250 | 302250 | 45750 | 12/15/2017
850 | CONGREGATE CARE FACILITIES | 096 | HUMAN RESOURCES ADMINISTRATION | ACSCCF | 002 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | Interior and rear courtyard renovations | 125 | DEPARTMENT FOR THE AGING | AG-1LEON | 003 | CONS | CAP | 94000 | 93187 | 93187 | 813 | 12/15/2017
850 | SIROVICH SC EXTERIOR MASONRY & WATERPROOFING | 125 | DEPARTMENT FOR THE AGING | AG1SIRR3 | 005 | CTGY | CAP | 74000 | 0 | 0 | 74000 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 008 | CONS | CAP | 61000 | 0 | 0 | 61000 | 12/15/2017
850 | SIROVICH ROOF TERRACE | 125 | DEPARTMENT FOR THE AGING | AG1SIRRTE | 010 | CONS | CAP | 5000 | 4560 | 4560 | 440 | 12/15/2017
850 | ABE STARK SENIOR CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-BOCCE | 004 | CONS | CAP | 46000 | 0 | 0 | 46000 | 12/15/2017
850 | NEW DORP SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AGC001NDF | 001 | DSGN | CAP | 41000 | 0 | 0 | 41000 | 12/15/2017
850 | NEW DORP SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AGC001NDF | 009 | CONS | CAP | 33000 | 0 | 0 | 33000 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 008 | DSGN | CAP | 17000 | 270307 | 269031 | -253307 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 014 | CONS | CAP | 39000 | 0 | 0 | 39000 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 016 | EQFN | CAP | 2000 | 3398 | 3398 | -1398 | 12/15/2017
850 | NYCHANGE PROJECT WITH DFTA | 125 | DEPARTMENT FOR THE AGING | AGNYCHANG | 004 | DSGN | CAP | 238000 | 237719 | 17829 | 281 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY05-6 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10PP | 001 | SVCS | CAP | 1400000 | 1387442 | 1387442 | 12558 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY08-09 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10UU | 001 | SVCS | CAP | 952000 | 952050 | 952050 | -50 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY08-09 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10UU | 006 | SVCS | CAP | 1000000 | 1000000 | 1000000 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 014 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 020 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10XX | 022 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACE 6 IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-743 | 004 | CONS | CAP | 6814000 | 0 | 0 | 6814000 | 12/15/2017
850 | REPLACE 6 IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-744 | 003 | CONS | CAP | 319000 | 0 | 0 | 319000 | 12/15/2017
850 | REPLACE 6-IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-745 | 007 | CTGY | CAP | 1500000 | 0 | 0 | 1500000 | 12/15/2017
850 | DIST MAIN IMPROVEMENT DUE TO REMOVAL OF HP SYSTEM | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-753 | 007 | CONS | CAP | 19000 | 0 | 0 | 19000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 022 | CONS | CAP | 76000 | 75697 | 75697 | 303 | 12/15/2017
850 | REPLACE WATER MAIN IN FLUSHING AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-764 | 601 | IFDS | IFA | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 22B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-767 | 003 | IFSP | IFA | 306000 | 305603 | 305603 | 397 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768A | 001 | CONS | CAP | 9854000 | 9843758 | 8828345 | 10242 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768A | 002 | CNSP | CAP | 1624000 | 1473807 | 1436161 | 150193 | 12/15/2017
850 | DIST MAIN IMPROVEMENT DUE TO REMOVAL OF HP SYSTEM | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-753 | 006 | CONS | CAP | 30000 | 0 | 0 | 30000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 015 | CONS | CAP | -14654000 | 0 | 0 | -14654000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 028 | IFDS | IFA | 88000 | 87080 | 87080 | 920 | 12/15/2017
850 | REPLACE WATER MAIN IN CRESCENT ST, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-762 | 010 | IFSP | IFA | 85000 | 36815 | 36815 | 48185 | 12/15/2017
850 | REPLACE WATER MAIN IN FLUSHING AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-764 | 010 | IFDS | IFA | 38000 | 37940 | 37940 | 60 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 20B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-765 | 001 | CONS | CAP | 4149000 | 4148171 | 4016240 | 829 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 20B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-765 | 006 | CNSP | CAP | 285000 | 284342 | 0 | 658 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 21B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-766 | 009 | CONS | CAP | 54000 | 53397 | 53397 | 603 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 21B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-766 | 012 | IFSP | IFA | 4000 | 3578 | 3578 | 422 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768A | 009 | CTGY | CAP | 5000000 | 0 | 0 | 5000000 | 12/15/2017
850 | REPLACEMENT OF 8" AND 12" AND 20" DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-771 | 602 | IFDS | IFA | 85000 | 6019 | 6019 | 78981 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 010 | CONS | CAP | 2047000 | 2042365 | 438955 | 4635 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 017 | CONS | CAP | 10000 | 9389 | 0 | 611 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 016 | CONS | CAP | 74000 | 73782 | 0 | 218 | 12/15/2017
850 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-780 | 001 | CONS | CAP | 1600000 | 0 | 0 | 1600000 | 12/15/2017
850 | wm & Comb swr replacment. Williamsbug bridge plaza, bklyn | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-797 | 603 | IFSP | IFA | 220000 | 0 | 0 | 220000 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 016 | CONS | CAP | 157000 | 157263 | 0 | -263 | 12/15/2017
850 | BROOKLYN ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BKDETCT2 | 009 | CTGY | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BROOKLYN ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BKDETCT2 | 011 | IFSP | IFA | 70000 | 69419 | 69419 | 581 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 022 | IFSP | IFA | 80000 | 80000 | 80000 | 0 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 012 | CONS | CAP | 3748000 | 3747284 | 3747284 | 716 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 031 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 200 DORMITORY BEDS AT ARDC | 072 | DEPARTMENT OF CORRECTION | C114ARDC | 002 | DSGN | CAP | 0 | 2395222 | 2395222 | -2395222 | 12/15/2017
850 | MODULAR & SPRUNGS TAKE DOWNS - CAPACITY REPLACEMENT PROGRAM | 072 | DEPARTMENT OF CORRECTION | C114CAPTD | 009 | IFSP | IFA | 45000 | 11977 | 11977 | 33023 | 12/15/2017
850 | CIFM STAFF LOCKERS | 072 | DEPARTMENT OF CORRECTION | C114DDMOD | 016 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 024 | CONS | CAP | 4833000 | 4832170 | 4832170 | 830 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 025 | DSGN | CAP | 1574000 | 1572998 | 1572998 | 1002 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 027 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 038 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 033 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 034 | CTGY | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | PERM ELEC FOR EAST/WEST (CON ED TIE-INS) | 072 | DEPARTMENT OF CORRECTION | C114MBE3B | 010 | CONS | CAP | 1331000 | 1150289 | 1150289 | 180711 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 003 | SVCS | CAP | 30000 | 0 | 0 | 30000 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 017 | CONS | CAP | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | NEW RIKERS ISLAND FACILITY | 072 | DEPARTMENT OF CORRECTION | C114NEWRI | 008 | IFSP | IFA | 1129000 | 348000 | 348000 | 781000 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 023 | IFSP | IFA | 4489000 | 4185999 | 4169317 | 303001 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 038 | EQFN | CAP | 567000 | 565922 | 565922 | 1078 | 12/15/2017
850 | VISIT HOUSE | 072 | DEPARTMENT OF CORRECTION | C114VHCIF | 019 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | OBCC SHOWER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C124-SHWR | 005 | CONS | CAP | 549000 | 549015 | 549015 | -15 | 12/15/2017
850 | ALTERATIONS TO POWER PLANT AT RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C130-P1 | 008 | CONS | CAP | 2000 | 0 | 0 | 2000 | 12/15/2017
850 | ALTERATIONS TO POWER PLANT AT RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C130-P1 | 023 | CONS | CAP | 41000 | 0 | 0 | 41000 | 12/15/2017
850 | POWERHOUSE WALL REHAB | 072 | DEPARTMENT OF CORRECTION | C130-PIPE | 005 | CONS | CAP | 521000 | 507949 | 507949 | 13051 | 12/15/2017
850 | POWERHOUSE WALL REHAB | 072 | DEPARTMENT OF CORRECTION | C130-PIPE | 010 | SVCS | CAP | 0 | 183721 | 183721 | -183721 | 12/15/2017
850 | POWERHOUSE WALL REHAB | 072 | DEPARTMENT OF CORRECTION | C130-PIPE | 012 | IFSP | IFA | 165000 | 95000 | 95000 | 70000 | 12/15/2017
850 | FAA TOWER | 072 | DEPARTMENT OF CORRECTION | C133-FAA | 001 | CONS | CAP | -2451000 | 0 | 0 | -2451000 | 12/15/2017
850 | NIC WINDOW REPLACEMENT | 072 | DEPARTMENT OF CORRECTION | C133WNDW | 002 | CONS | CAP | 20000 | 19241 | 19241 | 759 | 12/15/2017
850 | NIC WINDOW REPLACEMENT | 072 | DEPARTMENT OF CORRECTION | C133WNDW | 003 | CONS | CAP | 24000 | 23085 | 23085 | 915 | 12/15/2017
850 | JATC INTERIOR RENO | 072 | DEPARTMENT OF CORRECTION | C135-RENO | 009 | CNSP | CAP | 437000 | 0 | 0 | 437000 | 12/15/2017
850 | JATC INTERIOR RENO | 072 | DEPARTMENT OF CORRECTION | C135-RENO | 029 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CEILING RECON JATC,RI (W/C75-TRRF) | 072 | DEPARTMENT OF CORRECTION | C135-ROOF | 007 | CONS | CAP | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | REPLACEMENT OF PARAPETS | 072 | DEPARTMENT OF CORRECTION | C138-PARA | 015 | DSGN | CAP | 167000 | 1932008 | 1932008 | -1765008 | 12/15/2017
850 | FIRE/LIFE SAFETY RIKERS IS (EAST SIDE) | 072 | DEPARTMENT OF CORRECTION | C138FIR-D | 016 | CONS | CAP | 1462000 | 1461351 | 1154969 | 649 | 12/15/2017
850 | REPAVING AT AMKC,CIFM,GMDC,MDC AND NIC | 072 | DEPARTMENT OF CORRECTION | C138PAVE | 001 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | GRVC & RMSC YARD RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C139-500 | 005 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 013 | CONS | CAP | 3500000 | 0 | 0 | 3500000 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 047 | EQFN | CAP | 1610000 | 0 | 0 | 1610000 | 12/15/2017
850 | COOK SERVE #2---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV2 | 003 | CNSP | CAP | 5663000 | 0 | 0 | 5663000 | 12/15/2017
850 | RECONSTRUCTION BKLYN COURTS | 072 | DEPARTMENT OF CORRECTION | C75-BKCON | 012 | CONS | CAP | 343000 | 0 | 0 | 343000 | 12/15/2017
850 | INSTALLATION OF UNDER GROUND ETHANOL STORAGE TANKS-TRANS. | 072 | DEPARTMENT OF CORRECTION | C75-ETHAN | 003 | DSGN | CAP | 41000 | 40904 | 40904 | 96 | 12/15/2017
850 | AMKC BUILDINGS 1-5 HVAC/HOT WATER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C75AMKCHV | 001 | DSGN | CAP | 762000 | 761238 | 611238 | 762 | 12/15/2017
850 | AMKC BUILDINGS 1-5 HVAC/HOT WATER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C75AMKCHV | 007 | CONS | CAP | 942000 | 942329 | 872099 | -329 | 12/15/2017
850 | FACADE RESTORATION BKLYN HDM | 072 | DEPARTMENT OF CORRECTION | C75BKFCAD | 015 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | VARIOUS FACADE REPAIRS | 072 | DEPARTMENT OF CORRECTION | C75FCADE | 014 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 021 | SVCS | CAP | 66000 | 0 | 0 | 66000 | 12/15/2017
850 | LIRA MOTT SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AG-1LIMOT | 601 | IFSP | IFA | 10000 | 0 | 0 | 10000 | 12/15/2017
850 | BETANCES KITCHEN & ANSUL SUPP(VAR SITES) | 125 | DEPARTMENT FOR THE AGING | AG1BKE | 002 | DSGN | CAP | 57000 | 0 | 0 | 57000 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 010 | DSGN | CAP | 71000 | 70764 | 70764 | 236 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 011 | CONS | CAP | 131000 | 0 | 0 | 131000 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 022 | DSGN | CAP | 42000 | 136919 | 136919 | -94919 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 034 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | SIROVICH SC EXTERIOR MASONRY & WATERPROOFING | 125 | DEPARTMENT FOR THE AGING | AG1SIRR3 | 006 | IFSP | IFA | 50000 | 50000 | 50000 | 0 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 104 | CONS | CAP | 56000 | 0 | 0 | 56000 | 12/15/2017
850 | SIROVICH ROOF TERRACE | 125 | DEPARTMENT FOR THE AGING | AG1SIRRTE | 009 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 112 | IFSP | IFA | 15000 | 0 | 0 | 15000 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 114 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | HOPE GARDENS/ADA (FRONT DOOR) | 125 | DEPARTMENT FOR THE AGING | AGC001HGM | 004 | CONS | CAP | 14000 | 0 | 0 | 14000 | 12/15/2017
850 | KINGSBAY SENIOR CENTER, BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | AGC001KBC | 006 | SVCS | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 008 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 100 | IFDS | IFA | 499000 | 369999 | 354053 | 129001 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 018 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | DOROT, INC. | 125 | DEPARTMENT FOR THE AGING | AGDDORT | 001 | EQFN | CAP | 40000 | 39975 | 39975 | 25 | 12/15/2017
850 | JCC of Coney Island Computers | 125 | DEPARTMENT FOR THE AGING | AGPWDJCC | 001 | EQFN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 006 | IFSP | IFA | 500000 | 500000 | 500000 | 0 | 12/15/2017
850 | BORINGS, FY'00 BROOKLYN & QUEENS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10KK | 003 | CTGY | CAP | 70000 | 0 | 0 | 70000 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY05-6 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10QQ | 004 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 001 | SVCS | CAP | 2000000 | 2000000 | 2000000 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 002 | IFOT | IFA | 200000 | 0 | 0 | 200000 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 006 | SVCS | CAP | 200000 | 200000 | 190000 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10YY | 002 | SVCS | CAP | 1000000 | 0 | 0 | 1000000 | 12/15/2017
850 | REPLACE 6-IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-745 | 003 | IFSP | IFA | 56000 | 55573 | 55573 | 427 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768A | 008 | CNSP | CAP | 601000 | 570495 | 568449 | 30505 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768A | 011 | CONS | CAP | 947000 | 926589 | 797692 | 20411 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768B | 006 | CONS | CAP | 11306000 | 0 | 0 | 11306000 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 012 | CNSP | CAP | 1350000 | 1266038 | 1264575 | 83962 | 12/15/2017
850 | DCLA MMA - Air Handler Replacements: WHVAC-2, 3, 4, & 5 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ACEDCA437 | 002 | CONS | CAP | 1000 | 0 | 0 | 1000 | 12/15/2017
850 | DSNY - LIGHTING DEBUNDLING PROJECTS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ACEDOS501 | 002 | CONS | CAP | 303000 | 291116 | 261116 | 11884 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 004 | DSGN | CAP | 6000 | 5925 | 5925 | 75 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 005 | DSGN | CAP | 2080000 | 0 | 0 | 2080000 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 017 | CONS | CAP | 18824000 | 18223346 | 18223346 | 600654 | 12/15/2017
850 | Interior and rear courtyard renovations | 125 | DEPARTMENT FOR THE AGING | AG-1LEON | 010 | IFSP | IFA | 22000 | 21955 | 21955 | 45 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 007 | CONS | CAP | 650000 | 0 | 0 | 650000 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 007 | DSGN | CAP | 230000 | 853597 | 824847 | -623597 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 026 | CTGY | CAP | 59000 | 0 | 0 | 59000 | 12/15/2017
850 | SIROVICH FIRE CODE COMPLIANCE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR2 | 001 | DSGN | CAP | 77000 | 0 | 0 | 77000 | 12/15/2017
850 | SIROVICH FIRE CODE COMPLIANCE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR2 | 009 | CONS | CAP | 34000 | 0 | 0 | 34000 | 12/15/2017
850 | ABE STARK SENIOR CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-BOCCE | 001 | DSGN | CAP | 6000 | 0 | 0 | 6000 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 001 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 107 | IFSP | IFA | 153000 | 78736 | 78736 | 74264 | 12/15/2017
850 | NEW CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-QUEEN | 005 | CTGY | CAP | 63000 | 0 | 0 | 63000 | 12/15/2017
850 | NEW CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-QUEEN | 006 | CONS | CAP | 52000 | 0 | 0 | 52000 | 12/15/2017
850 | KINGSBAY SENIOR CENTER, BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | AGC001KBC | 022 | IFSP | IFA | 40000 | 0 | 0 | 40000 | 12/15/2017
850 | VANDALIA SR CTR/HVAC | 125 | DEPARTMENT FOR THE AGING | AGC001VCR | 013 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 012 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | NYCHANGE PROJECT WITH DFTA | 125 | DEPARTMENT FOR THE AGING | AGNYCHANG | 002 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | TODT HILL SENIOR CENTER - A/C SYSTEMS | 125 | DEPARTMENT FOR THE AGING | AGR001TAC | 012 | CONS | CAP | 578000 | 0 | 0 | 578000 | 12/15/2017
850 | JASA BRONX GROUP SERVICES | 125 | DEPARTMENT FOR THE AGING | AGX001LC | 010 | CONS | CAP | 25000 | 0 | 0 | 25000 | 12/15/2017
850 | JASA BRONX GROUP SERVICES | 125 | DEPARTMENT FOR THE AGING | AGX001LC | 013 | CONS | CAP | 17000 | 0 | 0 | 17000 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 011 | CONS | CAP | 201000 | 201000 | 201000 | 0 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 014 | CONS | CAP | 82000 | 81950 | 81950 | 50 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 015 | IFSP | IFA | 465000 | 464050 | 464050 | 950 | 12/15/2017
850 | SEWER CONSTRUCTION | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWC | 001 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BORINGS, FY'00 BROOKLYN & QUEENS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10KK | 001 | SVCS | CAP | 745000 | 740620 | 740620 | 4380 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY05-6 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10RR | 007 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10XX | 018 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACE 6-IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-745 | 008 | IFSP | IFA | 600000 | 599988 | 599988 | 12 | 12/15/2017
850 | Betts Boilers Replacement | 827 | DEPARTMENT OF SANITATION | ACEDOS503 | 002 | CONS | CAP | 480000 | 479004 | 0 | 996 | 12/15/2017
850 | Interior and rear courtyard renovations | 125 | DEPARTMENT FOR THE AGING | AG-1LEON | 009 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LIRA MOTT SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AG-1LIMOT | 007 | CONS | CAP | 253000 | 0 | 0 | 253000 | 12/15/2017
850 | BETANCES KITCHEN & ANSUL SUPP(VAR SITES) | 125 | DEPARTMENT FOR THE AGING | AG1BKE | 005 | IFSP | IFA | 68000 | 67590 | 67590 | 410 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 006 | CONS | CAP | 677000 | 677000 | 677000 | 0 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 033 | IFSP | IFA | 45000 | 9003 | 9003 | 35997 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 035 | IFDS | IFA | 25000 | 8907 | 8907 | 16093 | 12/15/2017
850 | SIROVICH FIRE CODE COMPLIANCE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR2 | 013 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SIROVICH-INT WATER DAMAGE REPAIR AND RENOVATIONS | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4 | 001 | DSGN | CAP | 81000 | 0 | 0 | 81000 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 010 | CONS | CAP | 6000 | 0 | 0 | 6000 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 105 | CONS | CAP | -531000 | 0 | 0 | -531000 | 12/15/2017
850 | KINGSBAY SENIOR CENTER, BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | AGC001KBC | 015 | IFDS | IFA | 49000 | 48982 | 48982 | 18 | 12/15/2017
850 | NEW DORP SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AGC001NDF | 010 | CTGY | CAP | 86000 | 18250 | 18250 | 67750 | 12/15/2017
850 | VANDALIA SR CTR/HVAC | 125 | DEPARTMENT FOR THE AGING | AGC001VCR | 001 | DSGN | CAP | 22000 | 0 | 0 | 22000 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 001 | DSGN | CAP | 41000 | 0 | 0 | 41000 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 009 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LEONARD COVELLO | 125 | DEPARTMENT FOR THE AGING | AGCOVELLO | 101 | IFSP | IFA | 481000 | 480999 | 385471 | 1 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 002 | DSGN | CAP | 113000 | 75000 | 75000 | 38000 | 12/15/2017
850 | JEWISH HOME AND HOSPITAL FOR THE AGED | 125 | DEPARTMENT FOR THE AGING | AGMHOME | 001 | EQFN | CAP | 226000 | 0 | 0 | 226000 | 12/15/2017
850 | JCC of Coney Island Computers | 125 | DEPARTMENT FOR THE AGING | AGPWDJCC | 002 | IFSP | IFA | 8000 | 0 | 0 | 8000 | 12/15/2017
850 | REPLACE SEWER | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWR | 011 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BORINGS, FY02 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10NN | 004 | SVCS | CAP | 500000 | 488732 | 485195 | 11268 | 12/15/2017
850 | REPLACE WATER MAIN IN CROPSEY AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-763 | 005 | IFSP | IFA | 255000 | 254924 | 254924 | 76 | 12/15/2017
850 | REPLACE WATER MAIN IN CROPSEY AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-763 | 009 | IFDS | IFA | 168000 | 167830 | 167830 | 170 | 12/15/2017
850 | REPLACE WATER MAIN IN CROPSEY AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-763 | 019 | IFDS | IFA | 7000 | 6465 | 6465 | 535 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 22B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-767 | 008 | CONS | CAP | 231000 | 230077 | 230077 | 923 | 12/15/2017
850 | TRUNK MAIN (72") IN FT HAMILTON PKWY - 86 ST AND SHORE RD | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-770 | 004 | CONS | CAP | 2289000 | 2288236 | 1730090 | 764 | 12/15/2017
850 | TRUNK MAIN (72") IN FT HAMILTON PKWY - 86 ST AND SHORE RD | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-770 | 015 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACEMENT OF DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-772 | 008 | IFSP | IFA | 949000 | 948317 | 948317 | 683 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 003 | CONS | CAP | 5845000 | 5844816 | 364100 | 184 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 010 | CONS | CAP | 103000 | 101380 | 5743 | 1620 | 12/15/2017
850 | CEILING RECON JATC,RI (W/C75-TRRF) | 072 | DEPARTMENT OF CORRECTION | C135-ROOF | 023 | CONS | CAP | 85000 | 0 | 0 | 85000 | 12/15/2017
850 | REPLACEMENT OF PARAPETS | 072 | DEPARTMENT OF CORRECTION | C138-PARA | 016 | CTGY | CAP | 2000000 | 0 | 0 | 2000000 | 12/15/2017
850 | REPLACEMENT OF PARAPETS | 072 | DEPARTMENT OF CORRECTION | C138-PARA | 031 | IFSP | IFA | 199000 | 198700 | 198700 | 300 | 12/15/2017
850 | FIRE/LIFE SAFETY RIKERS IS (EAST SIDE) | 072 | DEPARTMENT OF CORRECTION | C138FIR-D | 024 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | UTIL METERS-BLDGS ON RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C138METER | 007 | CTGY | CAP | 218000 | 0 | 0 | 218000 | 12/15/2017
850 | GRVC & RMSC YARD RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C139-500 | 013 | CONS | CAP | -100000 | 0 | 0 | -100000 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 015 | DSGN | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 028 | EQFN | CAP | 6266000 | 4588848 | 4588848 | 1677152 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 041 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 057 | EQFN | CAP | 1090000 | 1085650 | 1085650 | 4350 | 12/15/2017
850 | COOK SERVE #3---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV3 | 013 | DSGN | CAP | 345000 | 344627 | 344627 | 373 | 12/15/2017
850 | RECONSTRUCTION BKLYN COURTS | 072 | DEPARTMENT OF CORRECTION | C75-BKCON | 025 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 072 | DEPARTMENT OF CORRECTION | C75-FCAD | 007 | SVCS | CAP | 64000 | 2588876 | 2561546 | -2524876 | 12/15/2017
850 | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 072 | DEPARTMENT OF CORRECTION | C75-FCAD | 024 | CONS | CAP | -227000 | 0 | 0 | -227000 | 12/15/2017
850 | FACADE RESTORATION BKLYN HDM | 072 | DEPARTMENT OF CORRECTION | C75BKFCAD | 002 | DSGN | CAP | 43000 | 0 | 0 | 43000 | 12/15/2017
850 | FACADE RESTORATION BKLYN HDM | 072 | DEPARTMENT OF CORRECTION | C75BKFCAD | 004 | IFDS | IFA | 25000 | 0 | 0 | 25000 | 12/15/2017
850 | FACADE RESTORATION BKLYN HDM | 072 | DEPARTMENT OF CORRECTION | C75BKFCAD | 016 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRONX HDM RENO | 072 | DEPARTMENT OF CORRECTION | C75BXRENO | 017 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRONX HDM UTILITY PACKAGE | 072 | DEPARTMENT OF CORRECTION | C75BXUTIL | 008 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRONX HDM UTILITY PACKAGE | 072 | DEPARTMENT OF CORRECTION | C75BXUTIL | 009 | CONS | CAP | 200000 | 200000 | 200000 | 0 | 12/15/2017
850 | VARIOUS FACADE REPAIRS | 072 | DEPARTMENT OF CORRECTION | C75FCADE | 008 | CONS | CAP | 293000 | 57594 | 57594 | 235406 | 12/15/2017
850 | MDC FACADE LOCAL LAW 10 | 072 | DEPARTMENT OF CORRECTION | C75FCADE2 | 009 | SVCS | CAP | 2000 | 1572 | 1572 | 428 | 12/15/2017
850 | NIC SHOWER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C75NICSHW | 016 | DSGN | CAP | 10000 | 0 | 0 | 10000 | 12/15/2017
850 | STEAM UTILITY TUNNEL,RI | 072 | DEPARTMENT OF CORRECTION | C75TUNNEL | 040 | CTGY | CAP | 2500000 | 0 | 0 | 2500000 | 12/15/2017
850 | STEAM UTILITY TUNNEL,RI | 072 | DEPARTMENT OF CORRECTION | C75TUNNEL | 050 | CTGY | CAP | 248000 | 0 | 0 | 248000 | 12/15/2017
850 | CIFM Ceilling and Roof Replacement | 072 | DEPARTMENT OF CORRECTION | C76-CEIL | 005 | IFSP | IFA | 100000 | 100000 | 100000 | 0 | 12/15/2017
850 | REPLACEMENT OF ELEVATOR SYSTEMS | 072 | DEPARTMENT OF CORRECTION | C76ELEV1 | 012 | DSGN | CAP | 6000 | 5250 | 5250 | 750 | 12/15/2017
850 | MAIN,AMKC,K, & GMDC DORMS SHOWERS | 072 | DEPARTMENT OF CORRECTION | C95MAIN | 003 | IFSP | IFA | 310000 | 309999 | 309999 | 1 | 12/15/2017
850 | MAIN,AMKC,K, & GMDC DORMS SHOWERS | 072 | DEPARTMENT OF CORRECTION | C95MAIN | 013 | CTGY | CAP | 8000000 | 0 | 0 | 8000000 | 12/15/2017
850 | 1 CENTRE ST. - DCAS 21C3 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CC1C16 | 002 | EQFN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CC1C3 | 003 | EQFN | CAP | 310000 | 309424 | 309424 | 576 | 12/15/2017
850 | 100 GOLD- 21C3 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CC253B | 002 | CONS | CAP | 10989000 | 10762014 | 10034105 | 226986 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 008 | CONS | CAP | 1261000 | 1260790 | 1260790 | 210 | 12/15/2017
850 | WHITE STREET SITE ACQUISITION | 072 | DEPARTMENT OF CORRECTION | C109SITE | 002 | SITE | CAP | 115000 | 0 | 0 | 115000 | 12/15/2017
850 | MODULAR & SPRUNGS TAKE DOWNS - CAPACITY REPLACEMENT PROGRAM | 072 | DEPARTMENT OF CORRECTION | C114CAPTD | 004 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CIFM STAFF LOCKERS | 072 | DEPARTMENT OF CORRECTION | C114DDMOD | 004 | CONS | CAP | 557000 | 330872 | 330872 | 226128 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 013 | CONS | CAP | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 035 | CTGY | CAP | 300000 | 0 | 0 | 300000 | 12/15/2017
850 | PERM ELEC FOR EAST/WEST (CON ED TIE-INS) | 072 | DEPARTMENT OF CORRECTION | C114MBE3B | 009 | CTGY | CAP | 435000 | 0 | 0 | 435000 | 12/15/2017
850 | EAST/WEST PERMANENT POWER ENGINE GENERATOR | 072 | DEPARTMENT OF CORRECTION | C114MBE3C | 005 | CONS | CAP | 33000 | 21909 | 21909 | 11091 | 12/15/2017
850 | CAPACITY REPLACEMENT PROGRAM- BKDC RECON. & REPLACEMENT | 072 | DEPARTMENT OF CORRECTION | C114NEWF2 | 003 | DSGN | CAP | 6286000 | 6285855 | 6285854 | 145 | 12/15/2017
850 | CAPACITY REPLACEMENT PROGRAM- BKDC RECON. & REPLACEMENT | 072 | DEPARTMENT OF CORRECTION | C114NEWF2 | 008 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 009 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | OBCC BATHRM & SHWR FLOORS | 072 | DEPARTMENT OF CORRECTION | C124-FLOR | 012 | CONS | CAP | 15000 | 0 | 0 | 15000 | 12/15/2017
850 | ALTERATIONS TO POWER PLANT AT RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C130-P1 | 012 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ALTERATIONS TO POWER PLANT AT RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C130-P1 | 020 | CONS | CAP | 20000 | 0 | 0 | 20000 | 12/15/2017
850 | POWERHOUSE WALL REHAB | 072 | DEPARTMENT OF CORRECTION | C130-PIPE | 007 | SVCS | CAP | 1000 | 95105 | 95105 | -94105 | 12/15/2017
850 | MENTAL HEALTH INFIRMARY,R I (W/C-141) | 072 | DEPARTMENT OF CORRECTION | C133INFRM | 018 | IFSP | IFA | 38000 | 37362 | 37362 | 638 | 12/15/2017
850 | JATC INTERIOR RENO | 072 | DEPARTMENT OF CORRECTION | C135-RENO | 020 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CEILING RECON JATC,RI (W/C75-TRRF) | 072 | DEPARTMENT OF CORRECTION | C135-ROOF | 006 | CONS | CAP | 338000 | 5351 | 5011 | 332649 | 12/15/2017
850 | JATC RECONSTRUCTION-PHASE 2 | 072 | DEPARTMENT OF CORRECTION | C135JATC | 005 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | JATC RECONSTRUCTION-PHASE 2 | 072 | DEPARTMENT OF CORRECTION | C135JATC | 012 | IFSP | IFA | 1360000 | 89782 | 89782 | 1270218 | 12/15/2017
850 | LIFE/FIRE SAFETY UPGRADE @ 4 BORO FACILITIES | 072 | DEPARTMENT OF CORRECTION | C138-FIRE | 002 | CNSP | CAP | 1921000 | 0 | 0 | 1921000 | 12/15/2017
850 | LIFE/FIRE SAFETY UPGRADE @ 4 BORO FACILITIES | 072 | DEPARTMENT OF CORRECTION | C138-FIRE | 009 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LIFE/FIRE SAFETY UPGRADE @ 4 BORO FACILITIES | 072 | DEPARTMENT OF CORRECTION | C138-FIRE | 019 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACEMENT OF PARAPETS | 072 | DEPARTMENT OF CORRECTION | C138-PARA | 009 | DSGN | CAP | 51000 | 50271 | 50271 | 729 | 12/15/2017
850 | REPLACEMENT OF PARAPETS | 072 | DEPARTMENT OF CORRECTION | C138-PARA | 015 | CONS | CAP | 1768000 | 0 | 0 | 1768000 | 12/15/2017
850 | BKLYN HDM - FIRE LIFE SAFETY | 072 | DEPARTMENT OF CORRECTION | C138BKFIR | 008 | CTGY | CAP | 650000 | 0 | 0 | 650000 | 12/15/2017
850 | BKLYN HDM - FIRE LIFE SAFETY | 072 | DEPARTMENT OF CORRECTION | C138BKFIR | 010 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRONX HDM FACADE RENOVATION | 072 | DEPARTMENT OF CORRECTION | C138BXFAC | 004 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | FIRE/LIFE SAFETY RIKERS IS (EAST SIDE) | 072 | DEPARTMENT OF CORRECTION | C138FIR-D | 026 | IFSP | IFA | 350000 | 349999 | 349999 | 1 | 12/15/2017
850 | SMOKE DETECTION SYSTEM | 072 | DEPARTMENT OF CORRECTION | C138SMOKE | 006 | CTGY | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 011 | CNSP | CAP | 6890000 | 0 | 0 | 6890000 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 020 | CTGY | CAP | 4530000 | 0 | 0 | 4530000 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 002 | DSGN | CAP | 33000 | 0 | 0 | 33000 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 050 | CONS | CAP | 4000000 | 0 | 0 | 4000000 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 061 | IFSP | IFA | 115000 | 65000 | 65000 | 50000 | 12/15/2017
850 | LIRA MOTT SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AG-1LIMOT | 009 | CONS | CAP | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | BETANCES KITCHEN & ANSUL SUPP(VAR SITES) | 125 | DEPARTMENT FOR THE AGING | AG1BKE | 008 | CONS | CAP | 406000 | 0 | 0 | 406000 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 009 | CONS | CAP | 561000 | 561000 | 540950 | 0 | 12/15/2017
850 | PROJECT OPEN DOOR | 125 | DEPARTMENT FOR THE AGING | AG1OPDR | 015 | EQFN | CAP | 100000 | 99047 | 99047 | 953 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 007 | SVCS | CAP | 16000 | 0 | 0 | 16000 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 015 | CONS | CAP | 46000 | 0 | 0 | 46000 | 12/15/2017
850 | SIROVICH FIRE CODE COMPLIANCE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR2 | 014 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 104 | CTGY | CAP | 0 | 56000 | 56000 | -56000 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 110 | CONS | CAP | 2178000 | 2178000 | 2178000 | 0 | 12/15/2017
850 | SIROVICH ROOF TERRACE | 125 | DEPARTMENT FOR THE AGING | AG1SIRRTE | 003 | SVCS | CAP | 2000 | 0 | 0 | 2000 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 102 | CONS | CAP | 158000 | 156339 | 156339 | 1661 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 108 | CONS | CAP | 2000 | 0 | 0 | 2000 | 12/15/2017
850 | NEW CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-QUEEN | 003 | IFDS | IFA | 11000 | 11000 | 11000 | 0 | 12/15/2017
850 | KINGSBAY SENIOR CENTER, BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | AGC001KBC | 020 | IFSP | IFA | 109000 | 108419 | 108419 | 581 | 12/15/2017
850 | WOODSIDE SENIOR CENTER RECONSTRUCTION | 125 | DEPARTMENT FOR THE AGING | AGCWOODRE | 012 | CONS | CAP | 65000 | 0 | 0 | 65000 | 12/15/2017
850 | JASA BRONX GROUP SERVICES | 125 | DEPARTMENT FOR THE AGING | AGX001LC | 003 | DSGN | CAP | 10000 | 0 | 0 | 10000 | 12/15/2017
850 | RECONSTRUCTION OF ARMORIES IN BKLYN. AND THE BRONX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ARMORIES | 008 | IFSP | IFA | 114000 | 114000 | 114000 | 0 | 12/15/2017
850 | BORINGS, FY'99 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10II | 003 | SVCS | CAP | 65000 | 64696 | 64696 | 304 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY05-6 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10SS | 003 | IFOT | IFA | 120000 | 0 | 0 | 120000 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY08-9 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10TT | 003 | IFOT | IFA | 120000 | 0 | 0 | 120000 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10WW | 008 | SVCS | CAP | 300000 | 199999 | 189999 | 100001 | 12/15/2017
850 | DIST MAIN IMPROVEMENT DUE TO REMOVAL OF HP SYSTEM | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-753 | 004 | CONS | CAP | 4258000 | 0 | 0 | 4258000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 010 | CONS | CAP | -669000 | 0 | 0 | -669000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 030 | IFSP | IFA | 840000 | 16415 | 16415 | 823585 | 12/15/2017
850 | REPLACE WATER MAIN IN CRESCENT ST, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-762 | 004 | IFSP | IFA | 95000 | 94650 | 94650 | 350 | 12/15/2017
850 | REPLACE WATER MAIN IN CROPSEY AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-763 | 007 | CONS | CAP | 8985000 | 8982431 | 8636033 | 2569 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 20B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-765 | 016 | IFSP | IFA | 50000 | 48442 | 48442 | 1558 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 22B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-767 | 012 | IFSP | IFA | 39000 | 18507 | 18507 | 20493 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 016 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 018 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | OBCC BATHRM & SHWR FLOORS | 072 | DEPARTMENT OF CORRECTION | C124-FLOR | 015 | CONS | CAP | 6000 | 0 | 0 | 6000 | 12/15/2017
850 | POWERHOUSE WALL REHAB | 072 | DEPARTMENT OF CORRECTION | C130-PIPE | 006 | CTGY | CAP | 10000 | 0 | 0 | 10000 | 12/15/2017
850 | CEILING RECON JATC,RI (W/C75-TRRF) | 072 | DEPARTMENT OF CORRECTION | C135-ROOF | 001 | CONS | CAP | -44000 | 0 | 0 | -44000 | 12/15/2017
850 | CEILING RECON JATC,RI (W/C75-TRRF) | 072 | DEPARTMENT OF CORRECTION | C135-ROOF | 010 | CONS | CAP | 6000 | 0 | 0 | 6000 | 12/15/2017
850 | CEILING RECON JATC,RI (W/C75-TRRF) | 072 | DEPARTMENT OF CORRECTION | C135-ROOF | 017 | CONS | CAP | 4000 | 0 | 0 | 4000 | 12/15/2017
850 | CEILING RECON JATC,RI (W/C75-TRRF) | 072 | DEPARTMENT OF CORRECTION | C135-ROOF | 025 | CTGY | CAP | 2900000 | 0 | 0 | 2900000 | 12/15/2017
850 | CEILING RECON JATC,RI (W/C75-TRRF) | 072 | DEPARTMENT OF CORRECTION | C135-ROOF | 028 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | JATC RECONSTRUCTION-PHASE 2 | 072 | DEPARTMENT OF CORRECTION | C135JATC | 004 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LIFE/FIRE SAFETY UPGRADE @ 4 BORO FACILITIES | 072 | DEPARTMENT OF CORRECTION | C138-FIRE | 002 | DSGN | CAP | 72000 | 71538 | 71538 | 462 | 12/15/2017
850 | REPLACEMENT OF PARAPETS | 072 | DEPARTMENT OF CORRECTION | C138-PARA | 033 | IFSP | IFA | 1005000 | 953835 | 953835 | 51165 | 12/15/2017
850 | BROS & RIKERS ISLAND REFURBISHING PLAN | 072 | DEPARTMENT OF CORRECTION | C138-RIRP | 001 | DSGN | CAP | 6434000 | 0 | 0 | 6434000 | 12/15/2017
850 | BROS & RIKERS ISLAND REFURBISHING PLAN | 072 | DEPARTMENT OF CORRECTION | C138-RIRP | 002 | IFDS | IFA | 3000 | 2913 | 2913 | 87 | 12/15/2017
850 | BKLYN HDM - FIRE LIFE SAFETY | 072 | DEPARTMENT OF CORRECTION | C138BKFIR | 019 | CONS | CAP | 1000 | 0 | 0 | 1000 | 12/15/2017
850 | FIRE/LIFE SAFETY DEFERRED FACILITIES | 072 | DEPARTMENT OF CORRECTION | C138DEFIR | 018 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | FIRE/LIFE SAFETY (WEST SIDE) | 072 | DEPARTMENT OF CORRECTION | C138FIR-C | 012 | CONS | CAP | 740000 | 676331 | 676331 | 63669 | 12/15/2017
850 | FIRE/LIFE SAFETY RIKERS IS (EAST SIDE) | 072 | DEPARTMENT OF CORRECTION | C138FIR-D | 002 | DSGN | CAP | 206000 | 0 | 0 | 206000 | 12/15/2017
850 | FIRE/LIFE SAFETY RIKERS IS (EAST SIDE) | 072 | DEPARTMENT OF CORRECTION | C138FIR-D | 012 | CTGY | CAP | 1602000 | 0 | 0 | 1602000 | 12/15/2017
850 | WATER DISTRIBUTION SYSTEM AT RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C138WDIST | 003 | CONS | CAP | 287000 | 196435 | 196404 | 90565 | 12/15/2017
850 | COURTYARD WORK AT GRVC AND RMSC | 072 | DEPARTMENT OF CORRECTION | C139-YARD | 002 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | COURTYARD WORK AT GRVC AND RMSC | 072 | DEPARTMENT OF CORRECTION | C139-YARD | 003 | DSGN | CAP | 27000 | 26903 | 26903 | 97 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 006 | DSGN | CAP | 126000 | 0 | 0 | 126000 | 12/15/2017
850 | COOK SERVE #2---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV2 | 013 | DSGN | CAP | -272000 | 0 | 0 | -272000 | 12/15/2017
850 | COOK SERVE #3---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV3 | 007 | CTGY | CAP | 4683000 | 0 | 0 | 4683000 | 12/15/2017
850 | RECONSTRUCTION BKLYN COURTS | 072 | DEPARTMENT OF CORRECTION | C75-BKCON | 014 | CTGY | CAP | 250000 | 0 | 0 | 250000 | 12/15/2017
850 | RECONSTRUCTION BKLYN COURTS | 072 | DEPARTMENT OF CORRECTION | C75-BKCON | 027 | IFSP | IFA | 150000 | 149999 | 149999 | 1 | 12/15/2017
850 | INSTALLATION OF UNDER GROUND ETHANOL STORAGE TANKS-TRANS. | 072 | DEPARTMENT OF CORRECTION | C75-ETHAN | 013 | CONS | CAP | 102000 | 102029 | 102029 | -29 | 12/15/2017
850 | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 072 | DEPARTMENT OF CORRECTION | C75-FCAD | 016 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRONX HDM RENO | 072 | DEPARTMENT OF CORRECTION | C75BXRENO | 012 | DSGN | CAP | 96000 | 95054 | 95054 | 946 | 12/15/2017
850 | BRONX HDM RENO | 072 | DEPARTMENT OF CORRECTION | C75BXRENO | 019 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | VARIOUS FACADE REPAIRS | 072 | DEPARTMENT OF CORRECTION | C75FCADE | 001 | DSGN | CAP | 6000 | 0 | 0 | 6000 | 12/15/2017
850 | DCLA: MMA - Air Handler Replacements: EHVAC-1 & EHVAC-2 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | ACEDCA435 | 001 | CONS | CAP | 835000 | 834800 | 793060 | 200 | 12/15/2017
850 | BELLEVUE INTAKE CENTER | 096 | HUMAN RESOURCES ADMINISTRATION | ACSBELL | 039 | CONS | CAP | -18824000 | 0 | 0 | -18824000 | 12/15/2017
850 | LIRA MOTT SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AG-1LIMOT | 009 | CTGY | CAP | 19000 | 4634 | 4634 | 14366 | 12/15/2017
850 | BETANCES KITCHEN & ANSUL SUPP(VAR SITES) | 125 | DEPARTMENT FOR THE AGING | AG1BKE | 015 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 013 | CONS | CAP | 149000 | 0 | 0 | 149000 | 12/15/2017
850 | SIROVICH ROOF AND PARAPET | 125 | DEPARTMENT FOR THE AGING | AG1SIRR | 016 | CONS | CAP | 10000 | 0 | 0 | 10000 | 12/15/2017
850 | SIROVICH-INT WATER DAMAGE REPAIR AND RENOVATIONS | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4 | 010 | CONS | CAP | 33000 | 0 | 0 | 33000 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 111 | CONS | CAP | 557000 | 556000 | 556000 | 1000 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 113 | IFSP | IFA | 13000 | 12614 | 12614 | 386 | 12/15/2017
850 | SIROVICH SR CTR-INFRASTRUCTURE | 125 | DEPARTMENT FOR THE AGING | AG1SIRR4P | 116 | CONS | CAP | 397000 | 396340 | 396340 | 660 | 12/15/2017
850 | LENOX HILL PLAZA | 125 | DEPARTMENT FOR THE AGING | AGC-LENPL | 108 | EQFN | CAP | 5000 | 6935 | 6935 | -1935 | 12/15/2017
850 | NEW CENTER | 125 | DEPARTMENT FOR THE AGING | AGC-QUEEN | 011 | IFSP | IFA | 55000 | 0 | 0 | 55000 | 12/15/2017
850 | HOPE GARDENS/ADA (FRONT DOOR) | 125 | DEPARTMENT FOR THE AGING | AGC001HGM | 001 | DSGN | CAP | 2000 | 0 | 0 | 2000 | 12/15/2017
850 | KINGSBAY SENIOR CENTER, BROOKLYN | 096 | HUMAN RESOURCES ADMINISTRATION | AGC001KBC | 002 | DSGN | CAP | 17000 | 0 | 0 | 17000 | 12/15/2017
850 | NEW DORP SEN CENTER | 125 | DEPARTMENT FOR THE AGING | AGC001NDF | 017 | DSGN | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | NYCHANGE PROJECT WITH DFTA | 125 | DEPARTMENT FOR THE AGING | AGNYCHANG | 007 | CONS | CAP | 1734000 | 0 | 0 | 1734000 | 12/15/2017
850 | TODT HILL SENIOR CENTER - A/C SYSTEMS | 125 | DEPARTMENT FOR THE AGING | AGR001TAC | 006 | SVCS | CAP | -1000 | 0 | 0 | -1000 | 12/15/2017
850 | JASA BRONX GROUP SERVICES | 125 | DEPARTMENT FOR THE AGING | AGX001LC | 005 | SVCS | CAP | 16000 | 0 | 0 | 16000 | 12/15/2017
850 | SEWER CONSTRUCTION | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWC | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACE SEWER | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWR | 002 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REPLACE SEWER | 826 | DEPT OF ENVIRONMENTAL PROTECTION | AUGSEWR | 007 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BORING, FY01 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10LL | 003 | SVCS | CAP | 1020000 | 948284 | 948284 | 71716 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS, FY08-9 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BC-10TT | 004 | SVCS | CAP | 41000 | 0 | 0 | 41000 | 12/15/2017
850 | SERVICE CONTRACT FOR BORINGS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | BC-10XX | 004 | SVCS | CAP | 600000 | 599999 | 38771 | 1 | 12/15/2017
850 | REPLACE 6 IN MAINS, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-744 | 006 | IFSP | IFA | 66000 | 65606 | 65606 | 394 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 006 | CNSP | CAP | 1570000 | 275000 | 275000 | 1295000 | 12/15/2017
850 | REPLACE WATER MAIN IN CLINTON STREET, BROOKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-759 | 018 | CONS | CAP | 82000 | 0 | 0 | 82000 | 12/15/2017
850 | REPLACE WATER MAIN IN CRESCENT ST, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-762 | 600 | IFSP | IFA | 16000 | 16000 | 16000 | 0 | 12/15/2017
850 | REPLACE WATER MAIN IN CROPSEY AVE, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-763 | 012 | CONS | CAP | 344000 | 329602 | 329602 | 14398 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 20B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-765 | 015 | IFSP | IFA | 138000 | 137156 | 137156 | 844 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 014 | CONS | CAP | 99000 | 0 | 0 | 99000 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 21B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-766 | 003 | IFSP | IFA | 320000 | 319151 | 319151 | 849 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 21B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-766 | 008 | CONS | CAP | 43000 | 41836 | 41836 | 1164 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 22B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-767 | 001 | CONS | CAP | 11483000 | 11340804 | 11022148 | 142196 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 010 | CONS | CAP | 84000 | 83703 | 54404 | 297 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 013 | CONS | CAP | 15000 | 0 | 0 | 15000 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 019 | IFSP | IFA | 22000 | 21138 | 21138 | 862 | 12/15/2017
850 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-776 | 603 | IFDS | IFA | 50000 | 0 | 0 | 50000 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 014 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | DC1 | CONS | CAP | 964000 | 963999 | 826690 | 1 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 005 | CNSP | CAP | 1052000 | 1050840 | 1050840 | 1160 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 604 | IFSP | IFA | 102000 | 0 | 0 | 102000 | 12/15/2017
850 | wm & Comb swr replacment. Williamsbug bridge plaza, bklyn | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-797 | 601 | IFDS | IFA | 100000 | 0 | 0 | 100000 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 014 | CONS | CAP | 4000 | 3823 | 0 | 177 | 12/15/2017
850 | BRONX ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT2 | 004 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRONX ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT2 | 012 | IFSP | IFA | 48000 | 47231 | 47231 | 769 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 030 | CONS | CAP | 6298000 | 6297185 | 6297185 | 815 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 040 | CNSP | CAP | 278000 | 277699 | 277699 | 301 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 041 | CONS | CAP | 142000 | 138861 | 138861 | 3139 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 010 | CONS | CAP | 371000 | 371000 | 371000 | 0 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 017 | CONS | CAP | 2581000 | 2581000 | 2581000 | 0 | 12/15/2017
850 | 200 DORMITORY BEDS AT ARDC | 072 | DEPARTMENT OF CORRECTION | C114ARDC | 004 | CONS | CAP | 1862000 | 1862063 | 1862063 | -63 | 12/15/2017
850 | 200 DORMITORY BEDS AT ARDC | 072 | DEPARTMENT OF CORRECTION | C114ARDC | 009 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | MODULAR & SPRUNGS TAKE DOWNS - CAPACITY REPLACEMENT PROGRAM | 072 | DEPARTMENT OF CORRECTION | C114CAPTD | 007 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 036 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | GRVC Core Renovation | 072 | DEPARTMENT OF CORRECTION | C114GRVC | 001 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | PERM ELEC FOR EAST/WEST (CON ED TIE-INS) | 072 | DEPARTMENT OF CORRECTION | C114MBE3B | 004 | CONS | CAP | 3433000 | 3430070 | 3430070 | 2930 | 12/15/2017
850 | PERM ELEC FOR EAST/WEST (CON ED TIE-INS) | 072 | DEPARTMENT OF CORRECTION | C114MBE3B | 011 | CONS | CAP | 707000 | 706493 | 706493 | 507 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 001 | SVCS | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 026 | CONS | CAP | 9000 | 0 | 0 | 9000 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 034 | CTGY | CAP | 1960000 | 0 | 0 | 1960000 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 035 | CONS | CAP | 20000 | 20000 | 20000 | 0 | 12/15/2017
850 | NIC SHOWER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C75NICSHW | 007 | IFSP | IFA | 1825000 | 1719999 | 1687201 | 105001 | 12/15/2017
850 | NIC SHOWER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C75NICSHW | 014 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | REC VISITOR PROCESSING BLDG | 072 | DEPARTMENT OF CORRECTION | C75VISIT | 006 | IFSP | IFA | 2000 | 1263 | 1263 | 737 | 12/15/2017
850 | REPLACEMENT OF ELEVATOR SYSTEMS | 072 | DEPARTMENT OF CORRECTION | C76ELEV1 | 002 | IFSP | IFA | 24000 | 24000 | 24000 | 0 | 12/15/2017
850 | REPLACEMENT OF ELEVATOR SYSTEMS | 072 | DEPARTMENT OF CORRECTION | C76ELEV1 | 009 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | MAIN,AMKC,K, & GMDC DORMS SHOWERS | 072 | DEPARTMENT OF CORRECTION | C95MAIN | 007 | CTGY | CAP | 625000 | 0 | 0 | 625000 | 12/15/2017
850 | MAIN,AMKC,K, & GMDC DORMS SHOWERS | 072 | DEPARTMENT OF CORRECTION | C95MAIN | 011 | CONS | CAP | 565000 | 564920 | 559271 | 80 | 12/15/2017
850 | MAIN,AMKC,K, & GMDC DORMS SHOWERS | 072 | DEPARTMENT OF CORRECTION | C95MAIN | 034 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CONVERSION OF MENTAL HEALTH CENTER MOD1 TO SINGLE CELLS | 072 | DEPARTMENT OF CORRECTION | C95MENTAL | 001 | DSGN | CAP | 21000 | 20920 | 20920 | 80 | 12/15/2017
850 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CC1C3 | 008 | CONS | CAP | 137000 | 0 | 0 | 137000 | 12/15/2017
850 | CITY HALL RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CITYHALL2 | 003 | CONS | CAP | 921000 | 0 | 0 | 921000 | 12/15/2017
850 | FACIILITY RENOVATIONS AT CROSSROADS JC | 068 | ADMIN. FOR CHILDREN'S SERVICES | CJCREN | 012 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | QNS CRIMINAL ANNEX("Q1")CONT FROM CO264418 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO264418A | 038 | CONS | CAP | 37000 | 0 | 0 | 37000 | 12/15/2017
850 | QNS CRIMINAL ANNEX("Q1")CONT FROM CO264418 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO264418A | 042 | CONS | CAP | 13000 | 0 | 0 | 13000 | 12/15/2017
850 | QNS CRIMINAL ANNEX("Q1")CONT FROM CO264418 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO264418A | 049 | CONS | CAP | 10000 | 0 | 0 | 10000 | 12/15/2017
850 | NBHC FY98- FY99 COS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO270CO98 | 051 | CONS | CAP | 287000 | 287682 | 287682 | -682 | 12/15/2017
850 | 120 SCHERMERHORN ST.- FIRE ALARM/DETECTION | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO281FA | 003 | DSGN | CAP | 202000 | 202298 | 169894 | -298 | 12/15/2017
850 | 120 SCHERMERHORN ST.- INTERIOR RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO281K-CR | 127 | CTGY | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 120 SCHERMERHORN ST.- INTERIOR RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO281K-CR | 129 | EQFN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 120 SCHERMERHORN ST.- INTERIOR RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO281K-CR | 141 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 111 CENTRE ST.- EXTERIOR | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO284EXT2 | 100 | IFSP | IFA | 233000 | 232999 | 174321 | 1 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 039 | CONS | CAP | 19386000 | 0 | 0 | 19386000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 137 | SVCS | CAP | -6000 | 0 | 0 | -6000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 138 | EQFN | CAP | -1000 | 0 | 0 | -1000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 143 | CNSP | CAP | 26000 | 0 | 0 | 26000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 150 | EQFN | CAP | 13000 | 0 | 0 | 13000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 191 | CONS | CAP | 63000 | 0 | 0 | 63000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 195 | CNSP | CAP | 1000 | 0 | 0 | 1000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 231 | CNSP | CAP | 40000 | 0 | 0 | 40000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 298 | CNSP | CAP | -1000 | 0 | 0 | -1000 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768A | 004 | IFDS | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-776 | 002 | CONS | CAP | 2872000 | 0 | 0 | 2872000 | 12/15/2017
850 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-776 | 004 | CNSP | CAP | 1500000 | 0 | 0 | 1500000 | 12/15/2017
850 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-776 | 601 | IFDS | IFA | 300000 | 300000 | 300000 | 0 | 12/15/2017
850 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-776 | 604 | IFSP | IFA | 0 | 0 | 0 | 0 | 12/15/2017
850 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-776 | 623 | IFOT | IFA | 35000 | 10000 | 10000 | 25000 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 601 | IFDS | IFA | 65000 | 65000 | 65000 | 0 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 621 | IFDS | IFA | 50000 | 24999 | 14489 | 25001 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 651 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 019 | CNSP | CAP | 83000 | 82420 | 82420 | 580 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 008 | CONS | CAP | 189000 | 189000 | 189000 | 0 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 009 | CONS | CAP | 63000 | 63000 | 63000 | 0 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 606 | IFSP | IFA | 74000 | 0 | 0 | 74000 | 12/15/2017
850 | RECON OF WM IN KINGSTON AVE BTW EASTERN PKWY & EMPIRE BLVD | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-787 | 601 | IFDS | IFA | 700000 | 0 | 0 | 700000 | 12/15/2017
850 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-794 | 603 | IFDS | IFA | 61000 | 0 | 0 | 61000 | 12/15/2017
850 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-794 | 606 | IFSP | IFA | 61000 | 0 | 0 | 61000 | 12/15/2017
850 | Replacement of Water Mains in Avenue S | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-809 | 001 | CONS | CAP | 22756000 | 0 | 0 | 22756000 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 603 | IFDS | IFA | 1709000 | 700000 | 700000 | 1009000 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 606 | IFSP | IFA | 20000 | 0 | 0 | 20000 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-001 | 601 | IFDS | IFA | 1300000 | 49999 | 11474 | 1250001 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-002 | 602 | IFDS | IFA | 50000 | 0 | 0 | 50000 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 009 | CTGY | CAP | 808000 | 0 | 0 | 808000 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 106 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 111 | IFDS | IFA | 30000 | 0 | 0 | 30000 | 12/15/2017
850 | BRONX ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT2 | 001 | DSGN | CAP | 16000 | 0 | 0 | 16000 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 009 | CONS | CAP | 32000 | 32224 | 32224 | -224 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 025 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 006 | CTGY | CAP | 250000 | 0 | 0 | 250000 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 011 | CTGY | CAP | 5000000 | 0 | 0 | 5000000 | 12/15/2017
850 | CIFM STAFF LOCKERS | 072 | DEPARTMENT OF CORRECTION | C114DDMOD | 017 | IFSP | IFA | 70000 | 30924 | 30924 | 39076 | 12/15/2017
850 | CIFM FENCE | 072 | DEPARTMENT OF CORRECTION | C114FENCE | 001 | CONS | CAP | 1916000 | 1915100 | 1915100 | 900 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 017 | CONS | CAP | 21000 | 19987 | 19987 | 1013 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 002 | CONS | CAP | 7090000 | 7089677 | 1487176 | 323 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 013 | CONS | CAP | 12000 | 11305 | 0 | 695 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 021 | CNSP | CAP | 488000 | 487031 | 476356 | 969 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T Carlton & portland | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778A | 001 | CONS | CAP | 1898000 | 0 | 0 | 1898000 | 12/15/2017
850 | WM & Sewer work in Atlantic Ave (HWD10105, NDF-ATLAV) | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-785A | 603 | IFDS | IFA | 126000 | 0 | 0 | 126000 | 12/15/2017
850 | WM replacement Hamilton ave gowanus connector, BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-802 | 001 | CONS | CAP | 1600000 | 0 | 0 | 1600000 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 010 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 651 | IFOT | IFA | 20000 | 10000 | 10000 | 10000 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-001 | 003 | CONS | CAP | 402000 | 401748 | 158641 | 252 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-001 | 010 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-001 | 015 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BROOKLYN ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BKDETCT2 | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BROOKLYN ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BKDETCT2 | 013 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 101 | DSGN | CAP | 192000 | 191653 | 191653 | 347 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 109 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 010 | CTGY | CAP | 1900000 | 0 | 0 | 1900000 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 013 | CTGY | CAP | 915000 | 0 | 0 | 915000 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 055 | IFSP | IFA | 285000 | 183639 | 183639 | 101361 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 056 | CONS | CAP | 206000 | 0 | 0 | 206000 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 010 | CTGY | CAP | 1085000 | 0 | 0 | 1085000 | 12/15/2017
850 | EGRESS STAIRS AT B'KLYN HOUSE OF DETENTION | 072 | DEPARTMENT OF CORRECTION | C104EGRES | 005 | CONS | CAP | 108000 | 0 | 0 | 108000 | 12/15/2017
850 | EGRESS STAIRS AT B'KLYN HOUSE OF DETENTION | 072 | DEPARTMENT OF CORRECTION | C104EGRES | 011 | CNSP | CAP | 1016000 | 969464 | 969464 | 46536 | 12/15/2017
850 | 200 DORMITORY BEDS AT ARDC | 072 | DEPARTMENT OF CORRECTION | C114ARDC | 002 | CNSP | CAP | 2396000 | 0 | 0 | 2396000 | 12/15/2017
850 | CIFM STAFF LOCKERS | 072 | DEPARTMENT OF CORRECTION | C114DDMOD | 010 | CONS | CAP | 151000 | 150040 | 142538 | 960 | 12/15/2017
850 | CIFM FENCE | 072 | DEPARTMENT OF CORRECTION | C114FENCE | 002 | CNSP | CAP | 208000 | 205520 | 205520 | 2480 | 12/15/2017
850 | CIFM FENCE | 072 | DEPARTMENT OF CORRECTION | C114FENCE | 004 | CTGY | CAP | 240000 | 0 | 0 | 240000 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 028 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 012 | CONS | CAP | 12000 | 0 | 0 | 12000 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 019 | CONS | CAP | 6000 | 0 | 0 | 6000 | 12/15/2017
850 | EAST/WEST PERMANENT POWER ENGINE GENERATOR | 072 | DEPARTMENT OF CORRECTION | C114MBE3C | 006 | CONS | CAP | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | PERM ELEC FOR EAST/WEST (CON ED TIE-INS) | 072 | DEPARTMENT OF CORRECTION | C114MBE3B | 006 | IFSP | IFA | 898000 | 897128 | 897128 | 872 | 12/15/2017
850 | EAST/WEST PERMANENT POWER ENGINE GENERATOR | 072 | DEPARTMENT OF CORRECTION | C114MBE3C | 001 | CONS | CAP | 4055000 | 4054124 | 4054124 | 876 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 016 | CONS | CAP | 2000 | 0 | 0 | 2000 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 021 | CONS | CAP | 4000 | 0 | 0 | 4000 | 12/15/2017
850 | NEW RIKERS ISLAND FACILITY | 072 | DEPARTMENT OF CORRECTION | C114NEWRI | 001 | DSGN | CAP | 34085000 | 34085233 | 14456616 | -233 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 002 | CONS | CAP | 3912000 | 3912383 | 3912383 | -383 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 024 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 034 | CONS | CAP | 2066000 | 2065999 | 2057397 | 1 | 12/15/2017
850 | VISIT HOUSE | 072 | DEPARTMENT OF CORRECTION | C114VHCIF | 009 | CONS | CAP | 72000 | 0 | 0 | 72000 | 12/15/2017
850 | OBCC BATHRM & SHWR FLOORS | 072 | DEPARTMENT OF CORRECTION | C124-FLOR | 005 | IFSP | IFA | 207000 | 206920 | 206920 | 80 | 12/15/2017
850 | OBCC SHOWER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C124-SHWR | 008 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ALTERATIONS TO POWER PLANT AT RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C130-P1 | 021 | CONS | CAP | 14000 | 0 | 0 | 14000 | 12/15/2017
850 | ALTERATIONS TO POWER PLANT AT RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C130-P1 | 042 | CTGY | CAP | 59000 | 0 | 0 | 59000 | 12/15/2017
850 | POWERHOUSE WALL REHAB | 072 | DEPARTMENT OF CORRECTION | C130-PIPE | 004 | CTGY | CAP | 50000 | 0 | 0 | 50000 | 12/15/2017
850 | POWERHOUSE FEED WATER PUMP INSTALLATION | 072 | DEPARTMENT OF CORRECTION | C130PPUMP | 007 | DSGN | CAP | 82000 | 514227 | 514227 | -432227 | 12/15/2017
850 | MENTAL HEALTH INFIRMARY,R I (W/C-141) | 072 | DEPARTMENT OF CORRECTION | C133INFRM | 012 | CTGY | CAP | 22500000 | 0 | 0 | 22500000 | 12/15/2017
850 | JATC INTERIOR RENO | 072 | DEPARTMENT OF CORRECTION | C135-RENO | 003 | DSGN | CAP | 237000 | 28907 | 28907 | 208093 | 12/15/2017
850 | JATC INTERIOR RENO | 072 | DEPARTMENT OF CORRECTION | C135-RENO | 011 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | JATC INTERIOR RENO | 072 | DEPARTMENT OF CORRECTION | C135-RENO | 035 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | JATC INTERIOR RENO | 072 | DEPARTMENT OF CORRECTION | C135-RENO | 036 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BROOKLYN CORRECTIONAL FACILITY SPRINKLER SYSTEM | 072 | DEPARTMENT OF CORRECTION | C138-BCF | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | LIFE/FIRE SAFETY UPGRADE @ 4 BORO FACILITIES | 072 | DEPARTMENT OF CORRECTION | C138-FIRE | 018 | CONS | CAP | 530000 | 530000 | 530000 | 0 | 12/15/2017
850 | FIRE/LIFE SAFETY DEFERRED FACILITIES | 072 | DEPARTMENT OF CORRECTION | C138DEFIR | 012 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | FIRE/LIFE SAFETY DEFERRED FACILITIES | 072 | DEPARTMENT OF CORRECTION | C138DEFIR | 017 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | FIRE/LIFE SAFETY RIKERS IS (EAST SIDE) | 072 | DEPARTMENT OF CORRECTION | C138FIR-D | 001 | DSGN | CAP | 108000 | 0 | 0 | 108000 | 12/15/2017
850 | FIRE/LIFE SAFETY RIKERS IS (EAST SIDE) | 072 | DEPARTMENT OF CORRECTION | C138FIR-D | 025 | IFSP | IFA | 450000 | 450000 | 450000 | 0 | 12/15/2017
850 | SMOKE DETECTION SYSTEM | 072 | DEPARTMENT OF CORRECTION | C138SMOKE | 008 | DSGN | CAP | 37000 | 0 | 0 | 37000 | 12/15/2017
850 | GRVC & RMSC YARD RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C139-500 | 008 | DSGN | CAP | 378000 | 277493 | 277493 | 100507 | 12/15/2017
850 | GRVC & RMSC YARD RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C139-500 | 011 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | GRVC WATER MAIN REPLACEMENT | 072 | DEPARTMENT OF CORRECTION | C139-WTMN | 003 | DSGN | CAP | 1000 | 72113 | 72113 | -71113 | 12/15/2017
850 | COURTYARD WORK AT GRVC AND RMSC | 072 | DEPARTMENT OF CORRECTION | C139-YARD | 001 | SVCS | CAP | 39000 | 2437677 | 2426360 | -2398677 | 12/15/2017
850 | COOK/SERVE #1---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV1 | 054 | IFSP | IFA | 750000 | 749999 | 749999 | 1 | 12/15/2017
850 | CITY HALL-SOLAR PANEL INSTALLATION | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CHSOLAR | 002 | DSGN | CAP | 264000 | 124999 | 106723 | 139001 | 12/15/2017
850 | CITY HALL RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CITYHALL2 | 005 | CONS | CAP | 54680000 | 0 | 0 | 54680000 | 12/15/2017
850 | CITY HALL RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CITYHALL2 | 007 | EQFN | CAP | -53000 | 32215 | 32215 | -85215 | 12/15/2017
850 | CITY HALL RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CITYHALL2 | 013 | SVCS | CAP | 24000 | 23823215 | 23771199 | -23799215 | 12/15/2017
850 | QNS CRIMINAL ANNEX("Q1")CONT FROM CO264418 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO264418A | 023 | CONS | CAP | 9000 | 0 | 0 | 9000 | 12/15/2017
850 | QNS CRIMINAL ANNEX("Q1")CONT FROM CO264418 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO264418A | 044 | CONS | CAP | -14000 | 0 | 0 | -14000 | 12/15/2017
850 | NBHC FY98- FY99 COS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO270CO98 | 017 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | NBHC FY98- FY99 COS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO270CO98 | 049 | DSGN | CAP | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | 120 SCHERMERHORN ST.- INTERIOR RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO281K-CR | 003 | CONS | CAP | 23636000 | 23636000 | 23636000 | 0 | 12/15/2017
850 | 120 SCHERMERHORN ST.- INTERIOR RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO281K-CR | 121 | EQFN | CAP | 74000 | 73634 | 73634 | 366 | 12/15/2017
850 | 120 SCHERMERHORN ST.- INTERIOR RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO281K-CR | 124 | CONS | CAP | 600000 | 600000 | 600000 | 0 | 12/15/2017
850 | 120 SCHERMERHORN ST.- CODE COMPLIANT TOILET UPGRADE | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO281TOIL | 005 | IFOT | IFA | 7000 | 0 | 0 | 7000 | 12/15/2017
850 | 111 CENTRE STREET - RECONSTRUCTION OF THE SIDEWALK | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO284SW | 002 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 012 | EQFN | CAP | 121000 | 0 | 0 | 121000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 037 | CONS | CAP | 72345000 | 72344487 | 72344487 | 513 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 049 | CONS | CAP | -1514000 | 0 | 0 | -1514000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 054 | SVCS | CAP | 1167000 | 2957796 | 2424765 | -1790796 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 140 | CONS | CAP | -12000 | 0 | 0 | -12000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 146 | DSGN | CAP | 6000 | 0 | 0 | 6000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 153 | CONS | CAP | 239000 | 0 | 0 | 239000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 154 | SVCS | CAP | 9000 | 0 | 0 | 9000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 206 | SVCS | CAP | 23000 | 0 | 0 | 23000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 277 | EQFN | CAP | -1000 | 0 | 0 | -1000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 288 | CONS | CAP | 38000 | 0 | 0 | 38000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 307 | CONS | CAP | 47000 | 0 | 0 | 47000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 312 | SVCS | CAP | 1000 | 0 | 0 | 1000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 313 | CONS | CAP | 15000 | 0 | 0 | 15000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 317 | SVCS | CAP | 34000 | 0 | 0 | 34000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 319 | DSGN | CAP | 13000 | 0 | 0 | 13000 | 12/15/2017
850 | COOK SERVE #2---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV2 | 016 | DSGN | CAP | 56000 | 53930 | 53930 | 2070 | 12/15/2017
850 | COOK SERVE #3---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV3 | 001 | DSGN | CAP | 3542000 | 0 | 0 | 3542000 | 12/15/2017
850 | COOK SERVE #3---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV3 | 002 | IFDS | IFA | 50000 | 49999 | 49999 | 1 | 12/15/2017
850 | COOK SERVE #3---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV3 | 006 | CONS | CAP | 245000 | 0 | 0 | 245000 | 12/15/2017
850 | COOK SERVE #3---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV3 | 006 | DSGN | CAP | 10000 | 9250 | 9250 | 750 | 12/15/2017
850 | RECONSTRUCTION BKLYN COURTS | 072 | DEPARTMENT OF CORRECTION | C75-BKCON | 018 | CONS | CAP | 271000 | 0 | 0 | 271000 | 12/15/2017
850 | RECONSTRUCTION BKLYN COURTS | 072 | DEPARTMENT OF CORRECTION | C75-BKCON | 023 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | EPA SPILL PREVENTION AND RESPONSE PLAN | 072 | DEPARTMENT OF CORRECTION | C75-EPA | 006 | IFDS | IFA | 255000 | 224999 | 204822 | 30001 | 12/15/2017
850 | AMKC K DORM AIR CONDITIONING | 072 | DEPARTMENT OF CORRECTION | C75AMKCAC | 002 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | MDC FACADE RECONSTRUCTION - PHASE 11 | 072 | DEPARTMENT OF CORRECTION | C75FCADE3 | 003 | CONS | CAP | 1967000 | 1968235 | 1968235 | -1235 | 12/15/2017
850 | NIC SHOWER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C75NICSHW | 010 | CONS | CAP | 2151000 | 0 | 0 | 2151000 | 12/15/2017
850 | NIC SHOWER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C75NICSHW | 017 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | STEAM UTILITY TUNNEL,RI | 072 | DEPARTMENT OF CORRECTION | C75TUNNEL | 021 | CONS | CAP | 103000 | 103000 | 103000 | 0 | 12/15/2017
850 | REPLACEMENT OF ELEVATOR SYSTEM AT CIFM | 072 | DEPARTMENT OF CORRECTION | C76-ELEV | 001 | SVCS | CAP | 4000 | 0 | 0 | 4000 | 12/15/2017
850 | REPLACEMENT OF ELEVATOR SYSTEMS | 072 | DEPARTMENT OF CORRECTION | C76ELEV1 | 003 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 1 CENTRE ST.- OFFICES FROM 49-51 CHAMBERS ST. - 21C3 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CC1C3 | 010 | CONS | CAP | 36000 | 0 | 0 | 36000 | 12/15/2017
850 | Channel 13 WNET | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CCN6WNET | 001 | EQFN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CITY HALL RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CITYHALL2 | 013 | CONS | CAP | 22089000 | 0 | 0 | 22089000 | 12/15/2017
850 | CITY LIGHTS - STREET LIGHTING PROJECTS | 850 | DEPT. OF DESIGN & CONSTRUCTION | CITYLIGHT | 004 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | FACIILITY RENOVATIONS AT CROSSROADS JC | 068 | ADMIN. FOR CHILDREN'S SERVICES | CJCREN | 003 | DSGN | CAP | 5502000 | 0 | 0 | 5502000 | 12/15/2017
850 | OCME - Fire Alarm System Upgrade at 520 First Avenue | 816 | DEPARTMENT OF HEALTH | CME520BDG | 003 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | QNS CRIMINAL ANNEX("Q1")CONT FROM CO264418 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO264418A | 017 | CONS | CAP | 14000 | 0 | 0 | 14000 | 12/15/2017
850 | NBHC FY98- FY99 COS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO270CO98 | 004 | CONS | CAP | 18000 | 0 | 0 | 18000 | 12/15/2017
850 | 360 ADAMS ST.- CONVERSION TO CIVIL COURT | 312 | CONFLICTS OF INTEREST BOARD | CO278CONV | 004 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 360 ADAMS ST.- CONVERSION TO CIVIL COURT | 312 | CONFLICTS OF INTEREST BOARD | CO278CONV | 005 | CONS | CAP | 962000 | 959875 | 952902 | 2125 | 12/15/2017
850 | 120 SCHERMERHORN ST.- INTERIOR RENOVATIONS | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO281K-CR | 111 | DSGN | CAP | 487000 | 487174 | 427559 | -174 | 12/15/2017
850 | MANH SUPREME CRIM CT DASNY | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO282155 | 001 | SITE | CAP | 481000 | 0 | 0 | 481000 | 12/15/2017
850 | MANH SUPREME CRIM CT DASNY | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO282155 | 006 | SITE | CAP | 40000 | 0 | 0 | 40000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 100 | CONS | CAP | 722000 | 722475 | 551081 | -475 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 112 | SVCS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 183 | CNSP | CAP | 42000 | 0 | 0 | 42000 | 12/15/2017
850 | REPLACE WATER MAIN IN CRESCENT ST, BK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-762 | 002 | IFDS | IFA | 348000 | 347628 | 347628 | 372 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 22B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-767 | 002 | IFDS | IFA | 179000 | 178209 | 178209 | 791 | 12/15/2017
850 | REPLACEMENT OF 8" AND 12" AND 20" DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-771 | 005 | CONS | CAP | 1203000 | 1202118 | 1188098 | 882 | 12/15/2017
850 | REPLACEMENT OF DISTRIBUTION MAINS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-772 | 010 | IFSP | IFA | 253000 | 252591 | 252591 | 409 | 12/15/2017
850 | DISTRIBUTION WATER MAINS IN 4 AV - 80 ST AND 95 ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-774 | 012 | IFSP | IFA | 1612000 | 1500601 | 1500601 | 111399 | 12/15/2017
850 | WM REPLMT EAST NEW YORK AVE B/T HOWARD AV & PACIFIC ST, ETC | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-776 | 005 | CNSP | CAP | 287000 | 0 | 0 | 287000 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 008 | DSGN | CAP | 52000 | 51110 | 28803 | 890 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 002 | CONS | CAP | 5559000 | 5522162 | 5450496 | 36838 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T Carlton & portland | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778A | 601 | IFDS | IFA | 320000 | 320000 | 320000 | 0 | 12/15/2017
850 | SWR & WM EASTERN PKWY B/T GRAND ARMY PLAZA & WASHINGTON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-779 | 006 | CNSP | CAP | 487000 | 485254 | 467702 | 1746 | 12/15/2017
850 | RECON OF WM IN KINGSTON AVE BTW EASTERN PKWY & EMPIRE BLVD | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-787 | 003 | CONS | CAP | 112000 | 112000 | 0 | 0 | 12/15/2017
850 | DUMBO/Vinegar Hill Area Reconstruction & Plaza. | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-794 | 006 | DSGN | CAP | 67000 | 66994 | 66994 | 6 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 005 | CNSP | CAP | 106000 | 105639 | 0 | 361 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 600 | IFDS | IFA | 65000 | 64999 | 52043 | 1 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-001 | 008 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-003 | 001 | CONS | CAP | 17184000 | 17183177 | 0 | 823 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BRONX ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT2 | 008 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 032 | CONS | CAP | 416000 | 412040 | 412040 | 3960 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 042 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 005 | CNSP | CAP | 36000 | 35500 | 35500 | 500 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 018 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | QUEENS HDM INTERIOR RECON | 072 | DEPARTMENT OF CORRECTION | C-104QHDM | 032 | CONS | CAP | 150000 | 149871 | 149871 | 129 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 013 | CONS | CAP | 332000 | 331493 | 331493 | 507 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 016 | CONS | CAP | 883000 | 882021 | 882021 | 979 | 12/15/2017
850 | EGRESS STAIRS AT B'KLYN HOUSE OF DETENTION | 072 | DEPARTMENT OF CORRECTION | C104EGRES | 010 | CTGY | CAP | 5000000 | 0 | 0 | 5000000 | 12/15/2017
850 | 200 DORMITORY BEDS AT ARDC | 072 | DEPARTMENT OF CORRECTION | C114ARDC | 010 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | MODULAR & SPRUNGS TAKE DOWNS - CAPACITY REPLACEMENT PROGRAM | 072 | DEPARTMENT OF CORRECTION | C114CAPTD | 005 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CIFM FENCE | 072 | DEPARTMENT OF CORRECTION | C114FENCE | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 010 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 001 | DSGN | CAP | 1487000 | 121481 | 121481 | 1365519 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | DC7 | CNSP | CAP | 67000 | 66986 | 66986 | 14 | 12/15/2017
850 | WM & Sewer work in Atlantic Ave (HWD10105, NDF-ATLAV) | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-785A | 001 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | WM & Sewer work in Atlantic Ave (HWD10105, NDF-ATLAV) | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-785A | 006 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | WM & Sewer work in Atlantic Ave (HWD10105, NDF-ATLAV) | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-785A | 606 | IFSP | IFA | 126000 | 0 | 0 | 126000 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 013 | CONS | CAP | 33000 | 32107 | 0 | 893 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-001 | 012 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | Accelerated Distribution WM replcmnt & sewer rehab- BKLYN | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BEDA-003 | 602 | IFSP | IFA | 150000 | 0 | 0 | 150000 | 12/15/2017
850 | BROOKLYN ADDITION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BKDETCT2 | 014 | IFSP | IFA | 70000 | 69994 | 69994 | 6 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 007 | CONS | CAP | 4581000 | 4581423 | 4581423 | -423 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 008 | DSGN | CAP | 399000 | 398919 | 374370 | 81 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 029 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 043 | CNSP | CAP | 150000 | 0 | 0 | 150000 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 050 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 052 | IFSP | IFA | 131000 | 130728 | 130728 | 272 | 12/15/2017
850 | WHITE STREET JAIL | 072 | DEPARTMENT OF CORRECTION | C-109-3 | 005 | CONS | CAP | 26228000 | 0 | 0 | 26228000 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 003 | IFSP | IFA | 138000 | 137066 | 137066 | 934 | 12/15/2017
850 | PERIMETER CONDUIT CENTER | 072 | DEPARTMENT OF CORRECTION | C101PRMTR | 019 | CNSP | CAP | 219000 | 218900 | 218900 | 100 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 018 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 032 | DSGN | CAP | 225000 | 357762 | 357762 | -132762 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 034 | IFDS | IFA | 66000 | 65010 | 65010 | 990 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 039 | IFDS | IFA | 465000 | 359273 | 359273 | 105727 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 010 | CONS | CAP | 2000 | 0 | 0 | 2000 | 12/15/2017
850 | New Bronx Facility- Capacity Replacement and Reconstruction | 072 | DEPARTMENT OF CORRECTION | C114NEWF | 002 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | New Bronx Facility- Capacity Replacement and Reconstruction | 072 | DEPARTMENT OF CORRECTION | C114NEWF | 007 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | New Bronx Facility- Capacity Replacement and Reconstruction | 072 | DEPARTMENT OF CORRECTION | C114NEWF | 010 | CTGY | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 005 | DSGN | CAP | 2805000 | 2804800 | 2804800 | 200 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 006 | IFDS | IFA | 417000 | 416229 | 386768 | 771 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 012 | DSGN | CAP | 878000 | 0 | 0 | 878000 | 12/15/2017
850 | 800 DORMITORY BEDS AT RMSC | 072 | DEPARTMENT OF CORRECTION | C114RMSC | 019 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | OBCC BATHRM & SHWR FLOORS | 072 | DEPARTMENT OF CORRECTION | C124-FLOR | 022 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ALTERATIONS TO POWER PLANT AT RIKERS ISLAND | 072 | DEPARTMENT OF CORRECTION | C130-P1 | 010 | CONS | CAP | 22000 | 0 | 0 | 22000 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE I | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768A | 012 | DSGN | CAP | 31000 | 31000 | 31000 | 0 | 12/15/2017
850 | WATER MAIN CONNECTIONS TO SHAFT 23B - PHASE II | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-768B | 004 | CNSP | CAP | 1131000 | 0 | 0 | 1131000 | 12/15/2017
850 | REPLACEMENT OF VALVES AND REGULATORS | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-769 | 022 | IFSP | IFA | 120000 | 85805 | 85805 | 34195 | 12/15/2017
850 | DISTRIBUTION WATER MAINS IN 4 AV - 80 ST AND 95 ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-774 | 003 | CONS | CAP | 5015000 | 5009974 | 4574401 | 5026 | 12/15/2017
850 | DISTRIBUTION WATER MAINS IN 4 AV - 80 ST AND 95 ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-774 | 601 | IFDS | IFA | 70000 | 67123 | 67123 | 2877 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 600 | IFDS | IFA | 15000 | 14999 | 8140 | 1 | 12/15/2017
850 | WM REPLMT IN LEONARD STRET B/T DRIGGS AV AND MAUJER ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-777 | 603 | IFDS | IFA | 450000 | 450000 | 450000 | 0 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 018 | CONS | CAP | 240000 | 239044 | 0 | 956 | 12/15/2017
850 | TRUNK & DIST. W/M REPL IN ATALNTIC AV B/T CARLTON & CLASSON | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-778 | 020 | CNSP | CAP | 513000 | 512008 | 512008 | 992 | 12/15/2017
850 | RECON OF WM & SWR IN 5 AVE B/T 65 ST & 34 ST | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-780 | 603 | IFDS | IFA | 100000 | 0 | 0 | 100000 | 12/15/2017
850 | WM & Sewer work in Atlantic Ave (HWD10105, NDF-ATLAV) | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED-785A | 003 | CONS | CAP | 676000 | 676062 | 0 | -62 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 011 | CONS | CAP | 67000 | 66787 | 0 | 213 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 018 | CONS | CAP | 87000 | 86985 | 0 | 15 | 12/15/2017
850 | 72" Replacement in Flatbush Avenue between Sterling Pl & 8th | 826 | DEPT OF ENVIRONMENTAL PROTECTION | BED798 | 608 | IFSP | IFA | 105000 | 0 | 0 | 105000 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 002 | IFDS | IFA | 180000 | 180000 | 180000 | 0 | 12/15/2017
850 | BRIDGES DETENTION CENTER - LOCAL LAW #11/INTERIOR RENOVATION | 130 | DEPARTMENT OF JUVENILE JUSTICE | BXDETCT | 103 | IFSP | IFA | 352000 | 304788 | 304788 | 47212 | 12/15/2017
850 | BKDC PHASE B | 072 | DEPARTMENT OF CORRECTION | C-104A-1B | 024 | CONS | CAP | 173000 | 168309 | 168309 | 4691 | 12/15/2017
850 | EGRESS STAIRS AT B'KLYN HOUSE OF DETENTION | 072 | DEPARTMENT OF CORRECTION | C104EGRES | 002 | IFSP | IFA | 181000 | 180230 | 180230 | 770 | 12/15/2017
850 | WHITE STREET SITE ACQUISITION | 072 | DEPARTMENT OF CORRECTION | C109SITE | 001 | SITE | CAP | 1330000 | 0 | 0 | 1330000 | 12/15/2017
850 | 200 DORMITORY BEDS AT ARDC | 072 | DEPARTMENT OF CORRECTION | C114ARDC | 013 | IFSP | IFA | 421000 | 110624 | 110624 | 310376 | 12/15/2017
850 | CIFM STAFF LOCKERS | 072 | DEPARTMENT OF CORRECTION | C114DDMOD | 013 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 005 | IFDS | IFA | 170000 | 169425 | 169425 | 575 | 12/15/2017
850 | CAPACITY REPLACEMENT GRVC BED ADDITION | 072 | DEPARTMENT OF CORRECTION | C114GMOD | 006 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 002 | DSGN | CAP | 154000 | 87894 | 87894 | 66106 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 011 | CONS | CAP | 5000 | 0 | 0 | 5000 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 026 | CONS | CAP | 201000 | 0 | 0 | 201000 | 12/15/2017
850 | ELEC PERM POWER\GENERATORS-EAST/WEST STRUCTURES | 072 | DEPARTMENT OF CORRECTION | C114MBE3 | 036 | CONS | CAP | 16000 | 15608 | 15608 | 392 | 12/15/2017
850 | PERM ELEC FOR EAST/WEST (CON ED TIE-INS) | 072 | DEPARTMENT OF CORRECTION | C114MBE3B | 008 | CONS | CAP | 175000 | 175000 | 175000 | 0 | 12/15/2017
850 | EAST/WEST PERMANENT POWER ENGINE GENERATOR | 072 | DEPARTMENT OF CORRECTION | C114MBE3C | 002 | IFSP | IFA | 152000 | 151602 | 151602 | 398 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 006 | CONS | CAP | -46000 | 0 | 0 | -46000 | 12/15/2017
850 | PERM ELEC/LV SYSTEM - WEST SIDE CDU | 072 | DEPARTMENT OF CORRECTION | C114MBE3W | 018 | CONS | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 305 | SVCS | CAP | 3000 | 0 | 0 | 3000 | 12/15/2017
850 | DASNY - BRONX CRIMINAL CT COMPLEX | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO290XSB1 | 329 | DSGN | CAP | 6000 | 0 | 0 | 6000 | 12/15/2017
850 | BRONX CRIM CT COMPLEX PH II | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO291XSB2 | 003 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | QNS CRIM CT- ANNEX "Q2" | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO296418D | 004 | CNSP | CAP | 3908000 | 0 | 0 | 3908000 | 12/15/2017
850 | QNS CRIM CT- ANNEX "Q2" | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO296418D | 005 | CNSP | CAP | 2485000 | 0 | 0 | 2485000 | 12/15/2017
850 | QNS CRIM CT- ANNEX "Q2" | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO296418D | 011 | CNSP | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | QUEENS FAMILY COURT DASNY | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO298419A | 011 | EQFN | CAP | 760000 | 0 | 0 | 760000 | 12/15/2017
850 | QUEENS FAMILY COURT DASNY | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO298419A | 102 | CONS | CAP | 1939000 | 0 | 0 | 1939000 | 12/15/2017
850 | QUEENS FAMILY COURT DASNY | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO298419A | 104 | CONS | CAP | 58000 | 0 | 0 | 58000 | 12/15/2017
850 | 88-11 SUTPHIN BLVD.- ELEVATOR | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO300ELV2 | 002 | CONS | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | 88-11 SUTPHIN BLVD.- ELEVATOR | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO300ELV2 | 101 | IFDS | IFA | 260000 | 259999 | 179543 | 1 | 12/15/2017
850 | 88-11 SUTPHIN BLVD.- EXTERIOR LL11 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO300EXT2 | 002 | DSGN | CAP | 250000 | 0 | 0 | 250000 | 12/15/2017
850 | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO301LL | 001 | DSGN | CAP | 395000 | 0 | 0 | 395000 | 12/15/2017
850 | 130 STUYVESANT PL - FACADE REPAIRS LOCAL LAW 11 | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO301LL | 002 | CONS | CAP | 2843000 | 0 | 0 | 2843000 | 12/15/2017
850 | 27 MADISON AVE - ROOF & MISC. OPERATIONS SPACES UPGRADE | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO80ROOF2 | 004 | IFDS | IFA | 450000 | 325000 | 325000 | 125000 | 12/15/2017
850 | 31 CHAMBERST ST.- RENOVATE SKYLIGHT | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | CO81SKY2 | 007 | CONS | CAP | 882000 | 881906 | 0 | 94 | 12/15/2017
850 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 1 | 826 | DEPT OF ENVIRONMENTAL PROTECTION | CONISPH01 | 008 | CNSP | CAP | 126000 | 125457 | 88541 | 543 | 12/15/2017
850 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2A | 826 | DEPT OF ENVIRONMENTAL PROTECTION | CONISPH2A | 606 | IFSP | IFA | 128000 | 25000 | 25000 | 103000 | 12/15/2017
850 | SAN & STRM SWR, WM1, WM6 IN CONEY ISL AREA, PH 2B | 826 | DEPT OF ENVIRONMENTAL PROTECTION | CONISPH2B | 005 | DSGN | CAP | 28000 | 27750 | 13514 | 250 | 12/15/2017
850 | Storm and Sanitary Sewer, Trunk and Distribution Water Main | 826 | DEPT OF ENVIRONMENTAL PROTECTION | CONISPH3A | 010 | CONS | CAP | 66000 | 0 | 0 | 66000 | 12/15/2017
850 | PARALLEL SEWER-REDUCE CSO DISCHARGE FROM PUGSLEY CREEK | 826 | DEPT OF ENVIRONMENTAL PROTECTION | CS-ER-WCP | 012 | DSGN | CAP | 27000 | 26888 | 0 | 112 | 12/15/2017
850 | Flushing Bay Low Lying Sewer Diversion | 826 | DEPT OF ENVIRONMENTAL PROTECTION | CS-FB-LLD | 002 | CONS | CAP | 2860000 | 2859168 | 2669649 | 832 | 12/15/2017
850 | CONST. NEW CLASS ROOM FOR BED-STUY EARLY CHILD. DEVELOPMENT | 068 | ADMIN. FOR CHILDREN'S SERVICES | CSK001CDC | 004 | EQFN | CAP | 161000 | 129312 | 129312 | 31688 | 12/15/2017
850 | CITY TUNNEL #2, REPLACE GUARD VALVES @ 16A | 826 | DEPT OF ENVIRONMENTAL PROTECTION | CT2-INTER | 002 | CONS | CAP | 4479000 | 0 | 0 | 4479000 | 12/15/2017
850 | EMERGENCY GENERATOR FOR LEFRAK BLDG. | 826 | DEPT OF ENVIRONMENTAL PROTECTION | DEPEMGEN | 005 | CTGY | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | EMERGENCY GENERATOR FOR LEFRAK BLDG. | 826 | DEPT OF ENVIRONMENTAL PROTECTION | DEPEMGEN | 007 | IFDS | IFA | 35000 | 9910 | 9910 | 25090 | 12/15/2017
850 | DCAS - SUN BUILDING ENERGY UPGRADE | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | E14-0012 | 004 | IFDS | IFA | 221000 | 191000 | 117163 | 30000 | 12/15/2017
850 | DCAS - Queens Civil Court | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | E16-0002 | 004 | CONS | CAP | 924000 | 0 | 0 | 924000 | 12/15/2017
850 | DCAS - Queens Civil Court | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | E16-0002 | 102 | IFSP | IFA | 175000 | 0 | 0 | 175000 | 12/15/2017
850 | DCAS - BROOKLYN NORTH 1 DISTRICT &4 DISTRICT GARAGE | 856 | DEPARTMENT OF CITYWIDE ADMINISTRATIVE SERVICES | E17-0006 | 002 | CONS | CAP | 10136000 | 0 | 0 | 10136000 | 12/15/2017
850 | COOK SERVE #3---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV3 | 012 | DSGN | CAP | -1000 | 0 | 0 | -1000 | 12/15/2017
850 | COOK SERVE #3---PHASE 1 | 072 | DEPARTMENT OF CORRECTION | C141SERV3 | 015 | DSGN | CAP | 0 | 0 | 0 | 0 | 12/15/2017
850 | ARDC SHOWER RECONSTRUCTION | 072 | DEPARTMENT OF CORRECTION | C74-SHWR | 009 | CNSP | CAP | 251000 | 146953 | 146953 | 104047 | 12/15/2017
850 | RECONSTRUCTION BKLYN COURTS | 072 | DEPARTMENT OF CORRECTION | C75-BKCON | 029 | CONS | CAP | 28000 | 0 | 0 | 28000 | 12/15/2017
850 | EPA SPILL PREVENTION AND RESPONSE PLAN | 072 | DEPARTMENT OF CORRECTION | C75-EPA | 001 | DSGN | CAP | 100000 | 99856 | 99856 | 144 | 12/15/2017
850 | EPA SPILL PREVENTION AND RESPONSE PLAN | 072 | DEPARTMENT OF CORRECTION | C75-EPA | 004 | CONS | CAP | 788000 | 787774 | 787774 | 226 | 12/15/2017
850 | FACADE RECONSTRUCTION AT EMTC, NIC,QDC, MDC, and GRVC | 072 | DEPARTMENT OF CORRECTION | C75-FCAD | 008 | DSGN | CAP | 455000 | 454201 | 426047 | 799 | 12/15/2017

## KeyTerms
Budget | Key Terms
CONS - Construction
CNSP - Construction Management Consulting
CTGY - Contingency
DSGN - Design
IFxx - Inter-Funds Agreement: the Capital Fund reimburses the General Fund for operating expenses on capital projects
EQxx - Equipments
SVCS - Any services related to Design or Construction
Schedule | Milestones | Milestone Range | Phase
| Project Start | PS to DS | Initiation
| Design Start | DS to DC | Design
| Design Completion | DC to CS | Procurement
| Construction Start | CS to CC | Construction
| Construction Complesion | CC to PC | Project Closeout
Project Closeout
| Key Terms | Description
| Orginal (Org) | Generic date setup at the very biginning of a project
| Baseline | Fixed date setup at the start of Design and Construction Phase
| Projected | Dates projected at each phase (design, constrction, procurement, etc)
| Actual (Act) | Dates actualized a milestone
| Client Extended (ClientExt) | Extended or modified dates due to clients